## 3 Year GSC 05-06 to 07-08 Full (hidden)
| 1 | 2 |  | 3 | 4 | 5 | 6 | 7 | 8 |  | 9 | 10 | 11 | 11 | 12 | 13 | 14 | 15 | 16
|  | General Services Capital Programme |  | Gross Expenditure | [6 empty] | External or CFCR Funding Allocated | [5 empty] | Net Expenditure |  |  | APPENDIX 1 | Recurring Revenue consequences
|  | (Refer to Notes Below) | [18 empty] | for the proposed project
|  | DRAFT |  | Approved 17th Dec 2003 | Carried fwd from 04/05 | Additions/ (Deletions) | Revised | Approved 17th Dec 2003 + any additions |  |  | Approved 17th Dec 2003 | Carried fwd from 04/05 + any additions | Revised |  |  |  | (Council Contribution)
[5 empty] | from 2004/05 | from 2004/05 | [5 empty] | from 2004/05
|  |  |  | 2005/06 | 2005/06 | 2005/06 | 2005/06 | 2006/07 | 2007/08 |  | 2005/06 | 2005/06 | 2005/06 |  | 2006/07 | 2007/08 | 2005/06 | 2006/07 | 2007/08 |  | 2004/05 | 2005/06 | 2006/07
|  | Service / Project Name |  | £'000 | £'000 | £'000 | £'000 | £'000 | £'000 |  | £'000 | £'000 | £'000 |  | £'000 | £'000 | £'000 | £'000 | £'000
0
SERVICES TO PEOPLE
EDUCATION & COMMUNITY SERVICES
Abercromby PS
Alva Primary Extension
Beechwood Park
Lornshill Academy Sports Complex Phase 1
Lornshill Academy Sports Complex Phase 2
Pre Fives
Property Maintenance - additional from Revenue
Alloa Academy
Safer Routes to school
Strathdevon Primary
1 | 1 | Alva Academy - PPP Capital Support |  | 650 | 50 |  | 700 | 1050 | 1000 | [7 empty] | 700 | 1050 | 1000
Alva Academy SEN
Alloa Library
Catering Improvements
Heavy Equipment Replacement
Greenhead Pavilion
Relocation of PSSS
Sunnyside PS
Canoe Site Purchase
Claremont P S Huts
Community Facility, Fishcross
Community Facility, Hawkhill
Lime Tree House upgrade wiring
2 | 2 | Alloa Academy- PPP Capital Support | [5 empty] | 750 | 1250 | [7 empty] | 0 | 750 | 1250
3 | 3 | Lornshill Academy & Tulligarth Phase 2 - PPP Capital Support | [5 empty] | 1150 | 850 | [5 empty] | 0 |  | 0 | 1150 | 850
4 | 4 | DDA Compliance |  | 100 | 40 |  | 140 | 100 | [8 empty] | 140 | 100 | 0
5 | 5 | Kilncraigs 1936 @ |  | 250 |  | -250 | 0 | [9 empty] | 0 | 0 | 0
6 | 6 | Lochies - Specialist Accommodation |  | 50 |  |  | 50 | [9 empty] | 50 | 0 | 0
7 | 7 | Museum & Heritage Centre |  |  | 700 |  | 700 |  |  |  |  | 450 | 450 |  |  |  | 250 | 0 | 0
2.918 | 5.0633 | Lochies School |  |  |  |  | 0 | [9 empty] | 0 | 0 | 0
3.0328 | 5.3038 | Lochies School - Excellence Fund |  |  |  |  | 0 | [9 empty] | 0 | 0 | 0
3.1475 | 5.5443 | Lochies School - Schools Budget Income |  |  |  |  | 0 | [9 empty] | 0 | 0 | 0
3.2623 | 5.7848 | Museum & Heritage Centre - External Income |  |  |  |  | 0 | [9 empty] | 0 | 0 | 0
3.377 | 6.0253 | Property Maintenance |  |  |  |  | 0 | [9 empty] | 0 | 0 | 0
3.4918 | 6.2658 | Public Art |  |  |  |  | 0 | [9 empty] | 0 | 0 | 0
3.6066 | 6.5063 | Retentions/Legally committed |  |  |  |  | 0 | [9 empty] | 0 | 0 | 0
3.7213 | 6.7468 | SEN Adaptations |  |  |  |  | 0 | [9 empty] | 0 | 0 | 0
8 | 8 | School Building Alarm Systems |  | 25 |  | 275 | 300 | 300 | 8 | [7 empty] | 300 | 300 | 8 |  | some maintenance but reduction in insurance
9 | 9 | Schools Estate Renewal Programme |  | 763 |  | 199 | 962 | 1008 | 1055 |  | 763 | 199 | 962 |  | 1008 | 1055 | 0 | 0 | 0
11 | 10 | Tulligarth Sports Resurfacing - requirement of Lottery funding | [6 empty] | 40 | [7 empty] | 0 | 0 | 40
12 | 11 | Alloa Library Refurbishment |  |  |  | 100 | 100 | 100 | [8 empty] | 100 | 100 | 0
13 | 12 | Art Houses |  |  |  | 40 | 40 | [9 empty] | 40 | 0 | 0
14 | 13 | Heavy Equipment in Secondary Schools - Kilns etc |  |  |  | 60 | 60 | 30 | 30 | [7 empty] | 60 | 30 | 30
15 | 14 | IT Hardware Replacement in Schools |  |  |  | 100 | 100 | 100 | 100 |  |  | 40 | 40 |  | 40 | 40 | 60 | 60 | 60
16 | 15 | Legal Commitments - for projects undertaking in 04/05 |  |  |  | 25 | 25 | 25 | 25 | [7 empty] | 25 | 25 | 25
17 | 16 | Leisure Bowl - Complete refurbishment per 20yr Development plan | [5 empty] | 200 | 75 | [7 empty] | 0 | 200 | 75
18 | 17 | Primary & Nursery School Developments |  |  |  | 300 | 300 | 300 | 300 | [7 empty] | 300 | 300 | 300
19 | 18 | Accessibility Strategy (if revenue budget approved, no need for capital) | [14 empty] | 0 | 0 | 0
20 | 19 | Fir Ski Park Centre - upgrade to building |  |  | 50 | -2 | 48 |  |  |  |  | 48 | 48 |  |  |  | 0 | 0 | 0
|  | Total Education & Community Service |  | 1838 | 840 | 847 | 3525 | 5113 | 4733 |  | 763 | 737 | 1500 |  | 1048 | 1095 | 2025 | 4065 | 3638 |  | 0 | 0 | 0
|  | General Fund Housing - Enabling |  |  |  |  | 0
|  | SOCIAL SERVICES |  |  |  |  | 0
|  | Ludgate House (c/f from 00/01) |  |  |  |  | 0
|  | Office Relocations |  |  |  |  | 0
|  | Whins Resource Centre - Floor Heating System |  |  |  |  | 0
|  | Care in Community Safety (** new proposal - see attached schedule) |  |  |  |  | 0
|  | Upgrade 6 Marshill Alloa |  |  |  |  | 0
|  | Document Imaging System (** new proposal - see attached schedule) |  |  |  |  | 0
22 | 20 | DDA Compliance |  | 20 |  |  | 20 | 20 | [8 empty] | 20 | 20 | 0
23 | 21 | Joint FVNHS/ Adult Care Premises Occupation |  | NK |  |  | NK | NK | NK |  |  |  | NK |  | NK |  | NK | NK | NK
24 | 22 | Greenfield/Ludgate House Traffic Management System |  | 26 |  |  | 26 | 0 | [8 empty] | 26 | 0 | 0
25 | 23 | Menstrie House En-Suite Conversion |  | 294 | 560 | 86 | 940 | 50 | [8 empty] | 940 | 50 | 0
26 | 24 | Ludgate House Resource Centre |  |  |  | 6 | 6 | [9 empty] | 6 | 0 | 0
27 | 25 | Mental Health Services |  |  | 30 | 30 | 60 |  |  |  |  | 60 | 60 |  |  |  | 0 | 0 | 0
|  | Total Social Services |  | 340 | 590 | 122 | 1052 | 70 | 0 |  | 0 | 60 | 60 |  | 0 | 0 | 992 | 70 | 0 |  | 0 | 0 | 0
DEVELOPMENT & ENVIRONMENTAL SERVICES
Transportation
|  | A907 (carry forward of unused additional consent) | }
|  | A907 - Council Contribution | }
28 | 26 | Accident Prevention & Traffic Management |  | 100 |  | 50 | 150 | 100 | 100 | [7 empty] | 150 | 100 | 100 |  | 0 | 0 | 0
29 | 27 | Alloa Town Centre |  | 400 | 300 |  | 700 | [9 empty] | 700 | 0 | 0 |  | -200 | -200 | -200
|  | Accident Prevention & Traffic Management - Safer Roads, Cycling |  |  |  |  | 0 | [9 empty] | 0 | 0 | 0
30 | 28 | A91 East Stirling St. Alva Roundabout to access new school site | [6 empty] | 450 | [8 empty] | 0 | 450
31 | 29 | A908/B908 Sauchie, Roundabout to facilitate new hospital | [5 empty] | 275 | [9 empty] | 275
32 | 30 | B9140/ Collylands Cross Upgrade |  | 500 |  | -100 | 400 | 100 |  |  | 500 | -500 | 0 |  |  |  | 400 | 100 | 0 |  | 0 | 0 | 0
33 | 31 | B9140 Realignment of Bends | [5 empty] | 500 | 500 | [7 empty] | 0 | 500 | 500
34 | 32 | Bridge Strengthening |  | 150 |  | 340 | 490 | 150 | 400 | [7 empty] | 490 | 150 | 400 |  | 0 | 0 | 0
|  | Eastern Link Road |  |  |  |  | 0 | [9 empty] | 0 | 0 | 0
|  | Hall Park |  |  |  |  | 0 | [9 empty] | 0 | 0 | 0
|  | Footpath Maintenance |  |  |  |  | 0 | [9 empty] | 0 | 0 | 0
|  | Roads Maintenance |  |  |  |  | 0 | [9 empty] | 0 | 0 | 0
|  | Smithfield Loan |  |  |  |  | 0 | [9 empty] | 0 | 0 | 0
|  | Roads Structural Maintenance |  |  |  |  | 0 | [9 empty] | 0 | 0 | 0
35 | 33 | Flood Prevention |  | 60 |  |  | 60 | 100 | 100 | [7 empty] | 60 | 100 | 100 |  | 0 | 0 | 0
36 | 34 | Retentions |  | 50 |  |  | 50 | 60 | 60 | [7 empty] | 50 | 60 | 60 |  | 0 | 0 | 0
37 | 35 | Road & Footway Improvements (SRMCS), including town centres |  | 865 |  |  | 865 | 850 | 1000 | [7 empty] | 865 | 850 | 1000 |  | 0 | 0 | 0
38 | 36 | Cycling , Walking ,Safer Streets (CWSS) |  | 182 |  | -100 | 82 | 84 | 86 |  | 182 | -100 | 82 |  | 84 | 86 | 0 | 0 | 0 |  | 0 | 0 | 0
39 | 37 | Street Lighting |  | 135 |  | 3 | 138 | 150 | 165 | [7 empty] | 138 | 150 | 165 |  | 0 | 0 | 0
|  | Tullibody Bypass (to be funded from special capital receipts) |  |  |  |  | 0 | [9 empty] | 0 | 0 | 0
40 | 38 | Total SAK Rail Project & Alloa ELR Project Costs |  | 15000 | 18137 | 299 | 33436 | 750 |  |  | 14494 | 16923 | 31417 |  | 712 |  | 2019 | 38 | 0 |  | -20 | -20 | -20
41 | 39 | Tullibody By Pass ## |  | 600 | -600 |  | 0 |  |  |  | 400 | -400 | 0 |  |  |  | 0 | 0 | 0
42 | 40 | Tullibody By Pass c/f from 2004/05 |  |  | 35 |  | 35 | [5 empty] | 0 |  |  |  | 35 | 0 | 0
43 | 41 | 20mph speed reduction |  |  |  | 99 | 99 | 107 | 109 |  |  | 99 | 99 |  | 107 | 109 | 0 | 0 | 0
44 | 42 | Footways at Muirside, Tullibody |  |  |  | 50 | 50 | [9 empty] | 50 | 0 | 0
| 43 | SESTRAN Public Transport & Walking |  |  | 83 |  | 83 |  |  |  |  | 83 | 83 |  |  |  | 0 | 0 | 0
| 44 | SESTRAN Public Bus |  |  | 100 |  | 100 |  |  |  |  | 100 | 100 |  |  |  | 0 | 0 | 0
| 45 | SUSTRAN - Cycle Routes |  |  | 150 |  | 150 |  |  |  |  | 150 | 150 |  |  |  | 0 | 0 | 0
Environment
45 | 46 | Black Devon Landfill / Incinerator |  | 700 | 338 |  | 1038 | 200 | [8 empty] | 1038 | 200 | 0 |  | minimal savings >>>>>>>>>>>>>>
46 | 47 | Black Devon Landfill Gas Collection & Treatment Project | [6 empty] | 400 | [9 empty] | 400
47 | 48 | Cemeteries Strategy |  | 84 |  |  | 84 | 300 | [8 empty] | 84 | 300 | 0 |  | # | # | #
|  | Cycle Path Network |  |  |  |  | 0 | [9 empty] | 0 | 0 | 0
|  | Dollar Cemetery |  |  |  |  | 0 | [9 empty] | 0 | 0 | 0
|  | Environmental Improvements |  |  |  |  | 0 | [9 empty] | 0 | 0 | 0
|  | Old Alloa THI Project |  |  |  |  | 0 | [9 empty] | 0 | 0 | 0
|  | Hillfoots Initiative |  |  |  |  | 0 | [9 empty] | 0 | 0 | 0
|  | Incineration Plant Demolition |  |  |  |  | 0 | [9 empty] | 0 | 0 | 0
|  | Landward Village Initiative |  |  |  |  | 0 | [9 empty] | 0 | 0 | 0
48 | 49 | Contaminated Land |  | 50 |  |  | 50 | 50 |  |  | 50 |  | 50 |  | 50 |  | 0 | 0 | 0 |  | Budget already in place for Land Officer
|  | Tullis Factory Demolition | [14 empty] | 0 | 0 | 0
49 | 50 | Parks & Open Spaces | [6 empty] | 80 | [9 empty] | 80
50 | 51 | Outdoor Play Area Strategy | [6 empty] | 75 | [9 empty] | 75
51 | 52 | Shared Compost Facility @ Polmaise |  |  |  | 537 | 537 |  |  |  |  | 524 | 524 |  |  |  | 13
52 | 53 | Shared Transfer Facility @ Polmaise |  |  |  | 1700 | 1700 |  |  |  |  | 1300 | 1300 |  |  |  | 400
53 | 54 | Waste Recycling Project | [6 empty] | 400 | [9 empty] | 400
Partnerships
54 | 55 | Clackmannan Tolbooth |  | 170 |  |  | 170 | 0 | 161 |  | 170 |  | 170 |  |  | 104 | 0 | 0 | 57 |  | # | # | #
55 | 56 | National Cycle Route |  | 129 |  |  | 129 | 3 |  |  | 70 |  | 70 |  |  |  | 59 | 3 | 0 |  | # | # | #
56 | 57 | Old Alloa Townscape Heritage |  | 6 | 193 |  | 199 | [9 empty] | 199 | 0 | 0 |  | # | # | #
57 | 58 | Landscape Partnership - Conserve Ochills / Hillfoots | [6 empty] | 1125 | [6 empty] | 900 | 0 | 0 | 225
58 | 59 | Core Path Network for Access | [6 empty] | 50 | [6 empty] | 12 | 0 | 0 | 38
Property Services
59 | 60 | Asbestos Removal |  | 15 |  |  | 15 | 15 | [8 empty] | 15 | 15 | 0
60 | 61 | Centralised Kitchen |  |  | 350 | 350 | 700 | [9 empty] | 700 | 0 | 0
61 | 62 | Disability Discrimination Act |  |  |  | 33 | 33 | 1 | [8 empty] | 33 | 1 | 0
62 | 63 | Vehicle Replacement Programme |  |  |  | 1316 | 1316 | 794 | 570 | [7 empty] | 1316 | 794 | 570
[17 empty] | 0 | 0 | 0
Retentions Carry forward (projects to be identified)
|  | Total Development & Environmental Services |  | 19196 | 19086 | 4577 | 42859 | 4589 | 5831 |  | 15866 | 18179 | 34045 |  | 953 | 1211 | 8814 | 3636 | 4620 |  | -220 | -220 | -220
CORPORATE DEVELOPMENT
CCTV - Alloa South & East
Community Planning
63 | 64 | Efficient Government/Customer First Developments |  | 600 |  | -500 | 100 | 100 | 100 |  | 500 | -500 | 0 |  | 0 | 0 | 100 | 100 | 100
|  | Business Change & Organisational Development | } | [6 empty] | }
|  | Clack Web - eServices & eCommunity | } | [6 empty] | }
|  | Content & Knowledge Management | } | [6 empty] | }
|  | One Stop Shop & Customer Services Centre | } | [6 empty] | }
|  | Shared Services & Data Sharing | } | [6 empty] | }
Council Office - Rewiring
Information Services - Salaries
Kilncraigs Mill Develop. (consent brought forward)
64 | 65 | IT Services (No submissions received - this is an estimate) |  | 400 |  |  | 400 | 400 | 400 | [7 empty] | 400 | 400 | 400
65 | 66 | Finance Services - General Ledger system |  |  |  | 30 | 30 | 30 | 30 | [7 empty] | 30 | 30 | 30
|  | Total Corporate Development |  | 1000 | 0 | -470 | 530 | 530 | 530 |  | 500 | -500 | 0 |  | 0 | 0 | 530 | 530 | 530 |  | 0 | 0 | 0
CHIEF EXECUTIVE SERVICES
Economic Development
Dumyat Business Park Phase 2
66 | 67 | CSBP Restructuring |  |  | 500 |  | 500 |  |  |  |  | 250 | 250 |  |  |  | 250 | 0 | 0 |  | 0 | 0 | 0
67 | 68 | Econ. Dev. Infrastructure: Eastern Clackmannanshire Development Opportunities |  | 133 | 133 |  | 266 | 133 |  |  | 33 | 33 | 66 |  | 33 |  | 200 | 100 | 0 |  | 0 | 0 | 5
68 | 69 | Workspace Provision for Social Enterprises' Recycling project |  | 500 |  | -500 | 0 | [9 empty] | 0 |  |  |  | 0 | 10 | 10
69 | 70 | Kilncraigs Mill 1936 Building Envelop |  |  |  | 1350 | 1350 | [9 empty] | 1350 | 0 | 0
70 | 71 | Kilncraigs Mill 1904 Development of 3rd & 4th Floors |  |  |  |  | 0 | 310 | 310 | [7 empty] | 0 | 310 | 310
71 | 72 | Kilncraigs Mill 1904 Access Control & Zoning Services |  |  |  | 80 | 80 | [9 empty] | 80
72 | 73 | Pavilions Business Park Phase 2 |  |  |  | 1890 | 1890 |  |  |  |  | 1850 | 1850 |  |  |  | 40 | 0 | 0
73 | 74 | Dumyat Business Park Phase 3 |  |  |  | 1286 | 1286 |  |  |  |  | 1246 | 1246 |  |  |  | 40
Miscellaneous
74 | 75 | CCTV - Tron Court |  |  |  | 43 | 43 | [9 empty] | 43 | 0 | 0
75 | 76 | DDA & Asbestos Removal |  | 25 |  |  | 25 | 25 | [8 empty] | 25 | 25 | 0 |  | 0 | 0 | 0
|  | Total Chief Executives Services |  | 658 | 633 | 4149 | 5440 | 468 | 310 |  | 33 | 3379 | 3412 |  | 33 | 0 | 2028 | 435 | 310 |  | 0 | 0 | 0
|  | TOTAL CAPITAL PROGRAMME |  | 23032 | 21149 | 9225 | 53406 | 10770 | 11404 |  | 17162 | 21855 | 39017 |  | 2034 | 2306 | 14389 | 8736 | 9098 |  | -220 | -220 | -220
|  | UNALLOCATED FUNDING | [18 empty] | Key for Recurring Revenue Costs Section
76 | 77 | Capital Receipts Estimate (NET OF EXPENSES) | [14 empty] | 390 | 300 | No figures given
| 78 | Sale of Land at Dumyat Park & Ditch for Tullibody By Pass | [14 empty] | 400
77 | 79 | APM Sales | [14 empty] | 0 | 200 |  |  | # = | Costs considered but not
78 | 80 | ERDF Grants (from Kilncraigs to be used to refund extra s94 advance in previous years) | [14 empty] | 119 |  |  |  | Blank cells = | no info from service
79 | 81 | Repayment from Schools Devolved Budget for Computer Equipment | [14 empty] | 10
|  | TOTAL - ESTIMATED UNALLOCATED FUNDING | [14 empty] | 919 | 500 | 0
|  | NET FUNDING (SURPLUS) / DEFICIT |  |  | #REF! | #REF!
FINANCED BY C.F.C.R.
|  | Net Capital Expenditure to be Funded from Prudential Borrowing | [14 empty] | 13470 | 8236 | 9098
Ref to |  | List of External Allocated Funding referred to above
above |  | Contributions from other sources
| 3 | Foundation for Sports & Arts Grant | [12 empty] | 0
7 | 7 | Heritage & Lottery Grants for Museum Project | [9 empty] | 450 | 450
15 | 14 | National Priorities Action Fund - IT Hardware Replacement in Schools | [9 empty] | 40 | 40 |  | 40 | 40
20 | 19 | The Big Lottery Fund - Fir Ski Park Centre - upgrade to building | [9 empty] | 48 | 48
32 | 30 | Planning Gain Income for B9140/Collylands Cross | [8 empty] | 500 | -500 | 0
41 | 39 | Sale of Land @ Ditch Farm / Tullibody (originally earmarked for TBP, but now trf for general capital) | [8 empty] | 400 | -400 | 0
51 | 52 | Stirling Council - Shared Compost Facility @ Polmaise | [9 empty] | 524 | 524
52 | 53 | Stirling Council - Shared Transfer Facility @ Polmaise | [9 empty] | 1300 | 1300
54 | 55 | Heritage Lottery Fund for Clackmannan Tolbooth | [8 empty] | 125 |  | 125 |  |  | 32
54 | 55 | Historic Scotland Grant for Clackmannan Tolbooth | [8 empty] | 45 |  | 45 |  |  | 72
55 | 56 | National Cycle Route - Private | [8 empty] | 35 |  | 35
55 | 56 | National Cycle Route - Sustrans | [8 empty] | 35 |  | 35
57 | 58 | Heritage Lottery Fund for Landscape Partnership Project | [13 empty] | 900
58 | 59 | SNH - Core Path Network for Access | [13 empty] | 12
66 | 67 | Scarborough Development Group - CSBP Restructuring | [9 empty] | 250 | 250
67 | 68 | ERDF - Eastern Clackmannanshire Development Opportunities | [8 empty] | 33 | 33 | 66 |  | 33
72 | 73 | CSBP - Pavilions Business Park Phase 2 | [9 empty] | 1378 | 1378
72 | 73 | ERDF - Pavilions Business Park Phase 2 | [9 empty] | 472 | 472
73 | 74 | CSBP - Dumyat Business Park Phase 3 | [9 empty] | 924 | 924
73 | 74 | ERDF - Dumyat Business Park Phase 3 | [9 empty] | 322 | 322
[11 empty] | 1173 | 4841 | 6014 |  | 73 | 1056
Central Government Grants
9 | 9 | Special Grant for Schools Estate Renewal Programme | [8 empty] | 763 | 199 | 962 |  | 1008 | 1055
27 | 25 | Mental Health Services Scottish Executive | [9 empty] | 60 | 60
38 | 36 | Cycling, Walking, Safer Streets (CWSS) from SE | [8 empty] | 182 | -100 | 82 |  | 84 | 86
40 | 38 | Stirling / Alloa / Kincardine Rail Link - Specific Grant | [8 empty] | 14494 | 16923 | 31417 |  | 712
43 | 41 | 20mph Grant from Scottish Executive | [9 empty] | 99 | 99 |  | 107 | 109
| 43 | SESTRAN Public Transport & Walking | [9 empty] | 83 | 83
| 44 | SESTRAN Public Bus | [9 empty] | 100 | 100
| 45 | SUSTRAN - Cycle Routes | [9 empty] | 150 | 150
48 | 49 | Contaminated Land | [8 empty] | 50 |  | 50 |  | 50
63 | 64 | Efficient Government/Customer First Developments | [8 empty] | 500 | -500 | 0 |  | 0 | 0
[11 empty] | 15989 | 17014 | 33003 |  | 1961 | 1250
|  | Total External Funding Allocated | [8 empty] | 17162 | 21855 | 39017 |  | 2034 | 2306
| @ | = Refer to note in "Revenue & other Implication" sheet
| ## | = £600k Tullibody By Pass allocation returned to SAK Rail, having been utilised in 2004/05
| NK | = Costs or funding of project not known
= No submissions received in the current round of bids, but included here as bids received in the previous round of bids for the 3 year plan.

## Appd 1 GSCap06-07 to30-6-06 a (hidden)
| 0 |  |  | OK |  | OK |  |  | OK |  |  | OK |  | OK |  | OK
1 | 2 |  |  | 4 | 5 | 6 |  |  |  | 7 | 8 | 9 | 9 | 10 | 11 | 12 | 10 | 13 | 14 | 15 | 16 | 17 | 10 | 11 | 12 | 13 | 14 | 15 | 16
|  | Ledger codes |  | BUDGET 2005/06 | [9 empty] | Out-turn as at July 2005 |  |  |  |  | Project Status as at Mid August 2005 |  |  |  |  | 2006/07 |  |  | 2007/08 |  |  | Recurring Revenue consequences
for the proposed project
| General Services Capital Programme 2006/07 |  |  | BUDGET | [5 empty] | ACTUAL to 31st July |  |  |  | Out-turn reported at as at 14/8/06 |  |  |  |  | Project Status as at Mid July 2006 |  |  |  |  | (See Appendix 3) |  |  | (See Appendix 4)
|  |  |  | Approved Budget | External Grants | Borrowing (Council Contribution) | Projects c/f from 05/06 | Projects b/f from 07/08 |  | Total Expenditure | Total Income | Borrowing (Council Contribution) |  | Total Expenditure | Total Income | Borrowing (Council Contribution) |  | Variance on Budget | Tenders issued / received | Contractor Appointed | Project start date |  | If project is delayed to next year, proposal to bring forward project from 3 year approved programme | Gross | External Grants | Net (Council Contribution) | Gross | External Grants | Net (Council Contribution)
|  |  |  | Gross |  | Net |  |  | Total | Gross |  | Net |  |  |  | Net | [13 empty] | 2004/05 | 2005/06 | 2006/07
| Service / Project Name |  |  | £ | £ | £ | £ | £ | £ | £ | £ | £ |  | £ | £ | £ |  | £ | [5 empty] | £'000 | £'000 | £'000 | £'000 | £'000 | £'000
SERVICES TO PEOPLE
EDUCATION & COMMUNITY SERVICES
1,3,5 | PPP Capital Support | 90 10 7000 |  | 3450000 | 0 | 3450000 | 1200000 |  | 4650000 |  |  | 0 |  | 0 | 0 | 0 |  | 4650000 |  |  |  | As advised in previous report, in accordance with proper accounting practice, transfers of PPP budgets to a sinking fund cannot be capitalised currently for which no asset exits. These budgets will be carried forward to future years to be offset against unitary charges as and when the payments become due. |  | 1050 | 0 | 1050 | 1000 | 0 | 1000
17 | Primary & Nursery School Developments - Allocated to PPP |  |  | 0 | 0 | 0 | 175000 |  | 175000 |  |  | 0 |  |  |  | 0 |  | 175000 |  |  |  | As above |  | 300 | 0 | 300 | 300 | 0 | 300
4 | DDA Compliance | 90 10 6000 | } | 0 | 0 | 0 | 133000 |  | 133000 | 23423.4 |  | 23423.4 |  | 133000 |  | 133000 |  | 0 |  |  |  | The budget, which was carried forward from last year, is made up of a number of small projects. Some of them have been completed over the summer holidays. Further projects will be commissioned to utilise the funding available during the year. Spend on Accessibility Strategy is treated as part of DDA project. |  | 100 | 0 | 100 | 0 | 0 | 0
| Accessibility Strategy | 90 10 6100 | } |  |  | 0 |  |  | 0 | 1212.97 |  | 1212.97 |  |  |  | 0 |  | 0
7 | Museum & Heritage Centre | 90 10 5800 |  |  | 0 | 0 | 250000 |  | 250000 |  |  | 0 |  |  |  | 0 |  | 250000 |  |  |  | The budget will need to be carrifed forward. See details given in 11 below. |  | 0 | 0 | 0 | 0 | 0 | 0
8 | School Building Alarm Systems | 90 10 5700 |  | 10000 | 0 | 10000 | 294000 |  | 304000 | 1382 |  | 1382 |  | 304000 |  | 304000 |  | 0 |  |  |  | The bulk of the work was completed over the summer period. Final certificates will be processed in due course and the budget will be spent this year. |  | 300 | 0 | 300 | 8 | 0 | 8 | some maintenance but reduction in insurance
85,86 | ICT Hardware Replacement in Sec Schls & New IT Installation in Schools | 90 10 0440 |  | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0
9 | Schools Fund | 90 10 4900 |  | 1008000 | -1008000 | 0 | 0 |  | 0 | 457389.12 |  | 457389.12 |  | 1008000 | -1008000 | 0 |  | 0 |  |  |  | Major works at Deerpark / Lochies, Park PS, Coalsnaughton PS, Tillicoultry PS, Menstrie PS have been completed or nearly completed (in the case of Park PS) over the vacation. Once the final costs are available, any remaining funds will be used to tackle other projects. |  | 1008 | 1008 | 0 | 1055 | 1055 | 0
10 | Tulligarth Sports Resurfacing - requirement of Lottery funding |  |  | 0 |  | 0 | 0 |  | 0 |  |  | 0 |  |  |  | 0 |  | 0
11 | Alloa Library Refurbishment |  |  | 0 | 0 | 0 | 100000 |  | 100000 |  |  | 0 |  |  |  | 0 |  | 100000 |  |  |  | The Service will not spend any of this funding in this year because of the ongoing discussions about the wider issues of Alloa Town Centre Regeneration. There are on going discussions on how to best develop the Library provision and to link this with the current rationalisation of Council buildings , including the development of Museum & Heritage Centre and acomodation moves to Kilncraigs. All of these proposals are being considered by the CAMP team and will have a direct impact on the development of the Library provision. |  | 100 | 0 | 100 | 0 | 0 | 0
13 | Heavy Equipment in Secondary Schools - Kilns etc | 90 10 6600 |  | 0 | 0 | 0 | 60000 |  | 60000 | 40470 |  | 40470 |  | 40470 |  | 40470 |  | 19530 |  |  |  | Both projects are now complete and the balances are off-set each, with a slight overspend of £530. |  | 30 | 0 | 30 | 30 | 0 | 30
14 | IT Hardware Replacement in Schools | 90 10 6700 |  | 100000 | -40000 | 60000 | -139000 | 60000 | -19000 |  |  | 0 |  | 0 |  | 0 |  | -19000 | [5 empty] | 100 | 40 | 60 | 100 | 40 | 60
15 | Legal Commitments - for projects undertaking in 04/05 | 90 10 6900 |  | 25000 | 0 | 25000 | 0 |  | 25000 | 1586.49 |  | 1586.49 |  | 25000 |  | 25000 |  | 0 |  |  |  | This is provision for retentions for previous projects, which has been overspent to enable all retentions to be paid . |  | 25 | 0 | 25 | 25 | 0 | 25
16 | Leisure Bowl - refurbishment | 90 15 0100 |  | 200000 | 0 | 200000 | -14000 | 75000 | 261000 | 237327.62 |  | 237327.62 |  | 261000 |  | 261000 |  | 0 |  |  |  | Due to the decision to refurbish M&E and plant at Alloa Leisure Bowl in the current financial year, the spending profile this year is £260k. £14k was spent last year, bringing the total spend to £274k. The funding for this is £200k allocated this year and £75k brought forward from next year. |  | 200 | 0 | 200 | 75 | 0 | 75
87-91 | Future Developments |  |  | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 |  |  |  | 0 |  | 0
19 | Fir Park Ski Centre - upgrade to building | 90 10 5200 |  | 0 | 0 | 0 | 0 |  | 0 | 815.6 |  | 815.6 |  |  |  | 0 |  | 0 |  |  |  | Most of these are retentions to be met from legal commitments budget. See 15 above. |  | 0 | 0 | 0 | 0 | 0 | 0
| NOF & Sports Muchart Primary School | 90 10 5100 |  | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 |  |  |  | 0 |  | 0
| NOF & Sports Strathdevon & Clackmannan | 90 10 5300 |  | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 |  |  |  | 0 |  | 0
| Family Centre - Newmills | 90 10 3700 |  | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0
| Property Enhancement general | 90 10 2000 |  | 0 | 0 | 0 | 0 |  | 0 | 3402.5 |  | 3402.5 |  |  |  | 0 |  | 0 | [5 empty] | 5613 | 1048 | 4565 | 5233 | 1095 | 4138
| School Building Improvement | 90 10 4400 |  | 0 | 0 | 0 | 0 |  | 0 | 226.5 |  | 226.5 |  |  |  | 0 |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0
| SEN Adaptation | 90 10 0901 |  | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0
| Total Education & Community Service |  |  | 4793000 | -1048000 | 3745000 | 2059000 | 135000 | 5939000 | 767236.2 | 0 | 767236.2 |  | 1771470 | -1008000 | 763470 |  | 5175530 | [5 empty] | 8826 | 2096 | 6730 | 7826 | 2190 | 5636 | 0 | 0 | 0
SOCIAL SERVICES
20 | DDA Compliance |  |  | 20000 | 0 | 20000 | 16000 |  | 36000 |  |  | 0 |  | 36000 |  | 36000 |  | 0 |  |  |  | Earmarked for Alloa Centre & plans have been drawn. However, the project is awaiting approval as the Capital Asset Management Team carry out further assessment |  | 20 | 0 | 20 | 0 | 0 | 0
21 | Joint FVNHS/ Adult Care Premises Occupation |  |  | NK | NK | NK | NK |  | NK |  |  | 0 |  |  |  | 0 | [7 empty] | NK | NK | NK | NK | NK | NK
22 | Menstrie House En-Suite Conversion | 90 30 0350 |  | 800000 | 0 | 800000 | 38000 |  | 838000 | 17629.11 |  | 17629.11 |  | 838000 |  | 838000 |  | 0 |  |  |  | Originally a total budget of £1m was alloacted to this project. The Council approved a further £400k in May bringing the total to £1.4m. Of this £12k was spent last year. It is anticipated that £838k will be spent this year and £515k next year on completion, with a retention of £35k in 08/09. |  | 475 | 0 | 475 | 475 | 0 | 475
| Menstrie House External Works & Telephone system | 90 30 1500 |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0
| Menstrie House | 90 30 1500 | [6 empty] | 0 | 1807 |  | 1807 |  |  |  | 0 |  | 0
23 | Ludgate House External Fabric | 90 30 1600 |  | 20000 | 0 | 20000 | 0 |  | 20000 |  |  | 0 |  | 20000 |  | 20000 |  | 0 |  |  |  | Mainly enhancement works earmarked to be completed this year |  | 0 | 0 | 0 | 0 | 0 | 0
24 | Mental Health Services - Retentions | 90 30 1700 |  |  | 0 | 0 | 0 |  | 0 | 178.06 |  | 178.06 |  | 1000 |  | 1000 |  | -1000 |  |  |  | Small retentions from previous year |  | 0 | 0 | 0 | 0 | 0 | 0
66b | Ludgate Traffic Management - Retentions | 90 30 1900 |  |  | 0 | 0 | 0 |  | 0 | 431.75 |  | 431.75 |  | 1000 |  | 1000 |  | -1000
| Total Social Services |  |  | 840000 | 0 | 840000 | 54000 | 0 | 894000 | 20045.92 | 0 | 20045.92 |  | 896000 | 0 | 896000 |  | -2000 | [5 empty] | 495 | 0 | 495 | 475 | 0 | 475 | 0 | 0 | 0
DEVELOPMENT & ENVIRONMENTAL SERVICES
Roads & Transportation
26 | Accident Prevention & Traffic Management | 90 40 1020 |  | 100000 | 0 | 100000 | 0 |  | 100000 | 3113.73 |  | 3113.73 |  | 100000 |  | 100000 |  | 0 |  |  |  | This will be spent on three main projects, Tullibody Cross mini-roundabouts and pedestrian facilities (£45k), road safety improvements at A91 Tait’s Tomb and Cowden Bends (£45k) and Dollar, Fishcross and Coalsnaughton village gateways (£10k). |  | 100 | 0 | 100 | 100 | 0 | 100 | 0 | 0 | 0
27 | Alloa Town Centre | 90 40 1750 |  | 0 | 0 | 0 | 705000 |  | 705000 | 231584.86 |  | 231584.86 |  |  |  | 0 |  | 705000 |  |  |  | Ninian to provide details |  | 0 | 0 | 0 | 0 | 0 | 0 | -200 | -200 | -200
28 | A91 East Stirling St. Alva Roundabout to access new school site |  |  | 0 | 0 |  | 0 |  | 0 |  |  | 0 |  |  |  | 0 |  | 0
31a | B9140/ Collylands Cross Upgrade | 90 40 4500 |  | 0 | 0 | 0 | 343000 | 97000 | 440000 | 259496.42 |  | 259496.42 |  | 440000 |  | 440000 |  | 0 |  |  |  | In order to comeplete this project in the current year, next year's budget is brought forward. There may be a slight overspend of £17k according to the latest projections. |  | 600 | 0 | 600 | 500 | 0 | 500 | 0 | 0 | 0
31b | B9140 Realignment of Bends |  |  | 0 | 0 | 0 | -2310 | 22310 | 20000 |  |  | 0 |  | 20000 |  | 20000 |  | 0 |  |  |  | This work is now schedule to commence this year and £20k of next year's budget is brought forward to allow this. The total budget alloacted to this project in the 3 year capital programme was £1,000k. However, it is expected that an additional £272k may be required. Approval will be sought form the Council |  | 0 | 0 | 0 | 0 | 0 | 0
32 | Bridge Strengthening | 90 40 1700 |  | 150000 | 0 | 150000 | 437000 |  | 587000 | 126 |  | 126 |  | 587000 |  | 587000 |  | 0 |  |  |  | £450k is alloacted for three bridges in connection with work done on SAK Rail Link. These are Kenneth, Cattlemarket and Helnsfield, all sheduled to comeplete this financail year, although Helensfiled may run on to next year. The balance of £137k is for Shavelgaugh bridge, mainly for preparation work, public liability and survey fees. |  | 150 | 0 | 150 | 400 | 0 | 400 | 0 | 0 | 0
33 | Flood Prevention | 90 40 2700 |  | 100000 | 0 | 100000 | 0 |  | 100000 | 1176 |  | 1176 |  | 100000 |  | 100000 |  | 0 |  |  |  | Main schemes this year, Embankment wall reconstruction on Alva Burn, design of flood prevention scheme Gubber Hill, Alloa, safety measures at trash screens. On target to complete jobs on time |  | 100 | 0 | 100 | 100 | 0 | 100 | 0 | 0 | 0
34 | Retentions |  |  | 60000 | 0 | 60000 | 0 |  | 60000 |  |  | 0 |  | 60000 |  | 60000 |  | 0 |  |  |  | Provision for retentions on previous years' projects. |  | 60 | 0 | 60 | 60 | 0 | 60 | 0 | 0 | 0
35 | Road & Footway Improvements (SRMCS), including town centres | 90 40 3000 |  | 515000 | 0 | 515000 | -31334 |  | 483666 | 4941.49 |  | 4941.49 |  | 483666 |  | 483666 |  | 0 |  |  |  | Part of the budget was utilised in the previous year. This year's budget is earmarked for on A91 carriage way enhamncement (Dollar) and A91 Cowden Bends. |  | 850 | 0 | 850 | 1000 | 0 | 1000 | 0 | 0 | 0
36 | Cycling , Walking ,Safer Streets (CWSS) | 90 40 1310 |  | 84000 | -84000 | 0 |  |  | 0 | 17129.54 |  | 17129.54 |  | 84000 | -84000 | 0 |  | 0 |  |  |  | Main schemes this year are, safety improvements at zebra crossings (£20k), town centre parking and delivery parking Dollar, Tillicoultry and Alva (£29k), speed reduction works Alloa Road, Tullibody (£15k) and pedestrian improvements at Gartmorn / Keilarsbrae, Sauchie (£20k). |  | 84 | 84 | 0 | 86 | 86 | 0 | 0 | 0 | 0
37 | Street Lighting | 90 40 4000 |  | 150000 | 0 | 150000 | 0 |  | 150000 |  |  | 0 |  | 150000 |  | 150000 |  | 0 |  |  |  | Charlie to provide details |  | 150 | 0 | 150 | 165 | 0 | 165 | 0 | 0 | 0
40 | Tullibody By Pass c/f from 2004/05 | 90 40 3900 |  | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0
| A907 | 90 40 1650 |  | 0 | 0 | 0 | 0 |  | 0 | 1128 |  | 1128 |  |  |  | 0 |  | 0 | [5 empty] | 107 | 107 | 0 | 109 | 109 | 0
41 | 20mph speed reduction | 90 40 3200 |  | 107000 | -107000 | 0 | 0 |  | 0 | 103303.4 | -99000 | 4303.4 |  | 107000 | -107000 | 0 |  | 0 |  |  |  | Main schemes this year are 10 new sites for speed reactive warning signs (£25k), pedestrian crossings on B9096 Tullibody Road, Alloa (£30k), traffic calming at level crossing, Cambus (£10k), speed reduction scheme Walker Terrace, Tillicoultry (£42k). |  | 107 | 107 | 0 | 109 | 109 | 0
42 | Footways at Muirside, Tullibody | 90 40 4600 |  | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0
43 | SESTRAN Public Transport & Walking | 90 40 3600 |  | 0 | 0 | 0 | 0 |  | 0 | 0.27 |  | 0.27 |  |  |  | 0 |  | 0 |  |  |  | Alan, Any projects this year |  | 0 | 0 | 0 | 0 | 0 | 0
44 | SESTRAN Public Bus | 90 40 4200 |  | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0
45 | SUSTRAN - Cycle Routes | 90 40 3700 |  | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 |  |  |  | Alan, Any projects this year |  | 0 | 0 | 0 | 0 | 0 | 0
93 | A907 B910 / Helensfield Junction for Railway Line |  |  | 443000 | 0 | 443000 | 0 |  | 443000 |  |  | 0 |  | 20000 |  | 20000 |  | 423000 |  |  |  | Design of new roundabout underway. Timescale may change, originally it was expected that First Nuttall would carry out the works at the same time as their works on Helensfield Rail Bridge and Hilton Road. First Nuttall quote was too high. Job will go to tender but timing will be changed to 2007/08 to avoid First Nuttall works. There may be some cost in 2006/07 e.g. Public Utility diversions, design fees etc. will provide more detail of cost at later CPMG meetings
| Total - Roads & Transportation |  |  | 1709000 | -191000 | 1518000 | 1451356 | 119310 | 3088666 | 621999.71 | -99000 | 522999.71 |  | 2151666 | -191000 | 1960666 |  | 1128000
Environment
46 | Black Devon Landfill | 90 40 0100 | } | 200000 | 0 | 200000 | -101804 |  | 98196 | 5797.4 |  | 5797.4 |  | 98196 |  | 98196 |  | 0 |  |  |  | Wet land area is now substantially complete and is subject of an APSE award. |  | 200 | 0 | 200 | 0 | 0 | 0 | minimal savings >>>>>>>>>>>>>>
47 | Black Devon Landfill Gas Collection & Treatment Project | 90 40 0200 | } | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | [5 empty] | 0 | 0 | 0 | 400 | 0 | 400
53 | Shared Transfer Facility @ Polmaise |  | } | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | [5 empty] | 0 | 0 | 0 | 400 | 0 | 400
48 | Cemeteries Strategy | 90 41 0110 | ] | 200000 | 0 | 200000 | 7708 |  | 207708 | 317 |  | 317 |  | 50700 |  | 50700 |  | 157008 |  |  |  | £50k will be used to tidy up the old cemetery strategy. Tillicoultry work not going ahead - delays in Land purchase. Budget will be carried forward. New Strategy to go to Council. |  | 300 | 0 | 300 | 0 | 0 | 0 | # | # | #
| Sunnyside cemetery Extension | 90 41 0100 | ] | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | # | # | #
| Tullibody Cemetery | 90 41 0130 | ] | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 |  |  |  | 0 |  | 0
49 | Contaminated Land | 90 41 0200 |  | 50000 | -50000 | 0 | 81000 |  | 81000 | 5410.5 | -0.06 | 5410.44 |  | 131000 | -50000 | 81000 |  | 0 |  |  |  | Tenders have gone out for Bankhead depot (£81k). £50 k is for a number of different projects to implement contaminated land startegy (e.g Alva Gas works, Forthbank). |  | 50 | 50 | 0 | 0 | 0 | 0 | Budget already in place for Land Officer
50 | Parks & Open Spaces | 90 41 0400 |  | 80000 | 0 | 80000 | 0 |  | 80000 | 9948 |  | 9948 |  | 80000 |  | 80000 |  | 0 |  |  |  | Currently budget of £80k has been allocated for new fensing, footpaths & treeplanting at Abercromby Park, Tullibody & King George 5th Park , Clackmannan.
51 | Outdoor Play Area Strategy |  |  | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 |  |  |  | 0 |  | 0
54a | Waste Recycling Project |  |  | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 |  |  |  | 0 |  | 0
54b | Wheeled / Litter Bins | 90 45 0230 |  | 135000 | 0 | 135000 | 0 |  | 135000 |  |  | 0 |  | 135000 |  | 135000 |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0
| Gateways & Roundabouts | 90 41 0300 |  |  |  | 0 | 0 |  | 0 |  |  | 0 |  | 40000 |  | 40000 |  | -40000 |  |  |  | The Council approved a budget of £55k in June 2006, to be financed partly (£25k) by capital receipts from sale of land at CarronVale and the balance as an addition to the capital programme for 06/07. Budget has been allocated to enhance roundabouts at Arnsbrae, Menstrie, Muirside & Dumyat. Other sites have been considered with costs liekly to be offset by sponserhip.
| Total - Environment |  |  | 665000 | -50000 | 615000 | -13096 | 0 | 601904 | 21472.9 | -0.06 | 21472.84 |  | 534896 | -50000 | 484896 |  | 117008
Policy & Implementation
55 | Clackmannan Tollbooth | 90 50 3400 |  | 128000 | -71000 | 57000 | -1365 |  | 55635 | 16399.68 |  | 16399.68 |  | 55635 |  | 55635 |  | 0 |  |  |  | Provisionally programmed for current year. Internal assessment of the Cross (Monument) being carried out presently. There were associated difficulties with it being listed. Landscaping work, fabric & remedial work will start in the current year. The total cost of the project s £161k spread over 3 years, grant funded by CHT for £104k and the balance of £57k to be funded by Council, of which £1k was spent last year. |  | 0 | 0 | 0 | 161 | 104 | 57 | # | # | #
56 | National Cycle Route |  |  | 3000 | 0 | 3000 | 59000 |  | 62000 |  |  | 0 |  | 0 |  | 0 |  | 62000 |  |  |  | Complexities of funding from outside bodies, Agricultural Land Act requirements. No grant funding agreed yet. Budget will be carried forward. |  | 3 | 0 | 3 | 0 | 0 | 0 | # | # | #
57 | Old Alloa Townscape Heritage Phase 2 | 90 50 2700 |  | 0 | 0 | 0 | 255150 |  | 255150 |  |  | 0 |  | 0 |  | 0 |  | 255150 |  |  |  | As adivised in the last report, Candleriggs Lane (value £65k) will not proceed now until the envelop work on Kilncraigs' 1936 building is complete, as Lane will be used to access Envelop work. Lime Tree walk delayed by PPP revised programme, siting of building etc. Budget for both programmes will be carried forward, awaiting progress on the other related projects. | Lime tree walk delayed by PPP revised programme | 0 | 0 | 0 | 0 | 0 | 0 | # | # | #
58 | Landscape Partnership - converse Ochills / Hillfoots |  |  | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 |  |  |  | 0 |  | 0
| Old Alloa Townscape Heritage Phase 1 | 90 51 8812 |  | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 |  |  |  | 0 |  | 0
| Kirkgate | 90 51 8808 | [6 empty] | 0 | 16734.45 |  | 16734.45 |  |  |  | 0 |  | 0 |  |  |  | Accrued income from CHT to be obtained from Martin
| Alloa Docks | 90 60 1300 |  | 0 | 0 | 0 | 0 |  | 0 | 22290 |  | 22290 |  |  |  | 0 |  | 0 |  |  |  | Accrued Income - Ninian to invoice Earl of Mar
59 | Core Path network for Access |  |  | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 |  |  |  | 0 |  | 0
67 | CSBP Restructuring |  |  | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
68 | Econ. Dev. Infrastructure: Eastern Clackmannanshire Development Opportunities |  |  | 100000 | 0 | 100000 | 0 |  | 100000 |  |  | 0 |  |  |  | 0 |  | 100000 |  |  |  | Contingency sum for development in East Clackmannanshire awaiting results of meetings with Fife Enterprise. As advised last year, this is unlikely to proceed and the budget will be transferred to other projects yet to be approved by the Council. |  | 0 | 0 | 0 | 161 | 104 | 57 | 0 | 0 | 5
73 | Pavilions Business Park Phase 2 | 90 50 2400 |  | 300000 | 0 | 300000 | 40000 |  | 340000 |  |  | 0 |  | 40000 |  | 40000 |  | 300000 |  |  |  | Ninian, please provide project update |  | 0 | 0 | 0 | 0 | 0 | 0
74 | Dumyat Business Park Phase 3 | 90 50 2800 |  | 0 | 0 | 0 | 40000 |  | 40000 | 0 |  | 0 |  | 0 | 0 | 0 |  | 40000 |  |  |  | Ninian, please provide project update |  | 0 | 0 | 0 | 0 | 0 | 0
| Total - Policy & Implementation |  |  | 531000 | -71000 | 460000 | 392785 | 0 | 852785 | 55424.13 | 0 | 55424.13 |  | 95635 | 0 | 95635 |  | 757150
Property Services
60 | Asbestos Removal | 90 40 3300 |  | 15000 | 0 | 15000 | 0 |  | 15000 |  |  | 0 |  | 15000 |  | 15000 |  | 0 |  |  |  | Gordon, please provide project update for this budget. |  | 15 | 0 | 15 | 0 | 0 | 0
61 | Centralised Kitchen | 90 50 4400 |  | 0 | 0 | 0 | 23782 |  | 23782 | 1233.94 |  | 1233.94 |  | 23782 |  | 23782 |  | 0 |  |  |  | Retentions from previous year. |  | 0 | 0 | 0 | 0 | 0 | 0
62 | Disability Discrimination Act | 90 40 3400 |  | 0 | 0 | 0 | 0 |  | 0 | 2737 |  | 2737 |  |  |  | 0 |  | 0 | [5 empty] | 1 | 0 | 1 | 0 | 0 | 0
63a | Vehicle Replacement Programme (See details below) |  |  | 794000 | 0 | 794000 | 255000 |  | 1049000 | 95591 | 0 | 95591 |  | 989000 |  | 989000 |  | 60000 |  |  |  | Council were advised that £255k would be carried over from last year to oibatin better over all deal. This together with the current year's budget will be utilsed this year, except for £60k which will be carried forward to next year. |  | 794 | 0 | 794 | 570 | 0 | 570
63b | Keilarsbrae land Purchases | 90 40 4300 |  | 0 | 0 | 0 | 11272 |  | 11272 |  |  | 0 |  |  |  | 0 |  | 11272 |  |  |  | Admin & Legal are still investigating legal implications. Unlikely to spend budget this year. |  | 0 | 0 | 0 | 0 | 0 | 0
70 | Kilncraigs Mill 1936 Building Envelop | 90 50 4500 |  | 0 | 0 | 0 | 1289132 |  | 1289132 | 89061.8 |  | 89061.8 |  | 1550000 | -260000 | 1290000 |  | -868 |  |  |  | The Council alloacted a budget of £1,350k of which £ 61k was spent last year on fees. The contract came in at £1,464k. As advised in last report, approach to Historic Scotland for a grant of £260k was successful, to fund the balance of the contract sum plus fees. Retention of £60k will be carried forward to 07/08. Work progressing on site with external envelope including new roof, external rendering windows & glazed canopy at ground level. Completion date is January 2007.
71 | Kilncraigs Mill 1904 Development of 3rd & 4th Floors |  |  | 620000 | 0 | 620000 | 100000 |  | 720000 |  |  | 0 |  | 720000 |  | 720000 |  | 0 |  |  |  | This project was delayed pending decision rom ESEP re. Clawback of ERDF grant implications and future use of 1904 building. Proposal is now for Development & Environment to move to ground, 1st & 2nd floors. The 3rd & 4th floors to be fitted out for SMEs to compoensate clawback. Progress proposals are: Tender issue on 9th Oct; tender acceptance & site start 13th Nov 2006 and completion 2nd April 2007.
72a | Kilncraigs Mill 1904 Access Control & Zoning Services |  |  | 0 | 0 | 0 | 80000 |  | 80000 |  |  | 0 |  | 80000 |  | 80000 |  | 0 |  |  |  | Progressing as part of cotract for 3rd & 4th floor accomodation, but ground, 1st & 2nd floor requirements will be completed by December 2006. |  | 0 | 0 | 0 | 0 | 0 | 0
72b | Kilncraigs Mill Conversion | 90 50 3000 |  | 0 | 0 | 0 | 17000 |  | 17000 |  |  | 0 |  | 17000 |  | 17000 |  | 0 |  |  |  | Retention from previous year |  | 0 | 0 | 0 | 0 | 0 | 0
98 | Kilncraigs Mill 1904 Upgrade of Existing |  |  | 740000 | 0 | 740000 | 0 |  | 740000 |  |  | 0 |  | 350000 |  | 350000 |  | 390000 |  |  |  | Essentail works required for the 1904 building to allow Council occupancy and fit out requirements for SMEs on top two floors. Target programme is a s per project 71 above. Advance work in relation to the ground and second floors including IT upgrading, fire safety imrpovements, DDA compliance and alterations for occupancy to the value of £350k will be completed by January 2007. The balance will be carried forward to 07/08.
99 | Forthbank Accomodation Rationalisation |  |  | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 |  |  |  | 0 |  | 0
| Total - Property Services |  |  | 2169000 | 0 | 2169000 | 1776186 | 0 | 3945186 | 188623.74 | 0 | 188623.74 |  | 3744782 | -260000 | 3484782 |  | 460404
| Total Development & Environmental Services |  |  | 5074000 | -312000 | 4762000 | 3607231 | 119310 | 8488541 | 887520.48 | -99000.06 | 788520.42 |  | 6526979 | -501000 | 6025979 |  | 2462562 | [5 empty] | 3671 | 348 | 3323 | 4321 | 512 | 3809 | -200 | -200 | -195
CORPORATE DEVELOPMENT
64 | Efficient Government/Customer First Developments | 90 70 1900 |  | 100000 | 0 | 100000 | 41000 |  | 141000 |  |  | 0 |  | 141000 |  | 141000 |  | 0 |  |  |  | Proposal is for utlise budget for mobile and remote working. In addition is Joint working goes ahead, there will be need for licensing costs, IDOX, Reveneue & Benefits systems etc. |  | 100 | 0 | 100 | 100 | 0 | 100
65 | IT Services | 90 70 0451 |  | 360000 | 0 | 360000 | 0 |  | 360000 | 51117.61 | 0 | 51117.61 |  | 360000 |  | 360000 |  | 0 |  |  |  | The budget has been earmrked to proactively replace equipment required during the year. |  | 400 | 0 | 400 | 400 | 0 | 400
66a | Finance Services - General Ledger system | 90 70 1125 |  | 30000 | 0 | 30000 | 0 |  | 30000 | 6090.51 |  | 6090.51 |  | 30000 |  | 30000 |  | 0 |  |  |  | Earmarked for new payroll server and ancillary costs and updated strategix system. |  | 30 | 0 | 30 | 30 | 0 | 30
[7 empty] | 0 |  | 0 |  |  | 0 |  |  |  | 0 |  | 0
| Rewiring & IT Cabling of Greenfield | 90 70 2100 |  | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 |  |  |  | 0 |  | 0
| Greenfield Dining Room | 90 70 2500 |  | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 |  |  |  | 0 |  | 0
83 | Greenfield Driveway & Parking |  |  | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 |  |  |  | 0 |  | 0
| Total Corporate Development |  |  | 490000 | 0 | 490000 | 41000 | 0 | 531000 | 57208.12 | 0 | 57208.12 |  | 531000 | 0 | 531000 |  | 0 | [5 empty] | 530 | 0 | 530 | 530 | 0 | 530 | 0 | 0 | 0
CHIEF EXECUTIVE SERVICES
| Miscellaneous |  |  | 0 | 0 | 0 | 0 |  | 0
75 | CCTV - Tron Court & Greenfield | 90 20 0600 |  |  |  | 0 | 53000 |  | 53000 | 147 |  | 147 |  | 53000 |  | 53000 |  | 0 |  |  |  | Going ahead with Cameras in Civic Centre, Tullibody £10k. Bal is unallocated but looking at potential projects. |  | 0 | 0 | 0 | 0 | 0 | 0
76 | DDA & Asbestos Removal | 90 50 4300 |  | 25000 | 0 | 25000 | 19000 |  | 44000 | 37 |  | 37 |  | 44000 |  | 44000 |  | 0 |  |  |  | Gordon Stewart to provide update |  | 25 | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 0
| Mailroom Facilities & Franking Machine | 90 60 1700 |  | 0 | 0 | 0 | 0 |  | 0 | 15838.66 |  | 15838.66 |  | 16000 |  | 16000 |  | -16000 |  |  |  | Budget was approved by Council last year
82 | Council Office Improvements |  |  | 0 | 0 | 0 | 0 |  | 0
| Total Chief Executives Services |  |  | 25000 | 0 | 25000 | 72000 | 0 | 97000 | 16022.66 | 0 | 16022.66 |  | 113000 | 0 | 113000 |  | -16000 | [5 empty] | 25 | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 0
| TOTAL CAPITAL PROGRAMME (excluding SAK Rail Link) |  |  | 11222000 | -1360000 | 9862000 | 5833231 | 254310 | 15949541 | 1748033.38 | -99000.06 | 1649033.32 |  | 9838449 | -1509000 | 8329449 |  | 7620092 | [5 empty] | 13547 | 2444 | 11103 | 13152 | 2702 | 10450 | -200 | -200 | -195
38 | Total SAK Rail Project & Alloa ELR Project Costs | 90 50 3100 |  | 2057000 |  | 2057000 | -1132000 | -110000 | 815000 | 17125425.96 | -22373421.58 | -5247995.62 |  | 815000 |  | 815000 |  | 0 |  |  |  | Budget only shows the Council contribution here. As advised previously , the maximum Council Contribution of £2.5m directly related to the Rail Link has been agreed. Of this the Council has already made a contribution of £1.575m in the past four years, leaving a balance of £925k. The latest projections indicate that the Council will make a contribution of £815k this year and the remaining £110k in 07/08 |  | 750 | 712 | 38 | 0 | 0 | 0 | -20 | -20 | -20
| TOTAL CAPITAL PROGRAMME (including SAK Rail Link) |  |  | 13279000 | -1360000 | 11919000 | 4701231 | 144310 | 16764541 | 18873459.34 | -22472421.64 | -3598962.3 |  | 10653449 | -1509000 | 9144449 |  | 7620092
| UNALLOCATED FUNDING | [28 empty] | Key for Recurring Revenue Costs Section
77 | Capital Receipts Estimate (see details below) | 90 90 xxxx |  | -1085000 |  | -1085000 |  |  | -1085000 | 119.07 | -154.32 | -35.25 |  | -500000 |  | -500000 |  | -585000 |  |  |  | Apart from the two main receipts identidied below, the only other capital receipts expected this year is in respect of two properties which is still subject to discussion. If successful, the slaes may realise about £500k. The CAMP team are regularly reveiwng the rationalisation of Council properties and further updates will be given in future reports. |  |  |  | 300 |  |  | 300
78 | Sale of Land at Dumyat Park & Ditch for Tullibody By Pass |  | } | 0 | 0 | 0 | -1550000 |  | -1550000 |  |  | 0 |  | -1395000 |  | -1395000 |  | -155000 |  |  |  | The sale of Land @ rear of St. Mungo's is due to be completed on 22nd August. However, discussins are still on-going rearding Dumyat Park & Ditch. As advised previously there are issues regarding abnormanl site conditions. The sellers have appointed engineers who are examining the site. Also, there are on going discussions with Scottish Water on re-routing of quest pipe. There will be additonal costs in the region of £250k becuase of abnormal ground conditions & quest pipe re-routing. The net anticipated receipts for both lands is £3.145m. Of this £1.75m has been earmarked for the schools' PPP project as advised previiously, leaving a balance of £1.395m for the 06/07 capital programme. This is a decrease of £155k on the original estimate. |  |  |  | 0
78 | Sale of Land to rear of St.Mungo's |  | } | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | [7 empty] | 0
80 | ERDF Grants (from Kilncraigs to be used to refund extra s94 advance in previous years) |  |  | -119000 | 0 | -119000 | 0 |  | -119000 |  |  | 0 |  | -119000 |  | -119000 |  | 0 |  |  |  | These are retained ERDF Grants in respect of Kilncarigs, Allow Harbour, Alloa Tower & Allow West projects awaiting final audit which KPMG have almost completed. Retained grants will be released by Scottish Executive on satisfactory audit report. |  |  |  | 0 |  |  |  | Blank cells = | no info from service
81 | Repayment from Schools Devolved Budget for Computer Equipment | 90 10 4500 |  | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | [7 empty] | 0
[7 empty] | 0 |  | 0 |  |  | 0 |  |  |  | 0 |  | 0
|  |  |  | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 |  |  |  | 0 |  | 0
|  |  |  | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 |  |  |  | 0 |  | 0
| TOTAL - ESTIMATED UNALLOCATED FUNDING |  |  | -1204000 | 0 | -1204000 | -1550000 | 0 | -2754000 | 119.07 | -154.32 | -35.25 |  | -2014000 | 0 | -2014000 |  | -740000 | [7 empty] | 300 |  |  | 300
1
NET FUNDING (SURPLUS) / DEFICIT
FINANCED BY C.F.C.R.
Net Capital Programme
[6 empty] | 10715000 | 3151231 | 144310 | 14010541 | 18873578.41 | -22472575.96 | -3598997.55 |  | 8639449 | -1509000 | 7130449 |  | 6880092 | [7 empty] | 10803 |  |  | 10150
DETAILS PROPERTY CAPITAL RECEIPTS
77 | 22/4 Candleriggs, Alloa | 9090 6800 | [9 empty] | 0 |  |  |  | 0
77 | Skip Site - Hallpark, Sauchie | 9090 0726 | [9 empty] | 0 |  |  |  | 0
77 | Dewar St, Lorne Lane , Dollar | 9090 0800 | [9 empty] | 0 |  |  |  | 0
77 | Collyland - Fishcross | 9070 1700 | [9 empty] | 0 |  |  |  | 0
77 | Cowan Terrace Dollar | 9090 0875 | [9 empty] | 0 |  |  |  | 0
77 | Candleriggs, Alloa | 9090 0950 | [9 empty] | 0 |  |  |  | 0
77 | General Receipts | 9090 1000 | [9 empty] | 0 |  |  |  | 0
77 | Alexandra Street, Devonside | 9090 2200 | [9 empty] | 0 |  |  |  | 0
77 | Gap Site - Drysdale/Mill Street | 9090 1050 | [9 empty] | 0 |  |  |  | 0
77 | Bedford Place Alloa | 9090 1100 | [9 empty] | 0 |  |  |  | 0
77 | Bedford House - Alloa | 9090 1125 | [9 empty] | 0 |  |  |  | 0
77 | Cowden Park Alloa | 9090 1175 | [9 empty] | 0 |  |  |  | 0
77 | Forestmill Primary School | 9090 1325 | [9 empty] | 0 |  |  |  | 0
77 | Former School Clackmannan | 9090 1400 | [9 empty] | 0 |  |  |  | 0
77 | Orchard Tullibody - Housing Land | 9090 1525 | [9 empty] | 0 |  |  |  | 0
77 | Alloa West | 9090 0550 | [9 empty] | 0 |  |  |  | 0
77 | Alloa West - Autism Site | 9090 5800 | [9 empty] | 0 |  |  |  | 0
77 | Menstrie Centre Playground | 9090 1600 | [9 empty] | 0 |  |  |  | 0
77 | Collyland Road - Fishcross Housing Site | 9090 1700 | [9 empty] | 0 |  |  |  | 0
77 | Shops - Sauchie | 9090 1850 | [9 empty] | 0 |  |  |  | 0
77 | Kirkgate - Alloa | 9090 2100 | [9 empty] | 0 |  |  |  | 0
77 | Alexandra Street, Devonside | 9090 2200 | [9 empty] | 0 |  |  |  | 0
77 | Long Row Menstrie - Land | 9090 2700 | [9 empty] | 0 |  |  |  | 0
77 | Mar Place Sauchie WC | 9090 2800 | [9 empty] | 0 |  |  |  | 0
77 | 5 Muirside Road, Tullibody | 9090 3025 | [9 empty] | 0 |  |  |  | 0
77 | Park Street, Alva | 9090 3500 | [9 empty] | 0 |  |  |  | 0
77 | Bankhead - Devon Village | 9090 6100 | [9 empty] | 0 |  |  |  | 0
77 | Claremont Business Centre | 9090 1025 | [9 empty] | 0 |  |  |  | 0
77 | Dumyat Business Park | 9090 7000 | [9 empty] | 0 |  |  |  | 0
77 | Dumyat Business Park - Belhaven Breweries | 9090 7400 | [9 empty] | 0 |  |  |  | 0
77 | Earlsfield/Alloa Park | 9090 1750 | [9 empty] | 0 |  |  |  | 0
77 | Fishcross - Devon Riding Centre | 9090 6900 | [8 empty] | -154.32 | -154.32 |  |  |  | 0
77 | Land - Ochilvale Mill Alva | 9090 3900 | [9 empty] | 0 |  |  |  | 0
77 | St Mungos Wynd Alloa | 9090 4000 | [9 empty] | 0 |  |  |  | 0
77 | 28 Ramsay Street, Clackmannan | 9090 4100 | [9 empty] | 0 |  |  |  | 0
77 | Old Toll House, Muckhart | 9090 4200 | [9 empty] | 0 |  |  |  | 0
77 | Main St Coalsnaughton | 9090 4300 | [9 empty] | 0 |  |  |  | 0
77 | Baingle Crescent | 9090 4400 | [9 empty] | 0 |  |  |  | 0
77 | Gas Governor at the Baingle | 9090 4500 | [9 empty] | 0 |  |  |  | 0
77 | Fairfield Sauchie | 9090 4600 | [9 empty] | 0 |  |  |  | 0
77 | Scout Hall Main Street Sauchie | 9090 4700 | [9 empty] | 0 |  |  |  | 0
77 | 3/5 Lower Mains Dollar | 9090 4800 | [9 empty] | 0 |  |  |  | 0
77 | Railway Station Alloa Road | 9090 4900 | [9 empty] | 0 |  |  |  | 0
77 | Land at Shawpark garage | 9090 5000 | [9 empty] | 0 |  |  |  | 0
77 | Service Station Site / Ditch Farm | 9090 5100 | [9 empty] | 0 |  |  |  | 0
77 | Pavilions Phase 2 | 9090 5200 | [9 empty] | 0 |  |  |  | 0
77 | TOMA CPO | 9090 5300 | [9 empty] | 0 |  |  |  | 0
77 | Sinclairs Haulage - Land | 9090 5400 | [9 empty] | 0 |  |  |  | 0
77 | Alva House Stable Block | 9090 5500 | [9 empty] | 0 |  |  |  | 0
77 | 3/5 Henderson Avenue, Alloa | 9090 5600 | [9 empty] | 0 |  |  |  | 0
77 | Land at Rear 78/80 West Stirling Street Alva | 9090 5700 | [9 empty] | 0 |  |  |  | 0
77 | Fishcross - Land at Devonbank Cottage | 9090 7100 | [9 empty] | 0 |  |  |  | 0
77 | Washington House - Alva | 9090 5900 | [9 empty] | 0 |  |  |  | 0
77 | 23 Main Street Sauchie | 9090 6000 | [9 empty] | 0 |  |  |  | 0
77 | Bank Head, Devon Village Rescue | 9090 6100 | [9 empty] | 0 |  |  |  | 0
77 | Smithfield Loan - Railway Embankment | 9090 6200 | [9 empty] | 0 |  |  |  | 0
77 | Superiority - Smithfield Loan | 9090 6300 | [9 empty] | 0 |  |  |  | 0
77 | Land at Broad Street, Alloa | 9090 6400 | [9 empty] | 0 |  |  |  | 0
77 | Land for Access to Stirling St | 9090 6500 | [9 empty] | 0 |  |  |  | 0
77 | Garage Site Gartmorn Dam House | 9090 6600 | [9 empty] | 0 |  |  |  | 0
77 | Lochy Falls,15 Upper Hillfoot, Dollar | 9090 6700 | [9 empty] | 0 |  |  |  | 0
77 | Former Toilets - Alva | 9090 7800 | [9 empty] | 0 |  |  |  | 0
77 | Hillpark | 9090 3700 | [9 empty] | 0 |  |  |  | 0
77 | Hallpark/Main Street Sauchie | 9090 0700 | [9 empty] | 0 |  |  |  | 0
77 | Land at Park St Tillicoultry | 9090 7300 | [9 empty] | 0 |  |  |  | 0
77 | Land/Car Park - Erskine ST Alloa | 9090 3800 | [9 empty] | 0 |  |  |  | 0
77 | Housing Land The Orchard Tullibody | 9090 1525 | [9 empty] | 0 |  |  |  | 0
77 | Property Conversion Feasibility Study | 9090 7200 | [9 empty] | 0 |  |  |  | 0
77 | Former Thistle Brewery | 9090 7700 | [9 empty] | 0 |  |  |  | 0
77 | Tullis Factory | 9090 1575 | [7 empty] | 119.07 |  | 119.07 |  |  |  | 0
77 | Sale of Land at Tullibody (Ditch Farm) | 9090 5100 | [9 empty] | 0 |  |  |  | 0
77 | Other | [10 empty] | 0 |  |  |  | 0
0
| Total - Property Sales | [8 empty] | 119.07 | -154.32 | -35.25 |  | 0 | 0 | 0
DETAILS VEHICLE REPLACEMENT PROGRAMME
63a | DLO Vehicle - Property Contracts | 9045 0100 |  | 222000 |  | 222000 | 30000 |  | 252000
63a | DLO Vehicle - Refuse Collection | 9045 0110 |  | 273000 |  | 273000 | 130000 |  | 403000 | 80575 |  | 80575 |  |  |  | 0 |  | 322425
63a | DLO Vehicle - Street Cleaning | 9045 0120 |  | 70000 |  | 70000 |  |  | 70000
63a | DLO Vehicle - Land Services | 9045 0130 |  | 192600 |  | 192600 | 62000 |  | 254600 | 15016 |  | 15016
63a | DLO Vehicle - Roads Contracts | 9045 0140 |  | 120000 |  | 120000 | 31000 |  | 151000
63a | DLO Vehicle - Catering Services | 9045 0150 |  |  |  | 0 |  |  | 0
63a | DLO Vehicle - Transport Pool | 9045 0160 |  | 36000 |  | 36000 |  |  | 36000
63a | DLO Vehicle - Leisure | 9045 0170 |  |  |  | 0 |  |  | 0
63a | DLO Vehicle - Social Services | 9045 0200 |  |  |  | 0 |  |  | 0
63a | DLO Vehicle - Burial Services | 9045 0210 |  | 33250 |  | 33250 |  |  | 33250
63a | DLO Vehicle - Countryside Rangers | 9045 0220 |  |  |  | 0 |  |  | 0
63a | DLO Vehiclt - G F Housing | 9045 0225 |  |  |  | 0 |  |  | 0
| Glenochil Nursery |  |  | 1800 |  | 1800 |  |  | 1800
| Chief Executive |  |  | 11250 |  | 11250 |  |  | 11250
| Black devon |  |  | 26000 |  | 26000 |  |  | 26000
|  |  |  | -191900 |  | -191900 | 2000 |  | -189900
| Total - Vehicle Programme |  |  | 794000 | 0 | 794000 | 255000 |  | 1049000 | 95591 | 0 | 95591 |  | 0 | 0 | 0
Note on Z96: Authorised User: contractor August Sept on site November and spend third year subject to positive response from PPP

## Appd 1 GSC 06-09 to 31-7-06
| 0 |  |  | OK |  | OK |  |  | OK |  |  | OK |  | Out-Turn Out |  | OK
1 | 2 |  |  | 4 | 5 | 6 |  |  |  | 7 | 8 | 9 | 9 | 10 | 11 | 12 | 10 | 13 |  |  |  | 14 | 15 | 16 | 17 | 10 | 11 | 12 | 13 | 14 | 15 | 16
|  | Ledger codes |  | BUDGET 2005/06 | [9 empty] | Out-turn as at July 2005 | [7 empty] | Project Status as at Mid August 2005 |  |  |  |  | 2006/07 |  |  | 2007/08 |  |  | Recurring Revenue consequences
for the proposed project
| General Services Capital Programme 2006/07 to 2008/09 |  |  | APPROVED BUDGET 2006/07 |  |  | 2006/07 |  |  | ACTUAL for year to 31st July 2006 |  |  |  | 06/07 Out-turn reported at as at 14/8/06 |  |  |  |  | Approved budget for 2007/08 Borrowing (Council Contribution) | Approved budget for 2008/09 Borrowing (Council Contribution) | Total for 3 years Borrowing (Council Contribution) | Project Status as at Mid July 2006 |  |  |  |  | (See Appendix 3) |  |  | (See Appendix 4)
|  |  |  | Approved Budget | External Grants | Borrowing (Council Contribution) | Projects transferred from / (to) 05/06 | Projects transferred from 07/08 | Revised Borrowing (Council Contribution) | Total Expenditure | Total Income | Borrowing (Council Contribution) |  | Total Expenditure | Total Income | Borrowing (Council Contribution) |  | Variance on 06/07 Budget |  |  |  | Tenders issued / received | Contractor Appointed | Project start date |  | If project is delayed to next year, proposal to bring forward project from 3 year approved programme | Gross | External Grants | Net (Council Contribution) | Gross | External Grants | Net (Council Contribution)
|  |  |  | Gross |  | Net |  |  |  | Gross |  | Net |  |  |  | Net | [16 empty] | 2004/05 | 2005/06 | 2006/07
| Service / Project Name |  |  | £ | £ | £ | £ | £ | £ | £ | £ | £ |  | £ | £ | £ |  | £ | £ | £ | £ | [5 empty] | £'000 | £'000 | £'000 | £'000 | £'000 | £'000
SERVICES TO PEOPLE
EDUCATION & COMMUNITY SERVICES
1,3,5 | PPP Capital Support | 90 10 7000 |  | 3450000 | 0 | 3450000 | 1200000 |  | 4650000 |  |  | 0 |  | 0 | 0 | 0 |  | 4650000 | 3600000 | 3500000 | 11750000 |  |  |  | As advised in previous report, in accordance with proper accounting practice, transfers of PPP budgets to a sinking fund cannot be capitalised currently for which no asset exits. These budgets will be carried forward to future years to be offset against unitary charges as and when the payments become due. |  | 1050 | 0 | 1050 | 1000 | 0 | 1000
17 | Primary & Nursery School Developments - Allocated to PPP |  |  | 0 | 0 | 0 | 175000 |  | 175000 |  |  | 0 |  |  |  | 0 |  | 175000 |  |  | 175000 |  |  |  | As above |  | 300 | 0 | 300 | 300 | 0 | 300
17 | Primary & Nursery School Developments |  |  | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 |  | 1000000 | 1000000 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0
4 | DDA Compliance | 90 10 6000 | } | 0 | 0 | 0 | 133000 |  | 133000 | 23423.4 |  | 23423.4 |  | 133000 |  | 133000 |  | 0 |  |  | 133000 |  |  |  | The budget, which was carried forward from last year, is made up of a number of small projects. Some of them have been completed over the summer holidays. Further projects will be commissioned to utilise the funding available during the year. Spend on Accessibility Strategy is treated as part of DDA project. |  | 100 | 0 | 100 | 0 | 0 | 0
| Accessibility Strategy | 90 10 6100 | } |  |  | 0 |  |  | 0 | 1212.97 |  | 1212.97 |  |  |  | 0 |  | 0
7 | Museum & Heritage Centre | 90 10 5800 |  |  | 0 | 0 | 250000 |  | 250000 |  |  | 0 |  |  |  | 0 |  | 250000 |  |  | 250000 |  |  |  | The budget will need to be carried forward. See details given in 11 below. |  | 0 | 0 | 0 | 0 | 0 | 0
8 | School Building Alarm Systems | 90 10 5700 |  | 10000 | 0 | 10000 | 294000 |  | 304000 | 1382 |  | 1382 |  | 304000 |  | 304000 |  | 0 | 8000 |  | 312000 |  |  |  | The bulk of the work was completed over the summer period. Final certificates will be processed in due course and the budget will be spent this year. |  | 300 | 0 | 300 | 8 | 0 | 8 | some maintenance but reduction in insurance
85,86 | ICT Hardware Replacement in Sec Schls & New IT Installation in Schools | 90 10 0440 |  | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 |  | 600000 | 600000 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0
9 | Schools Fund | 90 10 4900 |  | 1008000 | -1008000 | 0 | 0 |  | 0 | 457389.12 |  | 457389.12 |  | 1008000 | -1008000 | 0 |  | 0 | [6 empty] | Major works at Deerpark / Lochies, Park PS, Coalsnaughton PS, Tillicoultry PS, Menstrie PS have been completed or nearly completed (in the case of Park PS) over the vacation. Once the final costs are available, any remaining funds will be used to tackle other projects. |  | 1008 | 1008 | 0 | 1055 | 1055 | 0
10 | Tulligarth Sports Resurfacing - requirement of Lottery funding |  |  | 0 |  | 0 | 0 |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 40000 |  | 40000
11 | Alloa Library Refurbishment |  |  | 0 | 0 | 0 | 100000 |  | 100000 |  |  | 0 |  |  |  | 0 |  | 100000 |  |  | 100000 |  |  |  | The Service will not spend any of this funding in this year because of the ongoing discussions about the wider issues of Alloa Town Centre Regeneration. There are on going discussions on how to best develop the Library provision and to link this with the current rationalisation of Council buildings , including the development of Museum & Heritage Centre and accommodation moves to Kilncraigs. All of these proposals are being considered by the Capital Asset Management & Planning Team (CAMP) and will have a direct impact on the development of the Library provision. |  | 100 | 0 | 100 | 0 | 0 | 0
13 | Heavy Equipment in Secondary Schools - Kilns etc | 90 10 6600 |  | 0 | 0 | 0 | 60000 |  | 60000 | 40470 |  | 40470 |  | 40470 |  | 40470 |  | 19530 |  |  | 40470 |  |  |  | Both projects are now complete and the balances are off-set against eachother , with a slight overspend of £530. The £60k budget for 07/08 was travsferred to 05/06. |  | 30 | 0 | 30 | 30 | 0 | 30
14 | IT Hardware Replacement in Schools | 90 10 6700 |  | 100000 | -40000 | 60000 | -139000 | 60000 | -19000 |  |  | 0 |  | 0 |  | 0 |  | -19000 | 60000 |  | 41000 | [5 empty] | 100 | 40 | 60 | 100 | 40 | 60
15 | Legal Commitments - for projects undertaking in 04/05 | 90 10 6900 |  | 25000 | 0 | 25000 | 0 |  | 25000 | 1586.49 |  | 1586.49 |  | 25000 |  | 25000 |  | 0 | 25000 | 50000 | 100000 |  |  |  | This is provision for retentions for previous projects which has been overspent, to enable all retentions to be paid . |  | 25 | 0 | 25 | 25 | 0 | 25
16 | Leisure Bowl - refurbishment | 90 15 0100 |  | 200000 | 0 | 200000 | -14000 | 75000 | 261000 | 237327.62 |  | 237327.62 |  | 261000 |  | 261000 |  | 0 | 75000 | 150000 | 486000 |  |  |  | Due to the decision to refurbish M&E and plant at Alloa Leisure Bowl in the current financial year, the spending profile this year is £260k. £14k was spent last year, bringing the total spend to £274k. The funding for this is £200k allocated this year and £75k brought forward from 07/08 to 06/07. |  | 200 | 0 | 200 | 75 | 0 | 75
87-91 | Future Developments |  |  | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 |  | 1050000 | 1050000
19 | Fir Park Ski Centre - upgrade to building | 90 10 5200 |  | 0 | 0 | 0 | 0 |  | 0 | 815.6 |  | 815.6 |  |  |  | 0 |  | 0 | [6 empty] | Most of these are retentions to be met from legal commitments budget. See 15 above. |  | 0 | 0 | 0 | 0 | 0 | 0
| NOF & Sports Muchart Primary School | 90 10 5100 |  | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 |  |  |  | 0 |  | 0
| NOF & Sports Strathdevon & Clackmannan | 90 10 5300 |  | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 |  |  |  | 0 |  | 0
| Family Centre - Newmills | 90 10 3700 |  | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0
| Property Enhancement general | 90 10 2000 |  | 0 | 0 | 0 | 0 |  | 0 | 3402.5 |  | 3402.5 |  |  |  | 0 |  | 0 | [8 empty] | 5613 | 1048 | 4565 | 5233 | 1095 | 4138
| School Building Improvement | 90 10 4400 |  | 0 | 0 | 0 | 0 |  | 0 | 226.5 |  | 226.5 |  |  |  | 0 |  | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0
| SEN Adaptation | 90 10 0901 |  | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0
| Total Education & Community Service |  |  | 4793000 | -1048000 | 3745000 | 2059000 | 135000 | 5939000 | 767236.2 | 0 | 767236.2 |  | 1771470 | -1008000 | 763470 |  | 5175530 | 3808000 | 6350000 | 16077470 | [5 empty] | 8826 | 2096 | 6730 | 7826 | 2190 | 5636 | 0 | 0 | 0
SOCIAL SERVICES
20 | DDA Compliance |  |  | 20000 | 0 | 20000 | 16000 |  | 36000 |  |  | 0 |  | 36000 |  | 36000 |  | 0 |  |  | 36000 |  |  |  | Earmarked for Alloa Centre & plans have been drawn. However, the project is awaiting approval as the CAMP team carry out further assessment |  | 20 | 0 | 20 | 0 | 0 | 0
21 | Joint FVNHS/ Adult Care Premises Occupation |  |  | NK | NK | NK | NK |  | NK |  |  | 0 |  |  |  | 0 |  |  |  | 50000 | 50000 | [5 empty] | NK | NK | NK | NK | NK | NK
22 | Menstrie House En-Suite Conversion | 90 30 0350 |  | 800000 | 0 | 800000 | 38000 |  | 838000 | 17629.11 |  | 17629.11 |  | 838000 |  | 838000 |  | 0 | 150000 |  | 988000 |  |  |  | Originally a total budget of £1m was allocated to this project. The Council approved a further £400k in May bringing the total to £1.4m. Of this £12k was spent last year. It is anticipated that £838k will be spent this year and £515k next year on completion, with a retention of £35k in 08/09. |  | 475 | 0 | 475 | 475 | 0 | 475
| Menstrie House External Works & Telephone system | 90 30 1500 |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0
| Menstrie House | 90 30 1500 | [6 empty] | 0 | 1807 |  | 1807 |  |  |  | 0 |  | 0
23 | Ludgate House External Fabric | 90 30 1600 |  | 20000 | 0 | 20000 | 0 |  | 20000 |  |  | 0 |  | 20000 |  | 20000 |  | 0 |  |  | 20000 |  |  |  | Mainly enhancement works earmarked to be completed this year |  | 0 | 0 | 0 | 0 | 0 | 0
24 | Mental Health Services - Retentions | 90 30 1700 |  |  | 0 | 0 | 0 |  | 0 | 178.06 |  | 178.06 |  | 1000 |  | 1000 |  | -1000 |  |  | 1000 |  |  |  | Small retentions from previous year |  | 0 | 0 | 0 | 0 | 0 | 0
66b | Ludgate Traffic Management - Retentions | 90 30 1900 |  |  | 0 | 0 | 0 |  | 0 | 431.75 |  | 431.75 |  | 1000 |  | 1000 |  | -1000 |  |  | 1000
| Total Social Services |  |  | 840000 | 0 | 840000 | 54000 | 0 | 894000 | 20045.92 | 0 | 20045.92 |  | 896000 | 0 | 896000 |  | -2000 | 150000 | 50000 | 1096000 | [5 empty] | 495 | 0 | 495 | 475 | 0 | 475 | 0 | 0 | 0
DEVELOPMENT & ENVIRONMENTAL SERVICES
Roads & Transportation
26 | Accident Prevention & Traffic Management | 90 40 1020 |  | 100000 | 0 | 100000 | 0 |  | 100000 | 3113.73 |  | 3113.73 |  | 100000 |  | 100000 |  | 0 | 100000 | 100000 | 300000 |  |  |  | The current year's budget will be spent on three main projects, Tullibody Cross mini-roundabouts and pedestrian facilities (£45k), road safety improvements at A91 Tait’s Tomb and Cowden Bends (£45k) and Dollar, Fishcross and Coalsnaughton village gateways (£10k). Details for 07/08 & 08/09 will be provided in future reports. |  | 100 | 0 | 100 | 100 | 0 | 100 | 0 | 0 | 0
27 | Alloa Town Centre | 90 40 1750 |  | 0 | 0 | 0 | 705000 |  | 705000 | 231584.86 |  | 231584.86 |  |  |  | 0 |  | 705000 |  |  | 705000 |  |  |  | Project involves three phases at different timescales to co-ordinate the public ways with Asda and the SAK Rail project. Council Contribution approved is £758k of which £53k was spent last year. Asda has contributed £606k. Phase 1 (Drysdale St/ Shillinghill to Ring Road will be completed end of slept 2006; Phase 2 (Ring Road to Station Sq to complete in November 2006; Phase 3 (Station Sq is dependent on completion of Rail Station. It is anticipated the balance of the Council contribution of £708k will be used this year, however, any unused budget will be carried forward. |  | 0 | 0 | 0 | 0 | 0 | 0 | -200 | -200 | -200
28 | A91 East Stirling St. Alva Roundabout to access new school site |  |  | 0 | 0 |  | 0 |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 225000 |  | 225000
31a | B9140/ Collylands Cross Upgrade | 90 40 4500 |  | 0 | 0 | 0 | 343000 | 97000 | 440000 | 259496.42 |  | 259496.42 |  | 440000 |  | 440000 |  | 0 | 100000 |  | 540000 |  |  |  | In order to complete this project in the current year, 2007/08 budget is brought forward. There may be a slight overspend of £7k according to the latest projections. |  | 600 | 0 | 600 | 500 | 0 | 500 | 0 | 0 | 0
31b | B9140 Realignment of Bends |  |  | 0 | 0 | 0 | -2310 | 22310 | 20000 |  |  | 0 |  | 20000 |  | 20000 |  | 0 | 500000 | 500000 | 1020000 |  |  |  | This work is now scheduled to commence this year and £20k of 07/08 budget is brought forward to allow this. The total budget allocated to this project in the 3 year capital programme was £1,000k. However, it is expected that an additional £772k may be required. Approval will be sought from the Council |  | 0 | 0 | 0 | 0 | 0 | 0
32 | Bridge Strengthening | 90 40 1700 |  | 150000 | 0 | 150000 | 437000 |  | 587000 | 126 |  | 126 |  | 587000 |  | 587000 |  | 0 | 400000 | 150000 | 1137000 |  |  |  | £450k is allocated for three bridges in connection with work done on SAK Rail Link. These are Kennet, Cattlemarket and Helensfield, all scheduled to be completed this financial year, although Helensfield may run on to next year. The balance of £137k is for Shavelhaugh bridge, mainly for design preparation work, public utilities and survey fees. Plans for 07/08 & 08/09 budgets will be provided in future reports. |  | 150 | 0 | 150 | 400 | 0 | 400 | 0 | 0 | 0
33 | Flood Prevention | 90 40 2700 |  | 100000 | 0 | 100000 | 0 |  | 100000 | 1176 |  | 1176 |  | 100000 |  | 100000 |  | 0 | 100000 | 100000 | 300000 |  |  |  | Main schemes this year, Embankment wall reconstruction on Alva Burn, design of flood prevention scheme Gubber Hill, Alloa, safety measures at trash screens. On target to complete jobs on time. Plans for 07/08 & 08/09 budgets will be provided in future reports. |  | 100 | 0 | 100 | 100 | 0 | 100 | 0 | 0 | 0
34 | Retentions |  |  | 60000 | 0 | 60000 | 0 |  | 60000 |  |  | 0 |  | 60000 |  | 60000 |  | 0 | 60000 | 60000 | 180000 |  |  |  | Provision for retentions on previous years' projects. |  | 60 | 0 | 60 | 60 | 0 | 60 | 0 | 0 | 0
35 | Road & Footway Improvements (SRMCS), including town centres | 90 40 3000 |  | 515000 | 0 | 515000 | -31334 |  | 483666 | 4941.49 |  | 4941.49 |  | 483666 |  | 483666 |  | 0 | 500000 | 500000 | 1483666 |  |  |  | Part of the budget was utilised in the previous year. This year's budget is earmarked for A91 carriageway enhancement at Tate's Tomb and A91 Cowden Bends. |  | 850 | 0 | 850 | 1000 | 0 | 1000 | 0 | 0 | 0
36 | Cycling , Walking ,Safer Streets (CWSS) | 90 40 1310 |  | 84000 | -84000 | 0 |  |  | 0 | 17129.54 |  | 17129.54 |  | 84000 | -84000 | 0 |  | 0 | [6 empty] | Main schemes this year are, safety improvements at zebra crossings (£20k), town centre parking and delivery parking Dollar, Tillicoultry and Alva (£29k), speed reduction works Alloa Road, Tullibody (£15k) and pedestrian improvements at Gartmorn / Keilarsbrae, Sauchie (£20k). Project is fully funded. |  | 84 | 84 | 0 | 86 | 86 | 0 | 0 | 0 | 0
37 | Street Lighting | 90 40 4000 |  | 150000 | 0 | 150000 | 0 |  | 150000 |  |  | 0 |  | 150000 |  | 150000 |  | 0 | 165000 | 185000 | 500000 |  |  |  | Contractor appointed and work in progress - completion September 2006. Schemes include Main Street, Sauchie; Newmills, Tullibody (Phase 1); Forthvale & Elmbank, Menstrie; Parkway/Sunnyside Road, Alloa. Plans for 07/08 & 08/09 budgets will be provided in future reports. |  | 150 | 0 | 150 | 165 | 0 | 165 | 0 | 0 | 0
40 | Tullibody By Pass c/f from 2004/05 | 90 40 3900 |  | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0
| A907 | 90 40 1650 |  | 0 | 0 | 0 | 0 |  | 0 | 1128 |  | 1128 |  |  |  | 0 |  | 0 | [8 empty] | 107 | 107 | 0 | 109 | 109 | 0
41 | 20mph speed reduction | 90 40 3200 |  | 107000 | -107000 | 0 | 0 |  | 0 | 103303.4 | -99000 | 4303.4 |  | 107000 | -107000 | 0 |  | 0 | [6 empty] | Main schemes this year are 10 new sites for speed reactive warning signs (£25k), pedestrian crossings on B9096 Tullibody Road, Alloa (£30k), traffic calming at level crossing, Cambus (£10k), speed reduction scheme Walker Terrace, Tillicoultry (£22k) and Smithfield Loan (£20k). Project is fully funded. |  | 107 | 107 | 0 | 109 | 109 | 0
42 | Footways at Muirside, Tullibody | 90 40 4600 |  | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0
43 | SESTRAN Public Transport & Walking | 90 40 3600 |  | 0 | 0 | 0 | 0 |  | 0 | 0.27 |  | 0.27 |  |  |  | 0 |  | 0 | [6 empty] | This will be spent on, new Puffin Crossings on Ring Road, Alloa (£40k), upgrade of Waggon Way, Alloa to link Mixed leisure route and National Cycle Route (£120k), resurfacing and new parking at bus station Murray Square, Tillicoultry (£40k) and junction / bus stop improvements, The Glen, Devonside (£20k). The project will be fully funded by capital grants. |  | 0 | 0 | 0 | 0 | 0 | 0
44 | SESTRAN Public Bus | 90 40 4200 |  | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0
45 | SUSTRAN - Cycle Routes | 90 40 3700 |  | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0
93 | A907 B910 / Helensfield Junction for Railway Line |  |  | 443000 | 0 | 443000 | 0 |  | 443000 |  |  | 0 |  | 20000 |  | 20000 |  | 423000 | 7000 |  | 450000 |  |  |  | Design of new roundabout underway. Timescale may change, originally it was expected that First Nuttall would carry out the works at the same time as their works on Helensfield Rail Bridge and Hilton Road. First Nuttall quote was too high. Job will go to tender but timing will be changed to 2007/08 to avoid First Nuttall works. There may be some cost in 2006/07 e.g. Public Utility diversions, design fees etc. More detail of cost will be provided at later CPMG meetings
| Total - Roads & Transportation |  |  | 1709000 | -191000 | 1518000 | 1451356 | 119310 | 3088666 | 621999.71 | -99000 | 522999.71 |  | 2151666 | -191000 | 1960666 |  | 1128000 | 2157000 | 1595000 | 6840666
Environment
46 | Black Devon Landfill | 90 40 0100 | } | 200000 | 0 | 200000 | -101804 |  | 98196 | 5797.4 |  | 5797.4 |  | 98196 |  | 98196 |  | 0 |  |  | 98196 |  |  |  | Landfill site restored and wet land area substantially complete. The project has been short listed for an APSE award. |  | 200 | 0 | 200 | 0 | 0 | 0 | minimal savings >>>>>>>>>>>>>>
47 | Black Devon Landfill Gas Collection & Treatment Project | 90 40 0200 | } | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 400000 |  | 400000 | [5 empty] | 0 | 0 | 0 | 400 | 0 | 400
53 | Shared Transfer Facility @ Polmaise |  | } | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | [8 empty] | 0 | 0 | 0 | 400 | 0 | 400
48 | Cemeteries Strategy | 90 41 0110 | ] | 200000 | 0 | 200000 | 7708 |  | 207708 | 317 |  | 317 |  | 50700 |  | 50700 |  | 157008 | 100000 |  | 307708 |  |  |  | The cemetery strategy is being updated and new strategy will go to Council. Tillicoultry work delayed due to Land acquisition problems. Budget to be carried forward. |  | 300 | 0 | 300 | 0 | 0 | 0 | # | # | #
| Sunnyside cemetery Extension | 90 41 0100 | ] | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | # | # | #
| Tullibody Cemetery | 90 41 0130 | ] | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 |  |  |  | 0 |  | 0
49 | Contaminated Land | 90 41 0200 |  | 50000 | -50000 | 0 | 81000 |  | 81000 | 5410.5 | -0.06 | 5410.44 |  | 131000 | -50000 | 81000 |  | 0 |  |  | 81000 |  |  |  | Tenders have gone out for Bankhead depot for which this budget will be used, although tenders are likely to be more. The grant of £50k receivable this year is earmarked for a number of different projects to implement contaminated land strategy (e.g. Alva Gas works, Forthbank). |  | 50 | 50 | 0 | 0 | 0 | 0 | Budget already in place for Land Officer
50 | Parks & Open Spaces | 90 41 0400 |  | 80000 | 0 | 80000 | 0 |  | 80000 | 9948 |  | 9948 |  | 80000 |  | 80000 |  | 0 | 80000 | 83000 | 243000 |  |  |  | Currently budget of £80k has been allocated for new fencing, footpaths & tree planting at Abercromby Park, Tullibody & King George 5th Park , Clackmannan. Plans for 07/08 & 08/09 budgets will be provided in future reports.
51 | Outdoor Play Area Strategy |  |  | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 75000 | 78000 | 153000
54a | Waste Recycling Project |  |  | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 400000 |  | 400000
54b | Wheeled / Litter Bins | 90 45 0230 |  | 135000 | 0 | 135000 | 0 |  | 135000 |  |  | 0 |  | 135000 |  | 135000 |  | 0 | 135000 | 135000 | 405000 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0
| Gateways & Roundabouts | 90 41 0300 |  |  |  | 0 | 0 |  | 0 |  |  | 0 |  | 40000 |  | 45000 |  | -45000 |  |  | 45000 |  |  |  | The Council approved a budget of £45k in June 2006, to be financed partly (£25k) by capital receipts from sale of land at Carronvale and the balance as an addition to the capital programme for 06/07. Budget has been allocated to enhance roundabouts at Arnsbrae, Menstrie, Muirside & Dumyat. Other sites have been considered with costs likely to be offset by sponsorship.
| Total - Environment |  |  | 665000 | -50000 | 615000 | -13096 | 0 | 601904 | 21472.9 | -0.06 | 21472.84 |  | 534896 | -50000 | 489896 |  | 112008 | 1190000 | 296000 | 2132904
Policy & Implementation
55 | Clackmannan Tollbooth | 90 50 3400 |  | 128000 | -71000 | 57000 | -1365 |  | 55635 | 16399.68 |  | 16399.68 |  | 55635 |  | 55635 |  | 0 |  |  | 55635 |  |  |  | Provisionally programmed for current year. Internal assessment of the Cross (Monument) being carried out presently. There were associated difficulties with it being listed. Landscaping work, fabric & remedial work will start in the current year. The total cost of the project is £161k spread over 3 years, grant funded by CHT (£32k) and Historic Scotland (£72k) and the balance of £57k to be funded by Council, of which £1k was spent last year. The HS grant is awaiting confirmation but the balance of Council contribution of £56k will be spent this year. |  | 0 | 0 | 0 | 161 | 104 | 57 | # | # | #
56 | National Cycle Route |  |  | 3000 | 0 | 3000 | 59000 |  | 62000 |  |  | 0 |  | 0 |  | 0 |  | 62000 |  |  | 62000 |  |  |  | Complexities of funding from outside bodies, Agricultural Land Act requirements. No grant funding agreed yet. Budget will be carried forward. |  | 3 | 0 | 3 | 0 | 0 | 0 | # | # | #
57 | Old Alloa Townscape Heritage Phase 2 | 90 50 2700 |  | 0 | 0 | 0 | 255150 |  | 255150 |  |  | 0 |  | 0 |  | 0 |  | 255150 |  |  | 255150 |  |  |  | As advised in the last report, Candleriggs Lane (value £65k) will not proceed now until the envelop work on Kilncraigs' 1936 building is complete, as Lane will be used to access envelop work. Lime Tree Walk (£189k) delayed by PPP revised programme, siting of building etc. Budget for both programmes will be carried forward, awaiting progress on the other related projects. | Lime tree walk delayed by PPP revised programme | 0 | 0 | 0 | 0 | 0 | 0 | # | # | #
58 | Landscape Partnership - converse Ochills / Hillfoots |  |  | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 225000 |  | 225000
| Old Alloa Townscape Heritage Phase 1 | 90 51 8812 |  | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 |  |  |  | 0 |  | 0
| Kirkgate | 90 51 8808 | [6 empty] | 0 | 16734.45 |  | 16734.45 |  |  |  | 0 |  | 0 | [6 empty] | Accrued income from CHT to be received this year
| Alloa Docks | 90 60 1300 |  | 0 | 0 | 0 | 0 |  | 0 | 22290 |  | 22290 |  |  |  | 0 |  | 0 | [6 empty] | Accrued income from thrid party to be received this year
59 | Core Path network for Access |  |  | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 38000 |  | 38000
67 | CSBP Restructuring |  |  | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
68 | Econ. Dev. Infrastructure: Eastern Clackmannanshire Development Opportunities |  |  | 100000 | 0 | 100000 | 0 |  | 100000 |  |  | 0 |  |  |  | 0 |  | 100000 |  |  | 100000 |  |  |  | Contingency sum for development in East Clackmannanshire awaiting results of meetings with Fife Enterprise. As advised last year, this is unlikely to proceed and the budget may be transferred to other projects yet to be approved by the Council. |  | 0 | 0 | 0 | 161 | 104 | 57 | 0 | 0 | 5
73 | Pavilions Business Park Phase 2 | 90 50 2400 |  | 300000 | 0 | 300000 | 40000 |  | 340000 |  |  | 0 |  | 40000 |  | 40000 |  | 300000 |  |  | 340000 |  |  |  | Work has commenced and due for completion in April 2007. Council contribution of £40k will be made to Joint Venture next year and the balance of £300k will be made on completion of project as advised in a report to the Council recently. |  | 0 | 0 | 0 | 0 | 0 | 0
74 | Dumyat Business Park Phase 3 | 90 50 2800 |  | 0 | 0 | 0 | 40000 |  | 40000 | 0 |  | 0 |  | 0 | 0 | 0 |  | 40000 |  |  | 40000 |  |  |  | The project is unlikely to proceed until Pavilions Phase 2 is complete as Joint Venture is unable to proceed with both projects. Position will be reviewed at the CSBP board meeting in October 2006. |  | 0 | 0 | 0 | 0 | 0 | 0
| Total - Policy & Implementation |  |  | 531000 | -71000 | 460000 | 392785 | 0 | 852785 | 55424.13 | 0 | 55424.13 |  | 95635 | 0 | 95635 |  | 757150 | 263000 | 0 | 1115785
Property Services
60 | Asbestos Removal | 90 40 3300 |  | 15000 | 0 | 15000 | 0 |  | 15000 |  |  | 0 |  | 15000 |  | 15000 |  | 0 |  |  | 15000 |  |  |  | Roof & walls of Land Services Building at Kelliebank. Tender to let in November 2006 |  | 15 | 0 | 15 | 0 | 0 | 0
61 | Centralised Kitchen | 90 50 4400 |  | 0 | 0 | 0 | 23782 |  | 23782 | 1233.94 |  | 1233.94 |  | 23782 |  | 23782 |  | 0 |  |  | 23782 |  |  |  | Retentions from previous year. |  | 0 | 0 | 0 | 0 | 0 | 0
62 | Disability Discrimination Act | 90 40 3400 |  | 0 | 0 | 0 | 0 |  | 0 | 2737 |  | 2737 |  |  |  | 0 |  | 0 |  | 20000 | 20000 | [5 empty] | 1 | 0 | 1 | 0 | 0 | 0
63a | Vehicle Replacement Programme (See details below) |  |  | 794000 | 0 | 794000 | 255000 |  | 1049000 | 95591 | 0 | 95591 |  | 989000 |  | 989000 |  | 60000 | 570000 | 500000 | 2119000 |  |  |  | Council were advised that £255k would be carried over from last year to obtain a better over all deal. This together with the current year's budget will be utilised this year, except for £60k which will be carried forward to next year. |  | 794 | 0 | 794 | 570 | 0 | 570
63b | Keilarsbrae land Purchases | 90 40 4300 |  | 0 | 0 | 0 | 11272 |  | 11272 |  |  | 0 |  |  |  | 0 |  | 11272 |  |  | 11272 |  |  |  | Admin & Legal are still investigating legal implications. Unlikely to spend budget this year. |  | 0 | 0 | 0 | 0 | 0 | 0
70 | Kilncraigs Mill 1936 Building Envelop | 90 50 4500 |  | 0 | 0 | 0 | 1289132 |  | 1289132 | 89061.8 |  | 89061.8 |  | 1605000 | -315000 | 1290000 |  | -868 |  |  | 1290000 |  |  |  | The Council allocated a budget of £1,350k of which £ 61k was spent last year on fees. The contract came in at £1,464k. As advised in last report, approach to Historic Scotland for a grant of £315k was successful to fund the balance of the contract sum plus fees. Retention of £60k will be carried forward to 07/08. Work progressing on site with external envelope including new roof, external rendering windows & glazed canopy at ground level. Completion date is January 2007.
71 | Kilncraigs Mill 1904 Development of 3rd & 4th Floors |  |  | 620000 | 0 | 620000 | 100000 |  | 720000 |  |  | 0 |  | 720000 |  | 720000 |  | 0 | 600000 | 30000 | 1350000 |  |  |  | This project was delayed pending decision from ESEP re. claw-back of ERDF grant implications and future use of 1904 building. Proposal is now for Development & Environment to move into ground level, 1st & 2nd floors. The 3rd & 4th floors to be fitted out for SMEs to compensate claw back. Progress proposals are: Tender issue on 9th Oct; tender acceptance & site start 13th Nov 2006 and completion 2nd April 2007.
72a | Kilncraigs Mill 1904 Access Control & Zoning Services |  |  | 0 | 0 | 0 | 80000 |  | 80000 |  |  | 0 |  | 80000 |  | 80000 |  | 0 |  |  | 80000 |  |  |  | Progressing as part of contract for 3rd & 4th floor accommodation, but ground, 1st & 2nd floor requirements will be completed by December 2006. |  | 0 | 0 | 0 | 0 | 0 | 0
72b | Kilncraigs Mill Conversion | 90 50 3000 |  | 0 | 0 | 0 | 17000 |  | 17000 |  |  | 0 |  | 17000 |  | 17000 |  | 0 |  |  | 17000 |  |  |  | Retention from previous year |  | 0 | 0 | 0 | 0 | 0 | 0
98 | Kilncraigs Mill 1904 Upgrade of Existing |  |  | 740000 | 0 | 740000 | 0 |  | 740000 |  |  | 0 |  | 350000 |  | 350000 |  | 390000 | 20000 |  | 760000 |  |  |  | Essential works required for the 1904 building to allow Council occupancy and fit out requirements for SMEs on top two floors. Target programme is a s per project 71 above. Advance work in relation to the ground and second floors including IT upgrading, fire safety improvements, DDA compliance and alterations for occupancy to the value of £350k will be completed by January 2007. The balance will be carried forward to 07/08.
99 | Forthbank Accommodation Rationalisation |  |  | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 |  | 75000 | 75000
| Total - Property Services |  |  | 2169000 | 0 | 2169000 | 1776186 | 0 | 3945186 | 188623.74 | 0 | 188623.74 |  | 3799782 | -315000 | 3484782 |  | 460404 | 1190000 | 625000 | 5761054
| Total Development & Environmental Services |  |  | 5074000 | -312000 | 4762000 | 3607231 | 119310 | 8488541 | 887520.48 | -99000.06 | 788520.42 |  | 6581979 | -556000 | 6030979 |  | 2457562 | 4800000 | 2516000 | 15850409 | [5 empty] | 3671 | 348 | 3323 | 4321 | 512 | 3809 | -200 | -200 | -195
CORPORATE DEVELOPMENT
64 | Efficient Government/Customer First Developments | 90 70 1900 |  | 100000 | 0 | 100000 | 41000 |  | 141000 |  |  | 0 |  | 141000 |  | 141000 |  | 0 | 100000 | 100000 | 341000 |  |  |  | Proposal is to utilise budget for mobile and remote working. In addition if Joint working goes ahead, there will be need for licensing costs, IDOX, Revenue & Benefits systems etc. |  | 100 | 0 | 100 | 100 | 0 | 100
65 | IT Services | 90 70 0451 |  | 360000 | 0 | 360000 | 0 |  | 360000 | 51117.61 | 0 | 51117.61 |  | 360000 |  | 360000 |  | 0 | 330000 | 300000 | 990000 |  |  |  | The budget has been earmarked to proactively replace equipment required during the year. |  | 400 | 0 | 400 | 400 | 0 | 400
66a | Finance Services - General Ledger system | 90 70 1125 |  | 30000 | 0 | 30000 | 0 |  | 30000 | 6090.51 |  | 6090.51 |  | 30000 |  | 30000 |  | 0 | 30000 | 40000 | 100000 |  |  |  | Earmarked for new payroll server and ancillary costs and updated Strategix system. |  | 30 | 0 | 30 | 30 | 0 | 30
[7 empty] | 0 |  | 0 |  |  | 0 |  |  |  | 0 |  | 0
| Rewiring & IT Cabling of Greenfield | 90 70 2100 |  | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 |  |  |  | 0 |  | 0
| Greenfield Dining Room | 90 70 2500 |  | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 |  |  |  | 0 |  | 0
83 | Greenfield Driveway & Parking |  |  | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 84000 |  | 84000
| Total Corporate Development |  |  | 490000 | 0 | 490000 | 41000 | 0 | 531000 | 57208.12 | 0 | 57208.12 |  | 531000 | 0 | 531000 |  | 0 | 544000 | 440000 | 1515000 | [5 empty] | 530 | 0 | 530 | 530 | 0 | 530 | 0 | 0 | 0
CHIEF EXECUTIVE SERVICES
|  |  |  | 0 | 0 | 0 | 0
75 | CCTV - Tron Court & Greenfield | 90 20 0600 |  |  |  | 0 | 53000 |  | 53000 | 147 |  | 147 |  | 53000 |  | 53000 |  | 0 |  |  | 53000 |  |  |  | Going ahead with cameras in Civic Centre, Tullibody (£10k). Balance is unallocated but looking at potential projects. |  | 0 | 0 | 0 | 0 | 0 | 0
76 | DDA & Asbestos Removal | 90 50 4300 |  | 25000 | 0 | 25000 | 19000 |  | 44000 | 37 |  | 37 |  | 44000 |  | 44000 |  | 0 |  |  | 44000 |  |  |  | DDA access work to Greenfield. Lighting, Door Alterations, roads & footpaths. Works to be completed by end of year. |  | 25 | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 0
| Mailroom Facilities & Franking Machine | 90 60 1700 |  | 0 | 0 | 0 | 0 |  | 0 | 15838.66 |  | 15838.66 |  | 16000 |  | 16000 |  | -16000 |  |  | 16000 |  |  |  | Budget was approved by Council last year
82 | Council Office Improvements |  |  | 0 | 0 | 0 | 0 |  | 0 | [10 empty] | 140000 | 140000
| Total Chief Executives Services |  |  | 25000 | 0 | 25000 | 72000 | 0 | 97000 | 16022.66 | 0 | 16022.66 |  | 113000 | 0 | 113000 |  | -16000 | 0 | 140000 | 253000 | [5 empty] | 25 | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 0
| TOTAL CAPITAL PROGRAMME (excluding SAK Rail Link) |  |  | 11222000 | -1360000 | 9862000 | 5833231 | 254310 | 15949541 | 1748033.38 | -99000.06 | 1649033.32 |  | 9893449 | -1564000 | 8334449 |  | 7615092 | 9302000 | 9496000 | 34791879 | [5 empty] | 13547 | 2444 | 11103 | 13152 | 2702 | 10450 | -200 | -200 | -195
38 | Total SAK Rail Project & Alloa ELR Project Costs | 90 50 3100 |  | 2057000 |  | 2057000 | -1132000 |  | 925000 | 17125425.96 | -22373421.58 | -5247995.62 |  | 815000 |  | 815000 |  | 110000 |  |  | 925000 |  |  |  | Budget only shows the Council contribution here. As advised previously , the maximum Council Contribution of £2.5m directly related to the Rail Link has been agreed. Of this the Council has already made a contribution of £1.575m in the past four years, leaving a balance of £925k. The latest projections indicate that the Council will make a contribution of £815k this year and the remaining £110k in 07/08 |  | 750 | 712 | 38 | 0 | 0 | 0 | -20 | -20 | -20
| TOTAL CAPITAL PROGRAMME (including SAK Rail Link) |  |  | 13279000 | -1360000 | 11919000 | 4701231 | 254310 | 16874541 | 18873459.34 | -22472421.64 | -3598962.3 |  | 10708449 | -1564000 | 9149449 |  | 7725092 | 9302000 | 9496000 | 35716879
| UNALLOCATED FUNDING | [5 empty] | Trfs (from) / to 05/06 | [25 empty] | Key for Recurring Revenue Costs Section
77 | Capital Receipts Estimate (see details below) | 90 90 xxxx |  | -1085000 |  | -1085000 |  |  | -1085000 | 119.07 | -154.32 | -35.25 |  | -500000 |  | -500000 |  | -585000 | -785000 | -1950000 | -3235000 |  |  |  | Apart from the two main receipts identified below, the only other capital receipts expected this year is in respect of two properties which is still subject to discussion. If successful, the sales may realise about £500k. The CAMP team are regularly reviewing the rationalisation of Council properties and further updates will be given in future reports. |  |  |  | 300 |  |  | 300
78 | Sale of Land at Dumyat Park & Ditch for Tullibody By Pass |  | } | 0 | 0 | 0 | -1550000 |  | -1550000 |  |  | 0 |  | -1395000 |  | -1395000 |  | -155000 |  |  | -1395000 |  |  |  | The sale of Land @ rear of St. Mungo's was completed on 22nd August. However, discussions are still on-going regarding Dumyat Park & Ditch. As advised previously there are issues regarding abnormal site conditions. The sellers have appointed engineers who are examining the site. Also, there are on going discussions with Scottish Water on re-routing of quest pipe. There will be additional costs in the region of £250k because of abnormal ground conditions & quest pipe re-routing. The net anticipated receipts for both lands is £3.145m. Of this £1.75m has been earmarked for the schools' PPP project as advised previously, leaving a balance of £1.395m for the 06/07 capital programme. This is a decrease of £155k on the original estimate. |  |  |  | 0
78 | Sale of Land to rear of St.Mungo's |  | } | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | [10 empty] | 0
80 | ERDF Grants (from Kilncraigs to be used to refund extra s94 advance in previous years) |  |  | -119000 | 0 | -119000 | 0 |  | -119000 |  |  | 0 |  | -119000 |  | -119000 |  | 0 |  |  | -119000 |  |  |  | These are retained ERDF Grants in respect of Kilncarigs, Allow Harbour, Alloa Tower & Allow West projects awaiting final audit which KPMG have almost completed. Retained grants will be released by Scottish Executive on satisfactory audit report. |  |  |  | 0 |  |  |  | Blank cells = | no info from service
81 | Repayment from Schools Devolved Budget for Computer Equipment | 90 10 4500 |  | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | [10 empty] | 0
[7 empty] | 0 |  | 0 |  |  | 0 |  |  |  | 0 |  | 0
|  |  |  | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 |  |  |  | 0 |  | 0
|  |  |  | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 |  |  |  | 0 |  | 0
| TOTAL - ESTIMATED UNALLOCATED FUNDING |  |  | -1204000 | 0 | -1204000 | -1550000 | 0 | -2754000 | 119.07 | -154.32 | -35.25 |  | -2014000 | 0 | -2014000 |  | -740000 | -785000 | -1950000 | -4749000 | [7 empty] | 300 |  |  | 300
1
NET FUNDING (SURPLUS) / DEFICIT
FINANCED BY C.F.C.R.
Net Capital Programme
[6 empty] | 10715000 | 3151231 | 254310 | 14120541 | 18873578.41 | -22472575.96 | -3598997.55 |  | 8694449 | -1564000 | 7135449 |  | 6985092 | 8517000 | 7546000 | 30967879 | [7 empty] | 10803 |  |  | 10150
| Project brought forward from 07/08 to 06/07 | [17 empty] | -254310
| Project carried forward from 06/07 to 07/08 | [17 empty] | 2963000
| PPP Allocation c/f to 08/09 | [17 empty] | -3600000 | 8425000
| Additional approved - Menstrie | [18 empty] | 400000 | 400000
Net Capital Programme (after transfers)
[19 empty] | 7625690 | 16371000 | 31367879
DETAILS PROPERTY CAPITAL RECEIPTS
77 | 22/4 Candleriggs, Alloa | 9090 6800 | [9 empty] | 0 |  |  |  | 0
77 | Skip Site - Hallpark, Sauchie | 9090 0726 | [9 empty] | 0 |  |  |  | 0
77 | Dewar St, Lorne Lane , Dollar | 9090 0800 | [9 empty] | 0 |  |  |  | 0
77 | Collyland - Fishcross | 9070 1700 | [9 empty] | 0 |  |  |  | 0
77 | Cowan Terrace Dollar | 9090 0875 | [9 empty] | 0 |  |  |  | 0
77 | Candleriggs, Alloa | 9090 0950 | [9 empty] | 0 |  |  |  | 0
77 | General Receipts | 9090 1000 | [9 empty] | 0 |  |  |  | 0
77 | Alexandra Street, Devonside | 9090 2200 | [9 empty] | 0 |  |  |  | 0
77 | Gap Site - Drysdale/Mill Street | 9090 1050 | [9 empty] | 0 |  |  |  | 0
77 | Bedford Place Alloa | 9090 1100 | [9 empty] | 0 |  |  |  | 0
77 | Bedford House - Alloa | 9090 1125 | [9 empty] | 0 |  |  |  | 0
77 | Cowden Park Alloa | 9090 1175 | [9 empty] | 0 |  |  |  | 0
77 | Forestmill Primary School | 9090 1325 | [9 empty] | 0 |  |  |  | 0
77 | Former School Clackmannan | 9090 1400 | [9 empty] | 0 |  |  |  | 0
77 | Orchard Tullibody - Housing Land | 9090 1525 | [9 empty] | 0 |  |  |  | 0
77 | Alloa West | 9090 0550 | [9 empty] | 0 |  |  |  | 0
77 | Alloa West - Autism Site | 9090 5800 | [9 empty] | 0 |  |  |  | 0
77 | Menstrie Centre Playground | 9090 1600 | [9 empty] | 0 |  |  |  | 0
77 | Collyland Road - Fishcross Housing Site | 9090 1700 | [9 empty] | 0 |  |  |  | 0
77 | Shops - Sauchie | 9090 1850 | [9 empty] | 0 |  |  |  | 0
77 | Kirkgate - Alloa | 9090 2100 | [9 empty] | 0 |  |  |  | 0
77 | Alexandra Street, Devonside | 9090 2200 | [9 empty] | 0 |  |  |  | 0
77 | Long Row Menstrie - Land | 9090 2700 | [9 empty] | 0 |  |  |  | 0
77 | Mar Place Sauchie WC | 9090 2800 | [9 empty] | 0 |  |  |  | 0
77 | 5 Muirside Road, Tullibody | 9090 3025 | [9 empty] | 0 |  |  |  | 0
77 | Park Street, Alva | 9090 3500 | [9 empty] | 0 |  |  |  | 0
77 | Bankhead - Devon Village | 9090 6100 | [9 empty] | 0 |  |  |  | 0
77 | Claremont Business Centre | 9090 1025 | [9 empty] | 0 |  |  |  | 0
77 | Dumyat Business Park | 9090 7000 | [9 empty] | 0 |  |  |  | 0
77 | Dumyat Business Park - Belhaven Breweries | 9090 7400 | [9 empty] | 0 |  |  |  | 0
77 | Earlsfield/Alloa Park | 9090 1750 | [9 empty] | 0 |  |  |  | 0
77 | Fishcross - Devon Riding Centre | 9090 6900 | [8 empty] | -154.32 | -154.32 |  |  |  | 0
77 | Land - Ochilvale Mill Alva | 9090 3900 | [9 empty] | 0 |  |  |  | 0
77 | St Mungo's Wynd Alloa | 9090 4000 | [9 empty] | 0 |  |  |  | 0
77 | 28 Ramsay Street, Clackmannan | 9090 4100 | [9 empty] | 0 |  |  |  | 0
77 | Old Toll House, Muckhart | 9090 4200 | [9 empty] | 0 |  |  |  | 0
77 | Main St Coalsnaughton | 9090 4300 | [9 empty] | 0 |  |  |  | 0
77 | Baingle Crescent | 9090 4400 | [9 empty] | 0 |  |  |  | 0
77 | Gas Governor at the Baingle | 9090 4500 | [9 empty] | 0 |  |  |  | 0
77 | Fairfield Sauchie | 9090 4600 | [9 empty] | 0 |  |  |  | 0
77 | Scout Hall Main Street Sauchie | 9090 4700 | [9 empty] | 0 |  |  |  | 0
77 | 3/5 Lower Mains Dollar | 9090 4800 | [9 empty] | 0 |  |  |  | 0
77 | Railway Station Alloa Road | 9090 4900 | [9 empty] | 0 |  |  |  | 0
77 | Land at Shawpark garage | 9090 5000 | [9 empty] | 0 |  |  |  | 0
77 | Service Station Site / Ditch Farm | 9090 5100 | [9 empty] | 0 |  |  |  | 0
77 | Pavilions Phase 2 | 9090 5200 | [9 empty] | 0 |  |  |  | 0
77 | TOMA CPO | 9090 5300 | [9 empty] | 0 |  |  |  | 0
77 | Sinclairs Haulage - Land | 9090 5400 | [9 empty] | 0 |  |  |  | 0
77 | Alva House Stable Block | 9090 5500 | [9 empty] | 0 |  |  |  | 0
77 | 3/5 Henderson Avenue, Alloa | 9090 5600 | [9 empty] | 0 |  |  |  | 0
77 | Land at Rear 78/80 West Stirling Street Alva | 9090 5700 | [9 empty] | 0 |  |  |  | 0
77 | Fishcross - Land at Devonbank Cottage | 9090 7100 | [9 empty] | 0 |  |  |  | 0
77 | Washington House - Alva | 9090 5900 | [9 empty] | 0 |  |  |  | 0
77 | 23 Main Street Sauchie | 9090 6000 | [9 empty] | 0 |  |  |  | 0
77 | Bank Head, Devon Village Rescue | 9090 6100 | [9 empty] | 0 |  |  |  | 0
77 | Smithfield Loan - Railway Embankment | 9090 6200 | [9 empty] | 0 |  |  |  | 0
77 | Superiority - Smithfield Loan | 9090 6300 | [9 empty] | 0 |  |  |  | 0
77 | Land at Broad Street, Alloa | 9090 6400 | [9 empty] | 0 |  |  |  | 0
77 | Land for Access to Stirling St | 9090 6500 | [9 empty] | 0 |  |  |  | 0
77 | Garage Site Gartmorn Dam House | 9090 6600 | [9 empty] | 0 |  |  |  | 0
77 | Lochy Falls,15 Upper Hillfoot, Dollar | 9090 6700 | [9 empty] | 0 |  |  |  | 0
77 | Former Toilets - Alva | 9090 7800 | [9 empty] | 0 |  |  |  | 0
77 | Hillpark | 9090 3700 | [9 empty] | 0 |  |  |  | 0
77 | Hallpark/Main Street Sauchie | 9090 0700 | [9 empty] | 0 |  |  |  | 0
77 | Land at Park St Tillicoultry | 9090 7300 | [9 empty] | 0 |  |  |  | 0
77 | Land/Car Park - Erskine ST Alloa | 9090 3800 | [9 empty] | 0 |  |  |  | 0
77 | Housing Land The Orchard Tullibody | 9090 1525 | [9 empty] | 0 |  |  |  | 0
77 | Property Conversion Feasibility Study | 9090 7200 | [9 empty] | 0 |  |  |  | 0
77 | Former Thistle Brewery | 9090 7700 | [9 empty] | 0 |  |  |  | 0
77 | Tullis Factory | 9090 1575 | [7 empty] | 119.07 |  | 119.07 |  |  |  | 0
77 | Sale of Land at Tullibody (Ditch Farm) | 9090 5100 | [9 empty] | 0 |  |  |  | 0
77 | Other | [10 empty] | 0 |  |  |  | 0
0
| Total - Property Sales | [8 empty] | 119.07 | -154.32 | -35.25 |  | 0 | 0 | 0
DETAILS VEHICLE REPLACEMENT PROGRAMME
63a | DLO Vehicle - Property Contracts | 9045 0100 |  | 222000 |  | 222000 | 30000 |  | 252000 |  |  | 0 |  | 252000 |  | 252000 |  | 0
63a | DLO Vehicle - Refuse Collection | 9045 0110 |  | 273000 |  | 273000 | 130000 |  | 403000 | 80575 |  | 80575 |  | 403000 |  | 403000 |  | 0
63a | DLO Vehicle - Street Cleaning | 9045 0120 |  | 70000 |  | 70000 |  |  | 70000 |  |  | 0 |  | 70000 |  | 70000 |  | 0
63a | DLO Vehicle - Land Services | 9045 0130 |  | 192600 |  | 192600 | 62000 |  | 254600 | 15016 |  | 15016 |  | 254600 |  | 254600 |  | 0
63a | DLO Vehicle - Roads Contracts | 9045 0140 |  | 120000 |  | 120000 | 31000 |  | 151000 |  |  | 0 |  | 151000 |  | 151000 |  | 0
63a | DLO Vehicle - Catering Services | 9045 0150 |  |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 0
63a | DLO Vehicle - Transport Pool | 9045 0160 |  | 36000 |  | 36000 |  |  | 36000 |  |  | 0 |  | 36000 |  | 36000 |  | 0
63a | DLO Vehicle - Leisure | 9045 0170 |  |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 0
63a | DLO Vehicle - Social Services | 9045 0200 |  |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 0
63a | DLO Vehicle - Burial Services | 9045 0210 |  | 33250 |  | 33250 |  |  | 33250 |  |  | 0 |  | 33250 |  | 33250 |  | 0
63a | DLO Vehicle - Countryside Rangers | 9045 0220 |  |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 0
63a | DLO Vehicle - G F Housing | 9045 0225 |  |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 0
| Glenochil Nursery |  |  | 1800 |  | 1800 |  |  | 1800 |  |  | 0 |  | 1800 |  | 1800 |  | 0
| Chief Executive |  |  | 11250 |  | 11250 |  |  | 11250 |  |  | 0 |  | 11250 |  | 11250 |  | 0
| Black Devon |  |  | 26000 |  | 26000 |  |  | 26000 |  |  | 0 |  | 26000 |  | 26000 |  | 0
|  |  |  | -191900 |  | -191900 | 2000 |  | -189900 |  |  | 0 |  | -249900 |  | -249900 |  | 60000
| Total - Vehicle Programme |  |  | 794000 | 0 | 794000 | 255000 |  | 1049000 | 95591 | 0 | 95591 |  | 989000 | 0 | 989000 |  | 60000
Note on H85: Authorised User: Not shown in 05/06 schedule as c/f to 06/07. But this was approved by Council later & therefore included here
Note on V59: Authorised User: £97k of the £100k has been b/f from 07/08 to 06/07
Note on V60: Authorised User: £22k of the £500k b/f from 07/08 to 06/07
Note on V82: Authorised User: Budget for 06/07 was originally £300k of which £100k was trf to 07/08. Since I have shown 06/07 as £200k, I have had to show 07/08 budget as £100k although this was a c/f from 06/07.
Note on AF97: Authorised User: contractor August Sept on site November and spend third year subject to positive response from PPP

## Apd 2 Proj Status as at 31-7-06 (hidden)
| 0 |  |  | OK |  | OK |  |  | OK |  |  | OK |  | Out-Turn Out |  | OK
1 | 2 |  |  | 4 | 5 | 6 |  |  |  | 7 | 8 | 9 | 9 | 10 | 11 | 12 | 10 | 13 |  |  |  | 14 | 15 | 16 | 17 | 10 | 11 | 12 | 13 | 14 | 15 | 16
|  | Ledger codes |  | BUDGET 2005/06 | [9 empty] | Out-turn as at July 2005 | [7 empty] | Project Status as at Mid August 2005 |  |  |  |  | 2006/07 |  |  | 2007/08 |  |  | Recurring Revenue consequences
for the proposed project
| General Services Capital Programme 2006/07 to 2008/09 |  |  | APPROVED BUDGET 2006/07 |  |  | 2006/07 |  |  | ACTUAL for year to 31st July 2006 |  |  |  | 06/07 Out-turn reported at as at 14/8/06 |  |  |  |  | Approved budget for 2007/08 Borrowing (Council Contribution) | Approved budget for 2008/09 Borrowing (Council Contribution) | Total for 3 years Borrowing (Council Contribution) | Project Status as at Mid July 2006 |  |  |  |  | (See Appendix 3) |  |  | (See Appendix 4)
|  |  |  | Approved Budget | External Grants | Borrowing (Council Contribution) | Projects transferred from / (to) 05/06 | Projects transferred from 07/08 | Revised Borrowing (Council Contribution) | Total Expenditure | Total Income | Borrowing (Council Contribution) |  | Total Expenditure | Total Income | Borrowing (Council Contribution) |  | Variance on 06/07 Budget |  |  |  | Tenders issued / received | Contractor Appointed | Project start date |  | If project is delayed to next year, proposal to bring forward project from 3 year approved programme | Gross | External Grants | Net (Council Contribution) | Gross | External Grants | Net (Council Contribution)
|  |  |  | Gross |  | Net |  |  |  | Gross |  | Net |  |  |  | Net | [16 empty] | 2004/05 | 2005/06 | 2006/07
| Service / Project Name |  |  | £ | £ | £ | £ | £ | £ | £ | £ | £ |  | £ | £ | £ |  | £ | £ | £ | £ | [5 empty] | £'000 | £'000 | £'000 | £'000 | £'000 | £'000
SERVICES TO PEOPLE
EDUCATION & COMMUNITY SERVICES
1,3,5 | PPP Capital Support | 90 10 7000 |  | 3450000 | 0 | 3450000 | 1200000 |  | 4650000 |  |  | 0 |  | 0 | 0 | 0 |  | 4650000 | 3600000 | 3500000 | 11750000 |  |  |  | As advised in previous report, in accordance with proper accounting practice, transfers of PPP budgets to a sinking fund cannot be capitalised currently for which no asset exits. These budgets will be carried forward to future years to be offset against unitary charges as and when the payments become due. |  | 1050 | 0 | 1050 | 1000 | 0 | 1000
17 | Primary & Nursery School Developments - Allocated to PPP |  |  | 0 | 0 | 0 | 175000 |  | 175000 |  |  | 0 |  |  |  | 0 |  | 175000 |  |  | 175000 |  |  |  | As above |  | 300 | 0 | 300 | 300 | 0 | 300
17 | Primary & Nursery School Developments |  |  | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 |  | 1000000 | 1000000 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0
4 | DDA Compliance | 90 10 6000 | } | 0 | 0 | 0 | 133000 |  | 133000 | 23423.4 |  | 23423.4 |  | 133000 |  | 133000 |  | 0 |  |  | 133000 |  |  |  | The budget, which was carried forward from last year, is made up of a number of small projects. Some of them have been completed over the summer holidays. Further projects will be commissioned to utilise the funding available during the year. Spend on Accessibility Strategy is treated as part of DDA project. |  | 100 | 0 | 100 | 0 | 0 | 0
| Accessibility Strategy | 90 10 6100 | } |  |  | 0 |  |  | 0 | 1212.97 |  | 1212.97 |  |  |  | 0 |  | 0
7 | Museum & Heritage Centre | 90 10 5800 |  |  | 0 | 0 | 250000 |  | 250000 |  |  | 0 |  |  |  | 0 |  | 250000 |  |  | 250000 |  |  |  | The budget will need to be carried forward. See details given in 11 below. |  | 0 | 0 | 0 | 0 | 0 | 0
8 | School Building Alarm Systems | 90 10 5700 |  | 10000 | 0 | 10000 | 294000 |  | 304000 | 1382 |  | 1382 |  | 304000 |  | 304000 |  | 0 | 8000 |  | 312000 |  |  |  | The bulk of the work was completed over the summer period. Final certificates will be processed in due course and the budget will be spent this year. |  | 300 | 0 | 300 | 8 | 0 | 8 | some maintenance but reduction in insurance
85,86 | ICT Hardware Replacement in Sec Schls & New IT Installation in Schools | 90 10 0440 |  | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 |  | 600000 | 600000 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0
9 | Schools Fund | 90 10 4900 |  | 1008000 | -1008000 | 0 | 0 |  | 0 | 457389.12 |  | 457389.12 |  | 1008000 | -1008000 | 0 |  | 0 | [6 empty] | Major works at Deerpark / Lochies, Park PS, Coalsnaughton PS, Tillicoultry PS, Menstrie PS have been completed or nearly completed (in the case of Park PS) over the vacation. Once the final costs are available, any remaining funds will be used to tackle other projects. |  | 1008 | 1008 | 0 | 1055 | 1055 | 0
10 | Tulligarth Sports Resurfacing - requirement of Lottery funding |  |  | 0 |  | 0 | 0 |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 40000 |  | 40000
11 | Alloa Library Refurbishment |  |  | 0 | 0 | 0 | 100000 |  | 100000 |  |  | 0 |  |  |  | 0 |  | 100000 |  |  | 100000 |  |  |  | The Service will not spend any of this funding in this year because of the ongoing discussions about the wider issues of Alloa Town Centre Regeneration. There are on going discussions on how to best develop the Library provision and to link this with the current rationalisation of Council buildings , including the development of Museum & Heritage Centre and accommodation moves to Kilncraigs. All of these proposals are being considered by the CAMP team and will have a direct impact on the development of the Library provision. |  | 100 | 0 | 100 | 0 | 0 | 0
13 | Heavy Equipment in Secondary Schools - Kilns etc | 90 10 6600 |  | 0 | 0 | 0 | 60000 |  | 60000 | 40470 |  | 40470 |  | 40470 |  | 40470 |  | 19530 |  |  | 40470 |  |  |  | Both projects are now complete and the balances are off-set each, with a slight overspend of £530. |  | 30 | 0 | 30 | 30 | 0 | 30
14 | IT Hardware Replacement in Schools | 90 10 6700 |  | 100000 | -40000 | 60000 | -139000 | 60000 | -19000 |  |  | 0 |  | 0 |  | 0 |  | -19000 | 60000 |  | 41000 | [5 empty] | 100 | 40 | 60 | 100 | 40 | 60
15 | Legal Commitments - for projects undertaking in 04/05 | 90 10 6900 |  | 25000 | 0 | 25000 | 0 |  | 25000 | 1586.49 |  | 1586.49 |  | 25000 |  | 25000 |  | 0 | 25000 | 50000 | 100000 |  |  |  | This is provision for retentions for previous projects, which has been overspent to enable all retentions to be paid . |  | 25 | 0 | 25 | 25 | 0 | 25
16 | Leisure Bowl - refurbishment | 90 15 0100 |  | 200000 | 0 | 200000 | -14000 | 75000 | 261000 | 237327.62 |  | 237327.62 |  | 261000 |  | 261000 |  | 0 | 75000 | 150000 | 486000 |  |  |  | Due to the decision to refurbish M&E and plant at Alloa Leisure Bowl in the current financial year, the spending profile this year is £260k. £14k was spent last year, bringing the total spend to £274k. The funding for this is £200k allocated this year and £75k brought forward from next year. |  | 200 | 0 | 200 | 75 | 0 | 75
87-91 | Future Developments |  |  | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 |  | 1050000 | 1050000
19 | Fir Park Ski Centre - upgrade to building | 90 10 5200 |  | 0 | 0 | 0 | 0 |  | 0 | 815.6 |  | 815.6 |  |  |  | 0 |  | 0 | [6 empty] | Most of these are retentions to be met from legal commitments budget. See 15 above. |  | 0 | 0 | 0 | 0 | 0 | 0
| NOF & Sports Muchart Primary School | 90 10 5100 |  | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 |  |  |  | 0 |  | 0
| NOF & Sports Strathdevon & Clackmannan | 90 10 5300 |  | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 |  |  |  | 0 |  | 0
| Family Centre - Newmills | 90 10 3700 |  | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0
| Property Enhancement general | 90 10 2000 |  | 0 | 0 | 0 | 0 |  | 0 | 3402.5 |  | 3402.5 |  |  |  | 0 |  | 0 | [8 empty] | 5613 | 1048 | 4565 | 5233 | 1095 | 4138
| School Building Improvement | 90 10 4400 |  | 0 | 0 | 0 | 0 |  | 0 | 226.5 |  | 226.5 |  |  |  | 0 |  | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0
| SEN Adaptation | 90 10 0901 |  | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0
| Total Education & Community Service |  |  | 4793000 | -1048000 | 3745000 | 2059000 | 135000 | 5939000 | 767236.2 | 0 | 767236.2 |  | 1771470 | -1008000 | 763470 |  | 5175530 | 3808000 | 6350000 | 16077470 | [5 empty] | 8826 | 2096 | 6730 | 7826 | 2190 | 5636 | 0 | 0 | 0
SOCIAL SERVICES
20 | DDA Compliance |  |  | 20000 | 0 | 20000 | 16000 |  | 36000 |  |  | 0 |  | 36000 |  | 36000 |  | 0 |  |  | 36000 |  |  |  | Earmarked for Alloa Centre & plans have been drawn. However, the project is awaiting approval as the Capital Asset Management Team carry out further assessment |  | 20 | 0 | 20 | 0 | 0 | 0
21 | Joint FVNHS/ Adult Care Premises Occupation |  |  | NK | NK | NK | NK |  | NK |  |  | 0 |  |  |  | 0 |  |  |  | 50000 | 50000 | [5 empty] | NK | NK | NK | NK | NK | NK
22 | Menstrie House En-Suite Conversion | 90 30 0350 |  | 800000 | 0 | 800000 | 38000 |  | 838000 | 17629.11 |  | 17629.11 |  | 838000 |  | 838000 |  | 0 | 150000 |  | 988000 |  |  |  | Originally a total budget of £1m was allocated to this project. The Council approved a further £400k in May bringing the total to £1.4m. Of this £12k was spent last year. It is anticipated that £838k will be spent this year and £515k next year on completion, with a retention of £35k in 08/09. |  | 475 | 0 | 475 | 475 | 0 | 475
| Menstrie House External Works & Telephone system | 90 30 1500 |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0
| Menstrie House | 90 30 1500 | [6 empty] | 0 | 1807 |  | 1807 |  |  |  | 0 |  | 0
23 | Ludgate House External Fabric | 90 30 1600 |  | 20000 | 0 | 20000 | 0 |  | 20000 |  |  | 0 |  | 20000 |  | 20000 |  | 0 |  |  | 20000 |  |  |  | Mainly enhancement works earmarked to be completed this year |  | 0 | 0 | 0 | 0 | 0 | 0
24 | Mental Health Services - Retentions | 90 30 1700 |  |  | 0 | 0 | 0 |  | 0 | 178.06 |  | 178.06 |  | 1000 |  | 1000 |  | -1000 |  |  | 1000 |  |  |  | Small retentions from previous year |  | 0 | 0 | 0 | 0 | 0 | 0
66b | Ludgate Traffic Management - Retentions | 90 30 1900 |  |  | 0 | 0 | 0 |  | 0 | 431.75 |  | 431.75 |  | 1000 |  | 1000 |  | -1000 |  |  | 1000
| Total Social Services |  |  | 840000 | 0 | 840000 | 54000 | 0 | 894000 | 20045.92 | 0 | 20045.92 |  | 896000 | 0 | 896000 |  | -2000 | 150000 | 50000 | 1096000 | [5 empty] | 495 | 0 | 495 | 475 | 0 | 475 | 0 | 0 | 0
DEVELOPMENT & ENVIRONMENTAL SERVICES
Roads & Transportation
26 | Accident Prevention & Traffic Management | 90 40 1020 |  | 100000 | 0 | 100000 | 0 |  | 100000 | 3113.73 |  | 3113.73 |  | 100000 |  | 100000 |  | 0 | 100000 | 100000 | 300000 |  |  |  | This will be spent on three main projects, Tullibody Cross mini-roundabouts and pedestrian facilities (£45k), road safety improvements at A91 Tait’s Tomb and Cowden Bends (£45k) and Dollar, Fishcross and Coalsnaughton village gateways (£10k). |  | 100 | 0 | 100 | 100 | 0 | 100 | 0 | 0 | 0
27 | Alloa Town Centre | 90 40 1750 |  | 0 | 0 | 0 | 705000 |  | 705000 | 231584.86 |  | 231584.86 |  |  |  | 0 |  | 705000 |  |  | 705000 |  |  |  | Project involves three phases at different timescale to co-ordinate the public ways with Asda and the SAK Rail project. Council Contribution approved is £758k of which £53k was spent last year. Asda has contributed £606k. Phase 1 (Drysdale St/ Shillinghill to Ring Road will be completed end of slept 2006; Phase 2 (Ring Road to Station Sq to complete in November 2006; Phase 3 (Station Sq is dependent on completion of Rail Station. It is anticipated the balance of the Council contribution of £708k will be used this year, however, any unused budget will be carried forward. |  | 0 | 0 | 0 | 0 | 0 | 0 | -200 | -200 | -200
28 | A91 East Stirling St. Alva Roundabout to access new school site |  |  | 0 | 0 |  | 0 |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 225000 |  | 225000
31a | B9140/ Collylands Cross Upgrade | 90 40 4500 |  | 0 | 0 | 0 | 343000 | 97000 | 440000 | 259496.42 |  | 259496.42 |  | 440000 |  | 440000 |  | 0 | 100000 |  | 540000 |  |  |  | In order to complete this project in the current year, next year's budget is brought forward. There may be a slight overspend of £17k according to the latest projections. |  | 600 | 0 | 600 | 500 | 0 | 500 | 0 | 0 | 0
31b | B9140 Realignment of Bends |  |  | 0 | 0 | 0 | -2310 | 22310 | 20000 |  |  | 0 |  | 20000 |  | 20000 |  | 0 | 500000 | 500000 | 1020000 |  |  |  | This work is now schedule to commence this year and £20k of next year's budget is brought forward to allow this. The total budget allocated to this project in the 3 year capital programme was £1,000k. However, it is expected that an additional £272k may be required. Approval will be sought form the Council |  | 0 | 0 | 0 | 0 | 0 | 0
32 | Bridge Strengthening | 90 40 1700 |  | 150000 | 0 | 150000 | 437000 |  | 587000 | 126 |  | 126 |  | 587000 |  | 587000 |  | 0 | 400000 | 150000 | 1137000 |  |  |  | £450k is allocated for three bridges in connection with work done on SAK Rail Link. These are Kennet, Cattlemarket and Helensfield, all scheduled to be completed this financial year, although Helensfield may run on to next year. The balance of £137k is for Shavelhaugh bridge, mainly for design preparation work, public utilities and survey fees. |  | 150 | 0 | 150 | 400 | 0 | 400 | 0 | 0 | 0
33 | Flood Prevention | 90 40 2700 |  | 100000 | 0 | 100000 | 0 |  | 100000 | 1176 |  | 1176 |  | 100000 |  | 100000 |  | 0 | 100000 | 100000 | 300000 |  |  |  | Main schemes this year, Embankment wall reconstruction on Alva Burn, design of flood prevention scheme Gubber Hill, Alloa, safety measures at trash screens. On target to complete jobs on time |  | 100 | 0 | 100 | 100 | 0 | 100 | 0 | 0 | 0
34 | Retentions |  |  | 60000 | 0 | 60000 | 0 |  | 60000 |  |  | 0 |  | 60000 |  | 60000 |  | 0 | 60000 | 60000 | 180000 |  |  |  | Provision for retentions on previous years' projects. |  | 60 | 0 | 60 | 60 | 0 | 60 | 0 | 0 | 0
35 | Road & Footway Improvements (SRMCS), including town centres | 90 40 3000 |  | 515000 | 0 | 515000 | -31334 |  | 483666 | 4941.49 |  | 4941.49 |  | 483666 |  | 483666 |  | 0 | 500000 | 500000 | 1483666 |  |  |  | Part of the budget was utilised in the previous year. This year's budget is earmarked for A91 carriageway enhancement at Tate's Tomb and A91 Cowden Bends. |  | 850 | 0 | 850 | 1000 | 0 | 1000 | 0 | 0 | 0
36 | Cycling , Walking ,Safer Streets (CWSS) | 90 40 1310 |  | 84000 | -84000 | 0 |  |  | 0 | 17129.54 |  | 17129.54 |  | 84000 | -84000 | 0 |  | 0 | [6 empty] | Main schemes this year are, safety improvements at zebra crossings (£20k), town centre parking and delivery parking Dollar, Tillicoultry and Alva (£29k), speed reduction works Alloa Road, Tullibody (£15k) and pedestrian improvements at Gartmorn / Keilarsbrae, Sauchie (£20k). |  | 84 | 84 | 0 | 86 | 86 | 0 | 0 | 0 | 0
37 | Street Lighting | 90 40 4000 |  | 150000 | 0 | 150000 | 0 |  | 150000 |  |  | 0 |  | 150000 |  | 150000 |  | 0 | 165000 | 185000 | 500000 |  |  |  | Contractor appointed and work in progress - completion September 2006. Schemes include Main Street, Sauchie; Newmills, Tullibody (Phase 1); Forthvale & Elmbank, Menstrie; Parkway/Sunnyside Road, Alloa. |  | 150 | 0 | 150 | 165 | 0 | 165 | 0 | 0 | 0
40 | Tullibody By Pass c/f from 2004/05 | 90 40 3900 |  | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0
| A907 | 90 40 1650 |  | 0 | 0 | 0 | 0 |  | 0 | 1128 |  | 1128 |  |  |  | 0 |  | 0 | [8 empty] | 107 | 107 | 0 | 109 | 109 | 0
41 | 20mph speed reduction | 90 40 3200 |  | 107000 | -107000 | 0 | 0 |  | 0 | 103303.4 | -99000 | 4303.4 |  | 107000 | -107000 | 0 |  | 0 | [6 empty] | Main schemes this year are 10 new sites for speed reactive warning signs (£25k), pedestrian crossings on B9096 Tullibody Road, Alloa (£30k), traffic calming at level crossing, Cambus (£10k), speed reduction scheme Walker Terrace, Tillicoultry (£22k) and Smithfield Loan (£20k). |  | 107 | 107 | 0 | 109 | 109 | 0
42 | Footways at Muirside, Tullibody | 90 40 4600 |  | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0
43 | SESTRAN Public Transport & Walking | 90 40 3600 |  | 0 | 0 | 0 | 0 |  | 0 | 0.27 |  | 0.27 |  |  |  | 0 |  | 0 | [6 empty] | This will be spent on, new Puffin Crossings on Ring Road, Alloa (£40k), upgrade of Waggon Way, Alloa to link Mixed leisure route and National Cycle Route (£120k), resurfacing and new parking at bus station Murray Square, Tillicoultry (£40k) and junction / bus stop improvements, The Glen, Devonside (£20k). The project will be fully funded by capital grants. |  | 0 | 0 | 0 | 0 | 0 | 0
44 | SESTRAN Public Bus | 90 40 4200 |  | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0
45 | SUSTRAN - Cycle Routes | 90 40 3700 |  | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0
93 | A907 B910 / Helensfield Junction for Railway Line |  |  | 443000 | 0 | 443000 | 0 |  | 443000 |  |  | 0 |  | 20000 |  | 20000 |  | 423000 | 7000 |  | 450000 |  |  |  | Design of new roundabout underway. Timescale may change, originally it was expected that First Nuttall would carry out the works at the same time as their works on Helensfield Rail Bridge and Hilton Road. First Nuttall quote was too high. Job will go to tender but timing will be changed to 2007/08 to avoid First Nuttall works. There may be some cost in 2006/07 e.g. Public Utility diversions, design fees etc. will provide more detail of cost at later CPMG meetings
| Total - Roads & Transportation |  |  | 1709000 | -191000 | 1518000 | 1451356 | 119310 | 3088666 | 621999.71 | -99000 | 522999.71 |  | 2151666 | -191000 | 1960666 |  | 1128000 | 2157000 | 1595000 | 6840666
Environment
46 | Black Devon Landfill | 90 40 0100 | } | 200000 | 0 | 200000 | -101804 |  | 98196 | 5797.4 |  | 5797.4 |  | 98196 |  | 98196 |  | 0 |  |  | 98196 |  |  |  | Landfill site restored and wet land area substantially complete. The project has been short listed for an APSE award. |  | 200 | 0 | 200 | 0 | 0 | 0 | minimal savings >>>>>>>>>>>>>>
47 | Black Devon Landfill Gas Collection & Treatment Project | 90 40 0200 | } | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 400000 |  | 400000 | [5 empty] | 0 | 0 | 0 | 400 | 0 | 400
53 | Shared Transfer Facility @ Polmaise |  | } | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | [8 empty] | 0 | 0 | 0 | 400 | 0 | 400
48 | Cemeteries Strategy | 90 41 0110 | ] | 200000 | 0 | 200000 | 7708 |  | 207708 | 317 |  | 317 |  | 50700 |  | 50700 |  | 157008 | 100000 |  | 307708 |  |  |  | The cemetery strategy is being updated and new strategy will go to Council. Tillicoultry work delayed due to Land acquisition problems. Budget to be carried forward. |  | 300 | 0 | 300 | 0 | 0 | 0 | # | # | #
| Sunnyside cemetery Extension | 90 41 0100 | ] | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | # | # | #
| Tullibody Cemetery | 90 41 0130 | ] | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 |  |  |  | 0 |  | 0
49 | Contaminated Land | 90 41 0200 |  | 50000 | -50000 | 0 | 81000 |  | 81000 | 5410.5 | -0.06 | 5410.44 |  | 131000 | -50000 | 81000 |  | 0 |  |  | 81000 |  |  |  | Tenders have gone out for Bankhead depot for which this budget will be used, although tenders are likely to me more. The grant of £50k during the year is earmarked for a number of different projects to implement contaminated land strategy (e.g. Alva Gas works, Forthbank). |  | 50 | 50 | 0 | 0 | 0 | 0 | Budget already in place for Land Officer
50 | Parks & Open Spaces | 90 41 0400 |  | 80000 | 0 | 80000 | 0 |  | 80000 | 9948 |  | 9948 |  | 80000 |  | 80000 |  | 0 | 80000 | 83000 | 243000 |  |  |  | Currently budget of £80k has been allocated for new fencing, footpaths & tree planting at Abercromby Park, Tullibody & King George 5th Park , Clackmannan.
51 | Outdoor Play Area Strategy |  |  | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 75000 | 78000 | 153000
54a | Waste Recycling Project |  |  | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 400000 |  | 400000
54b | Wheeled / Litter Bins | 90 45 0230 |  | 135000 | 0 | 135000 | 0 |  | 135000 |  |  | 0 |  | 135000 |  | 135000 |  | 0 | 135000 | 135000 | 405000 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0
| Gateways & Roundabouts | 90 41 0300 |  |  |  | 0 | 0 |  | 0 |  |  | 0 |  | 40000 |  | 40000 |  | -40000 |  |  | 40000 |  |  |  | The Council approved a budget of £55k in June 2006, to be financed partly (£25k) by capital receipts from sale of land at Carbondale and the balance as an addition to the capital programme for 06/07. Budget has been allocated to enhance roundabouts at Arnsbrae, Menstrie, Muirside & Dumyat. Other sites have been considered with costs likely to be offset by sponsorship.
| Total - Environment |  |  | 665000 | -50000 | 615000 | -13096 | 0 | 601904 | 21472.9 | -0.06 | 21472.84 |  | 534896 | -50000 | 484896 |  | 117008 | 1190000 | 296000 | 2127904
Policy & Implementation
55 | Clackmannan Tollbooth | 90 50 3400 |  | 128000 | -71000 | 57000 | -1365 |  | 55635 | 16399.68 |  | 16399.68 |  | 55635 |  | 55635 |  | 0 |  |  | 55635 |  |  |  | Provisionally programmed for current year. Internal assessment of the Cross (Monument) being carried out presently. There were associated difficulties with it being listed. Landscaping work, fabric & remedial work will start in the current year. The total cost of the project s £161k spread over 3 years, grant funded by CHT (£32k) and Historic Scotland (£72k) and the balance of £57k to be funded by Council, of which £1k was spent last year. The HS grant is awaiting confirmation but the balance of Council contribution of £56k will be spent this year. |  | 0 | 0 | 0 | 161 | 104 | 57 | # | # | #
56 | National Cycle Route |  |  | 3000 | 0 | 3000 | 59000 |  | 62000 |  |  | 0 |  | 0 |  | 0 |  | 62000 |  |  | 62000 |  |  |  | Complexities of funding from outside bodies, Agricultural Land Act requirements. No grant funding agreed yet. Budget will be carried forward. |  | 3 | 0 | 3 | 0 | 0 | 0 | # | # | #
57 | Old Alloa Townscape Heritage Phase 2 | 90 50 2700 |  | 0 | 0 | 0 | 255150 |  | 255150 |  |  | 0 |  | 0 |  | 0 |  | 255150 |  |  | 255150 |  |  |  | As advised in the last report, Candleriggs Lane (value £65k) will not proceed now until the envelop work on Kilncraigs' 1936 building is complete, as Lane will be used to access Envelop work. Lime Tree Walk (£189k) delayed by PPP revised programme, siting of building etc. Budget for both programmes will be carried forward, awaiting progress on the other related projects. | Lime tree walk delayed by PPP revised programme | 0 | 0 | 0 | 0 | 0 | 0 | # | # | #
58 | Landscape Partnership - converse Ochills / Hillfoots |  |  | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 225000 |  | 225000
| Old Alloa Townscape Heritage Phase 1 | 90 51 8812 |  | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 |  |  |  | 0 |  | 0
| Kirkgate | 90 51 8808 | [6 empty] | 0 | 16734.45 |  | 16734.45 |  |  |  | 0 |  | 0 | [6 empty] | Accrued income from CHT to be received this year
| Alloa Docks | 90 60 1300 |  | 0 | 0 | 0 | 0 |  | 0 | 22290 |  | 22290 |  |  |  | 0 |  | 0 | [6 empty] | Accrued income from CHT to be received this year
59 | Core Path network for Access |  |  | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 38000 |  | 38000
67 | CSBP Restructuring |  |  | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
68 | Econ. Dev. Infrastructure: Eastern Clackmannanshire Development Opportunities |  |  | 100000 | 0 | 100000 | 0 |  | 100000 |  |  | 0 |  |  |  | 0 |  | 100000 |  |  | 100000 |  |  |  | Contingency sum for development in East Clackmannanshire awaiting results of meetings with Fife Enterprise. As advised last year, this is unlikely to proceed and the budget will be transferred to other projects yet to be approved by the Council. |  | 0 | 0 | 0 | 161 | 104 | 57 | 0 | 0 | 5
73 | Pavilions Business Park Phase 2 | 90 50 2400 |  | 300000 | 0 | 300000 | 40000 |  | 340000 |  |  | 0 |  | 40000 |  | 40000 |  | 300000 |  |  | 340000 |  |  |  | Work has commenced and due for completion in April 2007. Council contribution of £40k will be made to Joint Venture next year and the balance of £300k will be made on completion of project as advised in a report to the Council recently. |  | 0 | 0 | 0 | 0 | 0 | 0
74 | Dumyat Business Park Phase 3 | 90 50 2800 |  | 0 | 0 | 0 | 40000 |  | 40000 | 0 |  | 0 |  | 0 | 0 | 0 |  | 40000 |  |  | 40000 |  |  |  | The project is unlikely to proceed until Pavilions Phase 2 is complete as Joint Venture is unable to proceed with both projects. Position will be reviewed at the CSBP board meeting in October 2006. |  | 0 | 0 | 0 | 0 | 0 | 0
| Total - Policy & Implementation |  |  | 531000 | -71000 | 460000 | 392785 | 0 | 852785 | 55424.13 | 0 | 55424.13 |  | 95635 | 0 | 95635 |  | 757150 | 263000 | 0 | 1115785
Property Services
60 | Asbestos Removal | 90 40 3300 |  | 15000 | 0 | 15000 | 0 |  | 15000 |  |  | 0 |  | 15000 |  | 15000 |  | 0 |  |  | 15000 |  |  |  | Roof & walls of Land Services Building at Kelliebank. Tender to let in November 2006 |  | 15 | 0 | 15 | 0 | 0 | 0
61 | Centralised Kitchen | 90 50 4400 |  | 0 | 0 | 0 | 23782 |  | 23782 | 1233.94 |  | 1233.94 |  | 23782 |  | 23782 |  | 0 |  |  | 23782 |  |  |  | Retentions from previous year. |  | 0 | 0 | 0 | 0 | 0 | 0
62 | Disability Discrimination Act | 90 40 3400 |  | 0 | 0 | 0 | 0 |  | 0 | 2737 |  | 2737 |  |  |  | 0 |  | 0 |  | 20000 | 20000 | [5 empty] | 1 | 0 | 1 | 0 | 0 | 0
63a | Vehicle Replacement Programme (See details below) |  |  | 794000 | 0 | 794000 | 255000 |  | 1049000 | 95591 | 0 | 95591 |  | 989000 |  | 989000 |  | 60000 | 570000 | 500000 | 2119000 |  |  |  | Council were advised that £255k would be carried over from last year to obtain a better over all deal. This together with the current year's budget will be utilised this year, except for £60k which will be carried forward to next year. |  | 794 | 0 | 794 | 570 | 0 | 570
63b | Keilarsbrae land Purchases | 90 40 4300 |  | 0 | 0 | 0 | 11272 |  | 11272 |  |  | 0 |  |  |  | 0 |  | 11272 |  |  | 11272 |  |  |  | Admin & Legal are still investigating legal implications. Unlikely to spend budget this year. |  | 0 | 0 | 0 | 0 | 0 | 0
70 | Kilncraigs Mill 1936 Building Envelop | 90 50 4500 |  | 0 | 0 | 0 | 1289132 |  | 1289132 | 89061.8 |  | 89061.8 |  | 1605000 | -315000 | 1290000 |  | -868 |  |  | 1290000 |  |  |  | The Council allocated a budget of £1,350k of which £ 61k was spent last year on fees. The contract came in at £1,464k. As advised in last report, approach to Historic Scotland for a grant of £315k was successful to fund the balance of the contract sum plus fees. Retention of £60k will be carried forward to 07/08. Work progressing on site with external envelope including new roof, external rendering windows & glazed canopy at ground level. Completion date is January 2007.
71 | Kilncraigs Mill 1904 Development of 3rd & 4th Floors |  |  | 620000 | 0 | 620000 | 100000 |  | 720000 |  |  | 0 |  | 720000 |  | 720000 |  | 0 | 600000 | 30000 | 1350000 |  |  |  | This project was delayed pending decision from ESEP re. Claw back of ERDF grant implications and future use of 1904 building. Proposal is now for Development & Environment to move to ground, 1st & 2nd floors. The 3rd & 4th floors to be fitted out for SMEs to compensate claw back. Progress proposals are: Tender issue on 9th Oct; tender acceptance & site start 13th Nov 2006 and completion 2nd April 2007.
72a | Kilncraigs Mill 1904 Access Control & Zoning Services |  |  | 0 | 0 | 0 | 80000 |  | 80000 |  |  | 0 |  | 80000 |  | 80000 |  | 0 |  |  | 80000 |  |  |  | Progressing as part of contract for 3rd & 4th floor accommodation, but ground, 1st & 2nd floor requirements will be completed by December 2006. |  | 0 | 0 | 0 | 0 | 0 | 0
72b | Kilncraigs Mill Conversion | 90 50 3000 |  | 0 | 0 | 0 | 17000 |  | 17000 |  |  | 0 |  | 17000 |  | 17000 |  | 0 |  |  | 17000 |  |  |  | Retention from previous year |  | 0 | 0 | 0 | 0 | 0 | 0
98 | Kilncraigs Mill 1904 Upgrade of Existing |  |  | 740000 | 0 | 740000 | 0 |  | 740000 |  |  | 0 |  | 350000 |  | 350000 |  | 390000 | 20000 |  | 760000 |  |  |  | Essential works required for the 1904 building to allow Council occupancy and fit out requirements for SMEs on top two floors. Target programme is a s per project 71 above. Advance work in relation to the ground and second floors including IT upgrading, fire safety improvements, DDA compliance and alterations for occupancy to the value of £350k will be completed by January 2007. The balance will be carried forward to 07/08.
99 | Forthbank Accommodation Rationalisation |  |  | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 |  | 75000 | 75000
| Total - Property Services |  |  | 2169000 | 0 | 2169000 | 1776186 | 0 | 3945186 | 188623.74 | 0 | 188623.74 |  | 3799782 | -315000 | 3484782 |  | 460404 | 1190000 | 625000 | 5761054
| Total Development & Environmental Services |  |  | 5074000 | -312000 | 4762000 | 3607231 | 119310 | 8488541 | 887520.48 | -99000.06 | 788520.42 |  | 6581979 | -556000 | 6025979 |  | 2462562 | 4800000 | 2516000 | 15845409 | [5 empty] | 3671 | 348 | 3323 | 4321 | 512 | 3809 | -200 | -200 | -195
CORPORATE DEVELOPMENT
64 | Efficient Government/Customer First Developments | 90 70 1900 |  | 100000 | 0 | 100000 | 41000 |  | 141000 |  |  | 0 |  | 141000 |  | 141000 |  | 0 | 100000 | 100000 | 341000 |  |  |  | Proposal is for utilise budget for mobile and remote working. In addition is Joint working goes ahead, there will be need for licensing costs, IDOX, Revenue & Benefits systems etc. |  | 100 | 0 | 100 | 100 | 0 | 100
65 | IT Services | 90 70 0451 |  | 360000 | 0 | 360000 | 0 |  | 360000 | 51117.61 | 0 | 51117.61 |  | 360000 |  | 360000 |  | 0 | 330000 | 300000 | 990000 |  |  |  | The budget has been earmarked to proactively replace equipment required during the year. |  | 400 | 0 | 400 | 400 | 0 | 400
66a | Finance Services - General Ledger system | 90 70 1125 |  | 30000 | 0 | 30000 | 0 |  | 30000 | 6090.51 |  | 6090.51 |  | 30000 |  | 30000 |  | 0 | 30000 | 40000 | 100000 |  |  |  | Earmarked for new payroll server and ancillary costs and updated strategic system. |  | 30 | 0 | 30 | 30 | 0 | 30
[7 empty] | 0 |  | 0 |  |  | 0 |  |  |  | 0 |  | 0
| Rewiring & IT Cabling of Greenfield | 90 70 2100 |  | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 |  |  |  | 0 |  | 0
| Greenfield Dining Room | 90 70 2500 |  | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 |  |  |  | 0 |  | 0
83 | Greenfield Driveway & Parking |  |  | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 84000 |  | 84000
| Total Corporate Development |  |  | 490000 | 0 | 490000 | 41000 | 0 | 531000 | 57208.12 | 0 | 57208.12 |  | 531000 | 0 | 531000 |  | 0 | 544000 | 440000 | 1515000 | [5 empty] | 530 | 0 | 530 | 530 | 0 | 530 | 0 | 0 | 0
CHIEF EXECUTIVE SERVICES
| Miscellaneous |  |  | 0 | 0 | 0 | 0 |  | 0
75 | CCTV - Tron Court & Greenfield | 90 20 0600 |  |  |  | 0 | 53000 |  | 53000 | 147 |  | 147 |  | 53000 |  | 53000 |  | 0 |  |  | 53000 |  |  |  | Going ahead with Cameras in Civic Centre, Tullibody £10k. Bal is unallocated but looking at potential projects. |  | 0 | 0 | 0 | 0 | 0 | 0
76 | DDA & Asbestos Removal | 90 50 4300 |  | 25000 | 0 | 25000 | 19000 |  | 44000 | 37 |  | 37 |  | 44000 |  | 44000 |  | 0 |  |  | 44000 |  |  |  | DDA access work to Greenfield. Lighting, Door Alterations, roads & footpaths. Works to be completed by end of year. |  | 25 | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 0
| Mailroom Facilities & Franking Machine | 90 60 1700 |  | 0 | 0 | 0 | 0 |  | 0 | 15838.66 |  | 15838.66 |  | 16000 |  | 16000 |  | -16000 |  |  | 16000 |  |  |  | Budget was approved by Council last year
82 | Council Office Improvements |  |  | 0 | 0 | 0 | 0 |  | 0 | [10 empty] | 140000 | 140000
| Total Chief Executives Services |  |  | 25000 | 0 | 25000 | 72000 | 0 | 97000 | 16022.66 | 0 | 16022.66 |  | 113000 | 0 | 113000 |  | -16000 | 0 | 140000 | 253000 | [5 empty] | 25 | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 0
| TOTAL CAPITAL PROGRAMME (excluding SAK Rail Link) |  |  | 11222000 | -1360000 | 9862000 | 5833231 | 254310 | 15949541 | 1748033.38 | -99000.06 | 1649033.32 |  | 9893449 | -1564000 | 8329449 |  | 7620092 | 9302000 | 9496000 | 34786879 | [5 empty] | 13547 | 2444 | 11103 | 13152 | 2702 | 10450 | -200 | -200 | -195
38 | Total SAK Rail Project & Alloa ELR Project Costs | 90 50 3100 |  | 2057000 |  | 2057000 | -1132000 |  | 925000 | 17125425.96 | -22373421.58 | -5247995.62 |  | 815000 |  | 815000 |  | 110000 |  |  | 925000 |  |  |  | Budget only shows the Council contribution here. As advised previously , the maximum Council Contribution of £2.5m directly related to the Rail Link has been agreed. Of this the Council has already made a contribution of £1.575m in the past four years, leaving a balance of £925k. The latest projections indicate that the Council will make a contribution of £815k this year and the remaining £110k in 07/08 |  | 750 | 712 | 38 | 0 | 0 | 0 | -20 | -20 | -20
| TOTAL CAPITAL PROGRAMME (including SAK Rail Link) |  |  | 13279000 | -1360000 | 11919000 | 4701231 | 254310 | 16874541 | 18873459.34 | -22472421.64 | -3598962.3 |  | 10708449 | -1564000 | 9144449 |  | 7730092 | 9302000 | 9496000 | 35711879
| UNALLOCATED FUNDING | [5 empty] | Trfs (from) / to 05/06 | [25 empty] | Key for Recurring Revenue Costs Section
77 | Capital Receipts Estimate (see details below) | 90 90 xxxx |  | -1085000 |  | -1085000 |  |  | -1085000 | 119.07 | -154.32 | -35.25 |  | -500000 |  | -500000 |  | -585000 | -785000 | -1950000 | -3235000 |  |  |  | Apart from the two main receipts identified below, the only other capital receipts expected this year is in respect of two properties which is still subject to discussion. If successful, the sales may realise about £500k. The CAMP team are regularly reviewing the rationalisation of Council properties and further updates will be given in future reports. |  |  |  | 300 |  |  | 300
78 | Sale of Land at Dumyat Park & Ditch for Tullibody By Pass |  | } | 0 | 0 | 0 | -1550000 |  | -1550000 |  |  | 0 |  | -1395000 |  | -1395000 |  | -155000 |  |  | -1395000 |  |  |  | The sale of Land @ rear of St. Mungo's was completed on 22nd August. However, discussions are still on-going regarding Dumyat Park & Ditch. As advised previously there are issues regarding abnormal site conditions. The sellers have appointed engineers who are examining the site. Also, there are on going discussions with Scottish Water on re-routing of quest pipe. There will be additional costs in the region of £250k because of abnormal ground conditions & quest pipe re-routing. The net anticipated receipts for both lands is £3.145m. Of this £1.75m has been earmarked for the schools' PPP project as advised previously, leaving a balance of £1.395m for the 06/07 capital programme. This is a decrease of £155k on the original estimate. |  |  |  | 0
78 | Sale of Land to rear of St.Mungo's |  | } | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | [10 empty] | 0
80 | ERDF Grants (from Kilncraigs to be used to refund extra s94 advance in previous years) |  |  | -119000 | 0 | -119000 | 0 |  | -119000 |  |  | 0 |  | -119000 |  | -119000 |  | 0 |  |  | -119000 |  |  |  | These are retained ERDF Grants in respect of Kilncarigs, Allow Harbour, Alloa Tower & Allow West projects awaiting final audit which KPMG have almost completed. Retained grants will be released by Scottish Executive on satisfactory audit report. |  |  |  | 0 |  |  |  | Blank cells = | no info from service
81 | Repayment from Schools Devolved Budget for Computer Equipment | 90 10 4500 |  | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | [10 empty] | 0
[7 empty] | 0 |  | 0 |  |  | 0 |  |  |  | 0 |  | 0
|  |  |  | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 |  |  |  | 0 |  | 0
|  |  |  | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 |  |  |  | 0 |  | 0
| TOTAL - ESTIMATED UNALLOCATED FUNDING |  |  | -1204000 | 0 | -1204000 | -1550000 | 0 | -2754000 | 119.07 | -154.32 | -35.25 |  | -2014000 | 0 | -2014000 |  | -740000 | -785000 | -1950000 | -4749000 | [7 empty] | 300 |  |  | 300
1
NET FUNDING (SURPLUS) / DEFICIT
FINANCED BY C.F.C.R.
Net Capital Programme
[6 empty] | 10715000 | 3151231 | 254310 | 14120541 | 18873578.41 | -22472575.96 | -3598997.55 |  | 8694449 | -1564000 | 7130449 |  | 6990092 | 8517000 | 7546000 | 30962879 | [7 empty] | 10803 |  |  | 10150
| Project brought forward from 07/08 to 06/07 | [17 empty] | -254310
| Project carried forward from 06/07 to 07/08 | [17 empty] | 2963000
| PPP Allocation c/f to 08/09 | [17 empty] | -3600000 | 8425000
| Additional approved - Menstrie | [18 empty] | 400000 | 400000
Net Capital Programme (after transfers)
[19 empty] | 7625690 | 16371000 | 31362879
DETAILS PROPERTY CAPITAL RECEIPTS
77 | 22/4 Candleriggs, Alloa | 9090 6800 | [9 empty] | 0 |  |  |  | 0
77 | Skip Site - Hallpark, Sauchie | 9090 0726 | [9 empty] | 0 |  |  |  | 0
77 | Dewar St, Lorne Lane , Dollar | 9090 0800 | [9 empty] | 0 |  |  |  | 0
77 | Collyland - Fishcross | 9070 1700 | [9 empty] | 0 |  |  |  | 0
77 | Cowan Terrace Dollar | 9090 0875 | [9 empty] | 0 |  |  |  | 0
77 | Candleriggs, Alloa | 9090 0950 | [9 empty] | 0 |  |  |  | 0
77 | General Receipts | 9090 1000 | [9 empty] | 0 |  |  |  | 0
77 | Alexandra Street, Devonside | 9090 2200 | [9 empty] | 0 |  |  |  | 0
77 | Gap Site - Drysdale/Mill Street | 9090 1050 | [9 empty] | 0 |  |  |  | 0
77 | Bedford Place Alloa | 9090 1100 | [9 empty] | 0 |  |  |  | 0
77 | Bedford House - Alloa | 9090 1125 | [9 empty] | 0 |  |  |  | 0
77 | Cowden Park Alloa | 9090 1175 | [9 empty] | 0 |  |  |  | 0
77 | Forestmill Primary School | 9090 1325 | [9 empty] | 0 |  |  |  | 0
77 | Former School Clackmannan | 9090 1400 | [9 empty] | 0 |  |  |  | 0
77 | Orchard Tullibody - Housing Land | 9090 1525 | [9 empty] | 0 |  |  |  | 0
77 | Alloa West | 9090 0550 | [9 empty] | 0 |  |  |  | 0
77 | Alloa West - Autism Site | 9090 5800 | [9 empty] | 0 |  |  |  | 0
77 | Menstrie Centre Playground | 9090 1600 | [9 empty] | 0 |  |  |  | 0
77 | Collyland Road - Fishcross Housing Site | 9090 1700 | [9 empty] | 0 |  |  |  | 0
77 | Shops - Sauchie | 9090 1850 | [9 empty] | 0 |  |  |  | 0
77 | Kirkgate - Alloa | 9090 2100 | [9 empty] | 0 |  |  |  | 0
77 | Alexandra Street, Devonside | 9090 2200 | [9 empty] | 0 |  |  |  | 0
77 | Long Row Menstrie - Land | 9090 2700 | [9 empty] | 0 |  |  |  | 0
77 | Mar Place Sauchie WC | 9090 2800 | [9 empty] | 0 |  |  |  | 0
77 | 5 Muirside Road, Tullibody | 9090 3025 | [9 empty] | 0 |  |  |  | 0
77 | Park Street, Alva | 9090 3500 | [9 empty] | 0 |  |  |  | 0
77 | Bankhead - Devon Village | 9090 6100 | [9 empty] | 0 |  |  |  | 0
77 | Claremont Business Centre | 9090 1025 | [9 empty] | 0 |  |  |  | 0
77 | Dumyat Business Park | 9090 7000 | [9 empty] | 0 |  |  |  | 0
77 | Dumyat Business Park - Belhaven Breweries | 9090 7400 | [9 empty] | 0 |  |  |  | 0
77 | Earlsfield/Alloa Park | 9090 1750 | [9 empty] | 0 |  |  |  | 0
77 | Fishcross - Devon Riding Centre | 9090 6900 | [8 empty] | -154.32 | -154.32 |  |  |  | 0
77 | Land - Ochilvale Mill Alva | 9090 3900 | [9 empty] | 0 |  |  |  | 0
77 | St Mungo's Wynd Alloa | 9090 4000 | [9 empty] | 0 |  |  |  | 0
77 | 28 Ramsay Street, Clackmannan | 9090 4100 | [9 empty] | 0 |  |  |  | 0
77 | Old Toll House, Muckhart | 9090 4200 | [9 empty] | 0 |  |  |  | 0
77 | Main St Coalsnaughton | 9090 4300 | [9 empty] | 0 |  |  |  | 0
77 | Baingle Crescent | 9090 4400 | [9 empty] | 0 |  |  |  | 0
77 | Gas Governor at the Baingle | 9090 4500 | [9 empty] | 0 |  |  |  | 0
77 | Fairfield Sauchie | 9090 4600 | [9 empty] | 0 |  |  |  | 0
77 | Scout Hall Main Street Sauchie | 9090 4700 | [9 empty] | 0 |  |  |  | 0
77 | 3/5 Lower Mains Dollar | 9090 4800 | [9 empty] | 0 |  |  |  | 0
77 | Railway Station Alloa Road | 9090 4900 | [9 empty] | 0 |  |  |  | 0
77 | Land at Shawpark garage | 9090 5000 | [9 empty] | 0 |  |  |  | 0
77 | Service Station Site / Ditch Farm | 9090 5100 | [9 empty] | 0 |  |  |  | 0
77 | Pavilions Phase 2 | 9090 5200 | [9 empty] | 0 |  |  |  | 0
77 | TOMA CPO | 9090 5300 | [9 empty] | 0 |  |  |  | 0
77 | Sinclairs Haulage - Land | 9090 5400 | [9 empty] | 0 |  |  |  | 0
77 | Alva House Stable Block | 9090 5500 | [9 empty] | 0 |  |  |  | 0
77 | 3/5 Henderson Avenue, Alloa | 9090 5600 | [9 empty] | 0 |  |  |  | 0
77 | Land at Rear 78/80 West Stirling Street Alva | 9090 5700 | [9 empty] | 0 |  |  |  | 0
77 | Fishcross - Land at Devonbank Cottage | 9090 7100 | [9 empty] | 0 |  |  |  | 0
77 | Washington House - Alva | 9090 5900 | [9 empty] | 0 |  |  |  | 0
77 | 23 Main Street Sauchie | 9090 6000 | [9 empty] | 0 |  |  |  | 0
77 | Bank Head, Devon Village Rescue | 9090 6100 | [9 empty] | 0 |  |  |  | 0
77 | Smithfield Loan - Railway Embankment | 9090 6200 | [9 empty] | 0 |  |  |  | 0
77 | Superiority - Smithfield Loan | 9090 6300 | [9 empty] | 0 |  |  |  | 0
77 | Land at Broad Street, Alloa | 9090 6400 | [9 empty] | 0 |  |  |  | 0
77 | Land for Access to Stirling St | 9090 6500 | [9 empty] | 0 |  |  |  | 0
77 | Garage Site Gartmorn Dam House | 9090 6600 | [9 empty] | 0 |  |  |  | 0
77 | Lochy Falls,15 Upper Hillfoot, Dollar | 9090 6700 | [9 empty] | 0 |  |  |  | 0
77 | Former Toilets - Alva | 9090 7800 | [9 empty] | 0 |  |  |  | 0
77 | Hillpark | 9090 3700 | [9 empty] | 0 |  |  |  | 0
77 | Hallpark/Main Street Sauchie | 9090 0700 | [9 empty] | 0 |  |  |  | 0
77 | Land at Park St Tillicoultry | 9090 7300 | [9 empty] | 0 |  |  |  | 0
77 | Land/Car Park - Erskine ST Alloa | 9090 3800 | [9 empty] | 0 |  |  |  | 0
77 | Housing Land The Orchard Tullibody | 9090 1525 | [9 empty] | 0 |  |  |  | 0
77 | Property Conversion Feasibility Study | 9090 7200 | [9 empty] | 0 |  |  |  | 0
77 | Former Thistle Brewery | 9090 7700 | [9 empty] | 0 |  |  |  | 0
77 | Tullis Factory | 9090 1575 | [7 empty] | 119.07 |  | 119.07 |  |  |  | 0
77 | Sale of Land at Tullibody (Ditch Farm) | 9090 5100 | [9 empty] | 0 |  |  |  | 0
77 | Other | [10 empty] | 0 |  |  |  | 0
0
| Total - Property Sales | [8 empty] | 119.07 | -154.32 | -35.25 |  | 0 | 0 | 0
DETAILS VEHICLE REPLACEMENT PROGRAMME
63a | DLO Vehicle - Property Contracts | 9045 0100 |  | 222000 |  | 222000 | 30000 |  | 252000 |  |  | 0 |  | 252000 |  | 252000 |  | 0
63a | DLO Vehicle - Refuse Collection | 9045 0110 |  | 273000 |  | 273000 | 130000 |  | 403000 | 80575 |  | 80575 |  | 403000 |  | 403000 |  | 0
63a | DLO Vehicle - Street Cleaning | 9045 0120 |  | 70000 |  | 70000 |  |  | 70000 |  |  | 0 |  | 70000 |  | 70000 |  | 0
63a | DLO Vehicle - Land Services | 9045 0130 |  | 192600 |  | 192600 | 62000 |  | 254600 | 15016 |  | 15016 |  | 254600 |  | 254600 |  | 0
63a | DLO Vehicle - Roads Contracts | 9045 0140 |  | 120000 |  | 120000 | 31000 |  | 151000 |  |  | 0 |  | 151000 |  | 151000 |  | 0
63a | DLO Vehicle - Catering Services | 9045 0150 |  |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 0
63a | DLO Vehicle - Transport Pool | 9045 0160 |  | 36000 |  | 36000 |  |  | 36000 |  |  | 0 |  | 36000 |  | 36000 |  | 0
63a | DLO Vehicle - Leisure | 9045 0170 |  |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 0
63a | DLO Vehicle - Social Services | 9045 0200 |  |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 0
63a | DLO Vehicle - Burial Services | 9045 0210 |  | 33250 |  | 33250 |  |  | 33250 |  |  | 0 |  | 33250 |  | 33250 |  | 0
63a | DLO Vehicle - Countryside Rangers | 9045 0220 |  |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 0
63a | DLO Vehicle - G F Housing | 9045 0225 |  |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 0
| Glenochil Nursery |  |  | 1800 |  | 1800 |  |  | 1800 |  |  | 0 |  | 1800 |  | 1800 |  | 0
| Chief Executive |  |  | 11250 |  | 11250 |  |  | 11250 |  |  | 0 |  | 11250 |  | 11250 |  | 0
| Black Devon |  |  | 26000 |  | 26000 |  |  | 26000 |  |  | 0 |  | 26000 |  | 26000 |  | 0
|  |  |  | -191900 |  | -191900 | 2000 |  | -189900 |  |  | 0 |  | -249900 |  | -249900 |  | 60000
| Total - Vehicle Programme |  |  | 794000 | 0 | 794000 | 255000 |  | 1049000 | 95591 | 0 | 95591 |  | 989000 | 0 | 989000 |  | 60000
Note on H85: Authorised User: Not shown in 05/06 schedule as c/f to 06/07. But this was approved by Council later & therefore included here
Note on V59: Authorised User: £97k of the £100k has been b/f from 07/08 to 06/07
Note on V60: Authorised User: £22k of the £500k b/f from 07/08 to 06/07
Note on V82: Authorised User: Budget for 06/07 was originally £300k of which £100k was trf to 07/08. Since I have shown 06/07 as £200k, I have had to show 07/08 budget as £100k although this was a c/f from 06/07.
Note on AF97: Authorised User: contractor August Sept on site November and spend third year subject to positive response from PPP

## Appendix 3 (hidden)
APPENDIX 3
CLACKMANNANSHIRE COUNCIL
CAPITAL PROGRAMME 2006/07
NET BORROWING REQUIREMENT
|  |  |  | As per Feb Out-turn | [5 empty] | Total
|  |  | 2006/07 |  | 2005/06 |  |  |  | 2006/07 | 04/05 & 05/06
|  | £'000 | £'000 | £'000 | £'000 |  |  | £'000 | £'000 | £'000
2006/07 Approved Budget Excluding SAK Rail Link (9th February 2006) |  |  | 8696 |  | 11605 |  |  |  | 9361 | 18057
SAK Rail (Council Contribution) as originally approved (but only a
| proportion will be required - see # below) |  | 2019
0
10715
2006/07 Projects Transferred to 2005/06 as advised in last report |  | -279
2005/06 Projects Transferred to 2006/07 as advised in last report |  | 4562
# SAK contributions made in 01/02 to 02/03 under s94, now to be included
| as part of total Council Contriution of £2.5m | -1132
3151
13866
Projects Brought Forward from 2007/08
| IT Hardware Replacement in Schools | 60
| Leisure Bowl | 75
| B9140 Upgrades | 97
| B9140 Realignment of Bends | 22
254
14120
Overspends/ Revised Project Costs
| Gateways & Roundabouts (Approved by Council) | 45 |  |  |  | 45
| Vehicle Replacement |  |  | 51 |  | -51
| Finance IT Servers |  |  | 17 |  | -17
| Shared Services Centre |  |  | 5 |  | -5
| Mailroom Facilities & Franking Machine |  |  | 12 |  | -12
| Council Office Improvements | 16
| Miscellaneous | 3 |  | 7 |  | -4
|  |  | 64 |  | 92 |  | -28 |  | 0 | 64
Project slippages (budget c/f to 07/08 required):
| PPP Capital Support | -4650 |  |  |  | -4650
| Schools Development - PPP Support | -175 |  |  |  | -175
| Museum & Heritage | -250 |  | -250 |  | 0 |  | 250
| Alloa Library Refurbishment | -100 |  | -100 |  | 0 |  | 100
| Accident Prevention & Traffic Management |  |  | -10 |  | 10
| Alloa Town Centre | -705 |  | -748 |  | 43 |  | 258
| Footways at Muirside, Tullibody |  |  | -21 |  | 21
| A907/B910 Helensfield Junction | -423
| Cemetery Strategy | -157 |  | -4 |  | -153
| National Cycle Route | -62 |  | -59 |  | -3 |  | 39
| Old Alloa Heritage Phase 2 | -255 |  | -249 |  | -6 |  | 157
| Eastern Clackmannanshire Development Opportunities | -100
| Pavilions Phase 2 | -300 |  |  |  | -300
| Dumyat Phase 2 | -40 |  | -40 |  | 0 |  | 40
| Vehicle Replacement Programme | -60 |  | -173 |  | 113
| Keilarsbrae Land Purchase | -11 |  | -12 |  | 1 |  | 12
| Kilncraigs Mill 1904 Upgrade of Existing | -390 |  | -100 |  | -290
| Rail Link (SAK) | -110 |  | -39 |  | -71
|  |  | -7788 |  | -1805 |  | -5983 |  | 856 | -6932
Income / Grants Shortfall
| Capital receipts from sale of assets | 585 |  | 363 |  | 222
Capital receipts from sale of Land at Dumyat Park & Ditch and
| Land at Rear of St. Mungo's | 155 |  | 1550 |  | -1395
|  |  |  | 119 |  | -119 |  | -119
|  |  | 740 |  | 2032 |  | -1292 |  | -119 | 621
Net Expenditure 06/07 |  |  | 7136 |  | 11924 | -6796 | -7303 |  | 10098 | 17234
| Ludgate Traffic management System - Retentions | 1 |  | 4
| Mental Health Services - Retentions | 1
| Kilncarigs Mill | 1 |  | 1
|  | 3 |  | 5
Note on C16: Authorised User: c/f to 06/07 as per Mar Report = £7883k less SAK =( £1841k) less c/f of Cap Receipts = (£1550) Add Contaminated Land budget approved = £89k Net total = £4573
Note on C37: Kish Parmar: see below##
Note on F37: Kish Parmar: see below ##

## Appendix 2(draft) (hidden)
APPENDIX 2
CLACKMANNSHIRE COUNCIL
CAPITAL PROGRAMME 2005/06
NET BORROWING REQUIREMENT
OUT-TURN AS PER NOVEMBER 2005 | [6 empty] | SEPTEMBER OUTTURN
Total
|  |  | 2005/06 |  | 2006/07 | 04/05 & 05/06 |  | 2005/06
|  | £'000 | £'000 | £'000 | £'000 | £'000 | £'000 | £'000
2005/06 Approved Budget (24th January 2005) |  |  | 11605 |  | 9361 | 20966 |  | 11605
0
Overspends/ Revised Project Costs
| Legal Commitments for Education Projects (Retentions) | 21 |  |  |  |  | 5 |  | 16
| Fir Park Ski Centre | 4 |  |  |  |  | 20 |  | -16
| Flood Prevention | 1 |  |  |  |  | 1 |  | 0
| Tullibody By Pass | 14 |  |  |  |  | 14 |  | 0
| Wheeled Litter Bins | 20 |  |  |  |  | 20 |  | 0
| CSBP Restructuring | -250 |  |  |  |  | -250 |  | 0
| Eastern Clackmannanshire Development | -200 |  |  |  |  | -200 |  | 0
| Vehicle Replacement Programme | [5 empty] | 104 |  | -104
| Efficient Government/Customer First | -55 | [6 empty] | -55
| Rewiring & IT Cabling | [5 empty] | 6 |  | -6
| Shared Services Centre | 10 | [6 empty] | 10
| Ludgate House Resource Centre | -1 | [6 empty] | -1
| Greenfield Dinning Room | 1 | [6 empty] | 1
[7 empty] | -1 |  | 1
|  |  | -435 |  | 0 | -435 |  | -281
Projects Brought Forward from 2006/07 & 2007/08
| IT Hardware Replacement in Schools | 120 |  | -60 |  |  | 120 |  | 0
| Leisure Bowl - Complete refurbishment 20yr Plan | 35 |  |  |  |  | 200 |  | -165
| Road & Footpath Improvements | 90 | [6 empty] | 90
| Black Devon Landfil Site | 200 |  |  |  |  | 200 |  | 0
| Clackmannan Tolbooth | 25 | [6 empty] | 25
|  |  | 470 |  | -60 |  |  | 520
Project slippages (budget c/f to 06/07 required):
| Museum & Heritage | -250 |  | 250 |  |  | -250 |  | 0
| Schools Building Alarm System | 0 |  | 300 |  |  | 0 |  | 0
| Alloa Library Refurbishment | -100 |  | 100 |  |  | -100 |  | 0
| Alloa Town Centre | -658 |  | 258 |  |  | -258 |  | -400
| B9140 Collylands Cross upgrade | -350 |  |  |  |  | -300 |  | -50
| Rail Link (SAK) | -2019 | [6 empty] | -2019
| Contaminated Land | 0 |  |  |  |  | 89 |  | -89
| National Cycle Route | -59 |  | 39 |  |  | -39 |  | -20
| Old Alloa Heritage Phase 2 | -157 |  | 157 |  |  | -157 |  | 0
| Pavilions Phase 2 | 0 |  | 40 |  |  | -40 |  | 40
| Dumyat Phase 2 | -40 |  | 40 |  |  | -40 |  | 0
| Centralised Kitchen | -20 |  |  |  |  | -20 |  | 0
| Vehicle Replacement Programme | -51 | [6 empty] | -51
| Keilarsbrae Land Purchase | -12 |  | 12 |  |  | -12 |  | 0
| Kilncraigs Mill 1936 Building Envelope | -1300 |  | 1300 |  |  | -1300 |  | 0
| Kilncraigs Mill 1904 Development of 3rd & 4th floors | -100 | [6 empty] | -100
| Kilncraigs Mill 1904 Access & Zoning | -80 | [6 empty] | -80
|  |  | -5196 |  | 2496 | -2700 |  | -2427
Capital Receipts earmarked for PPP Contractors, not
previously budgeted in 3 year plan.
Sale of Land at Dumyat Park & Ditch and Land at
| rear of St Mungo's to be set aside | 650 |  |  |  |  | 650 |  | 0
|  |  | 650 |  | 0 | 650 |  | 650
Income / Grants Shortfall or Delayed
| Capital receipts from sale of assets | 347 |  |  |  |  | 340 |  | 7
| ERDF - Kilncraigs | 119 |  | -119 |  |  | 119 |  | 0
|  |  | 466 |  | -119 | 347 |  | 459
Out turn for 2005/06 |  |  | 7560 |  | 11678 | 19238 |  | 10526 | -2966

## Roads & Transport (for CN & AM) (hidden)
| 1 | 2 |  |  | 4 | 5 | 6 |  | 6 | 7 | 8 | 9 | 9 | 10 | 10 | 11 | 12 | 13 | 14 | 10 | 11 | 12 | 13 | 14 | 15 | 16
|  |  | Ledger codes |  | BUDGET 2005/06 |  |  | Actual to 28th Feb 2006 | 11: Project Status as at November | 2006/07 |  |  | 2007/08 |  |  | Recurring Revenue consequences
for the proposed project
|  | General Services Capital Programme | [18 empty] | (See Appendix 3) |  |  | (See Appendix 4) | bar: 6 to 9; 10; 11 to 10
|  | Development & Environmental Services |  |  | Approved Budget | External Grants | Net (Council Contribution) | Contract Payments | Other Expenditure | Total Expenditure | Total Income | Net Expenditure |  | Out-Turn given @ Dec meeting |  | Tenders issued / received | Contractor Appointed | Project start date | Other details or if project is delayed, reasons for delay | If project is delayed to next year, proposal to bring forward project from 3 year approved programme | Gross | External Grants | Net (Council Contribution) | Gross | External Grants | Net (Council Contribution)
Roads & Transportation | bar: 6 to 9; 10; 11 to 10
|  | 2005/06 |  |  | Gross |  | Borrowing | [19 empty] | 2004/05 | 2005/06 | 2006/07 | bar: 6 to 9; 10; 11 to 10
|  | Service / Project Name |  |  | £ | £ | £ | £ | [12 empty] | £'000 | £'000 | £'000 | £'000 | £'000 | £'000 | bar: 6 to 9; 10; 11 to 10
Abercromby PS
Alva Primary Extension
Beechwood Park
Lornshill Academy Sports Complex Phase 1
Lornshill Academy Sports Complex Phase 2
Pre Fives
Property Maintenance - additional from Revenue
Alloa Academy
Safer Routes to school
Strathdevon Primary
1 | 26 | Accident Prevention & Traffic Management | 90 40 1020 | [5 empty] | 7: 3113.73; 8: 0; 9: 3113.73; 10: 100000 | 1050 | 0 | 1050 | 1000 | 0 | 1000
|  | Alva Academy SEN | [6 empty] | 7: 0; 9: 0
|  | Alloa Library | [6 empty] | 7: 0; 9: 0
|  | Catering Improvements | [6 empty] | 7: 0; 9: 0
|  | Heavy Equipment Replacement | [6 empty] | 7: 0; 9: 0
|  | Greenhead Pavilion | [6 empty] | 7: 0; 9: 0
|  | Relocation of PSSS | [6 empty] | 7: 0; 9: 0
|  | Sunnyside PS | [6 empty] | 7: 0; 9: 0
|  | Canoe Site Purchase | [6 empty] | 7: 0; 9: 0
|  | Claremont P S Huts | [6 empty] | 7: 0; 9: 0
|  | Community Facility, Fishcross | [6 empty] | 7: 0; 9: 0
|  | Community Facility, Hawkhill | [6 empty] | 7: 0; 9: 0
|  | Lime Tree House upgrade wiring | [6 empty] | 7: 0; 9: 0
2 |  | Alloa Academy- PPP Capital Support |  |  |  |  | 0 |  | 7: 0; 9: 0 | 750 | 0 | 750 | 1250 | 0 | 1250
3 |  | Lornshill Academy & Tulligarth Phase 2 - PPP Capital Support |  |  |  |  | 0 |  | 7: 0; 9: 0 | 1150 | 0 | 1150 | 850 | 0 | 850
4 |  | B9140 Muirside, Tullibody |  |  | 50000 |  | 50000 |  | 9: 0; 11: Works Issued; 12: Markon | 100 | 0 | 100 | 0 | 0 | 0
|  | A908 Rural Road safety |  |  | 25000 |  | 25000 |  | 9: 0; 13: AUG; 14: Hallpark/Main Street Completed - Marchglen issued | 500 | 0 | 500 | 500 | 0 | 500
5 | [6 empty] | 0 |  | 9: 0 | 0 | 0 | 0 | 0 | 0 | 0
6 |  | A91 Rural Road safety |  |  | 25000 |  | 25000 |  | 9: 0; 11: Works Issued; 12: Markon; 14: East design Almost complete | 0 | 0 | 0 | 0 | 0 | 0
7 |  | B9140 Rural Road safety |  |  | 25000 |  | 25000 |  | 9: 0 | 0 | 0 | 0 | 0 | 0 | 0
2.918 | [6 empty] | 0 |  | 9: 0 | 0 | 0 | 0 | 0 | 0 | 0
3.0328 | [6 empty] | 0 |  | 9: 0 | 0 | 0 | 0 | 0 | 0 | 0
3.1475 | [6 empty] | 0 |  | 9: 0 | 0 | 0 | 0 | 0 | 0 | 0
3.2623 | [6 empty] | 0 |  | 9: 0 | 0 | 0 | 0 | 0 | 0 | 0
3.377 | [6 empty] | 0 |  | 9: 0 | 0 | 0 | 0 | 0 | 0 | 0
3.4918 | [6 empty] | 0 |  | 9: 0 | 0 | 0 | 0 | 0 | 0 | 0
3.6066 | [6 empty] | 0 |  | 9: 0 | 0 | 0 | 0 | 0 | 0 | 0
3.7213 | [6 empty] | 0 |  | 9: 0 | 0 | 0 | 0 | 0 | 0 | 0
8 |  | A907 Rural Road safety |  |  | 25000 |  | 25000 |  | 6: 2; 9: 0 | 300 | 0 | 300 | 8 | 0 | 8 | some maintenance but reduction in insurance
|  | (Reduction by Exec Team) |  |  | -50000 |  | -50000 |  | 9: 0
|  | Total - Accident Prevention & Traffic Management |  |  | 100000 | 0 | 100000 | 0 | 6: 2; 7: 3113.73; 8: 0; 9: 3113.73; 10: 100000 | 3850 | 0 | 3850 | 3608 | 0 | 3608 | 0 | 0 | 0
General Fund Housing - Enabling
| 32 | Bridges | 90 40 1700 | [5 empty] | 7: 126; 8: 0; 9: 126
|  | Ludgate House (c/f from 00/01) |  |  |  | 0 | 0
|  | Office Relocations |  |  |  | 0 | 0
|  | Whins Resource Centre - Floor Heating System |  |  |  | 0 | 0
|  | Care in Community Safety (** new proposal - see attached schedule) |  |  |  | 0 | 0
|  | Upgrade 6 Marshill Alloa |  |  |  | 0 | 0
|  | Document Imaging System (** new proposal - see attached schedule) |  |  |  | 0 | 0
22 |  | Kennet railway Bridge |  |  | 100000 |  | 100000 |  | 9: 0; 14: Dependent on Rail Project Timing | 20 | 0 | 20 | 0 | 0 | 0
23 |  | Riccarton Over Railway (B910/20 |  |  | 100000 |  | 100000 |  | 9: 0; 14: Dependent on Rail Project Timing | NK | NK | NK | NK | NK | NK
25 |  | Helensfield Rail Bridge Widening |  |  | 250000 |  | 250000 |  | 9: 0; 14: Dependent on Rail Project Timing | 475 | 0 | 475 | 475 | 0 | 475
26 |  | Menstrie Foorbridge |  |  | 40000 |  | 40000 |  | 6: 5; 9: 0; 13: COMPLETE; 14: Work completed - fees not yet included | 0 | 0 | 0 | 0 | 0 | 0
27 |  | Retention/overpayment |  |  |  |  | 0 |  | 9: 0 | 0 | 0 | 0 | 0 | 0 | 0
27 | [6 empty] | 0 |  | 9: 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total - Bridges |  |  | 490000 | 0 | 490000 | 0 | 6: 5; 7: 126; 8: 0; 9: 126; 10: 0 | 495 | 0 | 495 | 475 | 0 | 475 | 0 | 0 | 0
| 37 | Street Lighting | 90 40 4000 | [5 empty] | 7: 0; 8: 0; 9: 0
|  | A907 (carry forward of unused additional consent) |  | }
|  | A907 - Council Contribution |  | }
|  | Devonway, Clackmannan |  |  | 25000 |  | 25000 |  | 9: 0; 14: DLO unable to do - Tender required
28 |  | Alloa Road, Clackmannan |  |  | 20000 |  | 20000 |  | 6: 8; 9: 0; 14: DLO unable to do - Tender required | 100 | 0 | 100 | 100 | 0 | 100 | 0 | 0 | 0
29 |  | C59, Kennet |  |  | 73000 |  | 73000 |  | 9: 0; 14: DLO unable to do - Tender required | 0 | 0 | 0 | 0 | 0 | 0 | -200 | -200 | -200
[7 empty] | 0 |  | 9: 0; 14: DLO unable to do - Tender required | 0 | 0 | 0 | 0 | 0 | 0
30 | [6 empty] | 0 |  | 9: 0; 14: DLO unable to do - Tender required | 0 | 0 | 0 | 450 | 225 | 225
31 | [6 empty] | 0 |  | 9: 0; 14: DLO unable to do - Tender required | 275 | 0 | 275 | 0 | 0 | 0
32 |  | Pompee Road etc, Sauchie |  |  | 20000 |  | 20000 |  | 9: 0; 14: DLO unable to do - Tender required | 600 | 0 | 600 | 500 | 0 | 500 | 0 | 0 | 0
33 |  | Retentions & Carry over |  |  |  |  | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0
34 | [20 empty] | 150 | 0 | 150 | 400 | 0 | 400 | 0 | 0 | 0
[7 empty] | 0 |  | 9: 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 |  | 9: 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 |  | 9: 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 |  | 9: 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 |  | 9: 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 |  | 9: 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total - Street Lighting |  |  | 113000 | 0 | 113000 |  | 7: 0; 8: 0; 9: 0; 10: 0
| 41 | 20mph speed reduction | 90 40 3200 | [5 empty] | 7: 103303.4; 8: -99000; 9: 4303.4
45 |  | Carsview/Newmill, Tullibody |  |  | 30000 | -30000 | 0 |  | 9: 0; 13: ON HOLD | 200 | 0 | 200 | 0 | 0 | 0 | minimal savings >>>>>>>>>>>>>>
46 |  | Hill St. area, Alloa |  |  | 20000 | -20000 | 0 |  | 9: 0; 14: Preliminary Design Stage - Awaiting Consultation | 0 | 0 | 0 | 400 | 0 | 400
47 |  | Stirling St. Alva |  |  | 14000 | -14000 | 0 |  | 9: 0; 13: AUG; 14: Site investigation required (Trial Holes) | 300 | 0 | 300 | 0 | 0 | 0 | # | # | #
[7 empty] | 0 |  | 9: 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 |  | 9: 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 |  | 9: 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 |  | 9: 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 |  | 9: 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 |  | 9: 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 |  | 9: 0 | 0 | 0 | 0 | 0 | 0 | 0
48 |  | Rosebank / Keilarsbrae, Sauchie |  |  | 20000 | -20000 | 0 |  | 6: 1; 9: 0; 13: SEPT/OCT; 14: Awaiting Works Estimate From DLO | 50 | 50 | 0 | 0 | 0 | 0 | Budget already in place for Land Officer
[7 empty] | 0 |  | 9: 0 | 0 | 0 | 0 | 0 | 0 | 0
49 | [6 empty] | 0 |  | 9: 0 | 0 | 0 | 0 | 80 | 0 | 80
50 | [6 empty] | 0 |  | 9: 0 | 0 | 0 | 0 | 75 | 0 | 75
51 |  | Caledonian Rd, Alloa |  |  | 15000 | -15000 | 0 |  | 9: 0; 13: SEPT/OCT; 14: Awaiting Works Estimate From DLO | 0 | 0 | 0 | 0 | 0 | 0
|  | Total - 20mph speed reduction |  |  | 99000 | -99000 | 0 |  | 7: 0; 8: 0; 9: 0; 10: 0
CCTV - Alloa South & East
Community Planning
90 40 3000
63 | 35 | Road & Footway Improvements (SRMCS), including town centres | [6 empty] | 7: 4941.49; 8: 0; 9: 4941.49 | 100 | 0 | 100 | 100 | 0 | 100
|  | Resurfacing A91 Bridge Street, Dollar |  |  | 41000 |  | 41000 |  | 9: 0; 11: Sch. Of Rates; 13: COMLPETE
|  | Resurfacing A908 - Shillinghill to Fairfield |  |  | 69000 |  | 69000 |  | 9: 0; 11: Sch. Of Rates; 12: Colas; 13: COMLPETE; 14: Next year's section included
|  | Resurfacing A908 - Sauchie to Fishcross |  |  | 40000 |  | 40000 |  | 9: 0; 11: ON HOLD; 14: Provisionally postponed to 06/07
|  | A908 - Devon Village to Devonside |  | 40 | 40000 |  | 40000 |  | 9: 0; 11: Sch. Of Rates; 12: Stirling; 13: COMLPETE
|  | A907 - Claremont to Arnsbrae |  |  | 41000 |  | 41000 |  | 9: 0; 11: Sch. Of Rates; 12: Tarmac; 13: COMLPETE
|  | A977 - near Blairingone |  |  | 28000 |  | 28000 |  | 9: 0; 11: Sch. Of Rates; 12: Tarmac; 13: COMLPETE
|  | A823 Muckhart to Rumbling Bridge |  |  | 50000 |  | 50000 |  | 9: 0; 11: Sch. Of Rates; 12: Tarmac; 13: COMLPETE
[7 empty] | 0 |  | 9: 0; 11: Sch. Of Rates; 12: Colas; 13: COMLPETE
[7 empty] | 0 |  | 9: 0; 11: Sch. Of Rates; 12: Colas; 13: COMLPETE
[7 empty] | 0 |  | 9: 0; 11: Sch. Of Rates; 12: Colas; 13: COMLPETE
64 |  | B9140 - Between Muirside Roundabout & Dollarbeg |  |  | 127000 |  | 127000 |  | 6: 6; 9: 0; 11: Sch. Of Rates; 12: Stirling; 13: COMLPETE | 400 | 0 | 400 | 400 | 0 | 400
|  | B910 - Between A977 & Clackmannan |  |  | 115000 |  | 115000 |  | 9: 0; 11: Sch. Of Rates; 12: Tarmac; 13: COMLPETE
65 |  | Footway Improvements |  |  | 314000 |  | 314000 |  | 9: 0; 12: Clacks DLO; 14: Underway | 30 | 0 | 30 | 30 | 0 | 30
|  | A907 - Cambus (c/f from 04/05) |  |  |  |  | 0 |  | 9: 0; 11: Sch. Of Rates; 12: Colas; 13: COMLPETE
|  | B934 - Dunning - Urgent resurfacing carried out - b/f from 06/07 |  |  |  |  | 0 |  | 9: 0; 11: Sch. Of Rates; 12: Tarmac; 13: COMLPETE; 14: Urgent work out at contract prices
|  | Total - Road & Footway Improvements |  |  | 865000 | 0 | 865000 | 0 | 6: 6; 7: 4941.49; 8: 0; 9: 4941.49; 10: 0 | 530 | 0 | 530 | 530 | 0 | 530 | 0 | 0 | 0
| 36 | Cycling , Walking ,Safer Streets (CWSS) | 90 40 1310 | [5 empty] | 7: 17129.54; 8: 0; 9: 17129.54
Dumyat Business Park Phase 2
69 |  | Disabled Bays, Alva |  |  | 6000 | -6000 | 0 |  | 9: 0; 13: SEPT; 14: Design complete - awaiting works issue | 0 | 0 | 0 | 0 | 0 | 0
70 |  | Claremont, Alloa |  |  | 34000 | -34000 | 0 |  | 9: 0; 14: Awaiting consultation | 310 | 0 | 310 | 310 | 0 | 310
71 |  | B9096 Stirling Road, Tullibody |  |  | 30000 | -30000 | 0 |  | 9: 0; 14: Design complete - awaiting partial consultation | 0 | 0 | 0 | 0 | 0 | 0
|  | Victoria St / Alexandra Dr. Alloa |  |  | 12000 | -12000 | 0 |  | 6: 6; 9: 0; 14: Further consultation required | 0 | 0 | 0 | 0 | 0 | 0
|  | St. Serfs Area, Tullibody |  |  |  |  | 0 |  | 9: 0; 14: Zebra crossing on Menstrie Road - consultation required
|  | Total - Cycling , Walking ,Safer Streets (CWSS) |  |  | 82000 | -82000 | 0 | 0 | 6: 6; 7: 17129.54; 8: 0; 9: 17129.54; 10: 0 | 310 | 0 | 310 | 310 | 0 | 310 | 0 | 0 | 0

## Appen 2; 05-06 (hidden)
| 1 | 2 |  | 3 | 4 | 5 | 6 |  | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
|  | General Services Capital Programme |  | Gross Expenditure |  |  |  |  | External Grants Allocated |  |  |  | Net Expenditure (Council Contribution) |  |  |  | APPENDIX 2 | Recurring Revenue consequences
for the proposed project
|  | 2005/06 |  | Approved 17th Dec 2003 | Carried fwd from 04/05 | Additions/ (Deletions) | Revised |  | Approved 17th Dec 2003 | Carried fwd from 04/05 | Additions/ (Deletions) | Revised | Approved 17th Dec 2003 | Carried fwd from 04/05 | Additions/ (Deletions) | Revised
[5 empty] | from 2004/05 | from 2004/05 |  |  |  | from 2004/05 | from 2004/05 |  |  | from 2004/05 | from 2004/05
|  |  |  | 2005/06 | 2005/06 | 2005/06 | 2005/06 |  | 2005/06 | 2005/06 | 2005/06 | 2005/06 | 2005/06 | 2005/06 | 2005/06 | 2005/06 |  | 2004/05 | 2005/06 | 2006/07
|  | Service / Project Name |  | £'000 | £'000 | £'000 | £'000 |  | £'000 | £'000 | £'000 | £'000 | £'000 | £'000 | £'000 | £'000
BUDGET OUT
SERVICES TO PEOPLE
EDUCATION & COMMUNITY SERVICES
Abercromby PS
Alva Primary Extension
Beechwood Park
Lornshill Academy Sports Complex Phase 1
Lornshill Academy Sports Complex Phase 2
Pre Fives
Property Maintenance - additional from Revenue
Alloa Academy
Safer Routes to school
Strathdevon Primary
1 | 1 | Alva Academy - PPP Capital Support |  | 650 | 50 |  | 700 | [5 empty] | 650 | 50 |  | 700
Alva Academy SEN
Alloa Library
Catering Improvements
Heavy Equipment Replacement
Greenhead Pavilion
Relocation of PSSS
Sunnyside PS
Canoe Site Purchase
Claremont P S Huts
Community Facility, Fishcross
Community Facility, Hawkhill
Lime Tree House upgrade wiring
2 | 2 | Alloa Academy- PPP Capital Support | [10 empty] | 0 |  |  | 0
3 | 3 | Lornshill Academy & Tulligarth Phase 2 - PPP Capital Support | [10 empty] | 0 |  |  | 0
4 | 4 | DDA Compliance |  | 100 | 40 |  | 140 | [5 empty] | 100 | 40 |  | 140
| 5 | General - PPP Capital Support |  |  |  | 500 | 500 | [7 empty] | 500 | 500
5 |  | Kilncraigs 1936 @ |  | 250 |  | -250 | 0 | [5 empty] | 250 |  | -250 | 0
6 | 6 | Lochies - Specialist Accommodation |  | 50 |  |  | 50 | [5 empty] | 50 |  |  | 50
7 | 7 | Museum & Heritage Centre |  |  | 700 |  | 700 |  |  | 450 |  | 450 | 0 | 250 |  | 250
2.918 |  | Lochies School |  |  |  |  | 0 | [5 empty] | 0 |  |  | 0
3.0328 |  | Lochies School - Excellence Fund |  |  |  |  | 0 | [5 empty] | 0 |  |  | 0
3.1475 |  | Lochies School - Schools Budget Income |  |  |  |  | 0 | [5 empty] | 0 |  |  | 0
3.2623 |  | Museum & Heritage Centre - External Income |  |  |  |  | 0 | [5 empty] | 0 |  |  | 0
3.377 |  | Property Maintenance |  |  |  |  | 0 | [5 empty] | 0 |  |  | 0
3.4918 |  | Public Art |  |  |  |  | 0 | [5 empty] | 0 |  |  | 0
3.6066 |  | Retentions/Legally committed |  |  |  |  | 0 | [5 empty] | 0 |  |  | 0
3.7213 |  | SEN Adaptations |  |  |  |  | 0 | [5 empty] | 0 |  |  | 0
8 | 8 | School Building Alarm Systems |  | 25 |  | 275 | 300 | [5 empty] | 25 |  | 275 | 300 |  | some maintenance but reduction in insurance
9 | 9 | Schools Estate Renewal Programme |  | 763 |  | 199 | 962 |  | 763 |  | 199 | 962 | 0 |  |  | 0
11 | 10 | Tulligarth Sports Resurfacing - requirement of Lottery funding | [10 empty] | 0 |  |  | 0
12 | 11 | Alloa Library Refurbishment |  |  |  | 100 | 100 | [5 empty] | 0 |  | 100 | 100
14 | 13 | Heavy Equipment in Secondary Schools - Kilns etc |  |  |  | 60 | 60 | [5 empty] | 0 |  | 60 | 60
15 | 14 | IT Hardware Replacement in Schools |  |  |  | 100 | 100 |  |  |  | 40 | 40 | 0 |  | 60 | 60
16 | 15 | Legal Commitments - for projects undertaking in 04/05 |  |  |  | 25 | 25 | [5 empty] | 0 |  | 25 | 25
17 | 16 | Leisure Bowl - Complete refurbishment per 20yr Development plan | [10 empty] | 0 |  |  | 0
18 | 17 | Primary & Nursery School Developments |  |  |  | 300 | 300 | [5 empty] | 0 |  | 300 | 300
19 |  | Accessibility Strategy (if revenue budget approved, no need for capital) | [10 empty] | 0 |  |  | 0
20 | 19 | Fir Ski Park Centre - upgrade to building |  |  | 50 | -2 | 48 |  |  | 50 | -2 | 48 | 0 |  |  | 0
|  | Total Education & Community Service |  | 1838 | 840 | 1307 | 3985 |  | 763 | 500 | 237 | 1500 | 1075 | 340 | 1070 | 2485 |  | 0 | 0 | 0
|  | General Fund Housing - Enabling |  |  |  |  | 0
SOCIAL SERVICES
|  | Ludgate House (c/f from 00/01) |  |  |  |  | 0
|  | Office Relocations |  |  |  |  | 0
|  | Whins Resource Centre - Floor Heating System |  |  |  |  | 0
|  | Care in Community Safety (** new proposal - see attached schedule) |  |  |  |  | 0
|  | Upgrade 6 Marshill Alloa |  |  |  |  | 0
|  | Document Imaging System (** new proposal - see attached schedule) |  |  |  |  | 0
22 | 20 | DDA Compliance |  | 20 |  |  | 20 | [5 empty] | 20 |  |  | 20
23 | 21 | Joint FVNHS/ Adult Care Premises Occupation |  | NK |  |  | NK |  |  |  |  | NK | NK |  |  | NK
25 | 22 | Menstrie House En-Suite Conversion |  | 294 | 560 | -804 | 50 | [5 empty] | 294 | 560 | -804 | 50
26 | 23 | Ludgate House Resource Centre |  |  |  | 6 | 6 | [5 empty] | 0 |  | 6 | 6
27 | 24 | Mental Health Services |  |  | 30 | 30 | 60 |  |  | 30 | 30 | 60 | 0 |  |  | 0
|  | Total Social Services |  | 314 | 590 | -768 | 136 |  | 0 | 30 | 30 | 60 | 314 | 560 | -798 | 76 |  | 0 | 0 | 0
DEVELOPMENT & ENVIRONMENTAL SERVICES
Transportation
|  | A907 (carry forward of unused additional consent) | }
|  | A907 - Council Contribution | }
28 | 26 | Accident Prevention & Traffic Management |  | 100 |  |  | 100 | [5 empty] | 100 |  |  | 100 |  | 0 | 0 | 0
29 | 27 | Alloa Town Centre |  | 400 | 358 |  | 758 | [5 empty] | 400 | 358 |  | 758 |  | -200 | -200 | -200
|  | Accident Prevention & Traffic Management - Safer Roads, Cycling |  |  |  |  | 0 | [5 empty] | 0 |  |  | 0
30 | 28 | A91 East Stirling St. Alva Roundabout to access new school site | [10 empty] | 0 |  |  | 0
31 | 29 | A908/B908 Sauchie, Roundabout to facilitate new hospital | [10 empty] | 0 |  |  | 0
32 | 31 | B9140/ Collylands Cross Upgrade | } | 500 |  | -100 | 400 |  | 500 |  | -500 | 0 | 0 |  | 400 | 400 |  | 0 | 0 | 0
33 |  | B9140 Realignment of Bends | } | [9 empty] | 0 |  |  | 0
34 | 32 | Bridge Strengthening |  | 150 |  | 340 | 490 | [5 empty] | 150 |  | 340 | 490 |  | 0 | 0 | 0
|  | Eastern Link Road |  |  |  |  | 0 | [5 empty] | 0 |  |  | 0
|  | Hall Park |  |  |  |  | 0 | [5 empty] | 0 |  |  | 0
|  | Footpath Maintenance |  |  |  |  | 0 | [5 empty] | 0 |  |  | 0
|  | Roads Maintenance |  |  |  |  | 0 | [5 empty] | 0 |  |  | 0
|  | Smithfield Loan |  |  |  |  | 0 | [5 empty] | 0 |  |  | 0
|  | Roads Structural Maintenance |  |  |  |  | 0 | [5 empty] | 0 |  |  | 0
35 | 33 | Flood Prevention |  | 60 |  |  | 60 | [5 empty] | 60 |  |  | 60 |  | 0 | 0 | 0
36 | 34 | Retentions |  | 50 |  |  | 50 | [5 empty] | 50 |  |  | 50 |  | 0 | 0 | 0
37 | 35 | Road & Footway Improvements (SRMCS), including town centres |  | 865 |  |  | 865 | [5 empty] | 865 |  |  | 865 |  | 0 | 0 | 0
38 | 36 | Cycling , Walking ,Safer Streets (CWSS) |  | 182 |  | -100 | 82 |  | 182 | -100 |  | 82 | 0 |  |  | 0 |  | 0 | 0 | 0
39 | 37 | Street Lighting |  | 135 |  | 3 | 138 | [5 empty] | 135 |  | 3 | 138 |  | 0 | 0 | 0
|  | Tullibody Bypass (to be funded from special capital receipts) |  |  |  |  | 0 | [5 empty] | 0 |  |  | 0
40 | 38 | Total SAK Rail Project & Alloa ELR Project Costs |  | 15000 | 18137 | 299 | 33436 |  | 14494 | 16923 |  | 31417 | 506 | 1214 | 299 | 2019 |  | -20 | -20 | -20
41 | 39 | Tullibody By Pass ## |  | 600 | -600 |  | 0 |  | 400 |  | -400 | 0 | 200 |  | -200 | 0
42 | 40 | Tullibody By Pass c/f from 2004/05 |  |  | 45 |  | 45 |  |  |  |  | 0 | 0 | 45 |  | 45
43 | 41 | 20mph speed reduction |  |  |  | 99 | 99 |  |  |  | 99 | 99 | 0 |  |  | 0
44 | 42 | Footways at Muirside, Tullibody |  |  |  | 50 | 50 |  |  |  |  | 0 | 0 |  | 50 | 50
| 43 | SESTRAN Public Transport & Walking |  |  | 83 |  | 83 |  |  |  | 83 | 83 | 0 |  |  | 0
| 44 | SESTRAN Public Bus |  |  | 100 |  | 100 |  |  |  | 100 | 100 | 0 |  |  | 0
| 45 | SUSTRAN - Cycle Routes |  |  | 150 |  | 150 |  |  |  | 150 | 150 | 0 |  |  | 0
Environment
45 | 46 | Black Devon Landfill / Incinerator |  | 700 | 338 |  | 1038 | [5 empty] | 700 | 338 |  | 1038 |  | minimal savings >>>>>>>>>>>>>>
46 | 47 | Black Devon Landfill Gas Collection & Treatment Project
47 | 48 | Cemeteries Strategy |  | 84 |  |  | 84 | [5 empty] | 84 |  |  | 84 |  | # | # | #
| 49 | Cycle Path Network |  |  |  |  | 0 | [5 empty] | 0
| 50 | Dollar Cemetery |  |  |  |  | 0 | [5 empty] | 0
| 51 | Environmental Improvements |  |  |  |  | 0 | [5 empty] | 0
| 52 | Old Alloa THI Project |  |  |  |  | 0 | [5 empty] | 0
| 53 | Hillfoots Initiative |  |  |  |  | 0 | [5 empty] | 0
| 54 | Incineration Plant Demolition |  |  |  |  | 0 | [5 empty] | 0
| 55 | Landward Village Initiative |  |  |  |  | 0 | [5 empty] | 0
48 | 49 | Contaminated Land |  | 50 |  |  | 50 |  | 50 |  |  | 50 | 0 |  |  | 0 |  | Budget already in place for Land Officer
| 57 | Tullis Factory Demolition | [10 empty] | 0
49 | 50 | Parks & Open Spaces
50 | 51 | Outdoor Play Area Strategy
51 | 52 | Shared Compost Facility @ Polmaise |  |  |  | 13 | 13 |  |  |  |  | 0 | 0 |  | 13 | 13
52 | 53 | Shared Transfer Facility @ Polmaise |  |  |  | 400 | 400 |  |  |  |  | 0 | 0 |  | 400 | 400
53 | 54a | Waste Recycling Project
| 54b | Wheeld /Litter Bins |  |  |  | 100 | 100 |  |  |  |  | 0 |  |  | 100 | 100
Partnerships
54 | 55 | Clackmannan Tolbooth |  | 170 |  |  | 170 |  | 170 |  |  | 170 | 0 |  |  | 0 |  | # | # | #
55 | 56 | National Cycle Route |  | 129 |  |  | 129 |  | 70 |  |  | 70 | 59 |  |  | 59 |  | # | # | #
56 | 57 | Old Alloa Townscape Heritage |  | 6 | 248 |  | 254 | [5 empty] | 6 | 248 |  | 254 |  | # | # | #
57 | 58 | Landscape Partnership - Conserve Ochills / Hillfoots | [10 empty] | 0 |  |  | 0
58 | 59 | Core Path Network for Access | [10 empty] | 0 |  |  | 0
Property Services
59 | 60 | Asbestos Removal |  | 15 |  |  | 15 | [5 empty] | 15 |  |  | 15
60 | 61 | Centralised Kitchen |  |  | 350 | 350 | 700 | [5 empty] | 0 | 350 | 350 | 700
61 | 62 | Disability Discrimination Act |  |  |  | 33 | 33 | [5 empty] | 0 |  | 33 | 33
62 | 63a | Vehicle Replacement Programme |  |  |  | 1316 | 1316 | [5 empty] | 0 |  | 1316 | 1316
| 63b | Keilarsbrae land Purchases |  |  |  | 12 | 12 | [5 empty] | 0 |  | 12 | 12
Retentions Carry forward (projects to be identified)
|  | Total Development & Environmental Services |  | 19196 | 19209 | 2815 | 41220 |  | 15866 | 16823 | -468 | 32221 | 3330 | 2553 | 3116 | 8999 |  | -220 | -220 | -220
CORPORATE DEVELOPMENT
CCTV - Alloa South & East
Community Planning
63 | 64 | Efficient Government/Customer First Developments |  | 600 |  | -500 | 100 |  | 500 | -500 |  | 0 | 100 |  |  | 100
|  | Business Change & Organisational Development | } |  |  |  |  | }
|  | Clack Web - eServices & eCommunity | } |  |  |  |  | }
|  | Content & Knowledge Management | } |  |  |  |  | }
|  | One Stop Shop & Customer Services Centre | } |  |  |  |  | }
|  | Shared Services & Data Sharing | } |  |  |  |  | }
Council Office - Rewiring
Information Services - Salaries
Kilncraigs Mill Develop. (consent brought forward)
64 | 65 | IT Services (No submissions received - this is an estimate) |  | 400 |  |  | 400 | [5 empty] | 400 |  |  | 400
65 | 66a | Finance Services - General Ledger system |  |  |  | 30 | 30 | [5 empty] | 0 |  | 30 | 30
| 66b | Council Offices - Greenfield Traffic management System |  |  |  | 26 | 26 | [7 empty] | 26 | 26
|  | Total Corporate Development |  | 1000 | 0 | -444 | 556 |  | 500 | -500 | 0 | 0 | 500 | 0 | 56 | 556 |  | 0 | 0 | 0
CHIEF EXECUTIVE SERVICES
Economic Development
Dumyat Business Park Phase 2
66 | 67 | CSBP Restructuring |  |  | 500 |  | 500 |  |  | 250 |  | 250 | 0 | 250 |  | 250 |  | 0 | 0 | 0
67 | 68 | Econ. Dev. Infrastructure: Eastern Clackmannanshire Development Opportunities |  | 133 | 133 |  | 266 |  | 33 | 33 |  | 66 | 100 | 100 |  | 200 |  | 0 | 0 | 5
68 | 69 | Workspace Provision for Social Enterprises' Recycling project |  | 500 |  | -500 | 0 | [5 empty] | 500 |  | -500 | 0 |  | 0 | 10 | 10
69 | 70 | Kilncraigs Mill 1936 Building Envelop |  |  |  | 1350 | 1350 | [5 empty] | 0 |  | 1350 | 1350
70 | 71 | Kilncraigs Mill 1904 Development of 3rd & 4th Floors |  |  |  | 100 | 100 | [5 empty] | 0 |  | 100 | 100
71 | 72a | Kilncraigs Mill 1904 Access Control & Zoning Services |  |  |  | 80 | 80 | [5 empty] | 0 |  | 80 | 80
| 72b | Kilncraigs Mill Conversion |  |  |  | 45 | 45 | [7 empty] | 45 | 45
72 | 73 | Pavilions Business Park Phase 2 |  |  |  | 1890 | 1890 |  |  |  | 1850 | 1850 | 0 |  | 40 | 40
73 | 74 | Dumyat Business Park Phase 3 |  |  |  | 1286 | 1286 |  |  |  | 1246 | 1246 | 0 |  | 40 | 40
Miscellaneous
74 | 75 | CCTV - Tron Court |  |  |  | 78 | 78 | [5 empty] | 0 |  | 78 | 78
75 | 76 | DDA & Asbestos Removal |  | 25 |  |  | 25 | [5 empty] | 25 |  |  | 25 |  | 0 | 0 | 0
|  | Total Chief Executives Services |  | 658 | 633 | 4329 | 5620 |  | 33 | 283 | 3096 | 3412 | 625 | 350 | 1233 | 2208 |  | 0 | 0 | 0
|  | TOTAL CAPITAL PROGRAMME |  | 23006 | 21272 | 7239 | 51517 |  | 17162 | 17136 | 2895 | 37193 | 5844 | 3803 | 4677 | 14324 |  | -220 | -220 | -220
|  | UNALLOCATED FUNDING | [15 empty] | Key for Recurring Revenue Costs Section
76 | 77 | Capital Receipts Estimate (NET OF EXPENSES) | [10 empty] | 390 |  |  | 390
41 | 78 | Sale of Land at Dumyat Park & Ditch for Tullibody By Pass | [12 empty] | 2200 | 2200
77 | 79 | APM Sales | [13 empty] | 0 |  | # = | Costs considered but not
78 | 80 | ERDF Grants (from Kilncraigs to be used to refund extra s94 advance in previous years) | [11 empty] | 119 |  | 119 |  | Blank cells = | no info from service
79 | 81 | Repayment from Schools Devolved Budget for Computer Equipment | [10 empty] | 10 |  |  | 10
0
|  | TOTAL - ESTIMATED UNALLOCATED FUNDING | [10 empty] | 400 | 119 | 2200 | 2719
|  | NET FUNDING (SURPLUS) / DEFICIT |  |  | #REF! | #REF!
FINANCED BY C.F.C.R.
|  | Net Capital Expenditure to be Funded from Prudential Borrowing | [10 empty] | 5444 | 3684 | 2477 | 11605
Ref to |  | List of External Allocated Funding referred to above
above |  | Contributions from other sources
7 | 7 | Heritage & Lottery Grants for Museum Project | [7 empty] | 450 |  | 450
15 | 14 | National Priorities Action Fund - IT Hardware Replacement in Schools | [8 empty] | 40 | 40
20 | 19 | The Big Lottery Fund - Fir Ski Park Centre - upgrade to building | [7 empty] | 50 | -2 | 48
32 | 31 | Planning Gain Income for B9140/Collylands Cross (now not expected ) | [6 empty] | 500 |  | -500 | 0
41 | 39 | Sale of Land @ Ditch Farm / Tullibody (originally earmarked for TBP, but now trf for general capital) | [6 empty] | 400 |  | -400 | 0
54 | 55 | Heritage Lottery Fund for Clackmannan Tolbooth | [6 empty] | 125 |  |  | 125
54 | 55 | Historic Scotland Grant for Clackmannan Tolbooth | [6 empty] | 45 |  |  | 45
55 | 56 | National Cycle Route - Private | [6 empty] | 35 |  |  | 35
55 | 56 | National Cycle Route - Sustrans | [6 empty] | 35 |  |  | 35
57 | 58 | Heritage Lottery Fund for Landscape Partnership Project | [9 empty] | 0
58 | 59 | SNH - Core Path Network for Access | [9 empty] | 0
66 | 67 | Scarborough Development Group - CSBP Restructuring | [7 empty] | 250 |  | 250
67 | 68 | ERDF - Eastern Clackmannanshire Development Opportunities | [6 empty] | 33 | 33 |  | 66
72 | 73 | CSBP - Pavilions Business Park Phase 2 | [8 empty] | 1378 | 1378
72 | 73 | ERDF - Pavilions Business Park Phase 2 | [8 empty] | 472 | 472
73 | 74 | CSBP - Dumyat Business Park Phase 3 | [8 empty] | 924 | 924
73 | 74 | ERDF - Dumyat Business Park Phase 3 | [8 empty] | 322 | 322
[9 empty] | 1173 | 783 | 2234 | 4190
Central Government Grants
9 | 9 | Special Grant for Schools Estate Renewal Programme | [6 empty] | 763 |  | 199 | 962
27 | 24 | Scottish Executive Grant for Mental Health Services | [7 empty] | 30 | 30 | 60
38 | 36 | Cycling, Walking, Safer Streets (CWSS) from SE | [6 empty] | 182 | -100 |  | 82
40 | 38 | Stirling / Alloa / Kincardine Rail Link - Specific Grant | [6 empty] | 14494 | 16923 |  | 31417
43 | 41 | 20mph Grant from Scottish Executive | [8 empty] | 99 | 99
| 43 | SESTRAN Public Transport & Walking | [8 empty] | 83 | 83
| 44 | SESTRAN Public Bus | [8 empty] | 100 | 100
| 45 | SUSTRAN - Cycle Routes | [8 empty] | 150 | 150
48 | 49 | Contaminated Land | [6 empty] | 50 |  |  | 50
63 | 64 | Efficient Government / Customer First Developments (converted to RSG) | [6 empty] | 500 | -500 |  | 0
[9 empty] | 15989 | 16353 | 661 | 33003
|  | Total External Funding Allocated | [6 empty] | 17162 | 17136 | 2895 | 37193
| @ | = Refer to note in "Revenue & other Implication" sheet
| ## | = £600k Tullibody By Pass allocation returned to SAK Rail, having been utilised in 2004/05
| NK | = Costs or funding of project not known
= No submissions received in the current round of bids, but included here as bids received in the previous round of bids for the 3 year plan.

## Appen 3; 06-07 (hidden)
| 1 | 2 |  | 3 | 4 | 5 | 6 |  | 7 | 8 | 9 | 10 | 11 | 11 | 12 | 13 | 14
|  | General Services Capital Programme |  | Gross Expenditure |  |  |  |  | 7: External Grants Allocated; 11: Net Expenditure (Council Contribution) | APPENDIX 3 | Recurring Revenue consequences
for the proposed project | bar: 7 to 10; 11 to 14
|  | 2006/07 |  | Approved 17th Dec 2003 | Carried fwd from 05/06 | Additions/ (Deletions) | Revised |  | Approved 17th Dec 2003 | Carried fwd from 05/06 | Additions/ (Deletions) | Revised |  | Approved 17th Dec 2003 | Carried fwd from 05/06 | Additions/ (Deletions) | Revised
[15 empty] | from 2004/05 | from 2004/05
|  |  |  | 2006/07 | 2006/07 | 2006/07 | 2006/07 |  | 2006/07 | 2006/07 | 2006/07 | 2006/07 |  | 2006/07 | 2006/07 | 2006/07 | 2006/07 |  | 2004/05 | 2005/06 | 2006/07
|  | Service / Project Name |  | £'000 | £'000 | £'000 | £'000 |  | £'000 | £'000 | £'000 | £'000 |  | £'000 | £'000 | £'000 | £'000
0
SERVICES TO PEOPLE
EDUCATION & COMMUNITY SERVICES
Abercromby PS
Alva Primary Extension
Beechwood Park
Lornshill Academy Sports Complex Phase 1
Lornshill Academy Sports Complex Phase 2
Pre Fives
Property Maintenance - additional from Revenue
Alloa Academy
Safer Routes to school
Strathdevon Primary
1 | 1 | Alva Academy - PPP Capital Support |  | 1050 |  |  | 1050 |  | 11: 1050; 14: 1050
Alva Academy SEN
Alloa Library
Catering Improvements
Heavy Equipment Replacement
Greenhead Pavilion
Relocation of PSSS
Sunnyside PS
Canoe Site Purchase
Claremont P S Huts
Community Facility, Fishcross
Community Facility, Hawkhill
Lime Tree House upgrade wiring
2 | 2 | Alloa Academy- PPP Capital Support |  |  |  | 750 | 750 |  | 11: 0; 13: 750; 14: 750
3 | 3 | Lornshill Academy & Tulligarth Phase 2 - PPP Capital Support |  | 1150 |  |  | 1150 |  | 300 |  | -300 | 0 |  | 850 |  | 300 | 1150
4 | 4 | DDA Compliance |  | 100 |  |  | 100 |  | 11: 100; 14: 100
| 5 | General - PPP Capital Support |  |  |  | 500 | 500 |  | 13: 500; 14: 500
5 |  | Kilncraigs 1936 @ |  | 500 |  | -500 | 0 |  | 11: 500; 13: -500; 14: 0
6 | 6 | Lochies - Specialist Accommodation |  |  |  |  | 0 |  | 11: 0; 14: 0
7 | 7 | Museum & Heritage Centre |  |  |  |  | 0 |  | 10: 0; 11: 0; 14: 0
2.918 | 5.0633 | Lochies School |  |  |  |  | 0 |  | 11: 0; 14: 0
3.0328 | 5.3038 | Lochies School - Excellence Fund |  |  |  |  | 0 |  | 11: 0; 14: 0
3.1475 | 5.5443 | Lochies School - Schools Budget Income |  |  |  |  | 0 |  | 11: 0; 14: 0
3.2623 | 5.7848 | Museum & Heritage Centre - External Income |  |  |  |  | 0 |  | 11: 0; 14: 0
3.377 | 6.0253 | Property Maintenance |  |  |  |  | 0 |  | 11: 0; 14: 0
3.4918 | 6.2658 | Public Art |  |  |  |  | 0 |  | 11: 0; 14: 0
3.6066 | 6.5063 | Retentions/Legally committed |  |  |  |  | 0 |  | 11: 0; 14: 0
3.7213 | 6.7468 | SEN Adaptations |  |  |  |  | 0 |  | 11: 0; 14: 0
8 | 8 | School Building Alarm Systems |  |  |  | 300 | 300 |  | 11: 0; 13: 300; 14: 300 |  | some maintenance but reduction in insurance
9 | 9 | Schools Estate Renewal Programme |  |  |  | 1008 | 1008 |  | 9: 1008; 10: 1008; 11: 0; 14: 0
11 | 10 | Tulligarth Sports Resurfacing - requirement of Lottery funding | [6 empty] | 11: 0; 14: 0
12 | 11 | Alloa Library Refurbishment |  |  |  | 100 | 100 |  | 11: 0; 13: 100; 14: 100
14 | 13 | Heavy Equipment in Secondary Schools - Kilns etc |  |  |  | 30 | 30 |  | 11: 0; 13: 30; 14: 30
15 | 14 | IT Hardware Replacement in Schools |  |  |  | 100 | 100 |  | 9: 40; 10: 40; 11: 0; 13: 60; 14: 60
16 | 15 | Legal Commitments - for projects undertaking in 04/05 |  |  |  | 25 | 25 |  | 11: 0; 13: 25; 14: 25
17 | 16 | Leisure Bowl - Complete refurbishment per 20yr Development plan |  |  |  | 200 | 200 |  | 11: 0; 13: 200; 14: 200
18 | 17 | Primary & Nursery School Developments |  |  |  | 300 | 300 |  | 11: 0; 13: 300; 14: 300
19 |  | Accessibility Strategy (if revenue budget approved, no need for capital) | [6 empty] | 11: 0; 14: 0
20 | 19 | Fir Ski Park Centre - upgrade to building |  |  |  |  | 0 |  | 10: 0; 11: 0; 14: 0
|  | Total Education & Community Service |  | 2800 | 0 | 2813 | 5613 |  | 300 | 0 | 748 | 1048 |  | 2500 | 0 | 2065 | 4565 |  | 0 | 0 | 0
|  | General Fund Housing - Enabling |  |  |  |  | 0
SOCIAL SERVICES
|  | Ludgate House (c/f from 00/01) |  |  |  |  | 0
|  | Office Relocations |  |  |  |  | 0
|  | Whins Resource Centre - Floor Heating System |  |  |  |  | 0
|  | Care in Community Safety (** new proposal - see attached schedule) |  |  |  |  | 0
|  | Upgrade 6 Marshill Alloa |  |  |  |  | 0
|  | Document Imaging System (** new proposal - see attached schedule) |  |  |  |  | 0
22 | 20 | DDA Compliance |  | 20 |  |  | 20 |  | 11: 20; 14: 20
23 | 21 | Joint FVNHS/ Adult Care Premises Occupation |  | NK |  |  | NK | bar: 7; 10; 11; 14
25 | 22 | Menstrie House En-Suite Conversion |  |  |  | 475 | 475 |  | 11: 0; 13: 475; 14: 475
26 | 23 | Ludgate House Resource Centre |  |  |  |  | 0 |  | 11: 0; 14: 0
27 | 24 | Mental Health Services |  |  |  |  | 0 |  | 10: 0; 11: 0; 14: 0
|  | Total Social Services |  | 20 | 0 | 475 | 495 |  | 0 |  | 0 | 0 |  | 20 | 0 | 475 | 495 |  | 0 | 0 | 0
DEVELOPMENT & ENVIRONMENTAL SERVICES
Transportation
|  | A907 (carry forward of unused additional consent) | }
|  | A907 - Council Contribution | }
28 | 26 | Accident Prevention & Traffic Management |  | 100 |  |  | 100 |  | 11: 100; 14: 100 |  | 0 | 0 | 0
29 | 27 | Alloa Town Centre |  |  |  |  | 0 |  | 11: 0; 14: 0 |  | -200 | -200 | -200
|  | Accident Prevention & Traffic Management - Safer Roads, Cycling |  |  |  |  | 0 |  | 11: 0; 14: 0
30 | 28 | A91 East Stirling St. Alva Roundabout to access new school site |  |  |  |  | 0 |  | 11: 0; 14: 0
31 | 29 | A908/B908 Sauchie, Roundabout to facilitate new hospital |  |  |  | 275 | 275 |  | 11: 0; 13: 275; 14: 275
32 | 31 | B9140/ Collylands Cross Upgrade |  |  |  | 600 | 600 |  | 10: 0; 11: 0; 13: 600; 14: 600 |  | 0 | 0 | 0
33 |  | B9140 Realignment of Bends |  |  |  |  | 0 |  | 11: 0; 14: 0
34 | 32 | Bridge Strengthening |  | 150 |  |  | 150 |  | 11: 150; 14: 150 |  | 0 | 0 | 0
|  | Eastern Link Road |  |  |  |  | 0 |  | 11: 0; 14: 0
|  | Hall Park |  |  |  |  | 0 |  | 11: 0; 14: 0
|  | Footpath Maintenance |  |  |  |  | 0 |  | 11: 0; 14: 0
|  | Roads Maintenance |  |  |  |  | 0 |  | 11: 0; 14: 0
|  | Smithfield Loan |  |  |  |  | 0 |  | 11: 0; 14: 0
|  | Roads Structural Maintenance |  |  |  |  | 0 |  | 11: 0; 14: 0
35 | 33 | Flood Prevention |  | 60 |  | 40 | 100 |  | 11: 60; 13: 40; 14: 100 |  | 0 | 0 | 0
36 | 34 | Retentions |  | 60 |  |  | 60 |  | 11: 60; 14: 60 |  | 0 | 0 | 0
37 | 35 | Road & Footway Improvements (SRMCS), including town centres |  | 850 |  |  | 850 |  | 11: 850; 14: 850 |  | 0 | 0 | 0
38 | 36 | Cycling , Walking ,Safer Streets (CWSS) |  |  |  | 84 | 84 |  | 9: 84; 10: 84; 11: 0; 14: 0 |  | 0 | 0 | 0
39 | 37 | Street Lighting |  | 150 |  |  | 150 |  | 11: 150; 14: 150 |  | 0 | 0 | 0
|  | Tullibody Bypass (to be funded from special capital receipts) |  |  |  |  | 0 |  | 11: 0; 14: 0
40 | 38 | Total SAK Rail Project & Alloa ELR Project Costs |  | 750 |  |  | 750 |  | 7: 712; 10: 712; 11: 38; 14: 38 |  | -20 | -20 | -20
41 | 39 | Tullibody By Pass |  |  |  |  | 0 |  | 10: 0; 11: 0; 14: 0
42 | 40 | Tullibody By Pass c/f from 2004/05 |  |  |  |  | 0 |  | 10: 0; 11: 0; 14: 0
43 | 41 | 20mph speed reduction |  |  |  | 107 | 107 |  | 9: 107; 10: 107; 11: 0; 14: 0
44 | 42 | Footways at Muirside, Tullibody |  |  |  |  | 0 |  | 11: 0; 14: 0
| 43 | SESTRAN Public Transport & Walking |  |  |  |  | 0 |  | 10: 0; 11: 0; 14: 0
| 44 | SESTRAN Public Bus |  |  |  |  | 0 |  | 10: 0; 11: 0; 14: 0
| 45 | SUSTRAN - Cycle Routes |  |  |  |  | 0 |  | 10: 0; 11: 0; 14: 0
Environment
45 | 46 | Black Devon Landfill / Incinerator |  | 200 |  |  | 200 |  | 11: 200; 14: 200 |  | minimal savings >>>>>>>>>>>>>>
46 | 47 | Black Devon Landfill Gas Collection & Treatment Project | [6 empty] | 11: 0; 14: 0
47 | 48 | Cemeteries Strategy |  | 300 |  |  | 300 |  | 11: 300; 14: 300 |  | # | # | #
|  | Cycle Path Network |  |  |  |  | 0 |  | 11: 0
|  | Dollar Cemetery |  |  |  |  | 0 |  | 11: 0
|  | Environmental Improvements |  |  |  |  | 0 |  | 11: 0
|  | Old Alloa THI Project |  |  |  |  | 0 |  | 11: 0
|  | Hillfoots Initiative |  |  |  |  | 0 |  | 11: 0
|  | Incineration Plant Demolition |  |  |  |  | 0 |  | 11: 0
|  | Landward Village Initiative |  |  |  |  | 0 |  | 11: 0
48 | 49 | Contaminated Land |  | 50 |  |  | 50 |  | 7: 50; 10: 50; 11: 0; 14: 0 |  | Budget already in place for Land Officer
|  | Tullis Factory Demolition | [6 empty] | 11: 0
49 | 50 | Parks & Open Spaces |  |  |  |  | 0 |  | 11: 0; 14: 0
50 | 51 | Outdoor Play Area Strategy |  |  |  |  | 0 |  | 11: 0; 14: 0
51 | 52 | Shared Compost Facility @ Polmaise |  |  |  |  | 0 |  | 10: 0; 11: 0; 14: 0
52 | 53 | Shared Transfer Facility @ Polmaise |  |  |  |  | 0 |  | 10: 0; 11: 0; 14: 0
53 | 54a | Waste Recycling Project |  |  |  |  | 0 |  | 10: 0; 11: 0; 14: 0
| 54b | Wheeled / Litter Bins |  |  |  |  | 0 |  | 10: 0; 11: 0; 14: 0
Partnerships
54 | 55 | Clackmannan Tolbooth |  | 0 |  |  | 0 |  | 10: 0; 11: 0; 14: 0 |  | # | # | #
55 | 56 | National Cycle Route |  | 3 |  |  | 3 |  | 10: 0; 11: 3; 14: 3 |  | # | # | #
56 | 57 | Old Alloa Townscape Heritage |  |  |  |  | 0 |  | 11: 0; 14: 0 |  | # | # | #
57 | 58 | Landscape Partnership - Conserve Ochills / Hillfoots | [6 empty] | 11: 0; 14: 0
58 | 59 | Core Path Network for Access | [6 empty] | 11: 0; 14: 0
Property Services
59 | 60 | Asbestos Removal |  | 15 |  |  | 15 |  | 11: 15; 14: 15
60 | 61 | Centralised Kitchen |  |  |  |  | 0 |  | 11: 0; 14: 0
61 | 62 | Disability Discrimination Act |  |  |  | 1 | 1 |  | 11: 0; 13: 1; 14: 1
62 | 63a | Vehicle Replacement Programme |  |  |  | 794 | 794 |  | 11: 0; 13: 794; 14: 794
Retentions Carry forward (projects to be identified)
| 63b | Keilarsbrae land Purchases
|  | Total Development & Environmental Services |  | 2688 | 0 | 1901 | 4589 |  | 762 | 0 | 191 | 953 |  | 1926 | 0 | 1710 | 3636 |  | -220 | -220 | -220
CORPORATE DEVELOPMENT
CCTV - Alloa South & East
Community Planning
63 | 64 | Efficient Government/Customer First Developments |  | 600 |  | -500 | 100 |  | 7: 500; 9: -500; 10: 0; 11: 100; 14: 100
|  | Business Change & Organisational Development | } |  |  |  |  | }
|  | Clack Web - eServices & eCommunity | } |  |  |  |  | }
|  | Content & Knowledge Management | } |  |  |  |  | }
|  | One Stop Shop & Customer Services Centre | } |  |  |  |  | }
|  | Shared Services & Data Sharing | } |  |  |  |  | }
Council Office - Rewiring | bar: 9 to 10; 12 to 14
Information Services - Salaries | bar: 9 to 10; 12 to 14
Kilncraigs Mill Develop. (consent brought forward) | bar: 9 to 10; 12 to 14
64 | 65 | IT Services (No submissions received - this is an estimate) |  | 400 |  |  | 400 |  | 11: 400; 14: 400
65 | 66a | Finance Services - General Ledger system |  |  |  | 30 | 30 |  | 11: 0; 13: 30; 14: 30
| 66b | Council Offices - Greenfield Traffic management System
|  | Total Corporate Development |  | 1000 | 0 | -470 | 530 |  | 500 | 0 | -500 | 0 |  | 500 | 0 | 30 | 530 |  | 0 | 0 | 0
CHIEF EXECUTIVE SERVICES
Economic Development
Dumyat Business Park Phase 2
66 | 67 | CSBP Restructuring |  |  |  |  | 0 |  | 10: 0; 11: 0; 14: 0 |  | 0 | 0 | 0
67 | 68 | Econ. Dev. Infrastructure: Eastern Clackmannanshire Development Opportunities |  | 133 |  |  | 133 |  | 7: 33; 10: 33; 11: 100; 14: 100 |  | 0 | 0 | 5
68 | 69 | Workspace Provision for Social Enterprises' Recycling project |  | 0 |  |  | 0 |  | 7: 0; 10: 0; 11: 0; 14: 0 |  | 0 | 10 | 10
69 | 70 | Kilncraigs Mill 1936 Building Envelop |  |  |  |  | 0 |  | 11: 0; 14: 0
70 | 71 | Kilncraigs Mill 1904 Development of 3rd & 4th Floors |  |  |  | 310 | 310 |  | 11: 0; 13: 310; 14: 310
71 | 72a | Kilncraigs Mill 1904 Access Control & Zoning Services |  |  |  |  | 0 |  | 11: 0; 14: 0
| 72b | Kilncraigs Mill Conversion
72 | 73 | Pavilions Business Park Phase 2 |  | 500 |  | -500 | 0 |  | 10: 0; 11: 500; 13: -500; 14: 0
73 | 74 | Dumyat Business Park Phase 3 |  |  |  |  | 0 |  | 10: 0; 11: 0; 14: 0
0
|  | Miscellaneous | [6 empty] | 11: 0
74 | 75 | CCTV - Tron Court |  |  |  |  | 0 |  | 11: 0; 14: 0
75 | 76 | DDA & Asbestos Removal |  | 25 |  |  | 25 |  | 11: 25; 14: 25 |  | 0 | 0 | 0
|  | Total Chief Executives Services |  | 658 | 0 | -190 | 468 |  | 33 | 0 | 0 | 33 |  | 625 | 0 | -190 | 435 |  | 0 | 0 | 0
|  | TOTAL CAPITAL PROGRAMME |  | 7166 | 0 | 4529 | 11695 |  | 1595 | 0 | 439 | 2034 |  | 5571 | 0 | 4090 | 9661 |  | -220 | -220 | -220
|  | UNALLOCATED FUNDING | [16 empty] | Key for Recurring Revenue Costs Section
76 | 77 | Capital Receipts Estimate (NET OF EXPENSES) | [6 empty] | 11: 300; 14: 300
| 78 | Sale of Land at Dumyat Park & Ditch for Tullibody By Pass
77 | 79 | APM Sales | [6 empty] | 11: 200; 13: -200; 14: 0 |  | # = | Costs considered but not
78 | 80 | ERDF Grants (from Kilncraigs to be used to refund extra s94 advance in previous years) | [6 empty] | 14: 0 |  | Blank cells = | no info from service
79 | 81 | Repayment from Schools Devolved Budget for Computer Equipment | [6 empty] | 14: 0
|  | TOTAL - ESTIMATED UNALLOCATED FUNDING | [6 empty] | 11: 500; 12: 0; 13: -200; 14: 300
|  | NET FUNDING (SURPLUS) / DEFICIT |  |  | #REF! | #REF!
FINANCED BY C.F.C.R.
|  | Net Capital Expenditure to be Funded from Prudential Borrowing | [6 empty] | 11: 5071; 12: 0; 13: 4290; 14: 9361
Ref to |  | List of External Allocated Funding referred to above
above |  | Contributions from other sources
| 3 | Foundation for Sports & Arts Grant for Tulligarth (now lapsed) | [6 empty] | 7: 300; 9: -300; 10: 0
7 | 7 | Heritage & Lottery Grants for Museum Project | [6 empty] | 10: 0
15 | 14 | National Priorities Action Fund - IT Hardware Replacement in Schools | [6 empty] | 9: 40; 10: 40
20 | 19 | The Big Lottery Fund - Fir Ski Park Centre - upgrade to building | [6 empty] | 10: 0
32 | 30 | Planning Gain Income for B9140/Collylands Cross | [6 empty] | 10: 0
41 | 39 | Sale of Land at Dumyat Park & Ditch for Tullibody By Pass | [6 empty] | 10: 0
51 | 52 | Stirling Council - Shared Compost Facility @ Polmaise | [6 empty] | 10: 0
52 | 53 | Stirling Council - Shared Transfer Facility @ Polmaise | [6 empty] | 10: 0
54 | 55 | Heritage Lottery Fund for Clackmannan Tolbooth | [6 empty] | 10: 0
54 | 55 | Historic Scotland Grant for Clackmannan Tolbooth | [6 empty] | 10: 0
55 | 56 | National Cycle Route - Private | [6 empty] | 10: 0
55 | 56 | National Cycle Route - Sustrans | [6 empty] | 10: 0
57 | 58 | Heritage Lottery Fund for Landscape Partnership Project | [6 empty] | 10: 0
58 | 59 | SNH - Core Path Network for Access | [6 empty] | 10: 0
66 | 67 | Scarborough Development Group - CSBP Restructuring | [6 empty] | 10: 0
67 | 68 | ERDF - Eastern Clackmannanshire Development Opportunities | [6 empty] | 7: 33; 10: 33
72 | 73 | CSBP - Pavilions Business Park Phase 2 | [6 empty] | 10: 0
72 | 73 | ERDF - Pavilions Business Park Phase 2 | [6 empty] | 10: 0
73 | 74 | CSBP - Dumyat Business Park Phase 3 | [6 empty] | 10: 0
73 | 74 | ERDF - Dumyat Business Park Phase 3 | [6 empty] | 10: 0
[9 empty] | 333 | 0 | -260 | 73
Central Government Grants
9 | 9 | Special Grant for Schools Estate Renewal Programme | [6 empty] | 9: 1008; 10: 1008
27 | 25 | Mental Health Services Scottish Executive | [6 empty] | 10: 0
38 | 36 | Cycling, Walking, Safer Streets (CWSS) from SE | [6 empty] | 9: 84; 10: 84
40 | 38 | Stirling / Alloa / Kincardine Rail Link - Specific Grant | [6 empty] | 7: 712; 10: 712
43 | 41 | 20mph Grant from Scottish Executive | [6 empty] | 9: 107; 10: 107
48 | 49 | Contaminated Land | [6 empty] | 7: 50; 10: 50
63 | 64 | Efficient Government / Customer First Developments (converted to RSG) | [6 empty] | 7: 500; 9: -500; 10: 0
[9 empty] | 1262 |  | 699 | 1961
|  | Total External Funding Allocated | [6 empty] | 7: 1595; 9: 439; 10: 2034
| @ | = Refer to note in "Revenue & other Implication" sheet
| NK | = Costs or funding of project not known
= No submissions received in the current round of bids, but included here as bids received in the previous round of bids for the 3 year plan.

## Appen 4; 07-08 (hidden)
| 1 | 2 |  | 3 |  | 4 | 5
|  | General Services Capital Programme |  | Proposed Budget |  | External Grants | Net Expenditure (Council Contribution) | APPENDIX 4 | Recurring Revenue consequences
for the proposed project
2007/08
|  |  |  | 2007/08 |  | 2007/08 | 2007/08 |  | 2004/05 | 2005/06 | 2006/07
|  | Service / Project Name |  | £'000 |  | £'000 | £'000
SERVICES TO PEOPLE
EDUCATION & COMMUNITY SERVICES
Abercromby PS
Alva Primary Extension
Beechwood Park
Lornshill Academy Sports Complex Phase 1
Lornshill Academy Sports Complex Phase 2
Pre Fives
Property Maintenance - additional from Revenue
Alloa Academy
Safer Routes to school
Strathdevon Primary
1 | 1 | Alva Academy - PPP Capital Support |  | 1000 |  |  | 1000
Alva Academy SEN
Alloa Library
Catering Improvements
Heavy Equipment Replacement
Greenhead Pavilion
Relocation of PSSS
Sunnyside PS
Canoe Site Purchase
Claremont P S Huts
Community Facility, Fishcross
Community Facility, Hawkhill
Lime Tree House upgrade wiring
2 | 2 | Alloa Academy- PPP Capital Support |  | 1250 |  |  | 1250
3 | 3 | Lornshill Academy & Tulligarth Phase 2 - PPP Capital Support |  | 850 |  |  | 850
4 | 4 | DDA Compliance |  |  |  |  | 0
| 5 | General - PPP Capital Suport |  | 500 |  |  | 500
5 |  | Kilncraigs 1936 |  |  |  |  | 0
6 | 6 | Lochies - Specialist Accommodation |  |  |  |  | 0
7 | 7 | Museum & Heritage Centre |  |  |  |  | 0
2.918 | 5.0633 | Lochies School |  |  |  |  | 0
3.0328 | 5.3038 | Lochies School - Excellence Fund |  |  |  |  | 0
3.1475 | 5.5443 | Lochies School - Schools Budget Income |  |  |  |  | 0
3.2623 | 5.7848 | Museum & Heritage Centre - External Income |  |  |  |  | 0
3.377 | 6.0253 | Property Maintenance |  |  |  |  | 0
3.4918 | 6.2658 | Public Art |  |  |  |  | 0
3.6066 | 6.5063 | Retentions/Legally committed |  |  |  |  | 0
3.7213 | 6.7468 | SEN Adaptations |  |  |  |  | 0
8 | 8 | School Building Alarm Systems |  | 8 |  |  | 8 |  | some maintenance but reduction in insurance
9 | 9 | Schools Estate Renewal Programme |  | 1055 |  | 1055 | 0
11 | 10 | Tulligarth Sports Resurfacing - requirement of Lottery funding |  | 40 |  |  | 40
12 | 11 | Alloa Library Refurbishment |  |  |  |  | 0
14 | 13 | Heavy Equipment in Secondary Schools - Kilns etc |  | 30 |  |  | 30
15 | 14 | IT Hardware Replacement in Schools |  | 100 |  | 40 | 60
16 | 15 | Legal Commitments - for projects undertaking in 04/05 |  | 25 |  |  | 25
17 | 16 | Leisure Bowl - Complete refurbishment per 20yr Development plan |  | 75 |  |  | 75
18 | 17 | Primary & Nursery School Developments |  | 300 |  |  | 300
19 |  | Accessibility Strategy (if revenue budget approved, no need for capital) |  |  |  |  | 0
20 | 18 | Fir Ski Park Centre - upgrade to building |  |  |  |  | 0
|  | Total Education & Community Service |  | 5233 |  | 1095 | 4138 |  | 0 | 0 | 0
General Fund Housing - Enabling
SOCIAL SERVICES
Ludgate House (c/f from 00/01)
Office Relocations
Whins Resource Centre - Floor Heating System
Care in Community Safety (** new proposal - see attached schedule)
Upgrade 6 Marshill Alloa
Document Imaging System (** new proposal - see attached schedule)
22 | 20 | DDA Compliance |  |  |  |  | 0
23 | 21 | Joint FVNHS/ Adult Care Premises Occupation |  | NK |  | NK | NK
25 | 22 | Menstrie House En-Suite Conversion |  | 475 |  |  | 475
26 | 23 | Ludgate House Resource Centre |  |  |  |  | 0
27 | 24 | Mental Health Services |  |  |  |  | 0
|  | Total Social Services |  | 475 |  | 0 | 475 |  | 0 | 0 | 0
DEVELOPMENT & ENVIRONMENTAL SERVICES
Transportation
|  | A907 (carry forward of unused additional consent) | }
|  | A907 - Council Contribution | }
28 | 26 | Accident Prevention & Traffic Management |  | 100 |  |  | 100 |  | 0 | 0 | 0
29 | 27 | Alloa Town Centre |  |  |  |  | 0 |  | -200 | -200 | -200
|  | Accident Prevention & Traffic Management - Safer Roads, Cycling |  |  |  |  | 0
30 | 28 | A91 East Stirling St. Alva Roundabout to access new school site |  | 450 |  | 225 | 225
31 | 29 | A908/B908 Sauchie, Roundabout to facilitate new hospital
32 | 31 | B9140/ Collylands Cross Upgrade |  | 500 |  |  | 500 |  | 0 | 0 | 0
33 |  | B9140 Realignment of Bends |  |  |  |  | 0
34 | 32 | Bridge Strengthening |  | 400 |  |  | 400 |  | 0 | 0 | 0
|  | Eastern Link Road |  |  |  |  | 0
|  | Hall Park |  |  |  |  | 0
|  | Footpath Maintenance |  |  |  |  | 0
|  | Roads Maintenance |  |  |  |  | 0
|  | Smithfield Loan |  |  |  |  | 0
|  | Roads Structural Maintenance |  |  |  |  | 0
35 | 33 | Flood Prevention |  | 100 |  |  | 100 |  | 0 | 0 | 0
36 | 34 | Retentions |  | 60 |  |  | 60 |  | 0 | 0 | 0
37 | 35 | Road & Footway Improvements (SRMCS), including town centres |  | 1000 |  |  | 1000 |  | 0 | 0 | 0
38 | 36 | Cycling , Walking ,Safer Streets (CWSS) |  | 86 |  | 86 | 0 |  | 0 | 0 | 0
39 | 37 | Street Lighting |  | 165 |  |  | 165 |  | 0 | 0 | 0
|  | Tullibody Bypass (to be funded from special capital receipts) |  |  |  |  | 0
40 | 38 | Total SAK Rail Project & Alloa ELR Project Costs |  |  |  |  | 0 |  | -20 | -20 | -20
41 | 39 | Tullibody By Pass |  |  |  |  | 0
42 | 40 | Tullibody By Pass c/f from 2004/05 |  |  |  |  | 0
43 | 41 | 20mph speed reduction |  | 109 |  | 109 | 0
44 | 42 | Footways at Muirside, Tullibody |  |  |  |  | 0
| 43 | SESTRAN Public Transport & Walking |  |  |  |  | 0
| 44 | SESTRAN Public Bus |  |  |  |  | 0
| 45 | SUSTRAN - Cycle Routes |  |  |  |  | 0
Environment
45 | 46 | Black Devon Landfill / Incinerator |  |  |  |  | 0 |  | minimal savings >>>>>>>>>>>>>>
46 | 47 | Black Devon Landfill Gas Collection & Treatment Project |  | 400 |  |  | 400
47 | 48 | Cemeteries Strategy |  |  |  |  | 0 |  | # | # | #
|  | Cycle Path Network |  |  |  |  | 0
|  | Dollar Cemetery |  |  |  |  | 0
|  | Environmental Improvements |  |  |  |  | 0
|  | Old Alloa THI Project |  |  |  |  | 0
|  | Hillfoots Initiative |  |  |  |  | 0
|  | Incineration Plant Demolition |  |  |  |  | 0
|  | Landward Village Initiative |  |  |  |  | 0
48 | 49 | Contaminated Land |  |  |  |  | 0 |  | Budget already in place for Land Officer
|  | Tullis Factory Demolition |  |  |  |  | 0
49 | 50 | Parks & Open Spaces |  | 80 |  |  | 80
50 | 51 | Outdoor Play Area Strategy |  | 75 |  |  | 75
51 | 52 | Shared Compost Facility @ Polmaise
52 | 53 | Shared Transfer Facility @ Polmaise
53 | 54a | Waste Recycling Project |  | 400 |  |  | 400
| 54b | Wheeled / Litter Bins
Partnerships
54 | 55 | Clackmannan Tolbooth |  | 161 |  | 104 | 57 |  | # | # | #
55 | 56 | National Cycle Route |  |  |  |  | 0 |  | # | # | #
56 | 57 | Old Alloa Townscape Heritage |  |  |  |  | 0 |  | # | # | #
57 | 58 | Landscape Partnership - Conserve Ochills / Hillfoots |  | 1125 |  | 900 | 225
58 | 59 | Core Path Network for Access |  | 50 |  | 12 | 38
Property Services
59 | 60 | Asbestos Removal |  |  |  |  | 0
60 | 61 | Centralised Kitchen |  |  |  |  | 0
61 | 62 | Disability Discrimination Act |  |  |  |  | 0
62 | 63a | Vehicle Replacement Programme |  | 570 |  |  | 570
Retentions Carry forward (projects to be identified)
| 63b | Keilarsbrae land Purchases
|  | Total Development & Environmental Services |  | 5831 |  | 1436 | 4395 |  | -220 | -220 | -220
CORPORATE DEVELOPMENT
CCTV - Alloa South & East
Community Planning
63 | 64 | Efficient Government/Customer First Developments |  | 100 |  | 0 | 100
|  | Business Change & Organisational Development | } |  | }
|  | Clack Web - eServices & eCommunity | } |  | }
|  | Content & Knowledge Management | } |  | }
|  | One Stop Shop & Customer Services Centre | } |  | }
|  | Shared Services & Data Sharing | } |  | }
Council Office - Rewiring
Information Services - Salaries
Kilncraigs Mill Develop. (consent brought forward)
64 | 65 | IT Services (No submissions received - this is an estimate) |  | 400 |  |  | 400
65 | 66a | Finance Services - General Ledger system |  | 30 |  |  | 30
| 66b | Council Offices - Greenfield Traffic management System
|  | Total Corporate Development |  | 530 |  | 0 | 530 |  | 0 | 0 | 0
CHIEF EXECUTIVE SERVICES
Economic Development
Dumyat Business Park Phase 2
66 | 67 | CSBP Restructuring |  |  |  |  | 0 |  | 0 | 0 | 0
67 | 68 | Econ. Dev. Infrastructure: Eastern Clackmannanshire Development Opportunities |  |  |  |  | 0 |  | 0 | 0 | 5
68 | 69 | Workspace Provision for Social Enterprises' Recycling project | [6 empty] | 0 | 10 | 10
69 | 70 | Kilncraigs Mill 1936 Building Envelop |  |  |  |  | 0
70 | 71 | Kilncraigs Mill 1904 Development of 3rd & 4th Floors |  | 310 |  |  | 310
71 | 72a | Kilncraigs Mill 1904 Access Control & Zoning Services
| 72b | Kilncraigs Mill Conversion
72 | 73 | Pavilions Business Park Phase 2 |  |  |  |  | 0
73 | 74 | Dumyat Business Park Phase 3
Miscellaneous
74 | 75 | CCTV - Tron Court |  |  |  |  | 0
75 | 76 | DDA & Asbestos Removal |  |  |  |  | 0 |  | 0 | 0 | 0
|  | Total Chief Executives Services |  | 310 |  | 0 | 310 |  | 0 | 0 | 0
|  | TOTAL CAPITAL PROGRAMME |  | 12379 |  | 2531 | 9848 |  | -220 | -220 | -220
|  | UNALLOCATED FUNDING | [6 empty] | Key for Recurring Revenue Costs Section
76 | 77 | Capital Receipts Estimate (NET OF EXPENSES) |  |  |  |  | 300
77 | 78 | APM Sales | [6 empty] | # = | Costs considered but not
78 | 79 | ERDF Grants (from Kilncraigs to be used to refund extra s94 advance in previous years) | [6 empty] | Blank cells = | no info from service
79 | 80 | Repayment from Schools Devolved Budget for Computer Equipment
|  | TOTAL - ESTIMATED UNALLOCATED FUNDING |  |  |  |  | 300
NET FUNDING (SURPLUS) / DEFICIT
FINANCED BY C.F.C.R.
|  | Net Capital Expenditure to be Funded from Prudential Borrowing |  |  |  |  | 9548
Ref to |  | List of External Allocated Funding referred to above
above |  | Contributions from other sources
7 | 7 | Heritage & Lottery Grants for Museum Project
15 | 14 | National Priorities Action Fund - IT Hardware Replacement in Schools |  |  |  | 40
20 | 19 | The Big Lottery Fund - Fir Ski Park Centre - upgrade to building
| 28 | No Details of Grant (A91 East Stirling St. Alva) |  |  |  | 225
32 | 30 | Planning Gain Income for B9140/Collylands Cross
41 | 39 | Sale of Land at Dumyat Park & Ditch for Tullibody By Pass
51 | 52 | Stirling Council - Shared Compost Facility @ Polmaise
52 | 53 | Stirling Council - Shared Transfer Facility @ Polmaise
54 | 55 | Heritage Lottery Fund for Clackmannan Tolbooth |  |  |  | 32
54 | 55 | Historic Scotland Grant for Clackmannan Tolbooth |  |  |  | 72
55 | 56 | National Cycle Route - Private
55 | 56 | National Cycle Route - Sustrans
57 | 58 | Heritage Lottery Fund for Landscape Partnership Project |  |  |  | 900
58 | 59 | SNH - Core Path Network for Access |  |  |  | 12
66 | 67 | Scarborough Development Group - CSBP Restructuring
67 | 68 | ERDF - Eastern Clackmannanshire Development Opportunities
72 | 73 | CSBP - Pavilions Business Park Phase 2
72 | 73 | ERDF - Pavilions Business Park Phase 2
73 | 74 | CSBP - Dumyat Business Park Phase 3
73 | 74 | ERDF - Dumyat Business Park Phase 3
1281
Central Government Grants
9 | 9 | Special Grant for Schools Estate Renewal Programme |  |  |  | 1055
27 | 25 | Mental Health Services Scottish Executive
38 | 36 | Cycling, Walking, Safer Streets (CWSS) from SE |  |  |  | 86
40 | 38 | Stirling / Alloa / Kincardine Rail Link - Specific Grant
43 | 41 | 20mph Grant from Scottish Executive |  |  |  | 109
48 | 49 | Contaminated Land
63 | 64 | Efficient Government/Customer First Developments |  |  |  | 0
1250
|  | Total External Funding Allocated |  |  |  | 2531
| NK | = Costs or funding of project not known
= No submissions received in the current round of bids, but included here as bids received in the previous round of bids for the 3 year plan.

## SAK Summary (hidden)
SAK Rail Summary
| CC | SEFV | SE (Grant) | SE (s.94) | Total
2001/02
Budget | 0 | 0 |  | 250000 | 250000 | s.94
Actual for 20001/02 | 0 | 0 |  | -125540 | -125540
Carry Forward to 02/03 | 0 | 0 |  | 124460 | 124460
2002/03
c/f from 2002/03 | 0 |  |  | 124460 | 124460
| 0 | 0 |  | 1047350 | 1047350 | s.94
Actual for 20002/03 | 0 | 0 |  | 1171810 | 1171810
2003/04
Actual for 20003/04 | 0 | 0 | 1010405 |  | 1010405 | Grant
2004/05
Originally approved | 1270000 | 0 | 18730000 |  | 20000000
Transfer to Tullibody By Pass | -600000 |  |  |  | -600000
| 670000 | 0 | 18730000 | 0 | 19400000
Additional in 04/05 |  | 397000 |  |  | 397000
Budget for 2004/05 | 670000 | 397000 | 18730000 | 0 | 19797000
Spend during year 04/05 | -56000 | -397000 | -1807000 |  | -2260000
Carry Forward to 05/06 | 614000 | 0 | 16923000 | 0 | 17537000
2005/06
c/f from 2004/05 | 614000 | 0 | 16923000 |  | 17537000
Origically approved | 506000 | 0 | 14494000 |  | 15000000
Refund of transfer from Tullibody By Pass | 600000 |  |  |  | 600000
| 1720000 | 0 | 31417000 | 0 | 33137000
Additional following MW meeting | 299000 |  |  |  | 299000
Budget for 2005/06 | 2019000 | 0 | 31417000 | 0 | 33436000
2006/07
c/f from 2004/05
Origically approved | 38000 | 0 | 712000 |  | 750000
Additional, following MW meeting |  | 0 | 0 |  | 0
Budget for 2006/07 | 38000 | 0 | 712000 | 0 | 750000
Total | 2113000 | 397000 | 34946405 | 1297350 | 38753755
|  |  |  | Check total>> | 38753755

## Revenue & Other Implications (hidden)
APPENDIX 2
CLACKMANNANSHIRE COUNCIL
3 YEAR CAPITAL PROGRAMME 2005/06 TO 2007/08
Notes on Revenue Implications received with bids
Revenue Implications
1 | School Building Alarm Systems | ~ £25k per annum maintenance costs
~ Savings in insurance costs??
2 | Alloa Library Refurbishment | There may be revenue implications in respect of the shop premises but these have not been costed.
3 | Pre-Fives Redevelopment - Deerpark PS alterations | Linked to closure of Sauchie NS; will release potential capital receipts & future revenue savings. (No figures given).
4 | Landscape Partnership - Conserve Ochills / Hillfoots | ~ 3-4 year Project Officer a requirement of HLF grant funding. PO2 grade likely. Total cost £40k pa.
~ £30k pa. HLF income likely.
5 | Vehicle Replacement Programme | Savings in maintenance costs of new vehicles, expected to be about £50k pa for three years.
6 | Flood Prevention | £26k per annum to fund new post (Flood Inspector AP 4/5)
7 | CCTV - Tron Court | Annual Rental Charge £1,500 pa
Annual maintenance contract £750 pa from 2007/08
Other Notes
1 | Kilncraigs 1936 (Education) | The budget approved for 2005/06 and 2006/07 of £250k & £500k respectively as part of PPP is no longer required. Development of the building is included as separate bids under "Economic Development"
2 | Schools Estate Renewal Programme | £175k will be used to support PPP in 2005/06 and 2006/07