##### APPENDIX 2 Progress Summary: Corporate Development

| ### Target Outcome |  |  | No. of targets 2006-07 | Complete | Good progress – on track | Running behind | Unlikely to complete | ### Comments |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| #### Finance Services |  |  |  |  |  |  |  |  |
| FS1 |  | A strong Finance service operates to secure better service delivery. | 3 | 0% | 100% | 0% | 0% | These targets are all on track and should be completed by end of year |
| FS2 |  | The financial aspects of significant corporate projects are soundly managed | 4 | 0% | 100% | 0% | 0% | All of these corporate projects are ongoing, but Finance will have serviced them all on target |
| FS3 |  | Improve financial service processes | 8 | 25% | 38% | 38% | 0% | Some slippage has occurred here, but with two already complete, we hope to catch up with all targets that are currently running behind. |
| #### Human Resources |  |  |  |  |  |  |  |  |
| HR1 |  | Strategic HR management facilitates Council Organisational Development in line with Corporate Priorities | 2 | 50% | 0% | 50% | 0% | Key area for added value from HR, increasing demands as corporate and service specific change programmes accelerate. |
| HR2 |  | HR policy and processes which promote and support corporate effectiveness | 11 | 36% | 45% | 9% | 9% | Resolving Equal Pay, Single Status & Job Evaluatioin is the overwhelming priority work area. This has become more complex and dynamic as the ramifications of Equal Pay challenges are felt by Councils and Trade Unions across the country, and as the anticipation of closer joint working is taken into consideration in our craetion of new pay, grading and conditions arrangements. |
| HR3 |  | Employee contribution to Council objectives is maximised through inclusive development and involvement opportunities | 7 | 0% | 57% | 43% | 0% | Competing priorities flowing from major prioritites above has required deferral/slippage of some individual projects. |
| HR4 |  | Corporate HR service fit for current and anticipated purpose within the Council | 5 | 0% | 80% | 20% | 0% | Comment above applies here also, although continuous attention is made to developing and changing HR service. |
| HR5 |  | Employees contribute to the development of policies which promote equality and diversity across the communities in Clackmannanshire | 3 | 67% | 33% | 0% | 0% | Major work programmes on track in what is also an expanding agenda. |
| #### BITS (Business Improvement – Business Change) |  |  |  |  |  |  |  |  |
| BC1 | The Council delivers better customer service and more efficient and effective service delivery at lower cost. |  | 8 | 37.5% | 50.0% | 12.5% | 0% | A blue-print for technology developments is in place, and progress is being made across a number of service areas in terms of improving customer service and service efficiency. |
| #### BITS (Business Improvement – Service Improvement) |  |  |  |  |  |  |  |  |
| SI1 | The Council has effective arrangements in place to secure continuous improvement in performance and delivery of services in the most effective, efficient and economical manner |  | 5 | 40% | 40% | 20% | 0% | Balanced scorecards are now reported to P&A quarterly. Working towards electronic reporting of service planning by year-end |
| SI2 | The Council’s exposure to risk is known and effectively managed |  | 2 | 50% | 0% | 50% | 0% | This will be progressed during the 2nd half of the year. |
| SI3 | The Council is an effective organisation and achieves continuous improvement |  | 3 | 33.3% | 0.0% | 66.7% | 0% | A key action is the implementation of the EFQM over the next 6 months. |
| #### BITS (Customer Service) |  |  |  |  |  |  |  |  |
| CS1 | Improved Customer Service ensuring quality improvements and financial savings are delivered. |  | 9 | 0% | 44% | 56% | 0% | Key action is to get Customer Services Strategy formally approved by Council, prior to any work being undertaken. |
| CS2 | Council-wide Customer Service orientation and culture change programme, delivered through a staff training and development programme. |  | 2 | 0% | 100% | 0% | 0% | Pilot project underway with Contact Centre staff undertaking SVQ qualifications. |
| CS3 | Deliver continuous improvement and service quality in Customer Services. |  | 3 | 0% | 33.3% | 66.7% | 0% | Council-wide Customer Service Network being established to lead on developments. |
| #### Service Information Technology |  |  |  |  |  |  |  |  |
| IT1 | Effective IT Governance in place |  | 4 | 75% | 25% | 0% | 0% | ITGG constitued since MAY 2006 |
| IT2 | Improve IT Strategy and Architecture |  | 4 | 0% | 100% | 0% | 0% | IT Strategy being reviewed and architecture upgraded |
| IT3 | Improve IT Service Management |  | 4 | 50% | 0% | 50% | 0% | IT Governance group and IT Service Delivery model agreed by Council's Executive Management team. |
| IT4 | Improve IT Service Delivery |  | 2 | 50% | 50% | 0% | 0% | IT Account managers and Service IT Coordinators introduced across all Council Service areas. to meet and discuss operational and service issues. |
| #### Procurement |  |  |  |  |  |  |  |  |
| PR1 | Procurement practices reflect Council objectives and deliver savings, efficiencies and best value. |  | 5 | 0% | 80% | 20% | 0% | Primarily all of the Target outcomes are in the position of being achieved within the period. Three of the targets are influenced by others with respect to AGL. Failure to deliver this product in the first half of the reporting period has had a knock on effect on other initiatives. Also priorities of the Shared Service agenda may influence the delivery of all target outcomes, but the Shared Service data collection may assist where the implementation of AGL has not taken place. |
| ###### Total / Average |  |  | 94 | 23% | 50% | 26% | 1% |  |