##### APPENDIX 3 Progress Summary: Development & Environmental Services

| ### Target Outcome |  | No. of targets 2006-07 | Complete | Good progress – on track | Running behind | Unlikely to complete | ### Comments |
| --- | --- | --- | --- | --- | --- | --- | --- |
| #### Property Services |  |  |  |  |  |  |  |
| PS1 | Provision of effective, efficient, modern and quality focussed property management and maintenance services | 17 | 12% | 53% | 24% | 12% | Long term illness in the senior management team has significantly delayed 3 targets, these are likely to be achieved by the end of the year (max. of 6 month delay. One other task has been changed to align with BV Review. |
| Environmental Services |  |  |  |  |  |  |  |
| ES1 | Provide quality, sustainable waste management which meet the local, national and EU demands and targets. | 7 | 14% | 71% | 14% | 0% | One project delayed for technical reasons. |
| ES2 | High quality services providing sustainable maintenance and development of open space in Clackmannanshire. | 9 | 22% | 56% | 22% | 0% | 2 projects delayed by land acquisition problems and reference to Information technology Governance Group. |
| ES3 | High quality environmental and consumer services protecting and improving the quality of life in Clackmannanshire. | 21 | 29% | 33% | 24% | 14% | Health Promotion Strategy development aborted due to resignation of Health Promotion Officer. Other delays minor and progressing. |
| #### Development Services |  |  |  |  |  |  |  |
| DS1 | Provide improved and modernized Development Quality and Building Standards services | 13 | 15% | 54% | 31% | 0% | Staff changes, vacancies and unplanned additional initiatives have impacted on progress with some key tasks. |
| DS2 | Provide quality Transport Planning, Roads construction and Maintenance services. | 12 | 25% | 42% | 33% | 0% | Filling of new posts has taken longer than expected resulting in slower progress on some key tasks. |
| #### Strategy & Support |  |  |  |  |  |  |  |
| SS1 | Achieve provision of an effective, efficient modern organization. | 17 | 12% | 47% | 24% | 18% |  |
| ### SS2 | ### High Quality Sustainable Development (Implementation) | 17 | 12% | 88% | 0% | 0% |  |
| ### SS3 | ### Improve, maintain and sustain the Environment | 13 | 46% | 46% | 8% | 0% |  |
| ###### Total / Average |  | 109 | 22% | 53% | 19% | 6% |  |