##### Progress Summary: Corporate Development

| ### Target Outcome |  |  | No. of targets 2006-07 | Complete | Good progress – on track | Running behind | Unlikely to complete | ### Comments |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| #### Finance Services |  |  |  |  |  |  |  |  |
| FS1 |  | A strong Finance service operates to secure better service delivery. | 3 | 0% | 100% | 0% | 0% | These targets are all on track and should be completed by end of year |
| FS2 |  | The financial aspects of significant corporate projects are soundly managed | 4 | 0% | 100% | 0% | 0% | All of these corporate projects are ongoing, but Finance will have serviced them all on target |
| FS3 |  | Improve financial service processes | 8 | 25% | 38% | 38% | 0% | Some slippage has occurred here, but with two already complete, we hope to catch up with all targets that are currently running behind. |
| #### Human Resources |  |  |  |  |  |  |  |  |
| HR1 |  | Strategic HR management facilitates Council Organisational Development in line with Corporate Priorities | 2 | 50% | 0% | 50% | 0% | Key area for added value from HR, increasing demands as corporate and service specific change programmes accelerate. |
| HR2 |  | HR policy and processes which promote and support corporate effectiveness | 11 | 36% | 45% | 9% | 9% | Resolving Equal Pay, Single Status & Job Evaluatioin is the overwhelming priority work area. This has become more complex and dynamic as the ramifications of Equal Pay challenges are felt by Councils and Trade Unions across the country, and as the anticipation of closer joint working is taken into consideration in our craetion of new pay, grading and conditions arrangements. |
| HR3 |  | Employee contribution to Council objectives is maximised through inclusive development and involvement opportunities | 7 | 0% | 57% | 43% | 0% | Competing priorities flowing from major prioritites above has required deferral/slippage of some individual projects. |
| HR4 |  | Corporate HR service fit for current and anticipated purpose within the Council | 5 | 0% | 80% | 20% | 0% | Comment above applies here also, although continuous attention is made to developing and changing HR service. |
| HR5 |  | Employees contribute to the development of policies which promote equality and diversity across the communities in Clackmannanshire | 3 | 67% | 33% | 0% | 0% | Major work programmes on track in what is also an expanding agenda. |
| #### BITS (Business Improvement – Business Change) |  |  |  |  |  |  |  |  |
| BC1 | The Council delivers better customer service and more efficient and effective service delivery at lower cost. |  | 8 | 37.5% | 50.0% | 12.5% | 0% | A blue-print for technology developments is in place, and progress is being made across a number of service areas in terms of improving customer service and service efficiency. |
| #### BITS (Business Improvement – Service Improvement) |  |  |  |  |  |  |  |  |
| SI1 | The Council has effective arrangements in place to secure continuous improvement in performance and delivery of services in the most effective, efficient and economical manner |  | 5 | 40% | 40% | 20% | 0% | Balanced scorecards are now reported to P&A quarterly. Working towards electronic reporting of service planning by year-end |
| SI2 | The Council’s exposure to risk is known and effectively managed |  | 2 | 50% | 0% | 50% | 0% | This will be progressed during the 2nd half of the year. |
| SI3 | The Council is an effective organisation and achieves continuous improvement |  | 3 | 33.3% | 0.0% | 66.7% | 0% | A key action is the implementation of the EFQM over the next 6 months. |
| #### BITS (Customer Service) |  |  |  |  |  |  |  |  |
| CS1 | Improved Customer Service ensuring quality improvements and financial savings are delivered. |  | 9 | 0% | 44% | 56% | 0% | Key action is to get Customer Services Strategy formally approved by Council, prior to any work being undertaken. |
| CS2 | Council-wide Customer Service orientation and culture change programme, delivered through a staff training and development programme. |  | 2 | 0% | 100% | 0% | 0% | Pilot project underway with Contact Centre staff undertaking SVQ qualifications. |
| CS3 | Deliver continuous improvement and service quality in Customer Services. |  | 3 | 0% | 33.3% | 66.7% | 0% | Council-wide Customer Service Network being established to lead on developments. |
| #### Service Information Technology |  |  |  |  |  |  |  |  |
| IT1 | Effective IT Governance in place |  | 4 | 75% | 25% | 0% | 0% | ITGG constitued since MAY 2006 |
| IT2 | Improve IT Strategy and Architecture |  | 4 | 0% | 100% | 0% | 0% | IT Strategy being reviewed and architecture upgraded |
| IT3 | Improve IT Service Management |  | 4 | 50% | 0% | 50% | 0% | IT Governance group and IT Service Delivery model agreed by Council's Executive Management team. |
| IT4 | Improve IT Service Delivery |  | 2 | 50% | 50% | 0% | 0% | IT Account managers and Service IT Coordinators introduced across all Council Service areas. to meet and discuss operational and service issues. |
| #### Procurement |  |  |  |  |  |  |  |  |
| PR1 | Procurement practices reflect Council objectives and deliver savings, efficiencies and best value. |  | 5 | 0% | 80% | 20% | 0% | Primarily all of the Target outcomes are in the position of being achieved within the period. Three of the targets are influenced by others with respect to AGL. Failure to deliver this product in the first half of the reporting period has had a knock on effect on other initiatives. Also priorities of the Shared Service agenda may influence the delivery of all target outcomes, but the Shared Service data collection may assist where the implementation of AGL has not taken place. |
| ###### Total / Average |  |  | 94 | 23% | 50% | 26% | 1% |  |

| #### TARGET OUTCOME FS1 |  | A strong Finance service operates to secure better service delivery. |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Ref. | 3 Year Target | Target 2006/07 | Completed | Good progress – on track with development | Running behind with development progress | Unlikely to complete | Position at 30th September 2006 and impact of / reasons for delays |
| FS1.1 | Budget monitoring performance management is supported by a set of relevant performance indicators. | Performance standards are fully embedded into service performance monitoring arrangements. |  |  |  |  | On target |
| FS1.2 | Budget setting is supported by a set of relevant performance indicators. | Performance standards are fully embedded into service performance monitoring arrangements. |  |  |  |  | On target |
| FS1.3 | All professional Finance staff are qualified to a level appropriate to their jobs. | 70% professional staff qualified to a level appropriate to their jobs. |  |  |  |  | Training & Development now given higher prominence by professional bodies as part of compulsory CPD targets. |

| #### TARGET OUTCOME FS2 |  | The financial aspects of significant corporate projects are soundly managed |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Ref. | 3 Year Target | Target 2006/07 | Completed | Good progress – on track with development | Running behind with development progress | Unlikely to complete | Position at 30th September 2006 and impact of / reasons for delays |
| FS2.1 | All Best Value Reviews benefit from the appropriate level of financial data and analysis. | Provide financial information and analysis for BV reviews. Support Review Panels. |  |  |  |  | All Finance inputs on target |
| FS2.2 | Assist with the financial aspects of redevelopment of the Secondary school estate Public Private Partenrship(PPP) project | To ensure affordability, VFM and forward budget impact issues are monitored and reported on to council throughout procurement stage |  |  |  |  | Project ongoing |
| FS2.3 | Contribute to and manage impact of Customer Service review from the Community Access Points (CAPs) and Contact Centre See CS 1.3 | To establish impact on service and reconfigure to reflect outcome. |  |  |  |  | Local Office working group looking at options |
| FS2.4 | Shared service delivery with partner organisations is established | ‘To provide financial support towards development of EGF Stage 2 bid’ |  |  |  |  | Business Case development ongoing |

| #### TARGET OUTCOME FS3 |  | Improve financial service processes |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Ref. | 3 Year Target | Target 2006/07 | Completed | Good progress – on track with development | Running behind with development progress | Unlikely to complete | Position at 30th September 2006 and impact of / reasons for delays |
| FS3.1 | Deliver service improvements in revenues and benefits through Modernising Government programme | Review results from 2005/06 and re-engineer other 50% of main business processes to deliver lower transaction costs |  |  |  |  | Electronic Document Management system now being progressed, but behind with timescales as there was some delay in separating this from joint working proposals. |
| FS3.2 | General Ledger system provides a quicker and more convenient service for users. | New chart of accounts implemented in September 2006, along with improved reporting through use of Crystal reports. |  |  |  |  | Task not completed by Sept. - delays due to additional testing of data and systems. Looking to implement in January 2007 |
| FS3.3 | To improve the capital Planning process. | To implement option appraisal process for capital plans – projects and funding. |  |  |  |  | Additional scrutiny through the CAMP team, Exec. Team, and BWG |
| FS3.4 | To keep up to date with additional requirements from changes in accounting practice. | 1. To comply with group accounting requirements for the first time for 05/06 accounts within the required deadline, and to receive a clean audit certificate on their production. |  |  |  |  | Completed on time with clean audit certificate |
|  |  | 2. Review impact of proposals to implement FRS25 – potential write-off of debt rescheduling premiums held on balance sheet. Report to Council if appropriate. |  |  |  |  | Being investigated by national bodies |
| FS3.5 | Reduce Benefit Fraud through efficient investigation and robust application of sanctions | Improve intervention and investigation processes leading to increased number of sanctions. |  |  |  |  | We are behind this target so far, but fully expect to make this up by the end of the year to exceeed our sanctions target |
| FS3.6 | Increase fraud awareness amongst public and employees | Increase public awareness through local media and other general information sources and internally through all available information sources |  |  |  |  | Development of service delivery plan by December 2006 will include fraud awareness sessions |
| FS3.7 | Aim towards internal zero tolerance of theft/fraud with particular reference to HB/CTB | Review existing policies and update where necessary. |  |  |  |  | Sanctions policy has been completed |

Human Resources

| #### TARGET OUTCOME HR1 |  | Strategic HR management facilitates Council Organisational Development in line with Corporate Priorities |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Ref. | 3 Year Target | Target 2006/07 | Completed | Good progress – on track with development | Running behind with development progress | Unlikely to complete | Position at 30th September 2006 and impact of / reasons for delays |
| HR1.1 | Corporate OD Strategy HR & Training & Development policy agreed and implemented consistently | Corporate HR Strategy implementation plan agreed by June 2006 |  |  |  |  | A single strategy document has not been collated. HR work is focussed on practical support of major Council developments and service redesign in line with strategic direction. |
|  |  | OD Framework in place September 2006 to guide approach to change initiatives |  |  |  |  | This is a major ongoing work stream. Change mgt support pack and programme in place. |

| #### TARGET OUTCOME HR2 |  | HR policy and processes which promote and support corporate effectiveness |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Ref. | 3 Year Target | Target 2006/07 | Completed | Good progress – on track with development | Running behind with development progress | Unlikely to complete | Position at 30th September 2006 and impact of / reasons for delays |
| HR2.1 | Pay and grading structures & terms and conditions revised Council-wide ( Single Status, Teachers, Joint Future) | Equal Pay liability proposals & Single Status employment package proposed by June 2006 & implemented thereafter. Programmed implementation of Single Status grading structures. |  |  |  |  | Major work programme of complex work strands. EP compensation offers made successfully. Pay modelling and grade design currently under consultation with Senior Mgt & TU's. Implementation strategy being revised in tandem with emerging Cosla national approaches. |
| HR2.2 | Policy and procedure framework which encourage modern flexible practices,positive employee relations & effective management practice | Flexible working policy and practices in place to meet new legislation and service delivery needs Dec 2006 |  |  |  |  | Legislative requirements are met. Current work is supporting D&E adopt new working arrangements. Council wide policy proposals under consultation. |
| HR2.3 | Programme for HR policy & procedures revamped on line to enable self service by managers& updated to met emerging needs/culture | Severance & redeployment by September 2006 |  |  |  |  | Focus shifted to ensure proposals would fit potential Joint Working Ongoing work area more widely across the Council and following recent pension regulation changes. |
|  |  | Workplace conflict and discipline by December 2006 |  |  |  |  | Work currently on hold - to be revisited 3rd quarter. |
| HR2.4 | Employee health, safety & wellbeing safeguarded | Health & Safety Executive Management Standards for tackling workplace stress achieved – corporate policy |  |  |  |  | Stress policy almost complete after Mgt/TU consultation. Working with HSE Inspector on programme. |
|  |  | The Council’s approach to promoting health at work is endorsed by the Scotland's Health at Work campaign – SHAW Bronze by June 2006 |  |  |  |  | Portfolio of improvement actions undertaken is completed, but whole Council accreditation still outstanding. Other priorities are greater than continuing to pursue at present - review for next year. |
|  |  | Comprehensive health surveillance programme in place across Council |  |  |  |  | Agreed programme now adopted. Will be ongoing work area with practice reviewed & developed in line with experience & feedback. |
| HR2.5 | Management Information systems support performance management and inform decision making & forward planning. | Establishment Mgt monitoring system fully operational. |  |  |  |  | More robust control measures introduced and pproving successful. |
|  |  | Extend HR online – Absence Mgt Reporting by June 2006 |  |  |  |  | Reporting system available - next stage is to roll out adoption across all services. |
| HR2.6 | Customer First Programme People Devt Strand delivered | Housing Services restructuring & business redesign completed |  |  |  |  | Agreed work programme on structure completed. Support for ongoing business change on track. |
|  |  | Support Development and Environment Services restructure |  |  |  |  | Work in discrete areas, eg waste services proceeding in line with service timescales. |

| #### TARGET OUTCOME HR3 |  | Employee contribution to Council objectives is maximised through inclusive development and involvement opportunities |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Ref. | 3 Year Target | Target 2006/07 | Completed | Good progress – on track with development | Running behind with development progress | Unlikely to complete | Position at 30th September 2006 and impact of / reasons for delays |
| HR3.1 | Employee resourcing, training and development anticipates & reflects corporate, service & individual needs consistently. | Performance Review and Development plans in place across Council and collated to inform development programmes |  |  |  |  | Systems in place. Services implementing in their planned timescales. |
|  |  | Corporate T& D group plan for integrated activities delivering efficiencies by October 2006 |  |  |  |  | Emerging plans for integration on phased basis as needs identified. |
|  |  | Develop programmes in line with identified skills needs |  |  |  |  | As above |
| HR3.2 | Managers ownership and practice of corporate working style. | Leadership Development programmes based on agreed leadership /manager competency model extended across management tiers |  |  |  |  | Ist phase completed successfully. Programmes in place for extension as planned. |
|  |  | Action plan to support managers redress key skills gaps and embed workforce and succession planning |  |  |  |  | Overall more progress needed on this. The diversity of workforce means that the focus is on specific initiatives rayther than uniform approach. |
| HR3.3 | Employee consultation and involvement mechanisms are inclusive and comprehensive. | Conduct staff attitude survey and action plan to address key results by September 2006 |  |  |  |  | Completion delayed, now scheduled for 3rd quarter. Actual programme and content agreed for implementation in November. |
|  |  | Trade Union recognition, facilities agreement and protocols completed by September 2006 |  |  |  |  | Deferred for other priorities. Proven very difficult to engage all parties in review. |

| #### TARGET OUTCOME HR4 |  | Corporate HR service fit for current and anticipated purpose within the Council |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Ref. | 3 Year Target | Target 2006/07 | Completed | Good progress – on track with development | Running behind with development progress | Unlikely to complete | Position at 30th September 2006 and impact of / reasons for delays |
| HR4.1 | HR Service redesigned, skilled & resourced to meet Corp Priorities & service needs | Best Value review action plan of service improvement and benchmarking implemented. |  |  |  |  | Being followed thorugh, but with some lessening of attention in favour of Council & external service demands. |
|  |  | Admin process review implemented to realise efficiency & allocate resource to development. |  |  |  |  | As above. |
| HR4.2 | Shared service delivery with partner organisations is established (see also F2.4) | Review and agree with partners areas of HR shared service potential : T&D initial area by September 2006 |  |  |  |  | Ongoing task in which considerable numebr of shared programmes are run successfully. Extent of joint working is being accelerated with Stirling in particular. |
|  |  | Corp Devt Shared Service Feasibility study completed Sept 2006 |  |  |  |  | Working in line with overall Council programme. |
|  |  | Plan for next steps in line with outcome by March 2007 |  |  |  |  | As above. |

| #### TARGET OUTCOME HR5 |  | Employees contribute to the development of policies which promote equality and diversity across the communities in Clackmannanshire |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Ref. | 3 Year Target | Target 2006/07 | Completed | Good progress – on track with development | Running behind with development progress | Unlikely to complete | Position at 30th September 2006 and impact of / reasons for delays |
| HR5.1 | Develop a high level of awareness across council and with partners of the importance of diversity, barrier free access and equality of opportunity in employment and service delivery. | Develop & publish Disability Equality scheme by November 2006 |  |  |  |  | Working across services to ensure programme remains on track. |
|  |  | Develop policy & procedure to ensure good practice and compliance with Age Discrimination Legislation by September 2006 |  |  |  |  | Ongoing awareness raising across the Council. |
|  |  | Introduce employment initiatives extending opportunities for less advantaged groups |  |  |  |  | 2 ticks and inclusive employment provsions in place. |

Business Change

| #### TARGET OUTCOME BC1 |  | The Council delivers better customer service and more efficient and effective service delivery at lower cost. |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Ref. | 3 Year Target | Target 2006/07 | Completed | Good progress – on track with development | Running behind with development progress | Unlikely to complete | Position at 30th September 2006 and impact of / reasons for delays |
| BC1.1 | Deliver a council-wide Change Programme (Customer First) in conjunction with Services. | Develop corporate technology infrastructure blueprint to support Customer First. |  |  |  |  |  |
|  |  | Implement priority components of technology blueprint. |  |  |  |  | This is a long term project. Significant progress has already been made. |
|  |  | Develop Council-wide business change roadmap. |  |  |  |  | Progress made but overall slippage on the roadmap programme. |
|  |  | Work with Housing to develop a Housing change agenda with identified and agreed benefits. |  |  |  |  | Change agenda agreed. Benefits identified and agreed in most areas. Some delayed until after Communities Scotland inspection, due November 2006. |
|  |  | Ensure compliance with National Programmes. |  |  |  |  | Good progress made at local level. However, there are delays with the national programme. |
| BC1.2 | Develop Service capacity to manage and deliver improvement & change projects. | Provide consultancy, skills transfer and support to Services on change projects. |  |  |  |  | Work ongoing on a number of areas providing support and consultancy. Skills transfer requires a long-term view, however, progress is being made. |
|  |  | Develop standard change methodology and templates. |  |  |  |  | "5-step" process in place. |
|  |  | Develop standard Programme / Project Management methodology and tools / templates. |  |  |  |  | Templates developed and communicated via COIN. |

Service Improvement

| #### TARGET OUTCOME SI1 |  | The Council has effective arrangements in place to secure continuous improvement in performance and delivery of services in the most effective, efficient and economical manner |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Ref. | 3 Year Target | Target 2006/07 | Completed | Good progress – on track with development | Running behind with development progress | Unlikely to complete | Position at 30th September 2006 and impact of / reasons for delays |
| SI1.1 | Successful Best Value audit. | Achieve favourable Best Value Audit outcome and commence implementation of improvement plan. |  |  |  |  | This work is now being led by the Head of Strategic Policy. Audit Scotland have completed their site work, with the first draft expected later in the year. |
| SI1.2 | The Council has in place a rigorous Best Value Review process and schedule | Revise process and schedule, reinforcing Challenge and Compete requirements |  |  |  |  | Process presently being revised for presentation to CMT during the autumn. |
| SI1.3 | Service planning and performance reporting is facilitated by the use of information technology. | Corporate Service Planning / Reporting database developed. All service plans and performance reports are administered via the networked database. |  |  |  |  | Working ongoing but delayed due to staff turnover within SI. |
| SI1.4 | Comprehensive performance information is readily available and accessible. | Extend performance management information and advice on the web/intranet. |  |  |  |  | SPIs available on website Balanced Scorecard available on COIN. |
| SI1.5 | Performance management at the service plan level is supported by a balanced set of performance indicators | Review use of balanced scorecards and refine where necessary. |  |  |  |  | Balanced Scorecards are now reported to P&A on a quarterly basis. Improvements and refinements will continue to be made on an ongoing basis. |

| #### TARGET OUTCOME SI2 |  | The Council’s exposure to risk is known and effectively managed |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Ref. | 3 Year Target | Target 2006/07 | Completed | Good progress – on track with development | Running behind with development progress | Unlikely to complete | Position at 30th September 2006 and impact of / reasons for delays |
| SI2.1 | The Council has a clear and up to date knowledge of its exposure to risk. | Governance processes for Council corporate risk management defined and in place. |  |  |  |  |  |
|  |  | Risk register maintained and high level risks reported and managed. |  |  |  |  | Disaster Recovery and Business Continuity Planning will be added to the register when they are available. |

| #### TARGET OUTCOME SI3 |  | The Council is an effective organisation and achieves continuous improvement |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Ref. | 3 Year Target | Target 2006/07 | Completed | Good progress – on track with development | Running behind with development progress | Unlikely to complete | Position at 30th September 2006 and impact of / reasons for delays |
| SI3.1 | EFQM Excellence Model integrated into Council improvement processes. | Formal commitment made to adoption of EFQM Excellence Model. |  |  |  |  | CMT approved the working group recommendation in November 2005. |
|  |  | Project established for implementation of EFQM Excellence model. |  |  |  |  | This work has slipped due to staff turnover and resource constraints. A Business Case is under development, which will be submitted to CMT over the autumn. |
|  |  | Impact of EFQM on Best Value Review and Service Planning understood. |  |  |  |  | This will be dealt with as part of the above mentioned Business Case. |

| #### TARGET OUTCOME CS1 |  | Improved Customer Service ensuring quality improvements and financial savings are delivered. |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Ref. | 3 Year Target | Target 2006/07 | Completed | Good progress – on track with development | Running behind with development progress | Unlikely to complete | Position at 30th September 2006 and impact of / reasons for delays |
| CS1.1 | Implement the Council’s Customer Service Strategy. | Obtain outline approval for the Customer Service Strategy ensuring linkage with other Council strategies (e.g. Libraries, Facilities). |  |  |  |  | Strategy and Action Plan completed, but still requires to be formally signed off by Council. |
|  |  | Develop the Business Case/ Project Initiation Document (PID) / plans for delivering the Customer Services Strategy. |  |  |  |  | PID will be developed once Strategy has been approved. |
|  |  | Obtain formal approval for Customer Service Strategy. |  |  |  |  | Strategy to be submitted to Council in November for formal approval. |
|  |  | Implement Customer Service deliverables planned for 2006/07. |  |  |  |  | Strategy to be submitted to Council in November for formal approval. |
| CS1.2 | Develop Contact Centre in line with updated route map. | Implement new services through Contact Centre planned for 06/07. |  |  |  |  | No new services to be added until current performance and resourcing issues have been addressed. |
|  |  | Capture and use Customer contact information to help planning within Customer Service. |  |  |  |  | Significant management information gathered from customer logging system (Raven). |
| CS1.3 | Develop Local Office Network/Customer Service Centres in line with Customer Services Strategy. | Implement Customer Service Centre(s) in accordance with Customer Services Strategy implementation timescales. |  |  |  |  | In line with Customer Services Strategy approval process. |
| CS1.4 | Develop ClacksWeb as a primary Customer Service channel. | Extend online functionality, in line with local/national electronic service delivery (ESD) priorities. |  |  |  |  | Progress ongoing to deliver more transactional services online. |
| CS1.5 | Improve access to council information and services, through new access channels. | Pilot use of a text messaging service (where business case exists) to improve customer communication & reduce transaction costs. |  |  |  |  | To be undertaken in second part of year, if resource is available. |

| #### TARGET OUTCOME CS2 |  | Council-wide Customer Service orientation and culture change programme, delivered through a staff training and development programme. |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Ref. | 3 Year Target | Target 2006/07 | Completed | Good progress – on track with development | Running behind with development progress | Unlikely to complete | Position at 30th September 2006 and impact of / reasons for delays |
| CS2.1 | Implement a council-wide Customer Service training programme. | Define Customer Service management & staff competency framework. |  |  |  |  | Pilot project underway with Contact Centre staff undertaking SVQ qualifications. |
|  |  | Define and deliver phase 1 of a council-wide Customer Services programme, initially focused on front line Customer Service staff (& the Housing Service). |  |  |  |  | Work in progress in partnership with HR. |

| #### TARGET OUTCOME CS3 |  | Deliver continuous improvement and service quality in Customer Services. |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Ref. | 3 Year Target | Target 2006/07 | Completed | Good progress – on track with development | Running behind with development progress | Unlikely to complete | Position at 30th September 2006 and impact of / reasons for delays |
| CS3.1 | Implement a range of customer service improvements, highlighted through regular customer & staff feedback. | Establish a corporate Customer Service group to agree priority areas for improvement. |  |  |  |  | Customer Service Network being formally established. |
|  |  | Establish customer service improvement teams, within & across service areas, to highlight improvement ideas. |  |  |  |  | To be established within services as part of the Customer Service Network. |
|  |  | Undertake annual customer satisfaction survey as part of Council’s consultation process and act on findings. |  |  |  |  | Aim is to undertake more regular surveying of customers through the Contact Centre (eg every 20 calls). Current resource levels do not allow this activity to be undertaken |

| #### TARGET OUTCOME IT1 |  | Effective IT Governance in place |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Ref. | 3 Year Target | Target 2006/07 | Completed | Good progress – on track with development | Running behind with development progress | Unlikely to complete | Position at 30th September 2006 and impact of / reasons for delays |
| IT1.1 | Implement Corporate approach to IT Governance | Develop, Issue and obtain approval for IT Governance Model. |  |  |  |  | IT Governance group now in place |
|  |  | Set up and chair IT Governance Group. |  |  |  |  | IT Manager chairs the IT Governance Group |
| IT1.2 | Centralisation of IT Budget | Obtain approval for budget centralisation. |  |  |  |  | Awaiting finalised budgets from Council Services before progressing |
|  |  | Manage budget through ITGG. |  |  |  |  | Business case provides ITGG with funding sources for approval |

| #### TARGET OUTCOME IT2 |  | Improve IT Strategy and Architecture |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Ref. | 3 Year Target | Target 2006/07 | Completed | Good progress – on track with development | Running behind with development progress | Unlikely to complete | Position at 30th September 2006 and impact of / reasons for delays |
| IT2.1 | Develop the IT Strategy to support the councils business strategy. | Review existing IT strategy and update to reflect business strategy. |  |  |  |  | Being reviewed in relation to joint management of service with Stirling Council |
| IT2.2 | Develop the IT Architecture | Develop current state Technology reference Model. |  |  |  |  | Being developed but is under review in line with Joint Management of service with Stirling Council |
|  |  | Develop future state technology reference Model. |  |  |  |  | Under review in line with joint management with Stirling Council |
| IT2.3 | Develop the IT Business Continuity / Disaster Recovery Strategy. | Assess implications of recommendations of Council BC/DR Review and develop plan for IT. |  |  |  |  | Working with Council's Emergency Planning Officer and Glen Abbot Consultants to produce outline strategic report |

| #### TARGET OUTCOME IT3 |  | Improve IT Service Management |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Ref. | 3 Year Target | Target 2006/07 | Completed | Good progress – on track with development | Running behind with development progress | Unlikely to complete | Position at 30th September 2006 and impact of / reasons for delays |
| IT3.1 | Implement Corporate approach to IT Service Management | Develop, Issue and obtain approval for IT Service Delivery Model. |  |  |  |  | Agreed by Executive team |
|  |  | Formalise roles of IT Account Manager and Service IT Co-ordinators. |  |  |  |  | Agreed by IT governance Group |
| IT3.2 | Develop processes and technologies to support effective Resource Management | Establish resource management framework. |  |  |  |  | Slow progress due to staffing resources to develop framework |
|  |  | Build IT core competency framework. |  |  |  |  | Other priorities have contributed to delay in progressing an IT Core Competency framework |

| #### TARGET OUTCOME IT4 |  | Improve IT Service Delivery |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Ref. | 3 Year Target | Target 2006/07 | Completed | Good progress – on track with development | Running behind with development progress | Unlikely to complete | Position at 30th September 2006 and impact of / reasons for delays |
| IT4.1 | Develop IT Service Definition and Service Level Agreement | Develop IT Service Definition and Service Level Agreement(s). |  |  |  |  | Draft Service Support Agreement produced for consultation |
|  |  | Issue documents for review / approval. |  |  |  |  | Draft Service Support Agreement issued to Services for feedback and amendments. |

| #### TARGET OUTCOME PR1 |  | Procurement practices reflect Council objectives and deliver savings, efficiencies and best value. |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Ref. | 3 Year Target | Target 2006/07 | Completed | Good progress – on track with development | Running behind with development progress | Unlikely to complete | Position at 30th September 2006 and impact of / reasons for delays |
| PR1.1 | Procurement practice is supported by clear policies, aimed at securing best value for the Council | Complete issue of Procurement Strategy |  |  |  |  | Drafted earlier this year for comments while awaiting Scottish Executive report on public sector procurement.SE defining some of the issues that would have an impact on the content. Anticipate in place for April 2007 |
| PR1.2 | Procurement processes are more efficient and cost effective | All procurement capable of being dealt with electronically. |  |  |  |  | Requires the switch on and roll out of theProcurement Module for Advanced General Ledger now due to be launched December 2006 Work can not be progressed on this until the AGL dependency is implimented due to staffing constaints.Also exploring the implementation of the SE PECOS system through the Shared Service business case |
| PR1.3 | Better value for money through procurement achieved by improving and extending purchase contracts to more accurately reflect the Council’s procurement needs | Spend categories redefined. Ledger codes redefined to reflect spend categories. |  |  |  |  | Redesign of detail codes have now taken place. As above will be utilised when AGL is switched on anticipated at this stage being 2006. The sub analysis feature will be used to more fully reflect spend categories. |
| PR1.4 | Budget savings arising from smarter procurement processes and practice are accurately identified | Detailed analysis of spending and targets savings established and results reported. |  |  |  |  | This is dependent on the implementation of AGL and Crystal reporting to be able to extrapolate information from the ledger system. independent of this some detailed analysis will be undertaken as part of the Shared Service Business Case development. |
| PR1.4 |  | KPI’s Identified and reporting mechanisms established |  |  |  |  | These have been defined but require some refinement in line with the SE McClelland report. Looks like we will have a clearer picture October / . Percentage of influenceable Council spend that Corporate Procurement influences Percentage of influenceable Council spend effected via e-Procurement. Percentage of influenceable Council spend where payment is made by P-Card Process Cost per Transaction Procurement Process Cost per £ of spend Savings achieved across the Council against previous contract cost |