##### Progress Summary: Services to People

| ### Target Outcome |  |  |  |  |  | No. of targets 2006-07 | Complete |  | Good progress – on track |  | Running behind | Unlikely to complete | ### Comments |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| #### Adult Care |  |  |  |  |  |  |  |  |  |  |  |  |  |
| AC1 | Local partnerships in place to ensure the provision of flexible and responsive care, support, prevention and rehabilitation services which enhance the overall health and wellbeing of people who are vulnerable due to age, sickness, addiction or disability. |  |  |  |  | 12 | 0% |  | 92% |  | 8% | 0% | The Joint Future Agenda has been integrated with the progress and development of the local Community Health Partnership There is further work to be done on strategic planning frameworks, the development of joint working arrangements and performance management |
| AC2 | Adults referred for community care assessments receive prompt, co-ordinated and flexible responses which are based on their individual needs. Services are provided in the most appropriate and cost effective way. |  |  |  |  | 8 | 0% |  | 88% |  | 13% | 0% | A Joint Commissioning Plan is being negotiated for older peoples services The single shared assessment process is being implemented Home care and meals services have been reconfigured Day provisions for people with physical learning disabilities will also be reviewed this year |
| AC3 | From an assessment of their individual needs, adults of all community care groups have access to further integrated services and supports which are responsive, and which promote independence and social inclusion. |  |  |  |  | 4 | 0% |  | 100% |  | 0% | 0% | Good progress on the development of single referral and care pathways in the Integrated Mental Health Service and on social inclusion initiatives such as supported employment for people with learning disabilities |
| AC4 | People who have drug and alcohol related problems, and other social work needs, receive information, support and services that promote healthy and crime-free lives. |  |  |  |  | 1 | 0% |  | 0% |  | 100% | 0% | Local research and needs assessment need to be undertaken, subject to resources available |
| AC5 | All eligible carers receive responsive services and other support, according to their identified needs and in relation to their caring role. |  |  |  |  | 3 | 0% |  | 100% |  | 0% | 0% | More carers are being identifed and their needs assessed. There is ongoing consultation through the local carers strategy group |
| AC6 | A skilled Social Services workforce providing high quality services, in conjunction with key partners, to people in all community care groups |  |  |  |  | 3 | 0% |  | 67% |  | 33% | 0% | The Changing Lives- 21st Century Workforce Development Group has been established to take forward a review and development plan |
| #### Early Years & Out of School Care |  |  |  |  |  |  |  |  |  |  |  |  |  |
| EY1 |  |  | Early years services are supported and developed |  |  | 2 | 50% |  | 50% |  | 0% | 0% | Ongoing |
| EY2 |  |  | Out of School Care Services are supported and developed |  |  | 1 | 0% |  | 100% |  | 0% | 0% | Work ongoing |
| EY3 |  |  | Children’s health and development are improved |  |  | 2 | 0% |  | 100% |  | 0% | 0% | Continued close partnership working to achieve targets |
| EY4 |  |  | Staff provide an effective service |  |  | 2 | 0% |  | 100% |  | 0% | 0% | Programmes ongoing |
| #### Child Care |  |  |  |  |  |  |  |  |  |  |  |  |  |
| CH1 |  |  |  | Children and young people referred as being in need of protection receive a prompt, professional service in response to their needs |  | 3 | 33.3% | 33.3% |  | 0.0% |  | 33.3% | On target. |
| CH2 |  |  |  | Young people leaving care receive an effective Throughcare service |  | 1 | 0% | 100% |  | 0% |  | 0% | On target |
| CH3 |  |  |  | Provide a high quality Family Placement and Adoptive Service meeting the needs of child and families |  | 2 | 100% | 0% |  | 0% |  | 0% | The Care Commission carried out the first inspection of the Fostering and Adoption Services in June 2006. Informal feedback indicates some recommendations, but no requirements. The final report is expected in October 2006. |
| CH4 |  |  |  | The Rights of Looked After and Looked After and Accommodated Children are enhanced |  | 2 | 50% | 0% |  | 50% |  | 0% | Staff shortages affecting performance. |
| CH5 |  |  |  | Effective and constructive measures are provided to those children and young people in trouble with the law to divert them away from offending behaviour |  | 1 | 0% | 0% |  | 100% |  | 0% | Due to an increase in persistent young offenders outcome is running behind target. The Youth Justice Social Work post is unfulfilled at the present time. |
| CH6 |  |  |  | Child Care Recruitment and Retention is improved |  | 1 | 0% | 0% |  | 100% |  | 0% | National recruitment difficulties continue. Looking at a number of local initiatives. |
| CH7 |  |  |  | Maintain ISO 9001:2000 Accreditation |  | 1 | 0% | 0% |  | 0% |  | 100% | A decision was taken in May 2006 to withdraw from ISO. A quality assurance system has been continued within the Service, ensuring that document and data control remains solid. |
| #### Criminal Justice Service |  |  |  |  |  |  |  |  |  |  |  |  |  |
| CJ1 |  | Increased safety and public protection through the provision of services which focus on reducing offending |  |  |  | 2 | 0% | 50% |  | 0% |  | 50% | Good progress on target. This was highlighted by a recent performance inspection of the service who looked at: 1. Assessments prepared for courts and parole board. 2. Supervision of offenders on probation. 3. Community Service. 4. Parole and non parole licence. |
| CJ2 |  | Greater social inclusion of offenders through rehabilitation |  |  |  | 2 | 100% | 0% |  | 0% |  | 0% | Target achieved. The service is pleased to note that the inspection highlighted many areas of good practice, good individual work with offenders and well delivered groupwork programmes. The report found that the service was operatng at standards, which are adequate or good, and in some instances very good. Some areas for improvement were highlighted in the inspection however these are being actively and systematically addressed through the performance monitoring regime. |
| CJ3 |  | Maintain ISO 9000:2000 accreditation |  |  |  | 1 | 0% | 100% |  | 0% |  | 0% | Target achieved. As well as maintaining accreditiation the service underwent a Best Value audit. Part of this process involved obtaining the views of the Sheriff who indicated that the service was fit for purpose. |
| CJ4 |  | Improve staff training in working with sex offenders in the community |  |  |  | 1 | 0% | 0% |  | 100% |  | 0% | Running Behind as training is not yet available. |
| #### Culture & Community Services |  |  |  |  |  |  |  |  |  |  |  |  |  |
| CC1 |  | The service will introduce a system for recording and celebrating learning achievement by 2008/09 |  |  |  | 16 | 31% |  | 69% | 0% |  | 0% | The service is on track with targets for 2006/07. The target to develop Junior Challenge Award within 2 community settings has been exceded, with 4 groups being established. |
| CC2 |  | The service will assist young people to engage in decision-making processes which affect their lives. |  |  |  | 18 | 28% |  | 72% | 0% |  | 0% | To date good progress is being made. The launch of a Youth Council, links with the Scottish Youth parliament and the publication of a youth page in the Wee County news every four weeks. Are some of the objectives completed to date. |
| CC3 |  | The service working practices will implement the national standards for community engagement |  |  |  | 10 | 10% |  | 90% | 0% |  | 0% | Good practices being achived. Working with social landlords in developing relationships and joint work. Health Boards - Homeless, recovering adults ect. and voluntary organisations. |
| CC4 |  | The service will continue to develop self evaluation and continuous improvement mechanisms. |  |  |  | 11 | 45% |  | 55% | 0% |  | 0% | Over demand for ESOL (english as a second language) learners identified, more sesional tutors are adressing this. Staff supervision sessions established to reflect How Good is our Community Learning and Developmen, and National Standards for Community Engagement. |
| CC5 |  | The service will develop and implement an action plan in response to HMIE report |  |  |  | 13 | 38% |  | 54% | 8% |  | 0% | Action plan accepted by HMIE.. |
| #### Leisure & Recreation |  |  |  |  |  |  |  |  |  |  |  |  |  |
| LR1 |  | To improve participation, ensure quality of facilities, deliver quality services, ensure viability and develop sustainability |  |  |  | 5 | 60% |  | 20% | 20% |  | 0% | Meeting all targets and timescales satisfactorily. Development of outdoor project requires a multi-agency approach. Propose meeting early January in order to set programme for Spring and Summer delivery. |
| #### Sports Development |  |  |  |  |  |  |  |  |  |  |  |  |  |
| SD1 |  |  | Establish partnerships with various internal and external agencies to create opportunities and pathways for education establishments, communities, individuals, clubs and targeted groups to be active, healthy and realise their sporting potential. |  |  | 11 | 9% |  | 82% | 9% |  | 0% | Meeting all targets and timescales, all partnerships maturing well, creating new opportunities and clearer pathways. Many sports and PE projects in Clackmannanshire used as examples of good practice across Scotland. |
| #### Housing & Advice Services |  |  |  |  |  |  |  |  |  |  |  |  |  |
| HA1 |  |  |  |  | Progress has been made to ensure a higher percentage of Social housing in Clackmannanshire has attained or exceeded the Scottish Housing Quality Standard and a realistic and achievable programme is in place to increase this to 70% by 2009 | 1 | 100% |  | 0% |  | 0% | 0% | Complete. Standard Delivery Plan has been approved by Communities Scotland |
| HA2 |  |  |  |  | Progress has been made to ensure an additional 20% of privately owned or rented housing has attained or exceeded the Scottish Housing Quality Standard and realistic and achievable proramme is in place to complete this by 2009 | 4 | 75% |  | 25% |  | 0% | 0% | Good progress 3 targets for 2006/07 have been complete. The stock condition survery will be reviewed by April. |
| HA3 |  |  |  |  | Progress has been made to ensure Housing Services are both customer and community oriented and a realistic and achievable programme is in place to complete this by 2009 | 12 | 33% |  | 67% |  | 0% | 0% | Good progress with all targets, 4 have already been complete (in preparation for Communities Scotland Inspection). Remaining targets are on schedule to complete by year end. |
| HA4 |  |  |  |  | Policies & Procedures Developed to promote sustainable communities | 10 | 10% |  | 70% |  | 20% | 0% | Good progress in most targets - Choice Based Lettings Scheme project is well advanced, and progress on policies and procedures for voids and homelessness is at an advanced stage. The homelessness strategy implementation plan is on target. The only target where slippage is the implementation of the Common Housing Register - this is due to the implementation of the Choice Based Letting. A revised target date for this project has been set for September 2007. |
| HA5 |  |  |  |  | The shortfall of specialist housing and housing support services promoting independent living is being addressed and is on track to be delivered by 2009 | 4 | 0% |  | 100% |  | 0% | 0% | Good progress on these targets, all due to be complete by year end. With regards to Action 5.4. a HEARTH bid has now been approved and we are on target to deliver. |
| #### Schools |  |  |  |  |  |  |  |  |  |  |  |  |  |
| SL1 |  | To implement ‘A Curriculum for Excellence (ACE)’ |  |  |  | 12 | 17% |  | 83% | 0% |  | 0% | Almost all targets are complete or good progress is being made in securing ytheir completion. Some of the targets are of a character which means that they may never be fully complete. |
| SL2 |  | To raise attainment |  |  |  | 24 | 8% |  | 83% | 8% |  | 0% | Statndards of attainment are on upward trends in relation to all key measures of performance. Some targets set for 2006/2007 and beyond are ambitious. Whether or not they are achived fully may be less important than the continuation of upward trends with steepr gradients. |
| SL3 |  | Create conditions conducive to learning |  |  |  | 18 | 22% |  | 78% | 0% |  | 0% | Significant progress is being made, particularly in relation to improving teaching standards in our schools; the authority is making a major commitmentto the promotion of co-operative learning. |
| ###### Total / Average |  |  |  |  |  | 224 | 22% |  | 70% | 7% |  | 1% |  |

Adult Care

| #### TARGET OUTCOME AC1 |  | Local partnerships in place to ensure the provision of flexible and responsive care, support, prevention and rehabilitation services which enhance the overall health and wellbeing of people who are vulnerable due to age, sickness, addiction or disability. |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Ref. | 3 Year Target | Target 2006/07 | Completed | Good progress – on track with development | Running behind with development progress | Unlikely to complete | Position at 30th September 2006 and impact of / reasons for delays |
| AC1.1 | To ensure that integrated Health, Housing and Social Services planning and service frameworks are in place to provide comprehensive services for all care groups | Integration of strategic planning frameworks from the Joint Future Agenda with the established Community Health Partnership |  |  |  |  | A Joint Strategic review is being undertaken The Community Health Partnership is established and the Joint Future Agenda has been partially integrated into the planning structure Further work to be done on Performance Management |
|  |  | Agree key Joint Local Improvement Targets and Outcomes for end- year reporting |  |  |  |  | Reports were submitted to the Scottish Executive Joint Future Unit in May 2006 and a Final Evaluation of our progress will be received in October 2006 |
| AC1.2 | Joint implementation of key objectives from the Housing and Homelessness Strategies for people with community care needs | Implement actions from the Housing Needs Assessment |  |  |  |  | A Particular Needs Housing Asseesment of Older People is nearing completion : a joint group will evaluate the findings from this consultation for future planning |
|  |  | Develop joint crisis response services for homeless people with social work needs |  |  |  |  | Work is ongoing to develop a shared assessment process |
|  |  | SMART homes development for 8 more people in supported accommodation |  |  |  |  | A new approach is being explored, to provide support in dispersed accomodation. A Telecare bid, to provide extended technological support, is being submitted end Oct.06. |
| AC1.3 | Children with additional support needs supported in their transition to adult services | Implementation of revised procedures for preparation and transitions from child  adult services 23 children 2006-7 |  |  |  |  | The Transition group continues to monitor plans for children with additional support needs who are leaving school |
| AC1.4 | Information sharing protocols, technology and procedures in place for joint service planning, delivery and monitoring | Establish SSA (Single Shared Assessment) process, and maintain interim solutions with NHS Forth Valley Increase the number and scope of SSA |  |  |  |  | Ongoing work for implementation and awaiting Forth Valley E-care |
| AC1.5 | Compliance with National Care standards and Registration Guidance | Maintain ISO standards in residential and day services |  |  |  |  | ISO accreditation is being maintained in residential and day services |
|  |  | Implement actions recommended from inspections |  |  |  |  | Responses prepared on recommendations from Inspection Reports |
|  |  | Capital Works to upgrade Menstrie House Care Home |  |  |  |  | Capital works have commenced at Menstrie House |
| AC1.6 | Consultation, involvement and advocacy frameworks in place for the effective engagement of service users and their carers | Integrate consultation and communication activities with community planning frameworks |  |  |  |  | This work is ongoing in local implementation groups. The Public Particpation Forum of the Community Health Partnership is established |
|  |  | Support the establishment of the Independent Advocacy Service Monitor progress |  |  |  |  | The Independent Advocacy Service has become established in a local base in Alloa |

| #### TARGET OUTCOME AC2 |  | Adults referred for community care assessments receive prompt, co-ordinated and flexible responses which are based on their individual needs. Services are provided in the most appropriate and cost effective way. |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Ref. | 3 Year Target | Target 2006/07 | Completed | Good progress – on track with development | Running behind with development progress | Unlikely to complete | Position at 30th September 2006 and impact of / reasons for delays |
| AC2.1 | National Community Care Core Priorities addressed in the development community-based services which support people at home | Joint development of reporting frameworks, prioritising identified needs for services |  |  |  |  | A Performance Framework is established and will be further developed following Scottish Executive evaluation in Oct06 |
|  |  | Maintain position on delayed discharges |  |  |  |  | Delayed discharges remain low and well within national targets |
|  |  | Develop services to prevent admissions and support discharges Increase use of joint rehabilitation service |  |  |  |  | The joint rehabilitation service is working well for older people. A transitional service is being established for older people with mental health problems. Crisis responses and rapid support are available to all community care groups |
|  |  | Implement review of existing provision of home care, MECS and home support services Evaluation of quality and cost |  |  |  |  | A review has been undertaken and changes made to home care services and the provision of meals-on-wheels |
| AC2.2 | Re-designed mental health services which are community based, with procedures and services in place for the implementation of new Mental Health legislation | Further integration of community based day services, working with the Home Treatment Team pilot project All MHOs and other relevant staff trained in MH legislation I additional trained MHO |  |  |  |  | Ongoing development of the Integrated Mental Health Service A single referral pathway will be launched in Jan07 with further planned integration of services. All relevant staff have been trained in MH legislation |
| AC2.3 | Redesigned models of services in partnership arrangements with Health | Integrate the learning disability service model, referral and care pathways Reconfigure day provisions |  |  |  |  | The outcomes of a Forth Valley wide strategic review and revision of the Partnership-in-Pratice agreement are awaited. A review of day provisions is being undertaken from Nov 06 |
|  |  | Focus on joint access to services and identify service gaps |  |  |  |  | There is joint access to some services through single shared assessment Ongoing work in older peoples services with a Joint Commissioning Plan and progress in integrated mental health and learning disability services Joint access to health and social services equipment through CES is established and working well |
| AC2.4 | People with sensory impairments receiving inclusive and integrated support and services | Take up of guide-communicator and mobility services to be monitored Spot purchasing arrangements in place for a range of supports and services from Forth Valley Resource Centre |  |  |  |  | Ongoing work with the Forth Valley Sensory Centre and shared contracts for services |

| #### TARGET OUTCOME AC3 |  | From an assessment of their individual needs, adults of all community care groups have access to further integrated services and supports which are responsive, and which promote independence and social inclusion. |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Ref. | 3 Year Target | Target 2006/07 | Completed | Good progress – on track with development | Running behind with development progress | Unlikely to complete | Position at 30th September 2006 and impact of / reasons for delays |
| AC3.1 | All key partners providing outreach services which promote social inclusion across all care groups and access to wider options for work and leisure | Counselling service pilot 2006-7 Extended out of hours provisions The establishment of a single referral pathway Focus on mental health and well being |  |  |  |  | Counselling services pilot set up and going well. The single referral pathway (Jan07)will promote further planned integration of services, including a new tier of preventitive and anticipatory care |
|  |  | Disability Equality Scheme by Nov. 2006 in accordance with provisions for the Disability Discrimination Act |  |  |  |  | A joint implementation group has been set up to work on the Disability Equality Scheme |
|  |  | More service users in employment (+10) Increase day care opportunities for young people with learning disabilities |  |  |  |  | Supported EmploymentScheme increasing uptake of employment opportunities. Day Services are under review, facilitated by the National Development Team |
| AC3.2 | Established system for Direct Payments across all care groups | Implement guidance on issuing direct payments to all eligible service users |  |  |  |  | No increase in uptake, and implementation is ongoing. A national consultation on new guidance will report in Jan07 |

| #### TARGET OUTCOME AC4 |  | People who have drug and alcohol related problems, and other social work needs, receive information, support and services that promote healthy and crime-free lives. |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Ref. | 3 Year Target | Target 2006/07 | Completed | Good progress – on track with development | Running behind with development progress | Unlikely to complete | Position at 30th September 2006 and impact of / reasons for delays |
| AC4.1 | Achieve targets set by the Forth Valley Substance Action Team for implementation in Clackmannanshire for people with community care needs | Ensure integrated service planning, care provision and support for people with community care needs Focus on those with mental health needs and dual diagnosis |  |  |  |  | Awaiting resource allocation for local research and needs assessment |

| #### TARGET OUTCOME AC5 |  | All eligible carers receive responsive services and other support, according to their identified needs and in relation to their caring role. |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Ref. | 3 Year Target | Target 2006/07 | Completed | Good progress – on track with development | Running behind with development progress | Unlikely to complete | Position at 30th September 2006 and impact of / reasons for delays |
| AC5.1 | Implementation of the National Guidance on Carers meeting the priorities of local Carers Strategy for 2005-2008 through the assessment process and the provision of support and services | Consultation on local needs Implement national recommendations in Carers Strategy Action Plans 2005-2008 |  |  |  |  | Ongoing work with the Carers Strategy into Action Group |
|  |  | Increase number of carers assessments recorded |  |  |  |  | More carers assessments are being recorded A health centre based project has identified 89 'hidden' carers |
|  |  | Provide increased support and respite 5 more properties offering flexible support |  |  |  |  | Work is ongoing on identified local properties to increase the range and choice of respite/short break options for carers |

| #### TARGET OUTCOME AC6 |  | A skilled Social Services workforce providing high quality services, in conjunction with key partners, to people in all community care groups |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Ref. | 3 Year Target | Target 2006/07 | Completed | Good progress – on track with development | Running behind with development progress | Unlikely to complete | Position at 30th September 2006 and impact of / reasons for delays |
| AC6.1 | Programme of staff training implemented to support continuing professional development and employee development | Local programme of CPD in place for all qualified staff. Progress SVQ + PQ programme for all staff Take forward recommendations from the 21st Century Social Work review |  |  |  |  | A workforce development group is being stablished to drive forward the programme for "Changing Lives "- 21st Century Social Work Review |
| AC6.2 | Joint training scheme accessible to staff employed in Social Services, Housing and Health Services | Complete training for Mental Health Act Implementation |  |  |  |  | A joint training programme has been accessible to all staff and is ongoing |
|  |  | More joint training in Single Shared Assessments and Care Management |  |  |  |  | Some local IT development and support has been provided to health services staff but further joint training initiatives are on hold pending Forth Valley E-care |

Early Years & Out of School Care

| #### TARGET OUTCOME EY1 |  | Early years services are supported and developed |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Ref. | 3 Year Target | Target 2006/07 | Completed | Good progress – on track with development | Running behind with development progress | Unlikely to complete | Position at 30th September 2006 and impact of / reasons for delays |
| EY1.1 | Support to vulnerable families is improved by extending services targeted at children aged 0-3 | 0-3 Initiative is evaluated |  |  |  |  | continuing to evaluate services to most needed areas |
| EY1.2 | Improve the quality and uptake of information available to the public on the Service | New leaflets are drawn up to reflect the changes in service provision |  |  |  |  | Revised service. New system being introduced through Scottish Executive. New training programme approved. |

| #### TARGET OUTCOME EY2 |  | Out of School Care Services are supported and developed |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Ref. | 3 Year Target | Target 2006/07 | Completed | Good progress – on track with development | Running behind with development progress | Unlikely to complete | Position at 30th September 2006 and impact of / reasons for delays |
| EY2.1 | Scope of Out of School Care is developed to include 13-16 year olds | Out of School Care for 13-16 year olds is established |  |  |  |  | Work ongoing to register service with Care Commission and put staffing in place. |

| #### TARGET OUTCOME EY3 |  | Children’s health and development are improved |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Ref. | 3 Year Target | Target 2006/07 | Completed | Good progress – on track with development | Running behind with development progress | Unlikely to complete | Position at 30th September 2006 and impact of / reasons for delays |
| EY3.1 | All early Years provision includes integrated Speech and Language Therapy (SALT) | 12 centres (school based nurseries, day nurseries and family centres) include service |  |  |  |  | New speech and language therapist appointed programme back on track |
| EY3.2 | Extend pre-school physical activity programme (Active Start) to include all children in toddler groups | Initiate a scheme to establish Active Start programmes in each Parent and Toddler group |  |  |  |  | work ongoing through close partnership with voluntary sector |

| #### TARGET OUTCOME EY4 |  | Staff provide an effective service |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Ref. | 3 Year Target | Target 2006/07 | Completed | Good progress – on track with development | Running behind with development progress | Unlikely to complete | Position at 30th September 2006 and impact of / reasons for delays |
| EY4.1 | All staff (including those in partner agencies in the voluntary sector and Childcare Partnership) have achieved or are working towards a professional qualification by 2007 | 10 staff presented for SVQ3 in Early Years |  |  |  |  | programme ongoing with staff on road to achieving professional qualification |
|  |  | 5 staff achieve Professional Development Award |  |  |  |  | 8 staff on programme |

Child Care

| #### TARGET OUTCOME CH1 |  | Children and young people referred as being in need of protection receive a prompt, professional service in response to their needs |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Ref. | 3 Year Target | Target 2006/07 | Completed | Good progress – on track with development | Running behind with development progress | Unlikely to complete | Position at 30th September 2006 and impact of / reasons for delays |
| CH1.1 | Implementation of relevant recommendations in “It’s Everyone’s Job to Make Sure I’m Alright” and “Getting Our Priorities Right” reports | Achieve targets set out in Scottish Executive Inspection and audit |  |  |  |  |  |
| CH1.2 | Raise awareness of child protection issues across all agencies and ensure that all Child Protection concerns are promptly and appropriately referred. | Review services in light of the National Framework for Standards for Child Protection and the joint HMIE, SWIA and Audit Scotland inspection of Child Protection Services |  |  |  |  | Awareness raised at Child protection Case Conferences and Planning Meetings which involve all agencies. Robust procedures ensure referrals are dealt with within departmental timescales. Proforma for child protection investigations has been amended to include information regarding children who require additional support. We also have regular liaison with CJS partners through the Sex Offenders Liaison Group which monitors perpetrators. |
|  |  | Gain MGF 3 Funding along with partners and prepare infrastructure in order to develop and implement an electronic single shared assessment |  |  |  |  | Bid unsucessful. |

| #### TARGET OUTCOME CH2 |  | Young people leaving care receive an effective Throughcare service |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Ref. | 3 Year Target | Target 2006/07 | Completed | Good progress – on track with development | Running behind with development progress | Unlikely to complete | Position at 30th September 2006 and impact of / reasons for delays |
| CH2.1 | Ensure that the new arrangements for Throughcare and Aftercare lead to a better service for young people | Ensure that existing system for payments and monitoring spend can respond to the increased numbers of young people requiring financial support expected in the year. |  |  |  |  | On target. Appropriate financial support provided depending on young persons circumstances. Whilst the TCAC post is vacant, this client group continues to receive a service from Child Care. |

| #### TARGET OUTCOME CH3 |  | Provide a high quality Family Placement and Adoptive Service meeting the needs of child and families |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Ref. | 3 Year Target | Target 2006/07 | Completed | Good progress – on track with development | Running behind with development progress | Unlikely to complete | Position at 30th September 2006 and impact of / reasons for delays |
| CH3.1 | Meet the national care standards for Fostering Services | Achieve registration with Care Commission |  |  |  |  | The Care Commission carried out the first inspection of the Service in June 2006. Informal feedback indicates some recommendations, but no requirements. The final report is expected in October 2006. |
| CH3.2 | Meet the national care standards for Adoption Services | Achieve registration with Care Commission |  |  |  |  | The Care Commission carried out the first inspection of the Service in June 2006. Informal feedback indicates some recommendations, but no requirements. The final report is expected in October 2006. |

| #### TARGET OUTCOME CH4 |  | The Rights of Looked After and Looked After and Accommodated Children are enhanced |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Ref. | 3 Year Target | Target 2006/07 | Completed | Good progress – on track with development | Running behind with development progress | Unlikely to complete | Position at 30th September 2006 and impact of / reasons for delays |
| CH4.1 | Performance related to six-monthly Reviews held under Section 31of the Children’s (Scotland) Act 1995 is improved | 60% Section 31 Review Reports are available seven days before review meetings |  |  |  |  | The shortage in child care staff has affected target. |
| CH4.2 | Performance related to Initial Health Assessments for Looked After and Accommodated Children is improved | 60% of requests for Initial Health Assessments are made within ten days of a child being accommodated |  |  |  |  | This is completed within timescales and monitored by Reviewing Officer. |

| #### TARGET OUTCOME CH5 |  | Effective and constructive measures are provided to those children and young people in trouble with the law to divert them away from offending behaviour |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Ref. | 3 Year Target | Target 2006/07 | Completed | Good progress – on track with development | Running behind with development progress | Unlikely to complete | Position at 30th September 2006 and impact of / reasons for delays |
| CH5.1 | Reduce Youth Crime in line with Scottish Executive National Standards | 10% reduction in number of offences by persistent offenders |  |  |  |  | Due to an increase in persistent young offenders outcome is running behind target. The Youth Justice Social Work post is unfilled at the present time |

| #### TARGET OUTCOME CH6 |  | Child Care Recruitment and Retention is improved |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Ref. | 3 Year Target | Target 2006/07 | Completed | Good progress – on track with development | Running behind with development progress | Unlikely to complete | Position at 30th September 2006 and impact of / reasons for delays |
| CH6.1 | Increase the percentage of qualified Child Care Social Workers to established levels. | 80% of all posts filled |  |  |  |  | National recruitment difficultites continue. Looking at a number of local initiatives and incentives. |

| #### TARGET OUTCOME CH7 |  | Maintain ISO 9001:2000 Accreditation |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Ref. | 3 Year Target | Target 2006/07 | Completed | Good progress – on track with development | Running behind with development progress | Unlikely to complete | Position at 30th September 2006 and impact of / reasons for delays |
| CH7.1 | Maintain accreditation following six-monthly surveillance visits | Maintain accreditation |  |  |  |  | A decision was taken in May 2006 to withdraw from ISO. A quality assurance system has been continued within the Service, ensuring that document and data control remains solid. |

Criminal Justice Service

| #### TARGET OUTCOME CJ1 |  | Increased safety and public protection through the provision of services which focus on reducing offending |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Ref. | 3 Year Target | Target 2006/07 | Completed | Good progress – on track with development | Running behind with development progress | Unlikely to complete | Position at 30th September 2006 and impact of / reasons for delays |
| CJ1.1 | Ensure Risk Assessment is integral in work with offenders | 80% of Probation cases inspected in monthly audit contain a completed Risk Assessment form known as RA1-3 |  |  |  |  |  |
| CJ1.2 | Establish new Enhanced Throughcare system in HMP Glenochil | Gain SPS support for Enhanced Throughcare programme following pilot which ends in March 2005 |  |  |  |  | The Enhanced Throughcare programme was replaced by Integrated Case Management which was introduced following recommendations made by the Management Of Offenders Act. ICM was implemented nationally on 1/06/06 and incorporated all aspects of Throughcare work. This process is a joint SPS and CJS initiative. Target requires to be reviewed. |

| #### TARGET OUTCOME CJ2 |  | Greater social inclusion of offenders through rehabilitation |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Ref. | 3 Year Target | Target 2006/07 | Completed | Good progress – on track with development | Running behind with development progress | Unlikely to complete | Position at 30th September 2006 and impact of / reasons for delays |
| CJ2.1 | Contribute to reducing drug related crime | Introduce Drug Testing and Treatment Orders |  |  |  |  |  |
| CJ2.2 | Improve the employment opportunities for ex-offenders | Increase referral rate to Apex and New Approaches by 10% |  |  |  |  | Referrals to Apex and New Approaches during the period April-September 2005 were 15. For the same period during 2006, there were 32 referrals. |

| #### TARGET OUTCOME CJ3 |  | Maintain ISO 9000:2000 accreditation |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Ref. | 3 Year Target | Target 2006/07 | Completed | Good progress – on track with development | Running behind with development progress | Unlikely to complete | Position at 30th September 2006 and impact of / reasons for delays |
| CJ3.1 | Maintain accreditation following six-monthly surveillance visits | Maintain accreditation |  |  |  |  |  |

| #### TARGET OUTCOME CJ4 |  | Improve staff training in working with sex offenders in the community |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Ref. | 3 Year Target | Target 2006/07 | Completed | Good progress – on track with development | Running behind with development progress | Unlikely to complete | Position at 30th September 2006 and impact of / reasons for delays |
| CJ4.1 | Staff undertake structured groupwork training | 80% of staff have undertaken Case Manager Training in the Community Sex Offender Groupwork Programme |  |  |  |  | New staff awaiting training becoming available. |

Culture & Community Services

| #### TARGET OUTCOME CC1 |  | The service will introduce a system for recording and celebrating learning achievement by 2008/09 |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Ref. | 3 Year Target | Target 2006/07 | Completed | Good progress – on track with development | Running behind with development progress | Unlikely to complete | Position at 30th September 2006 and impact of / reasons for delays |
| CC1.1 | Develop programme of opportunities recognising young peoples achievements and learning outcomes | Increase number of young people participating in the D of E (14-25yrs) Bronze from 15 to 20, Silver from 11 t0 14 and Gold from 5-9. |  |  |  |  | 28 Bronze 20 silver 1 Gold. difficult to retain interest in gold level. Expect % of current silver will move on to gold |
|  |  | Register 10 young people as Millenium Volunteers (15-25yrs) |  |  |  |  | completed |
|  |  | Develop Junior Challenge Award within 2 community settings (9-13yrs) |  |  |  |  | Target figure exceded, 4 groups established, Tullibody, Sauchie, Coalsnaughton, Tillicoultry |
|  |  | Pilot Youth Achievement Award with 6 young people. |  |  |  |  | Registered with Youth Scotland |
|  |  | Engage young people in coaching skills training. |  |  |  |  | Volunteers recruited and coaching being promoted |
| CC1.2 | Develop annual event to celebrate youth achievement | Raise awareness of CLD and young people. |  |  |  |  | Completed in conjunction with Volunteer Centre clackmannan (V.C.C) |
|  |  | Raise awareness of opportunities to develop skills. |  |  |  |  | Citizenship awareness and community classes running |
|  |  | Host event. |  |  |  |  | Event held in June `Buzz at the Recs` launch of summer programme. |
| CC1.3 | Maintain SVQ Centre Approval. | Ongoing |  |  |  |  | Annual process verification due within next six months |
| CC1.4 | Maintain / increase the range of SQA and other qualifications available to learners in line with the Council’s Community Planning and Economic Regeneration plans. | Ongoing |  |  |  |  | approval for SVQ childrens care learning development level 4 achived |
| CC1.5 | Maintaining Quality monitoring and recording of achievement through existing SQA, CTS and internal vocational qualification monitoring systems linked databases. | Ongoing |  |  |  |  | Continuous updates as and when required |
| CC1.6 | Extend the current end year certification ceremonies to include all learners. | Plan for March 2007 |  |  |  |  | Celebration planned for March for adult, skillseekers and all certificated courses |
| CC1.7 | Develop Fine Art Exhibition Series presenting evidence of learning & achievement through drawing, painting, and sculpture | Create x 2 opportunities for public display within alternative gallery spaces e.g. café ./ restaurant spaces, public buildings. |  |  |  |  | on target travelling gallery road show first week September |
|  |  | Create x 4 opportunities to display work in local and national venues e.g. via Historic Scotland, National Trust estate. |  |  |  |  |  |
| CC1.8 | Develop New Digital Media Exhibition Series. To highlight achievement in animation, photography, film. | Develop provision for 2 alternative gallery displays e.g. Shops, public building, Historic Scotland, National Trust. |  |  |  |  | 4 digital media group currently working on projects |
| CC1.9 | To develop and increase ICT skills in adults according to each person’s individual learning plan | TBC |  |  |  |  | Audit of processes identified need to improve recording plans for literacies referals. However marked increase for other adult classes provison |

| #### TARGET OUTCOME CC2 |  | The service will assist young people to engage in decision-making processes which affect their lives. |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Ref. | 3 Year Target | Target 2006/07 | Completed | Good progress – on track with development | Running behind with development progress | Unlikely to complete | Position at 30th September 2006 and impact of / reasons for delays |
| CC2.1 | Develop umbrella youth council/forum | Launch youth council |  |  |  |  | Inaugural meeting held 7th June |
|  |  | Develop participation and consultation strategy which will enable young people to participate in decision making |  |  |  |  | Consultation carried out in every community, report to follow. New work developed from consultation |
|  |  | Host annual youth citizenship event |  |  |  |  | Scheduled for 18th November 06 |
|  |  | Develop links with national bodies e.g. SYP |  |  |  |  | 4 young people attend Scottish Youth Parliament |
| CC2.2 | Develop information sharing, consultation and participation | Carry out youth consultation |  |  |  |  | taking place Oct - March |
|  |  | Develop consultation strategy |  |  |  |  |  |
|  |  | Develop Clacksyouth .com |  |  |  |  | re launch November |
|  |  | Develop monthly youth page in local press |  |  |  |  | Youth page in Wee county News every 4 weeks |
| CC2.3 | Develop youth participation in development of services for young people | Provide training for sessional staff and volunteers on youth participation and group work |  |  |  |  | Pilot core youth work training carried out. This will now be part of continuous ongoing training |
|  |  | Develop training for young people in developing own youth groups |  |  |  |  | Training given to Youth Council, Choose Sport First and Multi Media Group |
| CC2.4 | Engaging and progressing young people into training and employment | 150 |  |  |  |  |  |
| CC2.5 | We will support young people into training and work through our Skillseeker and Modern Apprenticeship programmes. | Meet SEFV outputs and outcomes for 06/07 |  |  |  |  |  |
| CC2.6 | We will help young people to achieve vocational qualifications which will enable them to make informed career choices. | .As above |  |  |  |  |  |
| CC2.7 | We will specifically target young people as a priority group within the Literacies Strategy for 2006 to 2008. | Targets for this priority group as per Literacies Strategic Plan 2006-2008. |  |  |  |  | Looking at creative literacies package. Target NEAT Group |
| CC2.8 | Instigation of Youth Arts & Culture Forum as primary cultural youth directive. | To create formal representation of members |  |  |  |  | Arts Academy held in summer |
|  |  | To strengthen youth directed cultural programming |  |  |  |  | Writer in residence advertised |
|  |  | To create opportunities for youth directed provision within Art House Project |  |  |  |  |  |
| CC2.9 | Develop international opportunity via placement with projects / training programmes | To engage young people in Amsterdam ISH Youth Dance Culture Training Programme |  |  |  |  | One young person currently in holland training for one year with ISH |

| #### TARGET OUTCOME CC3 |  | The service working practices will implement the national standards for community engagement |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Ref. | 3 Year Target | Target 2006/07 | Completed | Good progress – on track with development | Running behind with development progress | Unlikely to complete | Position at 30th September 2006 and impact of / reasons for delays |
| CC3.1 | Improve resources for increased involvement - support artist residencies via creation of Art House facility. | Continue to strengthen partnership linking with health, education and housing via Art House initiative. |  |  |  |  |  |
| CC3.2 | Support improved accessibility to engagement e.g. physical / intellectual and emotional accessibility . | Continue to strengthen relationship with housing, children & youth, community, education and creative arts. |  |  |  |  | Working with social landlords in developing relationships and joint work. Health Board - homeless, recovering adults ect. and voluntary organisations |
| CC3.3 | To develop mechanisms for sustainability beyond short term funded posts / artist partnership / residencies. | To encourage creative approach to service planning. |  |  |  |  |  |
| CC3.4 | Target areas for research / consultation / media | TBC |  |  |  |  |  |
|  | Develop and maintain mechanisms for communication networks with outside partner agencies. | Establish 3 types of networks through Local Forumes/Focus Groups and Community Learning and Development plan. |  |  |  |  |  |
| CC3.5 | Strengthen information of project availability / promote achievement via web, radio, newsletter, newspaper To host 2 national seminars on developing creative partnerships | Publish youth page every four weeks in local paper. Establish Clacks youth radio station. |  |  |  |  | Clacks Youth radio being developed by media group at click. Youth page printed in Wee county News |
| CC3.6 | Develop Arts House Project in the community to encourage improved family and cross community relationships | Establishment of one Arts House |  |  |  |  | Secured tenancy of shop in Tullibody |
| CC3.7 | To increase skills base by encouraging internal cross service partnership. Increase skills base by establishing sustained mechanisms for peer group tutoring. | Reach Clackmannanshire Literacies Partnership targets |  |  |  |  | Marketing strategy being developed for literacies partnership |
| CC3.8 | Encourage participation towards higher education/ project placements. | To strengthen network at local level Measure number of placements |  |  |  |  | 3 placements currently in children and youth team |
|  | HGICLD LEAP SAC interim report/ evaluation | Action points of evaluation |  |  |  |  |  |

| #### TARGET OUTCOME CC4 |  | The service will continue to develop self evaluation and continuous improvement mechanisms. |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Ref. | 3 Year Target | Target 2006/07 | Completed | Good progress – on track with development | Running behind with development progress | Unlikely to complete | Position at 30th September 2006 and impact of / reasons for delays |
| CC4.1 | Maintain SQMS accreditation. | Pass full audit. |  |  |  |  | Accreditation Achieved |
| CC4.2 | Maintain SQA Centre Status. | Successful Systems and programmes audits. Including development and approval of new programmes. |  |  |  |  | Approved |
| CC4.3 | Meet SEFV contractual requirements. | Output targets achieved. |  |  |  |  |  |
| CC4.4 | Meet Literacies in the Community requirements. | Evaluate and improve. |  |  |  |  | Over demand for ESOL learners identified more tutors taken on to address demand. |
| CC4.5 | Development of Client focus groups through New Approaches. | 2 meetings per year. Review outcomes (ongoing) |  |  |  |  | one meeting held in June |
| CC4.6 | New Approaches Conduct One to One client feedback (on going). | 200 per year |  |  |  |  | likely to exceed target |
| CC4.7 | Monitor community library services and educational library services. | Ongoing and as required. |  |  |  |  |  |
| CC4.8 | Consult with users on future development of community library services and educational library services. | As required. |  |  |  |  |  |
| CC4.9 | Develop staff training and support specific to youth work. | Pilot ‘Core youth work’ training pack with 5 part time members of staff (youth). |  |  |  |  | pilot complete and will now be part of on going training exceede target to 8 |
|  |  | Establish staff supervision sessions which will reflect How Good is our Community Learning and Development and National Standards for Community Engagement. |  |  |  |  | ongoing |
|  |  | Implement one support session for part time staff and volunteers per school term 9youth). |  |  |  |  | ongoing |

| #### TARGET OUTCOME CC5 |  | The service will develop and implement an action plan in response to HMIE report |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Ref. | 3 Year Target | Target 2006/07 | Completed | Good progress – on track with development | Running behind with development progress | Unlikely to complete | Position at 30th September 2006 and impact of / reasons for delays |
| CC5.1 | CCS will develop and implement a systematic approach for the provision of youth information and advice to facilitate progression to further learning opportunities across Clackmannanshire | Develop participation and consultation strategy which will enable young people to participate in decision making. |  |  |  |  | as before |
|  |  | Develop Clacksyouth.com. |  |  |  |  |  |
|  |  | Develop youth page in local press. |  |  |  |  |  |
| CC5.2 | The CCS will develop a systematic approach to monitor, record, evaluate and celebrate youth achievement in the authority. | Investigate and purchase suitable data base to track record of achievement. |  |  |  |  | Cognisoft system being purchased |
| CC5.3 | The CCS will extend and further develop it’s activities to ensure that young people are actively involved and consulted in the development of their communities. | Develop annual event to celebrate youth achievement |  |  |  |  | as before |
|  |  | Increase number of young people participating in Duke of Edinburgh awards (14 – 25yrs). |  |  |  |  |  |
|  |  | Invite young people to register as millennium volunteers (15 – 25yrs). |  |  |  |  |  |
|  |  | Develop junior challenge award within community settings (9 – 13yrs). |  |  |  |  |  |
| CC5.4 | The CCS through the Clackmannanshire Alliance will promptly publish the CLD strategy for the area. | Draft strategy out for consultation. |  |  |  |  |  |
|  |  | Development of working groups (subject to approval by the alliance and the Community Learning and Development Partnership??? |  |  |  |  |  |
| CC5.5 | Clackmannanshire Council will extend and embed its systems for planning, self-evaluation, staff review and development to the CCS. | Staff review and development will be in line with corporate guidelines adopted by the Authority (As per balanced score card indicators) |  |  |  |  |  |
| CC5.6 | Clackmannanshire Council will ensure that all staff, including sessional staff, undertake child protection training as a priority. | Child protection induction for all full time members. |  |  |  |  | completed as per corporate guidlines |
|  |  | Child protection sessional workers induction |  |  |  |  | as above |

Leisure & Recreation

| #### TARGET OUTCOME LR1 |  | To improve participation, ensure quality of facilities, deliver quality services, ensure viability and develop sustainability |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Ref. | 3 Year Target | Target 2006/07 | Completed | Good progress – on track with development | Running behind with development progress | Unlikely to complete | Position at 30th September 2006 and impact of / reasons for delays |
| LR1.1 | Reduce barriers to participation by being sensitive to the needs of all members of the community | Complete Community Consultation Exercise. Develop programme and record baseline figure for attendance. |  |  |  |  | Carried out a series of community roadshows in May and June to gain information on classes/ courses and set a n activity programme for August 2006 to February 2007 |
| LR1.2 | Provide and develop facilities which are effective, efficient, customer focussed and support the prioritised sports | Produce Facility Development Plan |  |  |  |  | Draft plan completed and out to consultation with elected members and senior staff. |
| LR1.3 | Provide quality delivery of leisure activities/service in an efficient and customer focussed manner, ensuring subsidy goes to those who need it most. | Investigate Quality Assurance Scheme. Develop Corporate Booking Service |  |  |  |  | New corporate booking service will be installed and operational from 1st January 2007. |
| LR1.4 | Create, promote and support development of active communities across Clackmannanshire that are vibrant and viable | Monitor and Review THLI Establish C and D/S Programme Support Alva Games 150th Celebration |  |  |  |  | Completed a review of THLI and signed a SLA for the coming year. Coalsnaughton and Devonside project established and service level agreement signed. A very successful Alva Games Celbrations programme deliver 1st - 8th July 2006. |
| LR1.5 | Promote the outdoor environment and, by use of it, a healthy lifestyle | Explore opportunity for partnership working for the delivery of services |  |  |  |  | Will progress this work in January 2007. |

Sports Development

| #### TARGET OUTCOME SD1 |  | Establish partnerships with various internal and external agencies to create opportunities and pathways for education establishments, communities, individuals, clubs and targeted groups to be active, healthy and realise their sporting potential. |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Ref. | 3 Year Target | Target 2006/07 | Completed | Good progress – on track with development | Running behind with development progress | Unlikely to complete | Position at 30th September 2006 and impact of / reasons for delays |
| SD1.1 | Ensure full partnership in the 3 year regional sports partnership (developing potential strand of sport 21) | Commitment from Council to joining partnership and is represented at exec meetings for 3 years from 1st April 2006 |  |  |  |  | No delay, three Clackmannanshire sports development staff appointed to sportcentral management positions |
| SD1.2 | Continue as a full partner in the Central Scottish Institute for Sport (CSIS) for 3 years (achieving excellence strand of sport 21) | Clackmannanshire joined in Aug 2005, continue to be represented at exec and mgt meetings with CSIS |  |  |  |  | This year Clackmannanshire is chair of the CSIS management team |
| SD1.3 | Compliment work of Leisure Team to build customer base and develop appropriate faclities | Link SD programmes to leisure facilities |  |  |  |  | Sport and leisure working together particularly on school holiday programmes and coach education |
| SD1.4 | Continue to develop programme of education and training | Maintain high standard and high participation rates of existing sports training booklet |  |  |  |  | Annual programme being delivered and most courses running to capacity |
| SD1.5 | Support development of local clubs in priority sports, physical activity and other sports. | Maintain and develop local sports p/ships in rugby, swimming, golf, football, athletics and gymnastics |  |  |  |  | Maintaining positive relationships and partnerships and specific links to sportcentral |
| SD1.6 | Use London Olympics 2012 and sportscotland targets for 2020 to focus all sport and physical activity | Launch focused approach to start from 2008 when countdown starts for 2012 |  |  |  |  | Working with YST and sportscotland on initiatives for secondary school pupils, presentation to secondary HTs well received – next stage to try to engage secondary PE depts in specific projects to build understanding and volunteer structure |
| SD1.7 | Deliver and develop physical activity for Clackmannanshire Childcare Partnership | Develop and increase Active Start team, establish sound reporting procedures |  |  |  |  | Increased demand for Active Start training from outwith Clackmannashire |
| SD1.8 | develop creativity within existing high quality provision of PE in primary and secondary | Primary PE syllabus connected to sec. PE curriculum Primary PE team linked to Enterprise Learning team |  |  |  |  | Extensive work with music and art to design and deliver inservice training on 21st November 2006 |
| SD1.9 | Develop Active Schools Initiative | All schools with a wide range of out of school hours activities Incr % of pupil participation 10 week holiday prog Develop playgrounds |  |  |  |  | Considerable progress has been achieved |
| SD1.10 | Extend the Active Additional Support Needs Project | Establish new 10 year MBA project as enhancement to present delivery |  |  |  |  | Considerable interest from throughout Scotland |
| SD1.11 | Create opportunities for young people to be physically active and make purposeful use of their time | In conjunction with other services design and deliver an annual programme of physical activities |  |  |  |  | New work delivered and ongoing with homelessness, children and youth work team, other agencies |

##### Housing

| #### TARGET OUTCOME HA1 |  | Progress has been made to ensure a higher percentage of Social housing in Clackmannanshire has attained or exceeded the Scottish Housing Quality Standard and a realistic and achievable programme is in place to increase this to 70% by 2009 |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Ref. | 3 Year Target | Target 2006/07 | Completed | Good progress – on track with development | Running behind with development progress | Unlikely to complete | Position at 30th September 2006 and impact of / reasons for delays |
| HA1.1 | Delivery plan in plan and on target | Final delivery plan approved |  |  |  |  | Delivery Plan positively assessed by Communities Scotland |

| #### TARGET OUTCOME HA2 |  | Progress has been made to ensure an additional 20% of privately owned or rented housing has attained or exceeded the Scottish Housing Quality Standard and realistic and achievable proramme is in place to complete this by 2009 |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Ref. | 3 Year Target | Target 2006/07 | Completed | Good progress – on track with development | Running behind with development progress | Unlikely to complete | Position at 30th September 2006 and impact of / reasons for delays |
| HA2.1 | Private Sector Stock Condition identified and prioritized/improved | Stock Condition Survey reviewed and prioritised |  |  |  |  | Project on target, brief has been finalised |
|  |  | Review private Sector housing grant and care and repair service and ensure it is targeted to those most in need |  |  |  |  | This has been reviewed and implemented |
| HA2.2 | Access to good quality and affordable homes improved | Develop a Private landlords forum and encourage good practice among private landlords |  |  |  |  |  |
| HA2.3 |  | Establish registration of private Landlords making relevant links with Housing of Multiple Occupation |  |  |  |  |  |

| #### TARGET OUTCOME HA3 |  | Progress has been made to ensure Housing Services are both customer and community oriented and a realistic and achievable programme is in place to complete this by 2009 |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Ref. | 3 Year Target | Target 2006/07 | Completed | Good progress – on track with development | Running behind with development progress | Unlikely to complete | Position at 30th September 2006 and impact of / reasons for delays |
| HA3.1 | New Service Structure is in place and operating effectively | Structure Reviewed |  |  |  |  | Restructure complete. Final element is to bring all housing services under one roof. Target date December 2006 |
|  |  | Implement Career Development Scheme in line with Corporate Scheme with Training Plan in place for Housing Services |  |  |  |  | On target, Career Development Scheme now in place and currently being implemented |
| HA3.2 | The Housing Service has achieved a “Good” rating against Communities Scotland Performance Standards | Complete Self-Assessment in preparation for inspection by Communities Scotland and implement resulting action plan |  |  |  |  | Self assessment of all Communities Scotland Performance Standards has now taken place |
|  |  | Inspection Submission Assembled for Community Scotland |  |  |  |  | Inspection Submission returned to inspectors meeting deadline |
| HA3.3 | Communications with public improved | Extend the use of the Contact Centre for Housing Enquiries |  |  |  |  | Current Service Level Agreement has been reviewed |
|  |  | Review Tenant Participation Strategy |  |  |  |  | Review Complete, strategy now out for agreement with other partners. |
|  |  | Review and Improve SIMCO partnering project with DSO Property Contracts |  |  |  |  |  |
| HA3.4 | Customer satisfaction benchmark established and service improvements achieved | Carry out customer satisfaction survey and identify service improvements |  |  |  |  | Customer Satisfaction Survey complete, Improvements have been identified and will be included in team plans |
| HA3.5 | Housing Service performance on equalities issues has been identified and appropriate action taken | Audit to be carried out for the accessibility of offices for Housing Service customers |  |  |  |  |  |
|  |  | Equal Opportunities Policy in place |  |  |  |  | Corporate Equal Opportunities policy will be followed. A self assessment of Equal opps was carried out in the service and an action plan has been put in place |
| HA3.6 | Business planning and review arrangements that meet the needs of the services and the council are in place | 10 year Business plan in place |  |  |  |  | Business Plan on Target to complete by April |
|  |  | Performance Management Framework rolled out to include all staff |  |  |  |  | Most housing staff have now received a SDP interview on target to complete by year end |

| #### TARGET OUTCOME HA4 |  | Policies & Procedures Developed to promote sustainable communities |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Ref. | 3 Year Target | Target 2006/07 | Completed | Good progress – on track with development | Running behind with development progress | Unlikely to complete | Position at 30th September 2006 and impact of / reasons for delays |
| HA4.1 | Common Housing Register established for Clackmannanshire | Identify & Develop IT Solution |  |  |  |  | Slippage due to implementation of Choice Based Lettings. Revised target date is September 2007. |
|  |  | Train Housing and Housing Association Staff |  |  |  |  | As above |
| HA4.2 | Performance on Empty Properties is improved | Choice Based Letting Scheme is implemented |  |  |  |  | Stage one of Allocations Policy is currently being implemented. Pilot CBL due to be launched for Craigview Sauchie. On target to implement CBL by April |
|  |  | Review Void Management Procedures |  |  |  |  | Self Assessment carried out on Void Management Processes - on target to finalise review of procedures |
| HA4.3 | Regeneration Programme is in place | Develop Master plans for regeneration |  |  |  |  |  |
|  |  | Develop proposals for Community Scotland funding |  |  |  |  |  |
| HA4.4 | Fuel Poverty issues have been identified and actions to reduce the risk of fuel poverty are in place | Fuel Poverty Strategy developed and the action implemented |  |  |  |  |  |
| HA4.5 | Make good progress in the prevention of homelessness in Clackmannanshire | Achieve 2006/07 targets in Homelessness Strategy |  |  |  |  |  |
| HA4.6 | Improve the delivery and accessibility of homelessness services | Review Policies and procedures for Homeless |  |  |  |  |  |
| HA4.7 | Increase and improve the options for temporary accommodation for people who are homeless | Achieve 2006/07 targets in Homelessness Strategy |  |  |  |  |  |

| #### TARGET OUTCOME HA5 |  | The shortfall of specialist housing and housing support services promoting independent living is being addressed and is on track to be delivered by 2009 |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Ref. | 3 Year Target | Target 2006/07 | Completed | Good progress – on track with development | Running behind with development progress | Unlikely to complete | Position at 30th September 2006 and impact of / reasons for delays |
| HA5.1 | A better balance of specialist housing and housing support services to promoting independent living has been achieved | Integrated adaptations service involving housing and social services introduced |  |  |  |  |  |
| HA5.2 | Single shared assessment is achieving improved tenancy outcomes | Single shared assessment developed to achieve improved tenancy outcomes |  |  |  |  |  |
| HA5.3 | Supporting people strategy reflects local needs | Complete review of supporting people strategy |  |  |  |  |  |
| HA5.4 | Additional Options available for older people | Deliver a sheltered project for frail and elderly |  |  |  |  | Health Bid approved on target to deliver |

Schools

| #### TARGET OUTCOME SL1 |  | To implement ‘A Curriculum for Excellence (ACE)’ |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Ref. | 3 Year Target | Target 2006/07 | Completed | Good progress – on track with development | Running behind with development progress | Unlikely to complete | Position at 30th September 2006 and impact of / reasons for delays |
| SL1.1 | Continue to employ curriculum flexibility to address the needs of young people | The ways in which pupils in S2 to S4 are given access to Standard Grade and/or equivalent courses are extended |  |  |  |  |  |
|  |  | pupils’ opportunities to study vocational courses are increased; the pupils achieve a > 90% success rate in their vocational courses |  |  |  |  | Pupils' attainments in college-based courses will not be known until leter on in the school session |
|  |  | pupils’ opportunities to follow personal development programmes, eg ASDAN, are increased; the pupils taking these courses achieve >90% success rate in these courses |  |  |  |  | See above |
| SL1.2 | Increase young people’s opportunities to become involved in enterprise education activities through, for example, the establishment of a ‘team’ of teachers dedicated to the promotion of enterprise in primary schools | There is a wide range of enterprise activities available to all young people available through the implementation of the authority’s Education for Enterprise/Determined to Succeed Action Plan |  |  |  |  | Work continues to extend and enhance provision for young people |
|  |  | Almost all pupils participate in at least one quality enterprise activity each session |  |  |  |  | See above |
|  |  | Audit, inspections, reports, and pupil surveys indicate that enterprise activities are having a positive impact on young people |  |  |  |  | This session's internal audit and external inspection prgramme gets underway in earlky-November |
| SL1.3 | Increase young people’s opportunities to become involved in activates promoting personal and social development, citizenship | All schools have effective pupil councils and other ways of giving pupils a voice in the life and work of their schools; all schools operate programmes of activity which promote citizenship including involvement in the Eco Schools Programme |  |  |  |  | All schools have pupil councils; almost all schools are involved in the Eco Schools Programme and a significant % of schools ahev been awarded a Green Flag. |
|  |  | Audit, inspections, reports, and pupil surveys indicate that schools make a positive contribution to the personal and social development of young people |  |  |  |  | This session's internal audit and external inspection prgramme gets underway in early-November |
| SL1.4 | Continue to promote health and well-being of young people | Implement the authority’s ‘Hungry for Success’ Action Plan by, for example, improving the quality of school meals leading to increased up-take of school meals |  |  |  |  | This is on-going |
|  |  | All schools have at least the lowest level of accreditation as a Health Promoting School by the end of June 2007 |  |  |  |  | A Forth Valley HPS Accreditation Scheme has been approved and is coming into operation. |
| SL1.5 | Increase young people’s access to sporting and cultural activities | All pupils in primary and secondary schools experience at least >100 minutes per week of a ‘quality experience of taught PE’ |  |  |  |  |  |
|  |  | All pupils in primary schools and the first two years of secondary school experience at least 100 minutes per week of a ‘quality experience of the expressive arts’ including, for example, involvement in the Youth Music Initiative and its related activities |  |  |  |  | This is achieved in secondary schools; it is achieved in a majority of primary schools. It will be achieved in all primary schools in 2007/2008. |

| #### TARGET OUTCOME SL2 |  | To raise attainment |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Ref. | 3 Year Target | Target 2006/07 | Completed | Good progress – on track with development | Running behind with development progress | Unlikely to complete | Position at 30th September 2006 and impact of / reasons for delays |
| SL2.1 | Continue to raise standards of attainment in reading, writing and mathematics in primary schools | % of pupils attaining national standards in reading, wreiting and mathematics will rise by 2-3% from the 2005/2006 baseline |  |  |  |  | Data relating to attainment in this school session will not be available fully until the end of June 2007 |
| SL2.2 | Continue to raise standards of attainment in reading, writing and mathematics in S1/S2 | % of pupils attaining national standards by the end of S2 in reading will be >60% from 206/2007 onwards |  |  |  |  | See above |
|  |  | % of pupils attaining national standards by the end of S2 in writing will be greater than 55% from 2006/2007 onwards |  |  |  |  | This is an ambitious target; it would seem more likely now that a figure of 50% will be achieved. |
|  |  | % of pupils attaining national standards by the end of S2 in mathematics will be greater than 65%from 2006/2007 onwards |  |  |  |  | Data relating to attainment in this school session will not be available fully until the end of June 2007 |
| SL2.3 | Raise the overall levels of attainment of pupils at the end of S4 | % of pupils attaining 5+ awards at Level 3 or better will increase by 6-7% to > 90% by 2007 |  |  |  |  | Data for attainments at the end of S4 will not be available until August 2007; 2006 results indicate that this is an achievable target |
|  |  | % of pupils attaining 5+ awards at Level 4 or better will increase by 5% to > 75% by 2007 |  |  |  |  | This is a focus for work in secondary schools in the current school session. |
|  |  | % of pupils attaining 5+ awards at Level 5 or better will increase by 4% to > 35% by 2007 |  |  |  |  | This may prove to be an ambitious target; an increas of 2005/2006 results to >30% may be a more achievable target. |
| SL2.4 | Raise the attainment of the lowest performing 20% of pupils at the end of S4 | Average tariff score of the lowest performing 20% increases by 8 points in each of the next 3 years |  |  |  |  | There was a significant increase in tariff score in 2005/2006; further increase can be anticipated in 2007. |
| SL2.5 | Raise overall levels of attainment of pupils at the end of S5 | % of pupils attaining 3+ awards at Level 6 or better will increase by 4% by 2007 |  |  |  |  | Attaiments at Higher increased in 2005/2006 |
|  |  | % of pupils attaining 5+ awards at Level 6 or better will increase by 2% by 2007 |  |  |  |  | See above |
| SL2.6 | Raise overall levels of attainment of pupil at the end of S6 | % of pupils attaining 1+ awards at Level 6 or better will increase by 6% by 2007 |  |  |  |  | See above |
|  |  | % of pupils attaining 3+ awards at Level 6 or better will increase by 6% by 2007 |  |  |  |  | See above |
|  |  | % of pupils attaining 5+ awards at Level 6 or better will increase by 25% by 2007 |  |  |  |  | See above |
| SL2.7 | Develop further pupils’ employability skills | Local and other employers report high levels of satisfaction with the skills of job applicants and employees recently attending school |  |  |  |  | Systematic surveys of employer perceptions will not be conducted until later on in the school session |
|  |  | The numbers of young people leaving school and becoming part of the NEET group is always less than 5% |  |  |  |  | There was a reduction in the nukbers of school leavers going into NEET on leaving school in 2005. 2006 dtata, compiled by Careers Scotland, will not be available unti November/December 2006. |
|  |  | At least 90% of pupils report themselves as having well-developed core/employability skills; they are confident and optimistic |  |  |  |  | Systematic surveys of pupils' perspectives will not be carried out until later on this session. |
| SL2.8 | Raise the overall levels of achievement and attainment of LAC, other vulnerable young people and children from black and ethnic minorities | Educational and other progress of LAC and other groups is tracked, monitored and reported on; appropriate interventions are undertaken |  |  |  |  | This work is on-going; the attainments and achievements of children looked after and accommodated by the Council continues to compare favourably with that of looked after children nationally and in other authorities. |
|  |  | All LAC attain at least an SCQF Level 3 award in English and Mathematics at the end of S4 |  |  |  |  | This level of attainment was not achievded in 2006 but it remains a legitimate target for 2007; data for 2007 will not be available until August of that year |
|  |  | The attainment generally, in primary and secondary schools of LAC, other vulnerable children and children from black and ethnic minorities will be at least the equivalent of the average of their peers |  |  |  |  | This was the case for 2006; numbers of young people falling into these categories are small and percentage figures always need to be interpreted with care. |
| SL2.9 | Develop further pupils’ problem-solving and thinking skills | The use of questioning and other techniques associated with the AifL Programme has been widely adopted in our schools: this work will be complemented by the use of P4C, Case and related programmes |  |  |  |  | Work on developing teaching methods continues and is making good progress in all of these areas. It is very unlikely that work here will be able to be described at any time as complete. |
|  |  | All pupils in P6 to S1, inclusive will have the opportunity to engage in at lease 4 constructivist/challenge events each school session from 2006/2007 onwards |  |  |  |  | The first of these events have been held. Further events have been planned. This may prove however to be an ambitious initial target |
| SL2.10 | Raise standards of attainment of pupils with ASN | Pupils with ASN have access to a wide range of appropriate course, units, etc |  |  |  |  | Work continues to extend an already wide range of opportunities |
|  |  | Pupils’ achievement/attainments at least match national standards |  |  |  |  | The percentage of pupils attaining at least 80% of the targets set with/for them in IEPs matches national expectations |
|  |  | Inspection and other audits indicate courses well-matched to pupils’ needs |  |  |  |  | Current inspection reports indicate that this is the case. |

| #### TARGET OUTCOME SL3 |  | Create conditions conducive to learning |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Ref. | 3 Year Target | Target 2006/07 | Completed | Good progress – on track with development | Running behind with development progress | Unlikely to complete | Position at 30th September 2006 and impact of / reasons for delays |
| SL3.1 | Inclusion: Continue to implement the existing policy on inclusion | All schools familiar and compliant with the policy |  |  |  |  | Work continues to support the implementation of the policy |
| SL3.2 | Introduce a common assessment framework in relation to pupils with ASN | A common assessment framework is in operation with which staff, pupils and parents/carers express a high degree of satisfaction. |  |  |  |  | This is under development |
|  |  | Inspection and other audits indicate courses, activities, etc well matched to pupils’ needs |  |  |  |  | An inspection of the authoritys progress in implementing the ASN (Scotland) Act is imminent |
| SL3.3 | Continue to operate a programme of staged intervention including revised policy & guidelines | Inspection and other audits report the effective use of staged intervention |  |  |  |  | This year's audit has been conducted; results are being collated. |
|  |  | Pupils involved in the staged intervention process overtake at least 80% of targets set with and for them |  |  |  |  | And see SL2.10 above in previous section |
|  |  | Their attainments in reading, writing and mathematics make appropriate progress and matches targets set for and with pupils |  |  |  |  | See above |
| SL3.4 | Continue to improve support for schools learning services in schools | Inspection and other audits report support for learning services as effective |  |  |  |  | This session's internal audit and external inspection prgramme gets underway in early-November; most individual reports from parents, e.g. those involved in CSP's, are positive |
|  |  | Parents report high levels of satisfaction with support for learning services |  |  |  |  | See above |
|  |  | Pupils’ attainments in reading, writing and mathematics make appropriate progress and matches targets set for and with them |  |  |  |  | Data on pupils' attainments in this school sessiion will not be available fully until June 2007 |
| SL3.5 | Continue to improve transition arrangements for pupils with ASN | Almost all pupils are satisfied with their transition arrangements |  |  |  |  | Most individual reports, e.g. from pupils involved in CSPs, are positive. |
| SL3.6 | Continue to improve ICT provision for and within schools | All desktop systems in schools at the start of 2001/2002 replaced by the end of 2006/2007; all schools have access to an enhanced, local education intranet and all schools have access to the SSDN and this services and have all staff trained in its use |  |  |  |  | The system replacement scheme continues; progress nationally in SSDN, now called GLOW is slightly delayed and this will make the completion of this target difficult to achieve |
| SL3.7 | Complete the introduction of SEEMIS | All relevant staff are able to use SEEMIS and almost all users report high levels of satisfaction with SEEMIS |  |  |  |  | Work on the implementation of SEEMIS continues |
| SL3.8 | Establish and implement an up-dated service-wide ICT strategy | All young people have access to a wide range of activities which engage them in the use of ICT for research, presentation and other purposes; inspection and other audits indicate effective use of ICT in support of pupils’ learning AND most staff and all pupils report themselves as having well-developed efficacy in the use of ICT |  |  |  |  | The quality and range of young people's work with ICT is observabale in schools; it was commented on positively in last year's school inspection programme |
| SL3.9 | Schools continue to provide their pupils and staff with a safe working environment | Inspection and other audits, surveys of pupils and parents indicate that schools provide a safe environment for teaching and learning; schools have a positive ethos |  |  |  |  | Both facets of the target were commented on positively in last year's school inspection programme; this session's internal audit and external inspection prgramme gets underway in early-November |
|  |  | Schools make appropriate use of praise and appropriate use of sanctions, including exclusions, to create a positive working environment for pupils and staff |  |  |  |  | See above |
|  |  | All schools have clear arrangements in place for dealing with bullying; they all use buddying and similar arrangements to promote positive relationships between and amongst pupils |  |  |  |  | While 'complete' all schools continue to work to improve their response to the challenge of bullying. |
| SL3.10 | Improve attendance in primary and secondary schools | Primary School attendance is greater than 95% |  |  |  |  | This attendance level was achieved in session 2005/2006. |
|  |  | Secondary school attendance is greater than 92% |  |  |  |  | This attendance level was achieved in session 2005/2006. |