# CLACKMANNANSHIRE COUNCIL

REPORT TO: 	THE PERFORMANCE & AUDIT COMMITTEE MEETING ON 25th JANUARY 2007

SUBJECT: 	GENERAL SERVICES CAPITAL PROGRAMME: SUMMARY OF 3 YEAR PROGRAMME 2006/07 TO 2008/09 AND FINANCIAL POSITION AS AT NOVEMBER 2006.

## PREPARED BY: 	KISH PARMAR, PRINCIPAL ACCOUNTANT

- SUMMARY

  - This report presents an update on the General Services Capital Programme for the three years from 2006/07 to 2008/09 as at November 2006 based on the discussions with project managers at the last Capital Monitoring Group meeting. This monitoring report concentrates on the progress in financial terms on all schemes in the three-year programme, and highlights any significant changes to the position previously reported.

  - The table below summarises capital borrowing requirement for the 3 years to 08/09 and shows the changes to the position reported previously:

|  | 2006/07 | ###### 2007/08 | 2008/09 | Total |
| --- | --- | --- | --- | --- |
| Revised Net Expenditure (Council Borrowing) as per previous report of 16th Nov 2006 | 7,272 | 8,173 | 15,424 | 30,869 |
| Additional projects to be transferred from 2006/07 to 2007/08 since the last report | (126) | 126 |  |  |
| Further Revision to programme / additional Over or Under spends as per current out-turn, since the last report | (9) |  |  | (9) |
| Capital Receipts delayed since the last report (see para. 3.3 below) | 500 | (500) |  |  |
| Revised Net Expenditure (Council Borrowing) as per current out-turns | 7,637 | 7,799 | 15,424 | 30,860 |

  - The current projections indicate that the net expenditure (Council borrowing) in 06/07 is expected to increase by £365k to £7,637k, after accounting for all transfers of budgets between the three years and transfers from previous year. The revised net expenditure for 07/08 and 08/09 is projected to be £7,799k and £15,424k respectively. The projected total net expenditure for all three years, including projects carried from 05/06 is £30,860k. which is a decrease of £9k from the previous projections, being minor savings in the capital budget.

- RECOMMENDATION

  - The Committee is asked to note the financial position and the borrowing requirement for capital programme for the three years to 2008/09 as at September 2006.

- BACKGROUND

  - This is an exception report, the purpose of which is to highlight only significant changes to the financial position reported previously.

  - Since the previous report a further £126k is expected to be transferred to 2007/08, the most significant being £46k for the CCTV project and an additional £56k for Vehicle purchases. There are no further anticipated changes to budget transfers between years from what was reported previously, at the time of writing the report. However, this is likely to change as Services consider the next 3-year capital programme. The budget transfers are necessary to accommodate the rescheduling of the capital programme as advised in the previous report. This is a continues process as project managers reassess and reappraise projects to best meet the needs of the Council.

  - In the previous report capital receipts from sale of general assets of £500k were anticipated. Latest indications are that these receipts will not be realised in the current year. The potential sites which were earmarked will not now be marketed until next year in order to utilise prevailing marketing conditions to maximum benefit. It is likely that the anticipated receipts will be more than the £500k, which will further reduce the borrowing requirement. Members will be updated in the next report

  - Appendix 1 gives brief details of any changes to the position in individual projects to that reported previously, including explanations for any further transfers of budgets between years.

- CONCLUSION

  - This report focuses on significant changes since the last report to the financial position on the Council borrowing requirement for the 3-year capital programme from 2006/07 to 2008/09. In summary, the current projections indicate a decrease of only £9k in Council borrowing over the three years to that reported previously, being minor savings in the capital budget. Capital receipts of £500k will be delayed to next year to maximise marketability. Indeed increased receipts are likely, which may reduce borrowing requirement further. The report also summarises the proposed transfers between years to facilitate rescheduling of capital programmes to the best advantage to the Council. Separate reports will be presented to the Committee by project managers on high risk capital schemes to be identified by the CAMP team.

- SUSTAINABILITY IMPLICATIONS

Not Applicable to monitoring reports

- IMPLICATION FOR THE COUNCIL

- 6.1	Financial implications:	As noted in the report.

- 6.2	Staff implications:	None

  - Strategic aims:

| Create strong, active, safe and caring communities |  |
| --- | --- |
| Achieve local economic prosperity and stability |  |
| Make the most of Clackmannanshire's unique built and natural environment |  |
| Develop a culture of personal achievement where everyone is valued |  |
| Improve the health of the people of Clackmannanshire |  |
| Represent and promote the interests of all of the people of Clackmannanshire |  |
| Ensure that the people of Clackmannanshire receive the highest quality services for the public pound - Declarations - The recommendations contained within this report support or implement Corporate Priorities, Council policies and/or the Community Plan: Corporate Priorities  Council Policies  Community Plan  - In adopting the recommendations contained in this report the Council is acting within its legal powers  3. The full financial implications of the recommendations contained in this report are set out in the report. This includes a reference to full life cycle costs where appropriate  |  |

- ___________________________________________________________

Director of Corporate Development

___________________________________________________________

Head of Finance

Report to Performance & Audit Committee

To accompany all Reports to Performance & Audit Committee Meetings

# To: Head of Administration Services

| Author: | Kish Parmar | Date: | 9 January 2007 |
| --- | --- | --- | --- |
| Service: | Corporate Development |  |  |
| Date of Meeting: | 25 January 2007 |  |  |
| Title of Report: | General Services Capital Programme: SUMMARY OF 3 YEAR PROGRAMME 2006/07 TO 2008/09 AND FINANCIAL POSITION AS AT NOVEMBER 2006 |  |  |

| Recommendation that the attached report be: |  |  |
| --- | --- | --- |
| 1. Given unrestricted circulation |  | (tick appropriate box) |
| 2. Taken in private |  |  |
| By virtue of paragraph of schedule 7A, Local Government (Scotland) Act 1973. |  |  |

Appendices attached to this report (if none, state “none”)

1. General Services Capital Programme 2006/07 to 2008/09 Detailed Schedule: Appendix 1

| List of Background Papers (if none, state “none”) |  |
| --- | --- |
| 1. 2. | “General Services Capital Programme: SUMMARY OF 3 YEAR PROGRAMME 2006/07 TO 2008/09 AND FINANCIAL POSITION AS AT SEPTEMBER 2006” Report presented to the Performance & Audit Committee on 16th November 2006 “3 Year Capital Programme – 2006/07 to 2008/09” Report presented to the Special Council Meeting on 9 February 2006. |
| 3. | “General Services Capital Programme 2005/06: Draft Final Position for the Year” Report presented to the Performance & Audit Committee on 20th April 2006 |
| 4. | “Management & Control of Capital Programme” Report presented to the Performance & Audit Committee on 24th August 2006 |
|  | Note: All documents specified must be kept available by the author for public inspection for four years from the date of the meeting at which the report is considered. |