## 2006-07 Exp & Income to 30.11.6
|  |  |  | OK | [6 empty] | 0 |  | OK |  | Out-turn Out | OK | OK
| 1 | 2 | 3 | 4 |  | 5 | 6 | 7 | 8 | 9 | 10 | 10 | 11 |  | 12 | 12 | 13 | 13 | 14 | 15 | 16
Housing Capital Programme 2006/07 |  |  | Underspent 05/06 budget. Possible c/f to 06/07? | Approved Budget for 2006/07 |  | 5: Actual for 8 months to 30th November 2006; 0 10: % of actual over Out-turn; OK 11: Out-turn for year intimated at HCL mtg of 7/12/06 | Out-turn for year (at Cap Liaison Mtg 14/6/05) | Out-turn for year (as reported to P&A meeting on 20/4/06) | Approved Proposed Budget for 2007/08 | Approved Proposed Budget for 2008/09 | Project Status as at November 2006
| Project | Ledger | 05/06 budget |  |  | Contract | Prof | Other | Total | Income | Net | [6 empty] | Tenders issued/ received | Contractor appointed | Project Start Date | Other Details
| Code | Code | possible c/f |  |  | Payments | Fees | Expend | Expend |  | Expend
|  |  | £ | £ | [9 empty] | £ |  | £ | £ | bar: 5 to OK 11
SCOTTISH HOUSING QUALITY STANDARD
TACKLING SERIOUS DISREPAIR
PRIMARY BUILDING ELEMENTS
Major items of spend incurred to date include asbestos testing and any subsequent removal work, and underpining works at Engelen Drive and the replacement of a retaining wall at Backwood Court. Future costs include investigation and works costs for pilot Blackburn property at Fairfield and also investigation of possible subsidence issue in Cobblecrook Gardens, Alva. Estimate does not include Fairfield works as no estimate yet available.
Structural Works |  | 92 02 | 20572 | 150000 |  | OK 11: 166991 |  |  | 150000 | 150000
47 Hareburn Rd Sound Insulation |  | 0140 |  |  |  | 8: 0; 0 10: 0
Cavity Wall Insulation - Garden Terrac. |  | 0141 |  |  |  | 8: 0; 0 10: 0
Cavity Wall Insulation - Garden Terrac. |  | 92 02 0141 |  |  |  | 8: 0; 0 10: 0
Substructure Works-Upgrade Dorran Houses Dollar | 1640(a) | 92 02 0146 |  |  |  | 8: 0; 0 10: 0
Structural Condition Report - Dollar (Dorrans) | 1640(b) | 92 02 0142 |  |  |  | 8: 0; 0 10: 0
99/00 Johnston Crescent | [5 empty] | 8: 0; 0 10: 0
99/00 Asbestos Survey/Rem | [5 empty] | 8: 0; 0 10: 0
03/04 Dorrans Upgrade, Dollar (new code) | 1640[c] | 92 02 0143. |  |  |  | 8: 0; 0 10: 0
Home Safety |  | 92 02 0151 |  |  |  | 8: 0; 0 10: 0
Structural Investigation Weir Alva |  | 92 02 0144 |  |  |  | 8: 0; 0 10: 0
Lintel renewal Dollar, etc | 1880 | 92 02 0181 |  |  |  | 8: 0; 0 10: 0
Porches Rosebank/Holton | 1708 | 92 02 0812 |  |  |  | 8: 0; 0 10: 0
Victim Centered Approach |  | 92 02 0152 |  |  |  | 8: 0; 0 10: 0
97/98 Crime Prevention |  | 0156 |  |  |  | 8: 0; 0 10: 0
Lintel Renewal (Alva) | 1524 | 0160/0606 |  |  |  | 8: 0; 0 10: 0
Stabilisation |  | 0163 |  |  |  | 8: 0; 0 10: 0
Henderson Ave. Structural | 1489 | 0164 |  |  |  | 8: 0; 0 10: 0
Craigview, Sauchie |  | 0165 |  |  |  | 8: 0; 0 10: 0
30 Windsor Street Menstrie | 1489(a) | 0166 |  |  |  | 8: 0; 0 10: 0
Garden Wall 46 Earn Court Alloa | 1328 | 92 02 0167 |  |  |  | 8: 0; 0 10: 0
Asbestos Survey Renewal |  | 92 02 0168 |  |  |  | 8: 0; 0 10: 0
Replacement Screens, Sauchie | 1487 | 92 02 0169 |  |  |  | 8: 0; 0 10: 0
Asbestos Works |  | 92 02 0170 |  |  |  | 7: 26282.45; 8: 26282.45; 0 10: 26282.45
01/02 Asbestos Survey | [5 empty] | 8: 0; 0 10: 0
Upgrade 49 Mansfield Avenue |  | 0158 |  |  |  | 8: 0; 0 10: 0
Demolish 3 + 5 Henderson Avenue |  | 0301 |  |  |  | 8: 0; 0 10: 0
General - 2006/09 Asbestos testing - Term contract | 2102 | 92 02 0173 |  |  |  | 5: 69010; 6: 22227; 8: 91237; 0 10: 91237
Argyle Place | 2072 | 92 02 0470 |  |  |  | 6: 294; 8: 294; 0 10: 294
Replacement of Retaining Walls - Various Locations | 1961 | 92 02 1961 |  |  |  | 6: 120.25; 8: 120.25; 9: -91; 0 10: 29.25
Asbestos Testing - Term Contract 2004/06 | 1978 | 92 02 0172 |  |  |  | 8: 0; 0 10: 0
Mill St, Alloa | 1579 | 92 02 0800 |  |  |  | 8: 0; 0 10: 0
Walkway, Primrose Place, Tilly | 1466 | 92 02 0802 |  |  |  | 8: 0; 0 10: 0
Walkway, High St, Tilly | 1598 | 92 02 0808 |  |  |  | 8: 0; 0 10: 0
Walkway, High St, Tilly | 1677 |  |  |  |  | 8: 0; 0 10: 0
Wier Timber Houses Alva |  | 92 02 0809 |  |  |  | 8: 0; 0 10: 0
Beam Strengthening Jamieson Gdns | 1799 | 92 02 0811 |  |  |  | 8: 0; 0 10: 0
Retaining Wall - Deerpark/Beechwood | 1860 | 92 07 1860 |  |  |  | 8: 0; 0 10: 0
25-31 Moir St Alloa - Replacement Lintels | 2071 | 92 02 1813 |  |  |  | 5: 3345; 6: 181.38; 8: 3526.38; 0 10: 3526.38
Blackburn Houses |  | 92 02 1855 |  |  |  | 6: 340; 8: 340; 0 10: 340
Underpinning at Engelen Drive | 2093 | 92 02 1880 |  |  |  | 5: 10803.97; 6: 160; 8: 10963.97; 0 10: 10963.97
Lock Ups - Murray Place Dollar |  | 92 02 1890 |  |  |  | 6: 0; 8: 0; 0 10: 0
Structural Work at Fairfield |  | 92 02 1896 |  |  |  | 5: 1082.9; 8: 1082.9; 0 10: 1082.9
Rem Works at Clackmannan | 2097 | 92 02 0417 |  |  |  | 6: 1408.05; 8: 1408.05; 0 10: 1408.05
Structural Works |  |  | 20572 | 150000 |  | 84241.87 | 24730.68 | 26282.45 | 135255 | -91 | 135164 | #DIV/0! | 166991 | 177000 | 0 | 150000 | 150000
SECONDARY BUILDING ELEMENTS
Full budget spend on major rot treatment improvement works identified. Transfer from revenue to capital yet to be processed.
Damp/Rot |  | 92 02 |  | 30000 |  | OK 11: 30000 |  |  | 30000 | 30000
Damp/Rot Area Teams) |  | 92 02 0200 |  |  |  | 5: 175; 7: 792; 8: 967; 0 10: 967
Damp/Rot Sundries |  | 0201 |  |  |  | 8: 0; 0 10: 0
99/00 Ashley Terrace Ph 1 | 1528} | 92 02 0210 |  |  |  | 8: 0; 0 10: 0
01/02 Ashley Terrace Ph 2 | 1723 | 92 02 0211 |  |  |  | 8: 0; 0 10: 0
Damp/Rot |  |  |  | 30000 |  | 175 | 0 | 792 | 967 | 0 | 967 | #DIV/0! | 30000 | 30000 | 0 | 30000 | 30000
Phase 1 contract at Sauchie completed two months ahead of programme. Phase 2 at Tullibody progressing but slightly behind programme due to weather. Flat roof work at Braehead almost complete. Tender issued for further flat roofing works as part of ongoing inspection and maintenance programme. Work expected to commence February 2007 at the earliest.
Roofs / Rainwater / External Walls |  | 92 02 |  | 450000 |  | OK 11: 388961 |  |  | 400000 | 400000
97/98 Cladding Ash Grove E/E | 1442 | 92 02 0455 |  |  |  | 8: 0; 0 10: 0
98/99 Pitched Roofs | 1490 | 92 02 0426 |  |  |  | 8: 0; 0 10: 0
98/99 Flat Roofs | 1473 | 92 02 0410 |  |  |  | 8: 0; 0 10: 0
Flat Roofs Remedial Works |  | 92 02 0411 |  |  |  | 8: 0; 0 10: 0
99/00 Cambus | 1320 | 92 02 0453/0465 |  |  |  | 8: 0; 0 10: 0
Remedial Render High St Tilly * | 1469 | 0457 |  |  |  | 8: 0; 0 10: 0
00/01 Cruden Roofs | 1523 | 0415 |  |  |  | 8: 0; 0 10: 0
99/00 Cruden Roofs | 1622(a)/1632 | 0416 |  |  |  | 8: 0; 0 10: 0
01/02 Cruden Roofs | 1777 | 92 02 0412 |  |  |  | 8: 0; 0 10: 0
99/00 Pitched Roofs Phase 1 | 1526(a) | 92 02 0427 |  |  |  | 8: 0; 0 10: 0
99/00 Pitched Roofs Phase 2 | 1526(b) | 0428 |  |  |  | 8: 0; 0 10: 0
99/00 Pitched Roofs Phase 3 | 1526(c) | 0429 |  |  |  | 8: 0; 0 10: 0
01-02 Pitched Roofs Phase 1 | 1757 (A) | 92 02 0434 |  |  |  | 8: 0; 0 10: 0
Chappelle Crescent | 1886 (A) | 92 02 0435 |  |  |  | 8: 0; 0 10: 0
03/04 Chapelle Cres Roofing | 1801 | 92 02 0437 |  |  |  | 8: 0; 0 10: 0
99/00 Maple Court | 1436 | 92 02 0433/0904 |  |  |  | 8: 0; 0 10: 0
[9 empty] | 0 |  | 0
Insulation of No Fines Mar Estate | 1686 | 0459 |  |  |  | 8: 0; 0 10: 0
100 Gean Rd Re-Inst. Roof | 1644 | 0430 |  |  |  | 8: 0; 0 10: 0
01/02 Maple Court Alloa (re-render) | 1751 | 92 02 0810 |  |  |  | 8: 0; 0 10: 0
00/01 Roof Recladding | 1693 | 92 02 0431 |  |  |  | 8: 0; 0 10: 0
2002/04 Felt Roofing Term Contract | 1809 | 92 02 0436 |  |  |  | 8: 0; 0 10: 0
2003/04 Pitched Roofs Phase 1 Coalsn't'n & Clack | 1932 | 92 02 0438 |  |  |  | 5: 3283.58; 8: 3283.58; 0 10: 3283.58
2004/05 Pitched Roofs Phase 1: Sauchie | 1992(a) | 92 02 0439 |  |  |  | 8: 0; 0 10: 0
2004/05 Re-roofing Phase 2 Sauchie | 1992(b) | 92 02 0440 |  |  |  | 8: 0; 0 10: 0
2005/06 Re-roofing Tullibody | 2082 | 92 02 0441 |  |  |  | 5: 128115; 6: 2603; 8: 130718; 0 10: 130718
Re-rendering at Clackmannan & Cambus | 1925 | 92 02 0813 |  |  |  | 8: 0; 0 10: 0
2005/06 Re-Roofing Main Street Sauchie |  | 92 02 0442 |  |  |  | 8: 0; 0 10: 0
14-28 Scotland Place, Tilly - Removal of Findlock gutters | 2104 | 92 02 0443 |  |  |  | 6: 540; 7: 290.2; 8: 830.2; 0 10: 830.2
Term Contract - 2006/09 flat roof repairs | 2110 | 92 02 0444 |  |  |  | 8: 0; 0 10: 0
Alloa/Tullibody 94/95 Pitched Roof A/1238 | A/1238 | 92 02 0463 |  |  |  | 8: 0; 0 10: 0
02/03 Re-roofing | 1817 | 92 02 1817 |  |  |  | 8: 0; 0 10: 0
03/04 Re-roofing | 1817(a) | 92 02 1809 |  |  |  | 8: 0; 0 10: 0
New Roof-Window 22 Stirling Street Tillicoultry | 2114 | 92 02 1850 |  |  |  | 8: 0; 0 10: 0
2006/07 Pitched Roof Replacements Phase 1 | 2129(a) | 92 02 0445 |  |  |  | 5: 142214.08; 6: 2121.05; 8: 144335.13; 0 10: 144335.13
2006/07 Pitched Roof Replacements Fascia Repairs | 2129(b) | 92 02 0446 |  |  |  | 5: 18296.22; 6: 381.37; 8: 18677.59; 0 10: 18677.59
Braehead, Alva - Roof Repairs | 2067 | 92 02 1812 |  |  |  | 6887.5 | 959.76 | 81.57 | 7928.83 |  | 7928.83
Non Traditional Inspection | 2122 | 92 02 0668 |  |  |  | 6: 1443.75; 8: 1443.75; 0 10: 1443.75
Structural Work Fairfield |  | 92 02 1896 |  |  |  | 5: 0; 8: 0; 0 10: 0
2006/07 Comm Improvement | 2124(a) | 92 02 0669 |  |  |  | 6: 481; 8: 481; 0 10: 481
Katrine Court 36-43 Refurb | 2130 | 92 02 0670 |  |  |  | 6: 385.75; 7: 326.11; 8: 711.86; 0 10: 711.86
2004/06 Flat Roof Improvements | 1968 | 92 02 1811 |  |  |  | 8: 0; 0 10: 0
Roofs / Rainwater / External Walls |  |  | 0 | 450000 |  | 298796.38 | 8915.68 | 697.88 | 308409.94 | 0 | 308409.94 | #DIV/0! | 388961 | 368000 | 0 | 400000 | 400000
Subject to contractor performance, programme should be completed this year with the exception of rogues. An article has been included in 'Homing In' to highlight rogue doors omitted from programme.
External Door, etc |  | 92 02 | 225628 | 1300000 |  | OK 11: 1434072 |  |  | 300000
98-99 Home Security Doors Phase 1 | 1491(a) | 0190 |  |  |  | 8: 0; 0 10: 0
98-99 Home Security Doors Phase 2 | 1491(b) | 0191 |  |  |  | 8: 0; 0 10: 0
98-99 Home Security Doors Phase 3 | 1491(c) | 0192 |  |  |  | 8: 0; 0 10: 0
98-99 Home Security Doors Phase 4 | 1491(d) | 0193 |  |  |  | 8: 0; 0 10: 0
99-00 Home Security Doors Phase 1 | 1534(a) | 92 02 0194 |  |  |  | 8: 0; 0 10: 0
99-00 Home Security Doors Phase 2 | 1534(b) | 0195 |  |  |  | 8: 0; 0 10: 0
99-00 Home Security Doors Phase 3 | 1534(c) | 0196 |  |  |  | 8: 0; 0 10: 0
99-00 Home Security Doors Phase 4 | 1534(d) | 92 02 0197 |  |  |  | 8: 0; 0 10: 0
99-00 Home Security Doors Phase 5 | 1534(e) | 92 02 0198 |  |  |  | 8: 0; 0 10: 0
99-00 Home Security Doors Phase 6 | 1534(f) | 92 02 0199 |  |  |  | 8: 0; 0 10: 0
99-00 Home Security Doors Phase 7 | 1534(g) | 92 02 0220 |  |  |  | 8: 0; 0 10: 0
99-00 Home Security Doors Phase 8 | 1534(h) | 92 02 0221 |  |  |  | 8: 0; 0 10: 0
Doors General | 1761 | 92 02 0223 |  |  |  | 8: 0; 0 10: 0
02-03 Doors general | 1820 | 92 02 1820 |  |  |  | 8: 0; 0 10: 0
02-03 Doors Ph 1 | 1820A | 92 02 1821 |  |  |  | 8: 0; 0 10: 0
01-02 Home Security Doors Phase 1 | 1759 (A/B) | 92 02 0224 |  |  |  | 8: 0; 0 10: 0
01-02 Home Security Doors Phase 2 | 1759 (B) | 0225 |  |  |  | 8: 0; 0 10: 0
01-02 Home Security Doors Phase 3 | 1759 (C/D) | 92 02 0226 |  |  |  | 5: 7650.5; 8: 7650.5; 0 10: 7650.5
01-02 Home Security Doors Phase 4 | 1759 (D) | 92 02 0227 |  |  |  | 8: 0; 0 10: 0
01-02 Home Security Doors General | 1759 | 92 02 0228 |  |  |  | 8: 0; 0 10: 0
Elmgrove | [5 empty] | 8: 0; 0 10: 0
[9 empty] | 0 |  | 0
Screens & Windows (Bill Wardrop) |  | 92 02 0229 |  |  |  | 8: 0; 0 10: 0
00-01 Home Security External Lighting | 1616(e) | 92 02 0240 |  |  |  | 8: 0; 0 10: 0
03-04 Door Replacement Alloa & Clack | 1873 | 92 02 1873 |  |  |  | 8: 0; 0 10: 0
03-04 Door Replacements Phase 1 (Hadden) | 1873(a) | 92 02 1874 |  |  |  | 8: 0; 0 10: 0
03-04 Door Replacements Phase 2 | 1873(b) | 92 02 1876 |  |  |  | 8: 0; 0 10: 0
03-04 Door Replacement Alva | 1873(c) | 92 02 1875 |  |  |  | 8: 0; 0 10: 0
2004/05 Door Replacement - Phase 1 - Alva | 1950(a) | 92 02 1828 |  |  |  | 5: 4103.22; 6: 365; 8: 4468.22; 0 10: 4468.22
2004/05 Fear of Crime (Door Replacement) (start 2004/05) | 1950(b) | 92 02 1825 |  |  |  | 5: 9165; 6: 1875; 8: 11040; 0 10: 11040
2005/06 Door Improvements - Various | 2011 | 92 02 1829 |  |  |  | 6: 1428; 8: 1428; 0 10: 1428
2005/06 Door Improvements - Phase 1 - Alloa | 2011(a) | 92 02 1833 |  |  |  | 5: 21325.6; 6: 3063; 8: 24388.6; 0 10: 24388.6
2005/06 Door Improvements - Phase 2 - Tillicoultry | 2011(b) | 92 02 1834 |  |  |  | 204660.74 | 6622 | 93.95 | 211376.69 |  | 211376.69
2005/06 Door Improvements - Phase 3 - Tullibody | 2011(c) | 92 02 1835 |  |  |  | 5: 68820.1; 6: 5590; 8: 74410.1; 0 10: 74410.1
Various Home Security - External lights phase 3 | 2011 (f) | 92 02 1836 |  |  |  | 8: 0; 0 10: 0
Various Home Security - Doors Phase 4 | 2011 (g) | 92 02 1837 |  |  |  | 5: 365622; 6: 2892.5; 8: 368514.5; 0 10: 368514.5
2005/06 Home Security - External Lights | 2011(d) | 92 02 1832 |  |  |  | 6: 224; 8: 224; 0 10: 224
General - 2006/07 Home Security Door Replacements | 2090 | 92 02 1877 |  |  |  | 5: 157035; 6: 1512; 8: 158547; 0 10: 158547
Phase 1 Alloa - 2006/07 Home Security door replacements | 2090(A) | 92 02 1878 |  |  |  | 6: 1063; 8: 1063; 0 10: 1063
Dollar & Tilly - 2006/07 Door Replacements phase 2 | 2090(B) | 92 02 1879 |  |  |  | 6: 1294; 8: 1294; 0 10: 1294
Budget transferred to Craigview Letting Initiative Ph 2 (see 'Communal Areas' below) |  |  |  | -21803
[9 empty] | 0 |  | 0
External Door, etc |  |  | 225628 | 1278197 |  | 838382.16 | 25928.5 | 93.95 | 864404.61 | 0 | 864404.61 | #DIV/0! | 1434072 | 937000 | 0 | 300000 | 0
ENERGY EFFICIENCY
Budget reduced at mid year point due to continued resourcing issues within Housing Service which have delayed work on production of report to Council on the future of the heating programme. Replacement of warm air systems in Carseview, Tullibody has been brought forward due to issues regarding flues. This work has been done under Heating Term Contract. Phases 1 and 2 delayed due to access problems for metering and provision of gas supplies in Tillicoultry. It is possible that the out-turn is further reduced . Members will be updated further in the next report.
Full/Efficient Central Heating |  | 92 02 | 86291 | 1200000 |  | OK 11: 818985 |  |  | 1200000 | 1456000
99/00 Heating | 1533(b) | 0617 |  |  |  | 8: 0; 0 10: 0
99/00 Heating Phase 2 | 1533(c) | 0619 |  |  |  | 8: 0; 0 10: 0
99/00 Heating Phase 1 | 1533(a) | 92 02 0620 |  |  |  | 8: 0; 0 10: 0
00/01 Heating Phase 2 | 1617(b) | 92 02 0626 |  |  |  | 8: 0; 0 10: 0
00/01 Heating Phase 3 | 1617[c] | 92 02 0629 |  |  |  | 8: 0; 0 10: 0
00/01 term contract | 1652 |  |  |  |  | 8: 0; 0 10: 0
Gas Supply |  | 92 02 0627 |  |  |  | 8: 0; 0 10: 0
01/02 Term Contract | 1758 | 92 02 0631 |  |  |  | 8: 0; 0 10: 0
Caroline Cres - Alva - Heating Renewal | 1740 | 92 02 0632 |  |  |  | 8: 0; 0 10: 0
00/01 term contract | 1652 | 92 02 0621/0625 |  |  |  | 8: 0; 0 10: 0
00/01 Fuel Changeover | [5 empty] | 8: 0; 0 10: 0
Fuel Change - Pers Pref |  | 0625 |  |  |  | 8: 0; 0 10: 0
00/01 Electric/Gas Conversions |  | 0630 |  |  |  | 8: 0; 0 10: 0
Term Ctrct Solid Fuel C/H 02/03 | 1641 | 92 02 1641 |  |  |  | 8: 0; 0 10: 0
Term Contract | 1816/1 | 92 02 0633 |  |  |  | 8: 0; 0 10: 0
Term Heating Contract (new phase) | 1816/7 | 92 02 0633 |  |  |  | 8: 0; 0 10: 0
Heating Safety |  | 92 02 0634 |  |  |  | 8: 0; 0 10: 0
2003-04 Heating Contract | 1882 | 92 02 0635 |  |  |  | 8: 0; 0 10: 0
Heating Enhancements -Warm Deal Initiative |  | 92 02 0636 |  |  |  | 8: 0; 0 10: 0
Gas Link - Mar Policies |  | 92 02 0638 |  |  |  | 8: 0; 0 10: 0
Gas Safety Incident | 1979 | 92 02 0639 |  |  |  | 8: 0; 0 10: 0
2004/05 Heating Replacements - Mar Estate (Remaining) | 1976(a) | 92 02 0641 |  |  |  | 6: 32; 8: 32; 0 10: 32
2004/05 Heating Replacements - Phase 2 | 1976(b) | 92 02 0644 |  |  |  | 8: 0; 0 10: 0
2004/05 Electric Central Heating Installation - Various | 1976(c) | 92 02 0645 |  |  |  | 8: 0; 0 10: 0
2004/05 Central Heating Replacements - Term Contract | 1977 | 92 02 0642 |  |  |  | 8: 0; 0 10: 0
2004/05 Central Heating Replacements - Warm Deal Initiative | 1977 | 92 02 0643 |  |  |  | 8: 0; 9: -232; 0 10: -232
Gas Link Monies - Fuel Switch Grant |  | 92 02 0646 |  |  |  | 8: 0; 0 10: 0
Heating Appliances |  | 92 02 0640 |  |  |  | 8: 0; 0 10: 0
2005/06 Term Contract - Heating Repairs | 2041 | 92 02 1647 |  |  |  | 8: 0; 0 10: 0
2005/06 Heating Replacements - Phase 1 | 2074(a) | 92 02 0648 |  |  |  | 44673.45 | 4646.69 | 142.39 | 49462.53 | -172.5 | 49290.03
2005/06 Heating Replacements - Phase 2 | 2074(b) | 92 02 0649 |  |  |  | 5: 1965.15; 8: 1965.15; 0 10: 1965.15
2005/06 Heating Replacements - Phase 3 : Various | 2074(c) | 92 02 0656 |  |  |  | 5: 7824.2; 8: 7824.2; 0 10: 7824.2
2005/06 Electric Central Heating - Phase 2 | 2074(d) | 92 02 0657 |  |  |  | 5: 5643; 6: 1086; 8: 6729; 0 10: 6729
Various 2005/07 Central Heating term Contract | 2035 | 92 02 0660 |  |  |  | 294491.93 | 3520 | 11842.5 | 309854.43 |  | 309854.43
General - 2005/06 Heating Replacements | 2074 | 92 02 0661 |  |  |  | 6: 42; 8: 42; 9: -180; 0 10: -138
2006/07 Central Heating Contract Phase 1 | 2115(a) | 92 02 0662 |  |  |  | 5: 87729; 6: 2940; 8: 90669; 0 10: 90669
2006/07 Central Heating Chapelle Crescent | 2115(b) | 92 02 0663 |  |  |  | 6: 126; 8: 126; 0 10: 126
03-04 Central Heating Mar Policies moved from Rewiring | 1882(a) | 92 02 0637 |  |  |  | 8: 0; 0 10: 0
Budget transferred to Craigview Letting Initiative Ph 2 (see 'Communal Areas' below) |  |  |  | -60841
[9 empty] | 0 |  | 0
Full/Efficient Central Heating |  |  | 86291 | 1139159 |  | 442326.73 | 12392.69 | 11984.89 | 466704.31 | -584.5 | 466119.81 | #DIV/0! | 818985 | 1321000 | 0 | 1200000 | 1456000
Work at Achray Court complete. Tender accepted for Katrine Court and work has commenced. Tender for Maree Court recently accepted also. Level of spend weather dependent, may achieve £570k. Architects carrying out commence design work for remedial treatment work to council owned Weir Multi-con properties in Alva
Thermal Insulation |  |  | 11311 | 600000 |  | OK 11: 568560 |  |  | 800000 | 600000
2005/08 Term Contract - Floor Coverings | 2043 | 92 02 0710 |  |  |  | 8: 0; 0 10: 0
Achray Court, Alloa Insulated Render to no fines Hse Phase 1 | 2075(A) | 92 02 0472 |  |  |  | 5: 161901.55; 6: 3052.5; 8: 164954.05; 0 10: 164954.05
2006/07 Katrine Court Insulation | 2117(a) | 92 02 0666 |  |  |  | 6: 629; 8: 629; 0 10: 629
2006/07 Maree Court Render | 2117(b) | 92 02 0667 |  |  |  | 6: 37; 8: 37; 0 10: 37
No fines Houses Insulated Rendering | 2075 | 92 02 0471 |  |  |  | 6: 693; 8: 693; 0 10: 693
[9 empty] | 0 |  | 0
Thermal Insulation |  |  | 11311 | 600000 |  | 161901.55 | 4411.5 | 0 | 166313.05 | 0 | 166313.05 | #DIV/0! | 568560 |  | 0 | 800000 | 600000
MODERN FACILITIES & SERVICES
Contractor performance problems in Phase 1. As a result it is proposed that around 70 properties be removed from the contract at this stage and awarded to contractor who has been working on Phase 3. Phase 2 fitting work recently commenced, but completed handovers slow. Property Services in discussions with contractor seeking to improve performance. Phase 3 work nearing completion on original properties. Contract now extended to include properties removed from Phase 1. Phase 4 expected to commence fitting work in late January. Final out-turn will be dependent on contractor performance in all phases.
Kitchen Renewal |  |  | 196787 | 3490000 |  | OK 11: 3057808 |  |  | 3860000 | 3860000
New Spend | 1760 | 92 02 0230 |  |  |  | 5: 32300; 8: 32300; 0 10: 32300
02/03 Kitchens Ph 1 | 1819 | 92 02 1819 |  |  |  | 8: 0; 0 10: 0
02/03 Kitchens Ph 2 | 1819(a) | 92 02 1822 |  |  |  | 8: 0; 0 10: 0
03/04 Kitchens Ph 1 Tullibody | 1895(a) | 92 02 1823 |  |  |  | 8: 0; 0 10: 0
2004/05 Kitchen replacements - various | 1949 | 92 02 1824 |  |  |  | 8: 0; 0 10: 0
2004/05 Kitchen replacements - Tullibody | 1949(a) | 92 02 1826 |  |  |  | 5: 1971.83; 6: 176; 8: 2147.83; 0 10: 2147.83
2004/05 Kitchen replacements Phase 2 - Sauchie | 1949(b) | 92 02 1827 |  |  |  | 5: 7598.22; 6: 1189; 8: 8787.22; 0 10: 8787.22
2004/05 Kitchen replacement Phase 3 | 1949(c) | 92 02 1830 |  |  |  | 5: 420; 8: 420; 0 10: 420
2004/05 Kitchen Replacements - Term Contract | 2012 | 92 02 1843 |  |  |  | 6: 4229; 8: 4229; 0 10: 4229
2005/06 Kitchen Replacements - various | 2006 | 92 02 1840 |  |  |  | 6: 1428; 8: 1428; 0 10: 1428
2005/06 Kitchen Replacements - Phase 1 Sauchie | 2006(a) | 92 02 1841 |  |  |  | 166499.8 | 2973 | 3094 | 172566.8 |  | 172566.8
2005/06 Kitchen Replacements - Phase 2 Tillicoultry | 2006(b) | 92 02 1842 |  |  |  | 1789 | 11723.13 | 6281.88 | 19794.01 |  | 19794.01
2005/06 Kitchen Replacements - Phase 3 Alloa | 2006(c) | 92 02 1845 |  |  |  | 40699 | 527 | 36320.17 | 77546.17 |  | 77546.17
General - 2006/07 Kitchen replacements | 2100 | 92 02 1846 |  |  |  | 43732 | 26214.48 | 5795.24 | 75741.72 |  | 75741.72
Phase 2 - 2006/07 Kitchen Replacements | 2100(b) | 92 02 1847 |  |  |  | 6: 5200.52; 7: 186; 8: 5386.52; 0 10: 5386.52
Phase 3 - 2006/07 Kitchen Replacements | 2100© | 92 02 1848 |  |  |  | 432000 | 33985.83 | 349.58 | 466335.41 |  | 466335.41
Phase 4 - 2006/07 Kitchen Replacements | 2100(d) | 92 02 1849 |  |  |  | 6: 4996.98; 8: 4996.98; 0 10: 4996.98
Capital Enhancements |  | 92 07 0300 |  | 0 |  | 8: 0; 0 10: 0
Budget transferred to Craigview Letting Initiative Ph 2 (see 'Communal Areas' below) |  |  |  | -42622
Kitchen Renewal |  |  | 196787 | 3447378 |  | 727009.85 | 92642.94 | 52026.87 | 871679.66 | 0 | 871679.66 | #DIV/0! | 3057808 | 900000 | 0 | 3860000 | 3860000
Tender for first phase accepted and work due to commence in New Year.
Bathroom Survey/Pilot |  |  |  | 250000 |  | 8: 0; 0 10: 0; OK 11: 294306 |  |  | 800000 | 1000000
Bathroom Replacements Various Locations |  | 92 02 1650 |  |  |  | 7: 1524.09; 8: 1524.09; 0 10: 1524.09
2006/07 Bathroom Cambus/Alva | 2128 | 92 02 1661 |  |  |  | 6: 3609.61; 8: 3609.61; 0 10: 3609.61
Sauchie & Tilly - 2005/06 Bathroom Replacement | 2076 | 92 02 1660 |  |  |  | 6: 441; 8: 441; 0 10: 441
Budget transferred to Craigview Letting Initiative Ph 2 (see 'Communal Areas' below) |  |  |  | -32201
Bathroom Survey/Pilot |  |  | 0 | 217799 | 0 | 0 | 4050.61 | 1524.09 | 5574.7 | 0 | 5574.7 | #DIV/0! | 294306 |  | 0 | 800000 | 1000000
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 50000 | 0 | 0 | 0
HEALTHY, SAFE & SECURE
Programme of re-wiring delayed as initial tenders very high. Work re-tendered and reduced costs returned. Contractor due to commence on site January 2007. Phase 1 electrical inspections have commenced, phase 2 delayed due to illness within Property Services. Tender now returned.
Internal Lead Pipework |  | 92 02 |  | 0
99/00 Lead Pipe Renewal | 1554 | 92 02 0804 |  |  |  | 8: 0; 0 10: 0
Lead Pipe Renewal Sundries |  | 92 02 0805 |  |  |  | 8: 0; 0 10: 0; OK 11: 0
[9 empty] | 0 |  | 0
Internal Lead Pipework |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 15000 | 0 | 0 | 0
Safe Electrical Systems |  | 92 02 | 43415 | 450000 |  | OK 11: 419121 |  |  | 450000 | 450000
97/98 Phase 1 (Hart) | 1372(a) | 0307 |  |  |  | 8: 0; 0 10: 0
98/99 Phase 1 (Sauchie/Tillicoultry) | 1465(a) | 92 02 0311 |  |  |  | 8: 0; 0 10: 0
Electrical Earth Testing * | 1507 | 0312 |  |  |  | 8: 0; 0 10: 0
98/99 Phase 2 * | 1465(b) | 0313 |  |  |  | 8: 0; 0 10: 0
99/00 Electrical Earth Testing | 1573 | 0314 |  |  |  | 8: 0; 0 10: 0
99/00 Rewiring Phase 1 | 1574(a) | 92 02 0316 |  |  |  | 8: 0; 0 10: 0
99/00 Rewiring Phase 2 | 1574(b) | 92 02 0317 |  |  |  | 8: 0; 0 10: 0
00-01 Electrical Earth Testing | 1642 | 92 02 0318 |  |  |  | 8: 0; 0 10: 0
00-01 Electrical Rewiring | 1694 | 92 02 0319 |  |  |  | 8: 0; 0 10: 0
00-01 Electrical Rewiring Phase 1 | 1694(a) | 92 02 0320 |  |  |  | 8: 0; 0 10: 0
00-01 Electrical Rewiring Phase 2 | 1694(b) | 92 02 0321 |  |  |  | 8: 0; 0 10: 0
00-01 Electrical Rewiring Sundries |  | 0329 |  |  |  | 8: 0; 0 10: 0
98/99 Close Lighting |  | 0950 |  |  |  | 8: 0; 0 10: 0
01-02 Electrical inspections | 1756 | 92 02 0330 |  |  |  | 8: 0; 0 10: 0
01-02 Rewire | 1781(a) | 92 02 0323 |  |  |  | 5: 1709; 6: 42; 8: 1751; 0 10: 1751
02-03 Rewiring | 1818 | 92 02 1818 |  |  |  | 8: 0; 0 10: 0
02-03 Electrical Installations | 1838 | 92 02 1838 |  |  |  | 8: 0; 0 10: 0
03-04 Electrical Inspection | 1936 (?) | 92 02 1863 |  |  |  | 8: 0; 0 10: 0
03-04 Electrical Inspection: Various | 1863 | 92 02 1864 |  |  |  | 8: 0; 0 10: 0
2004/05 Electrical Inspections: Alloa | 1938 | 92 02 1866 |  |  |  | 5: 5617.35; 6: 1470; 8: 7087.35; 0 10: 7087.35
04-05 Electrical Rewiring Various | 2017(a) | 92 02 1865 |  |  |  | 8: 0; 0 10: 0
05-06 Electrical Inspections - Various | 2055 | 92 02 1867 |  |  |  | 6: 768; 8: 768; 0 10: 768
Phase 1 : 2005/06 Electrical Rewiring | 2083(a) | 92 02 0332 |  |  |  | 6: 4738; 7: 15991; 8: 20729; 0 10: 20729
Phase 1 : 2006/07 Electrical Rewiring | 2116(a) | 92 02 0665 |  |  |  | 6: 1879; 8: 1879; 0 10: 1879
2006/2007 General Rewiring | 2116 | 92 02 0664 |  |  |  | 5: 3500; 6: 819; 8: 4319; 0 10: 4319
Electrical rewiring programme at various locations | 2083 | 92 02 0331 |  |  |  | 5: 87324; 6: 112; 8: 87436; 0 10: 87436
03-04 Central Heating & Rewiring Mar Policies | 1882(a) | 92 02 0637 |  |  |  | 8: 0; 0 10: 0
03-04 Central Heating Mar Policies moved to Heating | 1882(a) | 92 02 0637 |  |  |  | 8: 0; 0 10: 0
[9 empty] | 0 |  | 0
Safe Electrical Systems |  |  | 43415 | 450000 |  | 98150.35 | 9828 | 15991 | 123969.35 | 0 | 123969.35 | #DIV/0! | 419121 | 396000 | 0 | 450000 | 450000
Craigview phase 2 included within this budget head, nearing completion.
Communal Areas (Environmentals) |  | 92 03 | 148190 | 200000 |  | OK 11: 357467 |  |  | 200000 | 100000
98/99 Projects | [5 empty] | 8: 0; 0 10: 0
98/99 Env Imps General | 1480/1437 | 4000/0900 |  |  |  | 8: 0; 0 10: 0
98/99 Env Imps Garage Sites | 1481/1655 | 4001 |  |  |  | 8: 0; 0 10: 0
98/99 Env Imps Door Entry Etc | 1482 | 4002 |  |  |  | 8: 0; 0 10: 0
98/99 Env Imps Fencing Works | 1483 | 92 03 4003 |  |  |  | 8: 0; 0 10: 0
98/99 Env Imps Back Court Areas | 1484 | 4004 |  |  |  | 8: 0; 0 10: 0
99/00 Stair Lighting |  | 92 03 4005 |  |  |  | 8: 0; 0 10: 0
05/06 Communal Areas Environmental Improvements |  | 92 03 4022 |  |  |  | 5: 20675.63; 7: 10319.9; 8: 30995.53; 0 10: 30995.53
Door Entry Maintenance 02/04 | 1808 | 92 03 1808 |  |  |  | 8: 0; 0 10: 0
Door Entry | 1559/1631/1665 | 92 03 4006/12 |  |  |  | 8: 0; 0 10: 0
Door Entry | 1665 |  |  |  |  | 8: 0; 0 10: 0
Door Entry | 1761 | 9202 0223 |  |  |  | 8: 0; 0 10: 0
99/00 Earthworks, Eden Rd, Alloa |  | 4007 |  |  |  | 8: 0; 0 10: 0
99/00 Car Park Lighting Menstrie Rd. | 1667/1668 | 4009 |  |  |  | 8: 0; 0 10: 0
01/02 Env Imps Various |  | 4010-4017 |  |  |  | 8: 0; 0 10: 0
00/01 Env Imps Various | 1559 et al/1755 | 4018 |  |  |  | 8: 0; 0 10: 0
99/00 Lock Up's |  | 1050 |  |  |  | 8: 0; 0 10: 0
Door Entry Newmills, Tullibody | 1879 | 92 03 1879 |  |  |  | 8: 0; 0 10: 0
Close Improvements Backwood Court | 1413 (c) | 92 03 1225 |  |  |  | 8: 0; 0 10: 0
2004/06 Term Contract - Housing Door Entry Maintenance | 1969 | 92 02 1810 |  |  |  | 8: 0; 0 10: 0
Garage Lighting |  | 2209 |  |  |  | 8: 0; 0 10: 0
Retaining Wall Alloa Centre | 1995 | 92 02 1962 |  |  |  | 8: 0; 0 10: 0
Upgrading Craigview Nos 3-21 | 2096 | 92 02 0165 |  |  |  | 5: 187636.64; 6: 5979.79; 8: 193616.43; 0 10: 193616.43
3-21 Craigview, Sauchie - House Letting Initiative Phase 2 | 2078 | 92 02 1815 |  | 157467 |  | 8: 0; 0 10: 0
0
Communal Areas (Environmentals) |  |  | 148190 | 357467 |  | 208312.27 | 5979.79 | 10319.9 | 224611.96 | 0 | 224611.96 | #DIV/0! | 357467 | 150000 | 0 | 200000 | 100000
NON-SHS ELEMENTS
PARTICULAR NEEDS HOUSING (CITC)
Work nearing completion at Curlers Court.
Conversions & Upgradings |  |  | 62237 | 200000 |  | OK 11: 234332 |  |  | 200000 | 200000
98/99 Women's Aid | 2010 | 0401 |  |  |  | 8: 0; 0 10: 0
85 Upper Mill St (Women's Aid) | 1464 | 0402 |  |  |  | 8: 0; 0 10: 0
98/99 Sheltered Housing U/G - MS |  | 92 01 0210 |  |  |  | 8: 0; 0 10: 0
00/01 Sh Housing upgrade Phase 1 | 1651 | 92 01 0211 |  |  |  | 8: 0; 0 10: 0
99/00 Sheltered Housing U/G Phase 1 | 1557 |  |  |  |  | 8: 0; 0 10: 0
01/02 Sh Housing u/g Ph 2 | 1755 | 92 01 0213 |  |  |  | 8: 0; 0 10: 0
Curlers Court, Dollar - 2005/06 Amenity Conversions | 2077 | 92 02 1814 |  |  |  | 147516.81 | 8647.67 | 10309.33 | 166473.81 |  | 166473.81
03/04 Sh Housing u/g Ph 3 |  | 92 01 0214 |  |  |  | 8: 0; 0 10: 0
Ochil Court | 1822 | 92 01 1822 |  |  |  | 8: 0; 0 10: 0
Chalet Refurbishment | 1513 | 92 01 0156 |  |  |  | 8: 0; 0 10: 0
House Upgrading 1 School Rd, Muck. | 1504 | 0157 |  |  |  | 8: 0; 0 10: 0
Relocatable Chalet Homes |  | 92 01 0150 |  |  |  | 8: 0; 0 10: 0
Alterations to 40-43 Katrine Court Alloa | 2098 | 92 01 1877 |  |  |  | 6: 703; 8: 703; 0 10: 703
Structural Work Floor replacements/Joists |  | 92 02 0148 |  |  |  | 8: 0; 0 10: 0
Alterations to Maree Court Alloa | 1876 | 92 01 1876 |  |  |  | 8: 0; 0 10: 0
[9 empty] | 0 |  | 0
Conversions & Upgradings |  |  | 62237 | 200000 |  | 147516.81 | 9350.67 | 10309.33 | 167176.81 | 0 | 167176.81 | #DIV/0! | 234332 | 102000 | 0 | 200000 | 200000
Budget increased at mid year point due to high demand for adaptations. A priority system has been adopted to run for the remainder of 2006/07.
Disabled Adaptations |  | 92 01 |  | 200000 |  | OK 11: 200000 |  |  | 200000 | 200000
00/01 Heating Adaptations |  | 92 01 0202 |  |  |  | 8: 0; 0 10: 0
Conversions and Extensions | 1661/1721/1610 | 92 01 07/0807 |  |  |  | 8: 0; 0 10: 0
03/04 Heating Adaptations | 1882 | 92 01 0203 |  |  |  | 8: 0; 0 10: 0
2004/05 Central Heating Replacements - Disabled Adaptations | 1977 | 92 01 0204 |  |  |  | 8: 0; 0 10: 0
27 Garvalley Crescent Alloa - Disabled adaptations | 2101 | 92 01 0205 |  |  |  | 5: 57429.03; 6: 5326.57; 8: 62755.6; 0 10: 62755.6
Extension 6 Burnside Cres Clackmannan | 1836 | 92 02 0183 |  |  |  | 8: 0; 0 10: 0
Aids & Adaptations | 1419 | 92 01 0200 |  |  |  | 3650 | 9795 | 61877.03 | 75322.03 |  | 75322.03
S.W. Minor Adaptations (Area Teams) | 1035 | 92 01 0201 |  |  |  | 6: 170.38; 7: 16295.14; 8: 16465.52; 0 10: 16465.52
[9 empty] | 0 |  | 0
Disabled Adaptations |  |  | 0 | 200000 |  | 61079.03 | 15291.95 | 78172.17 | 154543.15 | 0 | 154543.15 | #DIV/0! | 200000 | 175000 | 0 | 200000 | 200000
Undertaken by Housing Operational teams, main projects include various fencing works, parking improvements and re-surfacing of access areas at lock up sites.
Area Improvements |  |  | 29797 | 200000 |  | OK 11: 200000 |  |  | 200000 | 100000
Replace Banking - Delph Pond |  | 92 07 1861 |  |  |  | 8: 0; 0 10: 0
Alloa Area |  | 92 03 2202 |  |  |  | 8: 0; 0 10: 0
Bowmar Area |  | 92 03 2203 |  |  |  | 8: 0; 0 10: 0
Alloa Area Improvements 2004-05 |  | 92 03 2302 |  |  |  | 8: 0; 0 10: 0
Sauchie Area |  | 92 03 2204 |  |  |  | 8: 0; 0 10: 0
Clackmannan Area |  | 92 03 2205 |  |  |  | 8: 0; 0 10: 0
Alva Area |  | 92 03 2206 |  |  |  | 8: 0; 0 10: 0
Alva Area Improvements 2004-05 |  | 92 03 2306 |  |  |  | 8: 0; 0 10: 0
Tullibody Area |  | 92 03 2208 |  |  |  | 8: 0; 0 10: 0
Tillicoultry Area | 1929(b) | 92 03 2207 |  |  |  | 8: 0; 0 10: 0
2004/05 Area Improvements - Tillicoultry | 2009(a) | 92 03 2307 |  |  |  | 6: 32; 8: 32; 0 10: 32
Area Improvements 2005/06 |  | 92 03 2310 |  |  |  | 7: 13534.48; 8: 13534.48; 0 10: 13534.48
2004/05 Area Imp - Bin Stores 12-44b High St Tillicoultry | 2009(b) | 92 03 2317 |  |  |  | 8: 0; 0 10: 0
2004/05 Area Imp Tullibody | 2009(c ) | 92 03 2308 |  |  |  | 8: 0; 0 10: 0
Coalsnaughton - Housing Land | 1954(e) | 92 02 1963 |  |  |  | 6: 672; 8: 672; 0 10: 672
Public open spaces - East Alloa Env. Improvements | 1954(g) | 92 02 1964 |  |  |  | 8: 0; 0 10: 0
General - 2005/06 Area Improvements | 2084 | 92 03 2215 |  |  |  | 6: 185; 8: 185; 0 10: 185
Maple Court - External Door Entry System | 1878 | 92 03 1878 |  |  |  | 5: 491.62; 6: 116; 8: 607.62; 0 10: 607.62
[9 empty] | 0 |  | 0
Area Improvements |  |  | 29797 | 200000 |  | 491.62 | 1005 | 13534.48 | 15031.1 | 0 | 15031.1 | #DIV/0! | 200000 |  |  | 200000 | 100000
Part of spend will be offset by grant, actual amounts not know until year end. Works undertaken in Hawkhill, Gaberston and Greenfield street areas. Tenders accepted for two projects in Sauchie, works total c£105k. A further three tenders due to be returned.
External Lead Pipe Replacement |  |  | 166719 | 300000 |  | 8: 0; 0 10: 0; OK 11: 395400 |  |  | 200000 | 250000
2005/09 Lead Pipe Replacement | 2029 | 92 02 0501 |  |  |  | 169307 | 2431 | 20 | 171758 |  | 171758
Water Supply Pipe Renewal |  | 92 02 0806 |  |  |  | 8: 0; 9: -2827.6; 0 10: -2827.6
[9 empty] | 0 |  | 0
External Lead Pipe Replacement |  |  | 166719 | 300000 |  | 169307 | 2431 | 20 | 171758 | -2827.6 | 168930.4 | #DIV/0! | 395400 |  | 0 | 200000 | 250000
Costs in relation to rehousing of Newmills and Ash Grove tenants, including reprovisioning at Katrine Court and also relocation of Alzheimers Day Care Centre formerly in Newmills.
Demolitions |  |  |  | 100000 |  | OK 11: 108627 |  |  | 200000 | 100000
Elmgrove Home Loss |  | 92 07 0813 |  |  |  | 8: 0; 0 10: 0
Elmgrove Demolition | 1791 | 92 07 0814 |  |  |  | 8: 0; 0 10: 0
Newmills Demolition |  | 92 07 0816 |  |  |  | 5: 340; 7: 33270.58; 8: 33610.58; 0 10: 33610.58
Ashgrove Demolition |  | 92 07 0817 |  |  |  | 7: 18000; 8: 18000; 0 10: 18000
Demolition Garages Dollar | 1933 | 92 02 0891 |  |  |  | 6: 294; 8: 294; 0 10: 294
[9 empty] | 0 |  | 0
Demolitions |  |  | 0 | 100000 |  | 340 | 294 | 51270.58 | 51904.58 | 0 | 51904.58 | #DIV/0! | 108627 | 29000 | 0 | 200000 | 100000
Feasibility Work |  |  |  | 50000 |  | OK 11: 50000 |  |  | 30000 | 30000
General Advice - Architects | 1328 | 92 07 0990 |  |  |  | 6: 9194.3; 8: 9194.3; 0 10: 9194.3
Standard Delivery Plan |  | 92 07 0995 |  |  |  | 6: 10770.66; 8: 10770.66; 0 10: 10770.66
New Project Contingency | [5 empty] | 0 10: 0
Feasibility Work |  |  | 0 | 50000 |  | 0 | 19964.96 | 0 | 19964.96 | 0 | 19964.96 | #DIV/0! | 50000 | 16000 | 0 | 30000 | 30000
Budget reduced at mid year. Sums allocated for Bowmar master planning exercise and also SSP/Business Plan development work. Some of spend may not be invoiced until 2007/08.
Other Costs |  | 92 07 |  | 200000 |  | OK 11: 100000 |  |  | 200000 | 200000
Dev Services Staff Costs | [5 empty] | 8: 0; 0 10: 0
Capital Programme Officer |  | 92 02 0100 |  |  |  | 8: 0; 0 10: 0
Covenant Repayment |  | 92 07 0650 |  |  |  | 8: 0; 0 10: 0
Amenity Contract |  | 92 01 0100 |  |  |  | 7: 46.05; 8: 46.05; 0 10: 46.05
Scottish Quality Standard |  | 92 07 0991 |  |  |  | 8: 0; 0 10: 0
SHQS/Stock options 2004 |  | 92 07 0993 |  |  |  | 8: 0; 0 10: 0
30 Lomond Court Alloa (to be recharged at y/e) |  | 92 07 0832 |  |  |  | 8: 0; 0 10: 0
Kilncraigs Relocation of Housing |  | 92 07 0840 |  |  |  | 6: 1974; 8: 1974; 0 10: 1974
Computer Equipment - New |  | 92 07 0841 |  |  |  | 8: 0; 0 10: 0
Walled Garden, Orchard Project, Alloa (start 2004/05) |  | 92 07 0815 |  |  |  | 8: 0; 0 10: 0
Other Costs |  |  | 0 | 200000 |  | 0 | 1974 | 46.05 | 2020.05 | 0 | 2020.05 | #DIV/0! | 100000 | 375000 | 0 | 200000 | 200000
TOTAL CAPITAL EXPENDITURE (EXC ILM) |  |  | 990947 | 9370000 |  | 3238030.62 | 239191.97 | 273065.64 | 3750288.23 | -3503.1 | 3746785.13 | #DIV/0! | 8824630 | #REF! | 0 | 9420000 | 9126000
The project is now complete and subject to external audit. The ERDF 'expenditure' shown of £108k is an ERDF grant accrual from previous year which the Council will receive subject to satisfactory completion of audit.
Plus AS&E ILM Funding |  |  |  | 0
Community Police Office |  | 92 07 0403 |  |  |  | 8: 0; 0 10: 0
LADA Centre | 1597 | 92 07 0404 |  |  |  | 8: 0; 0 10: 0
SIP ILM |  | 92 07 0900 |  |  |  | 8: 0; 0 10: 0
SIP |  | 92 07 0901 |  |  |  | 8: 0; 0 10: 0
Scottish Enterprise |  | 92 07 0902 |  |  |  | 8: 0; 0 10: 0
New Deal |  | 92 07 0903 |  |  |  | 8: 0; 0 10: 0
ESF |  | 92 07 0904 |  |  |  | 8: 0; 0 10: 0
ERDF |  | 92 07 0905 |  |  |  | 7: 108609; 8: 108609; 0 10: 108609
SIP PSHG Grant |  | 93 07 0906 |  |  |  | 8: 0; 0 10: 0
Training Costs |  | 92 07 0910 |  |  |  | 8: 0; 0 10: 0
Plus AS&E ILM Funding |  |  | 0 | 0 |  | 0 | 0 | 108609 | 108609 | 0 | 108609 |  | 0 |  | 0 | 0 | 0
TOTAL CAPITAL EXPENDITURE (INC ILM) |  |  | 990947 | 9370000 |  | 3238030.62 | 239191.97 | 381674.64 | 3858897.23 | -3503.1 | 3855394.13 | #DIV/0! | 8824630 | #REF! | 0 | 9420000 | 9126000
SALE OF COUNCIL PROPERTY |  | 92 08
Sale of Council Houses |  | 92 08 0100 |  | -3825000 |  |  | 59835.65 |  | 59835.65 | -2425990.1 | -2366154.45 | #DIV/0! | -3825000 |  |  | -3939000 | -4025000 |  |  |  | Latest projections indicate that budgeted sales will be achieved. In addition there is unbudgeted income from sale of shops and disposal of Council's share of shared-ownership of house.
Sale of Council Shops |  | 92 08 0150 |  |  |  |  | 147 |  | 147 | -149979.3 | -149832.3 | #DIV/0! | -150000
Sale of HRA Land |  | 0 |  |  |  | 6: 600; 8: 600; 0 10: 600; 0 10: #DIV/0!
Mortgage Rescue |  | 92 07 |  | 0
99/00 Mortgage Rescue |  | 92 07 0200 | [6 empty] | 0 | -89143.21 | -89143.21 | #DIV/0! | -89000
Homeless Units Upgrading * | 1486 | 0154 |  |  |  | 8: 0; 0 10: 0
Homeless Strategy Broad Street | 2046 | 92 07 0155 |  |  |  | 8: 0; 0 10: 0
|  |  | 0 | -3825000 |  | 0 | 60582.65 | 0 | 60582.65 | -2665112.61 | -2604529.96 | #DIV/0! | -4064000 |  | 0 | -3939000 | -4025000
GRANTS |  |  |  | 0
|  |  | 0 | 0 |  | OK 11: 0 |  | 0 | 0 | 0
NET EXPENDITURE |  |  | 990947 | 5545000 |  | 3238030.62 | 299774.62 | 381674.64 | 3919479.88 | -2668615.71 | 1250864.17 | #DIV/0! | 4760630 | #REF! | 0 | 5481000 | 5101000
Note on A225: 20 Newbiggin St Tullibody removed from contract
Note on A346: This should not come out of HRA budget. If there is any expenditure here, will need to ask JG which budget it is from?
Note on O207: After deducting Warm Deal income.
Note on O424: Covenant payment cash will be £196k. In accounts will be £360k (paid 31/3/04).
Note on O442: Ian Rosie expects to be close to budget - possibly up to £43k additional, but this will come out of Area Improvements budget.

## Sheet1 (hidden)
APPENDIX 1
| 2005/06 Budget Approved on 10 Feb 2005 | Expenditure to 28th Feb | Projected Out-turn for the Year | Variance between projected out-turn & budget | Project Status as at March
HRA Capital Programme 2005/06 |  | Expenditure to 31st July | Projected Out-turn for year | Variance between projected out-turn & budget | Tenders issued/ received | Contractor appointed | Project Start Date | Other Details
Projects |  |  |  | Expend
| £ | £ | £ | £
SCOTTISH HOUSING QUALITY STANDARD
TACKLING SERIOUS DISREPAIR
PRIMARY BUILDING ELEMENTS
Structural Works | 150000 | 85033 | 150000 | 0 | Lintel Replacement tender accepted. Engelen Dr tender accepted | Argyll Street & Whins Rd: Marshall Construction appointed Engelen Dr - Marshall Construction appointed | Lintel replacement now complete | Main projects in this area include asbestos treatment & removal and roof & lintel replacement. 6 roofs at Braehead, Alva replaced this year . Survey and investigations are ongoing for asbestos discovery. Engelen Dr: Work by Marshall Construction completed. Argyle St & Whins Rd work now complete. Chapelle Cr roof work - DLO instructed to do work. Retaining Walls, Backwood Court & Roundelwood - reports from CRA
SECONDARY BUILDING ELEMENTS
Damp/Rot | 30000 | 38038 | 38038 | 8038 |  |  |  | Provision was made at similar level to previous years for treatment/removal of Damp/rot identified during the year. Slightly overspend because of increased damp rot identified.
Roofs / Rainwater / External Walls | 450000 | 421070 | 439000 | -11000 | Tender accepted - Rennie Roofcare for £319k |  | Phase 1 started | Some roofing works have been carried over from last year. Survey of roofs in Carsview area of Tullibody complete & tender issued. Progress meeting with contractors satisfactory. 10 roofs to complete & quality is good. A start has been made on flat roofs inspection. Slight undewrspend reflects retentions to be paid next year.
External Door, etc | 1650000 | 576541 | 1470000 | -180000 | Phase 1 - 25/7/05. Phase 2 - 22/8/05 Phase 3 - Returned Phase 4 - out to tender | Phase 3 - Marshall Const appointed | Site start Late October | Currently working to a fixed programme. Door manufacturers in this year’s contracts are being tendered to provide measuring, supplying and fitting of doors, and also to carry out any associated works required (e.g. replace handrails as necessary, repair steps as necessary etc.) The successful tender is scrutinised closely to compare prices and work standards with last year’s programme. Supply & fit unit costs have reduced by going straight to door manufacturers. Tenants consultation continuing for different phases. Phase 4 contracted with SIDEY - only fees this year.
ENERGY EFFICIENCY
Full/Efficient Central Heating | 1200000 | 345417 | 1010000 | -190000 | Electric Heating - tenders issued. Also tenders issued for term contract and for heating in multifuel areas. Phase 2 - Elec heating tender accepted |  | Phase 1 - Elec heating almost complete Multi Fuel Areas - Contractor appointed & work to start in Dec Phase 2 - Work started beginning Jan | There are 3 phases involved and 158 properties have been identified. As provision of gas supplies have previously caused difficulties, revised application procedures have been negotiated. So far these revised procedures have not proved to be effective. This continues to be a problem despite discussions between Property Services & Transco. As a result gas heating will not be done this year, reflecting a decrease in the out-turn. Tenants have been advised . Procurement will be by standard contract with a term contract also being put in place. The All- Electric Heating programme has been tendered independently of the gas contract.
Thermal Insulation | 250000 | 6345 | 170000 | -80000 | Tender Issued & accepted |  |  | This is rendering in Achray Court. Multi-con properties, Alva - there was a meeting with owners in September. Two-thirds of properties have been sold. Works however are unlikely to start in this financial year, but investigations are continuing. A report was submitted to & approved by Council in Feb., agreeing options associated with this project. Awaiting outcome of grant funding from Community Scotland prior to further approach to owners. Returned tenders indicate 20% higher costs than expected. The project will be spread over two years.
MODERN FACILITIES & SERVICES
Kitchen Renewal | 1650000 | 1077637 | 1780000 | 130000 | Phase 2 (Tillicoultry) - accepted Phase 3 (Alloa) - accepted |  | Phase 1 (Sauchie) - 8/8/05 Bennets - now complete Phase 2 - site start date 27/9/05 Phase 3 - almost complete | Programme approved in April 2003 still being worked through. Noted that quality standard of current kitchen unit supplier (Howdens) is consistently high. Current programme of 450 installations are anticipated this year. Exhibitions have been held for Phase I (Sauchie); tender awarded (value £560K) and for Sauchie and Ashley Terrace, Alloa. The Kitchen Programme required more Property Services resource which has been resolved. The out-turn is higher due to upgraded spec.
Bathroom Survey/Pilot | 50000 | 0 | 30000 | -20000 | Phase 2 - Carsview out to tender in Feb |  | Work to begin in March | Details of properties given to Property Services. Will entail about 25 properties. 10 to be at Craigview phase 2, and remainder linked to kitchen programme in Sauchie/Tillicoultry. Lack of resources within Property Services causing difficulty. Budget may not be spent this year. Pricing schedule to be prepared by Q.S.
| 0 | 0 | 0 | 0
HEALTHY, SAFE & SECURE
Internal Lead Pipework | 15000 | 0 | 2500 | -12500 |  |  |  | This budget is a provision for pipes to be replaced as necessary on inspection at void stage. To date Service has not been informed of any needs.
Safe Electrical Systems | 450000 | 207377 | 386000 | -64000 | Phase 1 tender accepted. |  | Phase 1 now complete | Re-wiring installations which are 20/25 years old will be tackled in an orderly fashion. Addresses have been confirmed & the tender awarded. Coblecrook Garden - 100 properties to be completed by end of March but may overrun to 06/07
Communal Areas (Environmentals) | 250000 | 621 | 250000 | 0 | Craigview Phase 2 tender returned but not acceted yet |  |  | Includes common area lighting etc. and follows on from successful maisonette upgrades last year. This money is earmarked for Phase 2 of the project. Practicalities of getting drawings completed and problems with shortages of resources within Property Services are have delayed projects. Furthermore if projects are not identified within the next few weeks, there will be resources issues within Housing.
NON-SHS ELEMENTS
PARTICULAR NEEDS HOUSING (CITC)
Conversions & Upgrading | 200000 | 4812 | 70000 | -130000 | Contract out to tender |  | Completion in May 2006 | The out-turn is reduced because of difficulties in obtaining suitable alternative accommodation which meets needs of elderly in Curlers Court, Dollar. Programme may not proceed to timescale if suitable accommodation is not found. 2 decant property found but 3 needed
Disabled Adaptations | 200000 | 159742 | 160000 | -40000 |  | 1 external contractor (Tait) appointed |  | Individual projects are taken on as and when needs are identified by both Housing & Social Services Occupational Therapists.
Area Improvements | 100000 | 29702 | 100000 | 0 |  |  |  | Housing Management Operations have identified projects. To date £56k has been committed. Phase 2 - Pine Grove & Earn Court. Another possible area is High Street, Clackmannan but negotiations with owners continues to cause delays. Newmills door entry system to be replaced.
External Lead Pipe Replacement | 200000 | 46614 | 217000 | 17000 | Scottish Water to oversee project |  | Braehead, Alva is now complete. | A programme of works to replace corroded cast iron pipes at Braehead, Alva is complete. A recent survey has highlighted need to replace pipes at various locations thoughout district.A phase of lead pipe replacements in Alloa has commenced . May require to increase this year's budget to ensure that this phase is completed this year.
Demolitions | 150000 | 10565 | 20000 | -130000 |  |  |  | A report was submitted to Council for approval regarding Newmills Phase 2. Reprovisioning and rehousing are still outstanding issues. Land has been sold and work will start in 2006/07
Feasibility Work | 30000 | 19671 | 30000 | 0 |  |  |  | Provision for feasibility studies in relation to all capital projects.
Other Costs | 200000 | 236743 | 250000 | 50000 |  |  |  | The £200k relates to Covenant Repayment, which has already been paid. The £50 is in respect of computer purchase which can be financed by CFCR if required.
TOTAL CAPITAL EXPENDITURE (EXC ILM) | 7225000 | 3265928 | 6572538 | -652462
Plus AS&E ILM Funding | 35000 | 110369 | 35000 | 0 |  |  |  | The project is now complete and the budget of £35k is for retentions. The ERDF money of £108k is an ERDF grant accrual form previous year, which we are expecting to receive this year.
TOTAL CAPITAL EXPENDITURE (INC ILM) | 7260000 | 3376297 | 6607538 | -652462
SALE OF COUNCIL PROPERTY
Sale of Council Houses | -3678000 | -2994734 | -3200000 | 478000 |  |  |  | The projection for the sale of properties is based, amongst other factors, on enquiries and requests received last year. The updated projections indicate a decrease in sales, based on applications already in pipeline. It also takes into account last minute withdrawals. The updated projections show that total no. of sales will decrease from 150 to 117 with corresponding decrease in proceeds. The P&A will be advised of any further variances and the reasons at their next meeting.
Sale of Council Shops |  | -346133 | -346133 | -346133
Mortgage Rescue |  | -43530 | -43530 | -43530
Sale of HRA Land |  | -1365 | -1365 | -1365
| -3678000 | -3385762 | -3591028 | 86972
NET EXPENDITURE | 3582000 | -9465 | 3016510 | -565490

## Ledger Codes
TBC (????) |  | 92 03 4022 | ????
Relocatable Chalet Homes |  | 92 01 0150 | CARE IN THE COMMUNITY | Conversions & Upgradings
Chalet Refurbishment | 1513 | 92 01 0156 | CARE IN THE COMMUNITY | Conversions & Upgradings
House Upgrading 1 School Rd, Muck. | 1504 | 92 01 0157 | CARE IN THE COMMUNITY | Conversions & Upgradings
98/99 Sheltered Housing U/G - MS |  | 92 01 0210 | CARE IN THE COMMUNITY | Conversions & Upgradings
00/01 Sh Housing upgrade Phase 1 | 1651 | 92 01 0211 | CARE IN THE COMMUNITY | Conversions & Upgradings
01/02 Sh Housing u/g Ph 2 | 1755 | 92 01 0213 | CARE IN THE COMMUNITY | Conversions & Upgradings
03/04 Sh Housing u/g Ph 3 |  | 92 01 0214 | CARE IN THE COMMUNITY | Conversions & Upgradings
98/99 Womens Aid | 2010 | 92 01 0401 | CARE IN THE COMMUNITY | Conversions & Upgradings
85 Upper Mill St (Women's Aid) | 1464 | 92 01 0402 | CARE IN THE COMMUNITY | Conversions & Upgradings
Ochil Court | 1822 | 92 01 1822 | CARE IN THE COMMUNITY | Conversions & Upgradings
Alterations to Maree Court Alloa | 1876 | 92 01 1876 | CARE IN THE COMMUNITY | Conversions & Upgradings
Alterations to 40-43 Katrine Court Alloa | 2098 | 92 01 1877 | CARE IN THE COMMUNITY | Conversions & Upgradings
99/00 Sheltered Housing U/G Phase 1 | 1557 |  | CARE IN THE COMMUNITY | Conversions & Upgradings
Aids & Adaptations | 1419 | 92 01 0200 | CARE IN THE COMMUNITY | Disabled Adapt's/Conversions
S.W. Minor Adaptations (Area Teams) | 1035 | 92 01 0201 | CARE IN THE COMMUNITY | Disabled Adapt's/Conversions
00/01 Heating Adaptations |  | 92 01 0202 | CARE IN THE COMMUNITY | Disabled Adapt's/Conversions
03/04 Heating Adaptations | 1882 | 92 01 0203 | CARE IN THE COMMUNITY | Disabled Adapt's/Conversions | no code
2004/05 Central Heating Replacements - Disabled Adaptations | 1977 | 92 01 0204 | CARE IN THE COMMUNITY | Disabled Adapt's/Conversions | no code
27 Garvalley Crescent Alloa - Disabled adaptations | 2101 | 92 01 0205 | CARE IN THE COMMUNITY | Disabled Adapt's/Conversions
Conversions and Extensions | 1661/1721/1610 | 92 01 0707 | CARE IN THE COMMUNITY | Disabled Adapt's/Conversions
|  | 92 01 0807 | CARE IN THE COMMUNITY | Disabled Adapt's/Conversions
Homeless Units Upgrading * | 1486 | 92 07 0154 | CARE IN THE COMMUNITY | Homelessness
Homeless Strategy 19 Broad Street, Alloa | 2046 | 92 07 0155 | CARE IN THE COMMUNITY | Homelessness
99/00 Mortgage Rescue |  | 92 07 0200 | CARE IN THE COMMUNITY | Homelessness
2005/06 Heating Replacements - Phase 1 | 2074(a) | 92 02 0648 | ENERGY EFFICIENCY | Heating
2005/06 Heating Replacements - Phase 2 | 2074(b) | 92 02 0649 | ENERGY EFFICIENCY | Heating
2005/06 Heating Replacements - Phase 3:Various | 2074© | 92 02 0656 | ENERGY EFFICIENCY | Heating
Phase 2 : 2005/06 Electrical Central Heating | 2074 (d) | 92 02 0657 | ENERGY EFFICIENCY | Heating
Damp/Rot Area Teams) |  | 92 02 0200 | ENHANCEMENT | Damp/Rot
Damp/Rot Sundries |  | 92 02 0201 | ENHANCEMENT | Damp/Rot
99/00 Ashley Terrace Ph 1 | 1528} | 92 02 0210 | ENHANCEMENT | Damp/Rot
01/02 Ashley Terrace Ph 2 | 1723} | 92 02 0211 | ENHANCEMENT | Damp/Rot
Lintel renewal Dollar, etc | 1880 | 92 02 0181 | ENHANCEMENT
Elmgrove Home Loss |  | 92 07 0813 | ENVIRONMENTAL IMPROVEMENTS | Demolitions
Elmgrove Demolition | 1791 | 92 07 0814 | ENVIRONMENTAL IMPROVEMENTS | Demolitions
Newmills Demolition | ??? | 92 07 0816 | ENVIRONMENTAL IMPROVEMENTS | Demolitions
Ashgrove Demolition |  | 92 07 0817 | ENVIRONMENTAL IMPROVEMENTS | Demolitions
Door Entry | 1761 | 92 02 0223 | ENVIRONMENTAL IMPROVEMENTS
Door Entry Maintenance 02/04 | 1808 | 92 02 1808 | ENVIRONMENTAL IMPROVEMENTS
Door Entry M/N Term Contract 02/04 |  | 92 02 1808 | ENVIRONMENTAL IMPROVEMENTS
2004/06 Term Contract - Housing Door Entry Maintenance | 1969 | 92 02 1810 | ENVIRONMENTAL IMPROVEMENTS
|  | 92 03 0900 | ENVIRONMENTAL IMPROVEMENTS
99/00 Lock Up's |  | 92 03 1050 | ENVIRONMENTAL IMPROVEMENTS
Close Improvements Backwood Court | 1413 (c) | 92 03 1225 | ENVIRONMENTAL IMPROVEMENTS
Newmills Tullibody Env Door Improvement | 1879 | 92 03 1879 | ENVIRONMENTAL IMPROVEMENTS
Maple Court External Door Entry System | 1878 | 92 03 1878 | ENVIRONMENTAL IMPROVEMENTS
Alloa Area |  | 92 03 2202 | ENVIRONMENTAL IMPROVEMENTS
Alloa Area Improvements 2004-05 |  | 92 03 2302 | ENVIRONMENTAL IMPROVEMENTS
Bowmar Area |  | 92 03 2203 | ENVIRONMENTAL IMPROVEMENTS
Sauchie Area |  | 92 03 2204 | ENVIRONMENTAL IMPROVEMENTS
Clackmannan Area |  | 92 03 2205 | ENVIRONMENTAL IMPROVEMENTS
Alva Area |  | 92 03 2206 | ENVIRONMENTAL IMPROVEMENTS
Tillicoultry Area | 1929(b) | 92 03 2207 | ENVIRONMENTAL IMPROVEMENTS
Alva Area Improvements 2004-05 |  | 92 03 2307 | ENVIRONMENTAL IMPROVEMENTS
2004/05 Area Imp - Bin Stores 12-44b High St Tillicoultry | 2009(a) | 92 03 2307 | ENVIRONMENTAL IMPROVEMENTS
2004/05 Area Improvements - Tillicoultry | 2009(b) | 92 03 2317 | ENVIRONMENTAL IMPROVEMENTS
Tullibody Area | 2009(c ) | 92 03 2208 | ENVIRONMENTAL IMPROVEMENTS
Garage Lighting |  | 92 03 2209 | ENVIRONMENTAL IMPROVEMENTS
General - 2005/06 Area Improvements | 2084 | 92 03 2215 | ENVIRONMENTAL IMPROVEMENTS
2004/05 Area Imp Tullibody |  | 92 03 2308 | ENVIRONMENTAL IMPROVEMENTS
98/99 Env Imps General | 1480/1437 | 92 03 4000 | ENVIRONMENTAL IMPROVEMENTS
98/99 Env Imps Garage Sites | 1481/1655 | 92 03 4001 | ENVIRONMENTAL IMPROVEMENTS
98/99 Env Imps Door Entry Etc | 1482 | 92 03 4002 | ENVIRONMENTAL IMPROVEMENTS
98/99 Env Imps Fencing Works | 1483 | 92 03 4003 | ENVIRONMENTAL IMPROVEMENTS
98/99 Env Imps Back Court Areas | 1484 | 92 03 4004 | ENVIRONMENTAL IMPROVEMENTS
99/00 Stair Lighting |  | 92 03 4005 | ENVIRONMENTAL IMPROVEMENTS
Door Entry | 1665 | 92 03 4006 | ENVIRONMENTAL IMPROVEMENTS
99/00 Earthworks, Eden Rd, Alloa |  | 92 03 4007 | ENVIRONMENTAL IMPROVEMENTS
99/00 CarPark Lighting Menstrie Rd. | 1667/1668 | 92 03 4009 | ENVIRONMENTAL IMPROVEMENTS
01/02 Env Imps Various |  | 92 03 4010 | ENVIRONMENTAL IMPROVEMENTS
Door Entry | 1559/1631/1665 | 92 03 4012 | ENVIRONMENTAL IMPROVEMENTS
|  | 92 03 4017 | ENVIRONMENTAL IMPROVEMENTS
00/01 Env Imps Various | 1559 et al | 92 03 4018 | ENVIRONMENTAL IMPROVEMENTS
Replacement of Retaining Walls - Various Locations | 1961 | 92 02 1961 | ENVIRONMENTAL IMPROVEMENTS
Retaining Wall Alloa Centre | 1995 | 92 02 1962 | ENVIRONMENTAL IMPROVEMENTS
Coalsnaughton - Housing Land | 1954(e) | 92 02 1963 | ENVIRONMENTAL IMPROVEMENTS
Public open spaces - East Alloa Env. Improvements | 1954(g) | 92 02 1964 | ENVIRONMENTAL IMPROVEMENTS
Replace Banking - Delph Pond | 1924 | 92 07 1861 | ENVIRONMENTAL IMPROVEMENTS
SIP ILM |  | 92 07 0904 | ENVIRONMENTAL IMPROVEMENTS - Additional Training Work
General Advice - Architects | 1328 | 92 07 0990 | FEASIBILITY WORK & NEW PROJECTS | Feasibility Work
New Project Contingency |  |  | FEASIBILITY WORK & NEW PROJECTS | Feasibility Work
Standard Delivery Plan |  | 92 07 0995 | FEASIBILITY WORK & NEW PROJECTS | Feasibility Work
98-99 Home Security Doors Phase 1 | 1491(a) | 92 02 0190 | HOME SAFETY | Fear of Crime
98-99 Home Security Doors Phase 2 | 1491(b) | 92 02 0191 | HOME SAFETY | Fear of Crime
98-99 Home Security Doors Phase 3 | 1491(c) | 92 02 0192 | HOME SAFETY | Fear of Crime
98-99 Home Security Doors Phase 4 | 1491(d) | 92 02 0193 | HOME SAFETY | Fear of Crime
99-00 Home Security Doors Phase 1 | 1534(a) | 92 02 0194 | HOME SAFETY | Fear of Crime
99-00 Home Security Doors Phase 2 | 1534(b) | 92 02 0195 | HOME SAFETY | Fear of Crime
99-00 Home Security Doors Phase 3 | 1534(c) | 92 02 0196 | HOME SAFETY | Fear of Crime
99-00 Home Security Doors Phase 4 | 1534(d) | 92 02 0197 | HOME SAFETY | Fear of Crime
99-00 Home Security Doors Phase 5 | 1534(e) | 92 02 0198 | HOME SAFETY | Fear of Crime
99-00 Home Security Doors Phase 6 | 1534(f) | 92 02 0199 | HOME SAFETY | Fear of Crime
99-00 Home Security Doors Phase 7 | 1534(g) | 92 02 0220 | HOME SAFETY | Fear of Crime
99-00 Home Security Doors Phase 8 | 1534(h) | 92 02 0221 | HOME SAFETY | Fear of Crime
Doors General | 1761 | 92 02 0223 | HOME SAFETY | Fear of Crime
01-02 Home Security Doors Phase 1 | 1759 (A/B) | 92 02 0224 | HOME SAFETY | Fear of Crime
01-02 Home Security Doors Phase 2 | 1759 (B) | 92 02 0225 | HOME SAFETY | Fear of Crime
01-02 Home Security Doors Phase 3 | 1759 (C/D) | 92 02 0226 | HOME SAFETY | Fear of Crime
01-02 Home Security Doors Phase 4 | 1759 (D) | 92 02 0227 | HOME SAFETY | Fear of Crime
01-02 Home Security Doors General | 1759 | 92 02 0228 | HOME SAFETY | Fear of Crime
Screens & Windows (Bill Wardrop) |  | 92 02 0229 | HOME SAFETY | Fear of Crime
00-01 Home Security External Lighting | 1616(e) | 92 02 0240 | HOME SAFETY | Fear of Crime
02-03 Doors general | 1820 | 92 02 1820 | HOME SAFETY | Fear of Crime
02-03 Doors Ph 1 | 1820A | 92 02 1821 | HOME SAFETY | Fear of Crime
2004/05 Fear of Crime (Door Replacement) Phase 2 Alva & Cambus | 1950(b) | 92 02 1825 | HOME SAFETY | Fear of Crime
2005/06 Door Improvements - Various | 2011 | 92 02 1829 | HOME SAFETY | Fear of Crime
2005/06 Door Improvements - Phase 1 - Alloa | 2011(a) | 92 02 1833 | HOME SAFETY | Fear of Crime
2005/06 Door Improvements - Phase 2 - Tillicoultry | 2011(b) | 92 02 1834 | HOME SAFETY | Fear of Crime
2005/06 Door Improvements - Phase 3 - Tullibody | 2011(c) | 92 02 1835 | HOME SAFETY | Fear of Crime
Various Home Security - External lights phase 3 | 2011 (f) | 92 02 1836 | HOME SAFETY | Fear of Crime
Various Home Security - Doors Phase 4 | 2011 (g) | 92 02 1837 | HOME SAFETY | Fear of Crime
03-04 Door Replacement Alloa & Clack | 1873 | 92 02 1873 | HOME SAFETY | Fear of Crime
03-04 Door Replacements Phase 1 (Hadden) | 1873(a) | 92 02 1874 | HOME SAFETY | Fear of Crime
03-04 Door Replacements Phase 2 | 1873(b) | 92 02 1876 | HOME SAFETY | Fear of Crime
03-04 Door Replacement Alva | 1873 (c) | 92 02 1875 | HOME SAFETY | Fear of Crime
General - 2006/07 Home Security Door Replacements | 2090 | 92 02 1877 | HOME SAFETY | Fear of Crime
Phase 1 Alloa - 2006/07 Home Security door replacements | 2090(A) | 92 02 1878 | HOME SAFETY | Fear of Crime
Dollar & Tilly - 2006/07 Door Replacements phase 2 | 2090(B) | 92 02 1879 | HOME SAFETY | Fear of Crime
Elmgrove |  |  | HOME SAFETY | Fear of Crime
99/00 Lead Pipe Renewal | 1554 | 92 02 0804 | HOME SAFETY | Lead Pipe Replacement
Lead Pipe Renewal Sundries |  | 92 02 0805 | HOME SAFETY | Lead Pipe Replacement
Water Supply Pipe Renewal | 1717 | 92 02 0806 | HOME SAFETY | Lead Pipe Replacement
2005-09 Lead Pipe Replacement | 2029(A) | 92 02 0501 | HOME SAFETY | Lead Pipe Replacement
47 Hareburn Rd Sound Insulation |  | 92 02 0140 | HOME SAFETY | Upgrading Works
Cavity Wall Insulation - Garden Terrac. |  | 92 02 0141 | HOME SAFETY | Upgrading Works
Substructure Works-Upgrade Dorran Houses Dollar | 1640(a) | 92 02 0146 | HOME SAFETY | Upgrading Works
Structural Condition Report - Dollar (Dorrans) | 1640(b) | 92 02 0142 | HOME SAFETY | Upgrading Works
03/04 Dorrans Upgrade, Dollar (new code) | 1640[c] | 92 02 0143 | HOME SAFETY | Upgrading Works
Structural Investigation - Weir - Alva | 1746 | 92 02 0144 | HOME SAFETY | Upgrading Works
Structural Work Floor replacements/Joists |  | 92 02 0148 | HOME SAFETY | Upgrading Works
Home Safety |  | 92 02 0151 | HOME SAFETY | Upgrading Works
Victim Centered Approach |  | 92 02 0152 | HOME SAFETY | Upgrading Works
97/98 Crime Prevention |  | 92 02 0156 | HOME SAFETY | Upgrading Works
Upgrade 49 Mansfield Avenue |  | 92 02 0158 | HOME SAFETY | Upgrading Works
Lintel Renewal (Alva) | 1524 | 92 02 0160 | HOME SAFETY | Upgrading Works
Stabilisation |  | 92 02 0163 | HOME SAFETY | Upgrading Works
Henderson Ave. Structural | 1489 | 92 02 0164 | HOME SAFETY | Upgrading Works
Upgrading Craigview, Sauchie No 3-21 | 2096 | 92 02 0165 | HOME SAFETY | Upgrading Works
Beams Screen Craigview Sauchie |  | 92 02 0165 | HOME SAFETY | Upgrading Works
30 Windsor Street Menstrie | 1489(a) | 92 02 0166 | HOME SAFETY | Upgrading Works
Garden Wall 46 Earn Ct, Zetland St,etc | 1328 | 92 02 0167 | HOME SAFETY | Upgrading Works
Asbestos Survey Renewal |  | 92 02 0168 | HOME SAFETY | Upgrading Works
Replacement Screens, Sauchie | 1487 | 92 02 0169 | HOME SAFETY | Upgrading Works
Asbestos Works |  | 92 02 0170 | HOME SAFETY | Upgrading Works
Asbestos testing - Term Contract 2004/06 | 1978 | 92 02 0172 | HOME SAFETY | Upgrading Works
General - 2006/09 Asbestos testing - Term contract | 2102 | 92 02 0173 | HOME SAFETY | Upgrading Works
Extension 6 Burnside Crescent Clackmannan | 1836 | 92 02 0183 | HOME SAFETY | Upgrading Works
Demolish 3 + 5 Henderson Avenue |  | 92 02 0301 | HOME SAFETY | Upgrading Works
Mill St, Alloa | 1579 | 92 02 0800 | HOME SAFETY | Upgrading Works
Walkway, Primrose Place, Tilly | 1466 | 92 02 0802 | HOME SAFETY | Upgrading Works
Walkway, High St, Tilly | 1598 | 92 02 0808 | HOME SAFETY | Upgrading Works
Wier Timber Houses Alva |  | 92 02 0809 | HOME SAFETY | Upgrading Works
Porches Rosebank/Holton | 1708 | 92 02 0812 | HOME SAFETY | Upgrading Works
Beam Strengthening Jamieson Gdns | 1799 | 92 02 0811 | HOME SAFETY | Upgrading Works
99/00 Johnston Crescent |  |  | HOME SAFETY | Upgrading Works
99/00 Asbestos Survey/Rem |  |  | HOME SAFETY | Upgrading Works
01/02 Asbestos Survey |  |  | HOME SAFETY | Upgrading Works
Walkway, High St, Tilly | 1677 |  | HOME SAFETY | Upgrading Works
Electrical Enhancement Works Void Properties 2006/07 |  | 92 02 0820 | SAFE ELECTRICAL SYSTEMS
Capitalised Enhancements |  | 92 07 0300 | IMPROVEMENT & ENHANCEMENT | Capitalised Enhancements
00/01 term contract | 1652 |  | IMPROVEMENT & UPGRADE | Heating
Curlers Court, Dollar - 2005/06 Amenity Conversions | 2077 | 92 02 1814 | IMPROVEMENTS | Amenity Conversions
99/00 Heating | 1533(b) | 92 02 0617 | IMPROVEMENTS | Heating
99/00 Heating Phase 2 | 1533(c) | 92 02 0619 | IMPROVEMENTS | Heating
99/00 Heating Phase 1 | 1533(a) | 92 02 0620 | IMPROVEMENTS | Heating
00/01 term contract | 1652 | 92 02 0621 | IMPROVEMENTS | Heating
00/01 Fuel Changeover |  | 92 02 0625 | IMPROVEMENTS | Heating
Fuel Change - Pers Pref |  | 92 02 0625 | IMPROVEMENTS | Heating
00/01 Heating Phase 2 | 1617(b) | 92 02 0626 | IMPROVEMENTS | Heating
Gas Supply |  | 92 02 0627 | IMPROVEMENTS | Heating
00/01 Heating Phase 3 | 1617[c] | 92 02 0629 | IMPROVEMENTS | Heating
00/01 Electric/Gas Conversions |  | 92 02 0630 | IMPROVEMENTS | Heating
01/02 Term Contract | 1758 | 92 02 0631 | IMPROVEMENTS | Heating
Caroline Cres - Alva - Heating Renewal | 1740 | 92 02 0632 | IMPROVEMENTS | Heating
Term Contract | 1816/1 | 92 02 0633 | IMPROVEMENTS | Heating
03/04 Heating Term Contract | 1882 | 92 02 0635 | IMPROVEMENTS | Heating
Heating Safety (new code) |  | 92 02 0634 | IMPROVEMENTS | Heating
Heating Enhancements -Warm Deal Initiative | 1882 | 92 02 0636 | IMPROVEMENTS | Heating
2004/05 Central Heating Replacements - Warm Deal Initiative | 1977 | 92 02 0643 | IMPROVEMENTS | Heating
Gas Link - Mar Policies |  | 92 02 0638 | IMPROVEMENTS | Heating
Gas Safety Incident | 1979 | 92 02 0639 | IMPROVEMENTS | Heating
Heating Appliances |  | 92 02 0640 | IMPROVEMENTS | Heating
2004/05 Heating Replacements - Mar Estate (Remaining) | 1976(a) | 92 02 0641 | IMPROVEMENTS | Heating
2004/05 Heating Replacements - Phase 2 | 1976(b) | 92 02 0644 | IMPROVEMENTS | Heating
Various 2005/07 Central heating term contract | 2035 | 92 02 0660 | IMPROVEMENTS | Heating
2006/07 Central Heating Contract Phase 1 | 2115(a) | 92 02 0662 | IMPROVEMENTS | Heating
Chapelle Crescent 06/07 Central Heating Phase 2 | 2115(b) | 92 02 0663 | IMPROVEMENTS | Heating
General - 2006/07 Electrical re-wiring | 2116 | 92 02 0664 | IMPROVEMENTS | re-wiring
Phase 1 2006/07 Electrical re-wiring | 2116(a) | 92 02 0665 | IMPROVEMENTS | re-wiring
Katrine Court Alloa 2006/07 insulated render | 2117(a) | 92 02 0666 | IMPROVEMENTS | Thermal Insulation
Maree Court Alloa 2006/07 render | 2117(b) | 92 02 0667 | IMPROVEMENTS | Thermal Insulation
Various 2006/07 Communal Improvement | 2124(a) | 92 02 0669 | IMPROVEMENTS | Heating
36-43 Katrine Court Alloa Alterations & Refurbishment | 2130 | 92 02 0670 | IMPROVEMENTS | Heating
2004/05 Electric Central Heating Installation - Various | 1976(c) | 92 02 0645 | IMPROVEMENTS | Heating
Gas Link Monies - Fuel Switch Grant |  | 92 02 0646 | IMPROVEMENTS | Heating
General - 2005/06 Heating Replacements | 2074 | 92 02 0661 | IMPROVEMENTS | Heating
2005/06 Term Contract - Heating Repairs | 2041 | 92 02 1647 | IMPROVEMENTS | Heating
2004/05 Central Heating Replacements - Term Contract | 1977 | 92 02 0642 | IMPROVEMENTS | Heating
Term Ctrct Solid Fuel C/H 02/03 | 1641 | 92 02 1641 | IMPROVEMENTS | Heating
3-21 Craigview, Sauchie - House Letting Initiative Phase 2 | 2078 | 92 02 1815 | IMPROVEMENTS | House Letting Initiative
Bathroom Replacements Various Locations |  | 92 02 1650 | IMPROVEMENTS | Modern Facilities & Services
Sauchie & Tilly - 2005/06 Bathroom Replacement | 2076 | 92 02 1660 | IMPROVEMENTS | Modern Facilities & Services
2006/07 Bathroom Replacements Cambus & Alva | 2128 | 92 02 1661 | IMPROVEMENTS | Modern Facilities & Services
Term Contract - 2006/09 Door Entry Maintenance | 2111 | 92 02 1815 | IMPROVEMENTS | Modern Facilities & Services
New Roof-Window 22 Stirling Street Tillicoultry | 2114 | 92 02 1850 | IMPROVEMENTS | Modern Facilities & Services
97/98 Phase 1 (Hart) | 1372(a) | 92 02 0307 | IMPROVEMENTS | Rewiring
98/99 Phase 1 (Sauchie/Tillicoultry) | 1465(a) | 92 02 0311 | IMPROVEMENTS | Rewiring
Electrical Earth Testing * | 1507 | 92 02 0312 | IMPROVEMENTS | Rewiring
98/99 Phase 2 * | 1465(b) | 92 02 0313 | IMPROVEMENTS | Rewiring
99/00 Electrical Earth Testing | 1573 | 92 02 0314 | IMPROVEMENTS | Rewiring
99/00 Rewiring Phase 1 | 1574(a) | 92 02 0316 | IMPROVEMENTS | Rewiring
99/00 Rewiring Phase 2 | 1574(b) | 92 02 0317 | IMPROVEMENTS | Rewiring
00-01 Electrical Earth Testing | 1642 | 92 02 0318 | IMPROVEMENTS | Rewiring
00-01 Electrical Rewiring | 1694 | 92 02 0319 | IMPROVEMENTS | Rewiring
00-01 Electrical Rewiring Phase 1 | 1694(a) | 92 02 0320 | IMPROVEMENTS | Rewiring
00-01 Electrical Rewiring Phase 2 | 1694(b) | 92 02 0321 | IMPROVEMENTS | Rewiring
01-02 Rewire | 1781(a) | 92 02 0323 | IMPROVEMENTS | Rewiring
00-01 Electrical Rewiring Sundries |  | 92 02 0329 | IMPROVEMENTS | Rewiring
01-02 Electrical inspections | 1756 | 92 02 0330 | IMPROVEMENTS | Rewiring
Phase 1 : 2005/06 Electrical Rewiring | 2083(a) | 92 02 0332 | IMPROVEMENTS | Rewiring
2005/06 Electrical rewiring programme at Various Locations | 2083 | 92 02 0331 | IMPROVEMENTS | Rewiring
03-04 Central Heating & Rewiring - Mar Policies | 1882(a) | 92 02 0637 | IMPROVEMENTS | Rewiring
98/99 Close Lighting |  | 92 02 0950 | IMPROVEMENTS | Rewiring
02-03 Rewiring | 1818 | 92 02 1818 | IMPROVEMENTS | Rewiring
02-03 Electrical Installations | 1838 | 92 02 1838 | IMPROVEMENTS | Rewiring
03-04 Electrical Inspection | 1936 (?) | 92 02 1863 | IMPROVEMENTS | Rewiring
03-04 Electrical Inspection: Various | 1863 | 92 02 1864 | IMPROVEMENTS | Rewiring
2004/05 Electrical Inspections: Alloa | 1938 | 92 02 1866 | IMPROVEMENTS | Rewiring
2005/06 Electrical Inspections - Various | 2055 | 92 02 1867 | IMPROVEMENTS | Rewiring
04-05 Electrical Rewiring Various | 2017(a) | 92 02 1865 | IMPROVEMENTS | Rewiring
98/99 Flat Roofs | 1473 | 92 02 0410 | IMPROVEMENTS | Roofs / Rainwater / Cladding
Flat Roofs Remedial Works |  | 92 02 0411 | IMPROVEMENTS | Roofs / Rainwater / Cladding
01/02 Cruden Roofs | 1777 | 92 02 0412 | IMPROVEMENTS | Roofs / Rainwater / Cladding
00/01 Cruden Roofs | 1523 | 92 02 0415 | IMPROVEMENTS | Roofs / Rainwater / Cladding
99/00 Cruden Roofs | 1622(a)/1632 | 92 02 0416 | IMPROVEMENTS | Roofs / Rainwater / Cladding
98/99 Pitched Roofs | 1490 | 92 02 0426 | IMPROVEMENTS | Roofs / Rainwater / Cladding
99/00 Pitched Roofs Phase 1 | 1526(a) | 92 02 0427 | IMPROVEMENTS | Roofs / Rainwater / Cladding
99/00 Pitched Roofs Phase 2 | 1526(b) | 92 02 0428 | IMPROVEMENTS | Roofs / Rainwater / Cladding
99/00 Pitched Roofs Phase 3 | 1526(c) | 92 02 0429 | IMPROVEMENTS | Roofs / Rainwater / Cladding
100 Gean Rd Re-Inst. Roof | 1644 | 92 02 0430 | IMPROVEMENTS | Roofs / Rainwater / Cladding
00/01 Roof Recladding | 1693 | 92 02 0431 | IMPROVEMENTS | Roofs / Rainwater / Cladding
Maple Court Alloa | 1436 | 92 02 0433 | IMPROVEMENTS | Roofs / Rainwater / Cladding
01-02 Pitched Roofs Phase 1 | 1757 (A) | 92 02 0434 | IMPROVEMENTS | Roofs / Rainwater / Cladding
Chappelle Crescent | 1886 (A) | 92 02 0435 | IMPROVEMENTS | Roofs / Rainwater / Cladding
2002/04 Felt Roofing Term Contract | 1809 | 92 02 0436 | IMPROVEMENTS | Roofs / Rainwater / Cladding
Chapelle Crescent Roofing | 1801 | 92 02 0437 | IMPROVEMENTS | Roofs / Rainwater / Cladding
2003/04 Pitched Roofs Phase 1 Coalsn't'n & Clack | 1932 | 92 02 0438 | IMPROVEMENTS | Roofs / Rainwater / Cladding
2004/05 Pitched Roofs Phase 1; Sauchie | 1992(a) | 92 02 0439 | IMPROVEMENTS | Roofs / Rainwater / Cladding
2004/05 Re-Roofing Phase 2 Sauchie | 1992(b) | 92 02 0440 | IMPROVEMENTS | Roofs / Rainwater / Cladding
2005/06 Re-Roofing Tullibody | 2082 | 92 02 0441 | IMPROVEMENTS | Roofs / Rainwater / Cladding
14-28 Scotland Place, Tilly - Removal of Findlock gutters | 2104 | 92 02 0443 | IMPROVEMENTS | Roofs / Rainwater / Cladding
Term Contract - 2006/09 flat roof repairs | 2110 | 92 02 0444 | IMPROVEMENTS | Roofs / Rainwater / Cladding
2006/07 Pitched Roof Replacements Phase 1 | 2129(a) | 92 02 0445 | IMPROVEMENTS | Roofs / Rainwater / Cladding
2006/07 Pitched Roof Replacements Fascia Repairs | 2129(b) | 92 02 0446 | IMPROVEMENTS | Roofs / Rainwater / Cladding
99/00 Cambus | 1320 | 92 02 0453 | IMPROVEMENTS | Roofs / Rainwater / Cladding
97/98 Cladding Ash Grove E/E | 1442 | 92 02 0455 | IMPROVEMENTS | Roofs / Rainwater / Cladding
Remedial Render High St Tilly * | 1469 | 92 02 0457 | IMPROVEMENTS | Roofs / Rainwater / Cladding
Insulation of No Fines Mar Estate | 1686 | 92 02 0459 | IMPROVEMENTS | Roofs / Rainwater / Cladding
Argyle Place, Alloa - replacement rainwater goods | 2072 | 92 02 0470 | IMPROVEMENTS | Roofs / Rainwater / Cladding
No - fines houses insulated render | 2075 | 92 02 0471 | IMPROVEMENTS | Roofs / Rainwater / Cladding
Achray Court, Alloa - insulated render to no-fines Hse. Phase 1 | 2075(A) | 92 02 0472 | IMPROVEMENTS | Roofs / Rainwater / Cladding
Alloa & Tullibody 1994/95 pitched roofs | A/1238 | 92 02 0473 | IMPROVEMENTS | Roofs / Rainwater / Cladding
Hareburn Rd Phase 2 Rend/Roofs |  | 92 02 0465 | IMPROVEMENTS | Roofs / Rainwater / Cladding
01/02Maple Court Alloa (re-render) | 1751 | 92 02 0810 | IMPROVEMENTS | Roofs / Rainwater / Cladding
Re-rendering at Clackmannan & Cambus | 1925 | 92 02 0813 | IMPROVEMENTS | Roofs / Rainwater / Cladding
99/00 Maple Court | 1436 | 92 02 0904 | IMPROVEMENTS | Roofs / Rainwater / Cladding
02/03 Re-roofing | 1817 | 92 02 1817 | IMPROVEMENTS | Roofs / Rainwater / Cladding
03/04 Re-roofing | 1817(a) | 92 02 1809 | IMPROVEMENTS | Roofs / Rainwater / Cladding
2004/06 Flat Roof Improvements | 1968 | 92 02 1811 | IMPROVEMENTS | Roofs / Rainwater / Cladding
Braehead, Alva - Roof Repairs | 2067 | 92 02 1812 | IMPROVEMENTS | Roofs / Rainwater / Cladding
25-31 Moir St Alloa - Replacement Lintols | 2071 | 92 02 1813 | IMPROVEMENTS | Roofs / Rainwater / Cladding
98/99 Maple Court |  | 92 02 0904 | IMPROVEMENTS | Windows
98/99 New Spend | 1479 | 92 02 0905 | IMPROVEMENTS | Windows
99/00 Window Replacements |  | 92 02 0906 | IMPROVEMENTS | Windows
Ashley Terrace |  | 92 02 1831 | IMPROVEMENTS | Windows
Rem Works at Clackmannan | 2097 | 92 02 0417 | IMPROVEMENTS
2005/08 Term Contract - Floor Coverings | 2043 | 92 02 0710 | INSULATION??? | Floor Coverings
New Spend | 1760 | 92 02 0230 | KITCHENS ETC.
02/03 Kitchens Ph 1 | 1819 | 92 02 1819 | KITCHENS ETC.
02/03 Kitchens Ph 2 | 1819(a) | 92 02 1822 | KITCHENS ETC.
03/04 Kitchen replacement Ph 1 Tullibody | 1895(a) | 92 02 1823 | KITCHENS ETC.
04/05 Kitchen Replacements - Various | 1949 | 92 02 1824 | KITCHENS ETC.
04/05 Kitchen replacement at Tullibody | 1949(a) | 92 02 1826 | KITCHENS ETC.
04/05 Kitchen replacement Phase 2 - Sauchie | 1949(b) | 92 02 1827 | KITCHENS ETC.
04/05 Kitchen replacement Phase 3 | 1949(c) | 92 02 1830 | KITCHENS ETC.
2004/05 Kitchen Replacements - Term Contract | 2012 | 92 02 1843 | KITCHENS ETC.
2005/06 Kitchen Replacements - various | 2006 | 92 02 1840 | KITCHENS ETC.
2005/06 Kitchen Replacements - Phase 1 Sauchie | 2006(a) | 92 02 1841 | KITCHENS ETC.
2005/06 Kitchen Replacements - Phase 2 Tillicoultry | 2006(b) | 92 02 1842 | KITCHENS ETC.
2005/06 Kitchen Replacements - Phase 3 Alloa | 2006© | 92 02 1845 | KITCHENS ETC.
General - 2006/07 Kitchen replacements | 2100(a) | 92 02 1846 | KITCHENS ETC.
Phase 2 - 2006/07 Kitchen Replacements | 2100(b) | 92 02 1847 | KITCHENS ETC.
Phase 3 - 2006/07 Kitchen Replacements | 2100© | 92 02 1848 | KITCHENS ETC.
Phase 4 - 2006/07 Kitchen Replacements | 2100(d) | 92 02 1849 | KITCHENS ETC.
Conversions and Extensions |  |  | Main Heading | Subheading
OT Salaries |  | 92 01 0100 | OTHER COSTS AND PROJECTS
Capital Programme Officer |  | 92 02 0100 | OTHER COSTS AND PROJECTS
Senior Capital Program Officer |  | 92 02 0101 | OTHER COSTS AND PROJECTS
Kersegreen Clacks |  | 92 03 0400 | OTHER COSTS AND PROJECTS
Local Housing Strategy Funding (new code) |  | 92 07 0230 | OTHER COSTS AND PROJECTS
Right to Compensation |  | 92 07 0250 | OTHER COSTS AND PROJECTS
Computer Equipment * |  | 92 07 0350 | OTHER COSTS AND PROJECTS
Purchase of Transit Van |  | 92 07 0610 | OTHER COSTS AND PROJECTS
Covenant Repayment |  | 92 07 0650 | OTHER COSTS AND PROJECTS
Computer Equipment * |  | 92 07 0750 | OTHER COSTS AND PROJECTS
Insurance Claims Shortfall |  | 92 07 0805 | OTHER COSTS AND PROJECTS
Option Appraisal Elm Grove |  | 92 07 0806 | OTHER COSTS AND PROJECTS
SIMCO |  | 92 07 0809 | OTHER COSTS AND PROJECTS
Coop Drysdale Street |  | 92 07 0810 | OTHER COSTS AND PROJECTS
Posthill |  | 92 07 0811 | OTHER COSTS AND PROJECTS
Homelessness |  | 92 07 0812 | OTHER COSTS AND PROJECTS
Homelessness Strat Broad Street | 2046 | 92 07 0155 | OTHER COSTS AND PROJECTS
Office Moves - Clacks |  | 92 07 0830 | OTHER COSTS AND PROJECTS
49 Chapelle Cresc Tilly |  | 92 07 0831 | OTHER COSTS AND PROJECTS
30 Lomond Court Alloa. Purchased by Council-email S Norris 23/6/04 (to be recharged to future owners at 04/05 y/e) |  | 92 07 0832 | OTHER COSTS AND PROJECTS
Kilncraigs Relocation of Housing |  | 92 07 0840 | OTHER COSTS AND PROJECTS
Scottish Quality Standard |  | 92 07 0991 | OTHER COSTS AND PROJECTS
Professional Fees |  | 92 07 0992 | OTHER COSTS AND PROJECTS
SHQS/Stock options 2004 | ??? | 92 07 0993 | OTHER COSTS AND PROJECTS
Newmills - Demolish Wall |  | 92 07 1811 | OTHER COSTS AND PROJECTS
Retaining Wall _ Deerpark | 1860 | 92 07 1860 | OTHER COSTS AND PROJECTS
Walled Garden, Orchard Project, Alloa |  | 92 07 0815 | OTHER COSTS AND PROJECTS
Staff Costs - Sale of Council Property | 3000 | 92 08 0100 | OTHER COSTS AND PROJECTS
Housing Needs/Staff Resources |  |  | OTHER COSTS AND PROJECTS
Underpinning at Engelen Drive | 2093 | 92 02 1880 | PRIMARY BUILDING ELEMENTS | Structural Works
Lock Ups - Murray Place Dollar |  | 92 02 1890 | PRIMARY BUILDING ELEMENTS | Structural Works
Demolition of Garages Murray Place & West Burnside Dollar | 1933 | 92 02 1891 | PRIMARY BUILDING ELEMENTS | Structural Works
Chapelle Crescent Tillicoultry - Roof Trusses |  | 92 02 1895 | PRIMARY BUILDING ELEMENTS | Structural Works
Structural Work Fairfield Sauchie | 2122 | 92 02 1896 | PRIMARY BUILDING ELEMENTS | Structural Works
Various- Inspection of non-trad. Houses | 2122 | 92 02 0668 | IMPROVEMENTS | Structural Works
Sale of Council Houses |  | 92 08 0100 | SALE OF COUNCIL PROPERTY
Sale of Council Shops |  | 92 08 0150 | SALE OF COUNCIL PROPERTY
Sale of HRA Land |  | 92 08 0200 | SALE OF COUNCIL PROPERTY
2004/05 Door Replacement - Phase 1 - Alva | 1950(a) | 92 02 1828 | SECONDARY BUILDING ELEMENTS | External Doors etc
2005/06 Re-Roofing Main Street Sauchie |  | 92 02 0442 | SECONDARY BUILDING ELEMENTS | Roofs / Rainwater / External Walls
SIP ILM |  | 92 07 0900 | SIP
SIP |  | 92 07 0901 | SIP
Community Police Office |  | 92 08 0403 | SIP
LADA Centre | 1597 | 92 08 0404 | SIP
Scottish Enterprise |  | 92 08 0902 | SIP
New Deal |  | 92 08 0903 | SIP
ESF |  | 92 08 0904 | SIP
2005/06 Home Security - External Lights | 2011(d) | 92 02 1832
Server Renewal |  | 92 07 0841
Scottish Enterprise |  | 92 07 0902
ERDF |  | 92 07 0905
Note on A12: New code 2/10/03. Should go to 7302-0084, David Newlands, Alloa SIP Office, Candleriggs. All coding now corrected, GL0974 & inv sent to David Newlands.
Note on A42: Code seet up 5/5/04
Note on A154: Code set up 8/10/03 - £29201 total budgeted spend
Note on A249: Set up 1/11/04
Note on B57: Not sure if this code relates to Tilli and ledger code