# CLACKMANNANSHIRE COUNCIL

REPORT TO: 	THE PERFORMANCE & AUDIT COMMITTEE MEETING ON 22ND FEBRUARY 2007

SUBJECT: 	HOUSING CAPITAL PROGRAMME: 2006/07 DECEMBER OUT-TURN AND 3 YEAR SUMMARY TO 2008/09.

## PREPARED BY: 	KISH PARMAR, PRINCIPAL ACCOUNTANT & SHEELAGH NORRIS, POLICY PLANNING MANAGER, HOUSING SERVICES

- Summary

  - This report presents an update on the Housing Capital Programme for 2006/07 as at December 2006, together with a summary of the budgets for 2007/08 and 2008/09. This monitoring report concentrates on the progress in projects and highlights any significant changes to the position previously reported.

  - The table below summarises the capital borrowing requirement for the three years to 2008/09 and shows changes to approved budgets:

| £’000 | 2006/07 Approved Budget (Council Report 9th Feb 2006 | 2006/07 As per Mid Year Report |  | 2006/07 Out Turn as at Dec 2006 | 2007/08 Proposed Budget (Report to Council on 8th Feb 2007) | 2008/09 Proposed Budget (Report to Council on 8th Feb 2007 | Total for 3 years |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Gross Expenditure | 9,370 | 9,370 |  | 8,350 | 9,510 | 8,665 | 26,525 |
| Approved budgets brought forward from 05/06 as per Mid Year Report |  | 225 |  | 394 |  |  | 394 |
| Capital Receipts | (3,825) | (4,064) |  | (4,064) | (3,939) | (4,025) | (12,028) |
| Net expenditure (Council borrowing) | 5,545 | 5,531 |  | 4,680 | 5,571 | 4,640 | 14,891 |
| Gross Expenditure Variance from Approved 06/07 budget |  | 235 2.5% |  | (626) (6.7%) |  |  |  |
| Gross Expenditure Variance from Mid Year figures |  |  |  | (851) (8.9%) |  |  |  |

- Recommendation

  - The Committee is asked to note the financial position and the borrowing requirement for Housing capital programme for the three years to 2008/09.

- BACKGROUND

  - A report reviewing the mid year position of the Housing Capital Programme for 2006/07 was presented to the Council meeting of 19th October 2006. The Council approved the mid year adjustments proposed in that report which showed projected gross expenditure of £9,595k, including £225k of approved budget carried over from 2005/06 (an increase of 2.5% from the budgeted position). The projected capital receipts of £3,825k from Right to Buy sales were expected to remain as budgeted. However, this would be augmented by receipts of £239k from sale of land/property held on the HRA, thereby reducing the net borrowing requirement for 2006/07 to £5,531k.

  - The current anticipated expenditure for 06/07 is £8,744k which is a decrease of £851k (8.9%) compared to the projected gross expenditure as per the Mid Year report. It is a slight decrease of £81k to the out-turn reported in the previous report  The main variances in the current period are as follows:

- External Doors:    Problems in one of the contracts may delay the programme slightly. Balance of budget will be carried forward

- Bathrooms:    Lack of central suitable venue to hold tenants meeting, meant delays in site start. Any unutilised budget will have to be carried forward

- Disabled adaptations: Out-turn increased by £100k. There was an error in the  out-turn reported in the previous report. The error was highlighted to the members by a verbal report.

- External Lead Pipe Replacement: The out-turn of £429k includes a payment of £169k to Scottish Water which relates to previous year. It is proposed that this be funded by bringing forward the appropriate unspent budget from 05/06. The current year’s budget will be used in 06/07 with any advance payments to Scottish Water accrued to 07/08

  - The latest outturn does not show any projected changes to capital receipts since the mid year report. The net expenditure (Council Borrowing) is expected to be £4,680k

  - It should be emphasised that the above projection for 2006/07 is subject to a number of important qualifications and explanations that were set out in the Mid Year report to the Council.

  - A report proposing the 3-year Housing Capital programme from 2007/08 to 2009/10 was presented to the Council at the Special Council meeting on 8th February 2007. The report recommended that the Council approve the budget for 2007/08, with officers to bring forward more detailed proposals when available.  The 3-year capital programme proposals take into account the Council’s progress towards meeting the SHQS and work towards completion of kitchen and bathroom replacement programme for all tenants.

  - Appendix 1 shows actual expenditure against budget for 2006/07 with details of possible budgets to be carried over from 2005/06 to 2006/07.  Column 16 shows the current status of the main projects.

  - In the last report members were advised that, where appropriate, Housing Services will seek approval to carry forward unused budgets from 2005/06 to 2006/07, to be added to the budgets already approved by the Council for 2006/07 in  order to complete the projects. The mid year report requested a carry forward of £225k. The current projections indicate that a further carry forward of £169k of unutilised budget for External Lead Pipe Replacement will be required.

- CONCLUSION

  - The current projections indicate that, while there are both adverse and favourable variances in several projects, there is a slight decrease overall in the net expenditure & borrowing requirement for 2006/07 compared to the out-turn reported in the last report. The projected the borrowing of £4,680k is about 15% lower compared to the mid year position.

  - The 3 year budgets for 2007/08 to 2009/10 presented to Council takes account of the SHQS and ‘Clackmannanshire Standard’. The net borrowing requirement for the total of three years to 2008/09 shows a decrease of £452k, principally due to a reduced proposed budget for 2008/09. This is consistent with the Business Plan to deliver the SHQS and ‘Clackmannanshire Standard’ in consultation with the Council’s tenants and their advisors.

- SUSTAINABILITY IMPLICATIONS

Not applicable to monitoring reports

- IMPLICATIONS FOR COUNCIL

- 6.1	Financial implications:	As noted in the report.

- 6.2	Staff implications:	None

| - Declarations - The recommendations contained within this report support or implement Corporate Priorities, Council policies and/or the Community Plan: Corporate Priorities  Council Policies  Community Plan  - In adopting the recommendations contained in this report the Council is acting within its legal powers  - The full financial implications of the recommendations contained in this report are set out in the report. This includes a reference to full life cycle costs where appropriate  |  |
| --- | --- |

___________________________________________________________

Director of Corporate Development

___________________________________________________________

Head of Finance

Report to Performance  & Audit Committee

To accompany all Reports to Performance & Audit Committee Meetings

# To: Head of Administration Services

| Author: |  | Kish Parmar, Principal Accountant |  |  | Date: | 5 January 2007 |
| --- | --- | --- | --- | --- | --- | --- |
| Service: |  | Corporate Development |  |  |  |  |
| Date of Meeting: |  | 22 February 2007 |  |  |  |  |
| Title of Report: |  | HOUSING CAPITAL PROGRAMME: 2006/07 DECEMBER OUT-TURN AND 3 YEAR SUMMARY TO 2008/09. |  |  |  |  |
| Recommendation that the attached report be: |  |  |  |  |  |  |
| 1. Given unrestricted circulation |  |  |  | (tick appropriate box) |  |  |
| 2. Taken in private |  |  |  |  |  |  |
| By virtue of paragraph of schedule 7A, Local Government (Scotland) Act 1973. |  |  |  |  |  |  |
| Appendices attached to this report (if none, state “none”) |  |  |  |  |  |  |
| 1. | Appendix 1 : Housing Capital Programme 2006/07 to 2008/09 Budget; Actual & Out-Turn for 2006/07 |  |  |  |  |  |

| List of Background Papers (if none, state “none”) |  |
| --- | --- |
| 1 | “Housing Revenue Budget 2006/07 and Capital Programme 2006/07 to 2008/09” presented to the Council meeting on 9th February 2006 |
| 2 | “Housing Capital Programme 2005/06: Draft Final Position” presented to the Performance & Audit Committee Meeting on 15th June 2006 |
| 3 | “Housing Capital Programme: 2006/07 November Out-Turn and 3 Year Summary to 2008/09” presented to Performance & Audit Committee Meeting on 25th January 2007 |
| 4 | Housing (HRA) Capital Programme 2006/07 – Mid Year Review (5 months) presented to Council meeting on 19th October 2006 |
|  | Note: All documents specified must be kept available by the author for public inspection for four years from the date of the meeting at which the report is considered. |