## Mar07
Clackmannanshire Community Safety Partnership: Antisocial Behaviour Strategy Progress Report
Area of activity | Description | Contact | Current status | Comments/ Issues
Implementation of the ASB Act: measures
Antisocial Behaviour Orders (ASBOs) | Preventative orders to protect victims of ASB and the wider community from further acts of antisocial behaviour. | Janice McCrum - Council/ Legal Services; Stuart McQueen - Council/ CALM Team | 5 interim and 3 full ASBOs currently in force
ASBOs on conviction | Establishment of working practices between Sheriffs/ PF and Legal Services for sentencing option of and ASBO on conviction | Janice McCrum - Council/ Legal Services; Stuart McQueen - Council/ CALM Team | None in place locally; joint working on development of local process has begun. | Feedback from the Scot Exec that Crown Office and the Court Service are currrently in discussion re. responsibilities and guidance for criminal ASBOs
ASB Notices (ABNs) (Part 7) | Administering notices | Ian Doctor | None currently in force. See also below.
Registration of Private Landlords (Part 8) | Part 7 & 8 of ASB Act require registration of all private landlords in the Council area | Ian Doctor - Council Environmental Health | Grant allocation to be directed towards engagement of Officer to deal with registration and enfocement of Parts 7 & 8. Approvals to be sought for such use of grant.
Acceptable Behaviour Contracts (ABCs) | Establishment of procedures to implement ABCs | Stuart McQueen - Council CALM Team | Police and CALM team have agreed a draft process for dealing with Youth ASB which includes utilising ABC's. To be presented to Education, Youth Services and Social Work at the next YJRAG meeting on 20th February
Parenting Orders | Establishment of procedures and provision for Parenting Orders | Council Child Care | Preventative family support in place; framework for potential orders established. | There is no current use of Parenting Orders in Scotland
Central Register of ASBOs | Establishment and maintenance of a central register of all ASBOs issued in the Clacks area | Stuart McQueen - Council CALM Team | Register established
Graffiti removal notices | Establishment of procudures for enforcement of graffiti removal under Act | Ewart McAuslane - Council Environmental Services | Trial of graffiti identfication and removal system linked to the LEAMS streetcare outputs underway; will be reviewed before a position is taken on graffiti removal enforcement.
Fixed Penalty Notices for Littering, Fly-tipping, Dog-fouling | Establishment of procedures for issuing FPNs by Council employees for litter, fly-tipping & dog fouling | Ewart McAuslane - litter & fly-tipping; Ian Doctor - dog fouling | Notices for dog-fouling in place. | Procedures will be modified to allow for fly-tipping and littering enforcement
Ban on selling spray paint to U16s | Procedures for enforcement | Trading Standards | Complete | Enforcement issue similar to other legislative enforcement by Trading Standards (eg. sale of cigarettes to minors).
Restriction of Liberty Orders: extension to U16s | Preparation of procedures and processes for RLOs | Council Criminal Justice & Child Care | None in place locally | Only 4 used in period up to September 2006: Dundee, Glasgow, Kilmarnock
Supervision requirements - conditions restricting movements | Establishment of Intensive Support and Monitoring Services to provide this provision | Council Child Care | None in place locally | Subject of pilot elsewhere - awaiting evaluation
Community Reparation Orders: new orders for people aged 12 or over | Preparation of procedures and processes for CROs | Council Criminal Justice | None in place locally | Subject of pilot in specific areas: Dundee, Highland, Inverclyde.
Dispersal of Groups | Establishment of procedures allowing enforcement of legislation complete | Sgt. Neil Wilson - Central Scotland Police | Dispersal Order enforced in Sauchie at end of 2006. | Report to Community Safety Partnership in February.
Closure of premises | Establishment of procedures allowing enforcement of legislation complete | Sgt. Neil Wilson - Central Scotland Police | None in place locally
Seizure of vehicles | Establishment of procedures allowing enforcement of legislation complete | Sgt. Neil Wilson - Central Scotland Police | Warnings issued 29 Vehicles seized 1 Failed to stop 1
Fixed Penalty Notices for minor crime | Procedures for enforcement of FPNs for a number of minor crimes | Sgt. Neil Wilson - Central Scotland Police | Evaluation of pilot in Tayside to be rolled out across Scotland. Central Scotland procedures in development
Other supporting areas of work
Information sharing | Protocol covering agencies in Forth Valley allowing exchange of information in relation to ASB under Section 139 of the Act | Sgt. Neil Wilson - Central Scotland Police | Final approval from main signatories in September 2006; currently being circulated to Registered Social Landlords for consideration.
Forth Valley GIS Information Sharing Project | Proposal to develop tri-council and police electronic GIS based information system to be applied to ASB | Douglas Ralph | Funding for project granted from COSLA Innovation Fund. First meeting of the project board held in January 2007. | Current development on the estate management module will use the intergrated software application of the GIS project.
Problem Solving Training | Training in identification and dealing with the root cause(s) of problems | Christine MacLean | 40 people now trained in problem solving techniques; approaches being implemented via the ASB Operational Group | Funding from the Scot Exec will allow a further round of training after April 2007. Further training options are also currently being investigated.
Training to deal with ASB complaints | Procedures and skills for dealing with complaints. | Douglas Ralph | 7 Community & 4 Estate Wardens trained; estate management module training scheduled for March 2007; will include all Housing Officers
Trained mediators across the Partnership | Staff with mediation skills to address ASB issues. | Karen Hay - Council CALM Team | 14 mediators trained and operational
Noise complaints addressed via the Professional Mediation Scheme | Noise complaints referred and dealt with via scheme | Karen Hay - Council CALM Team | In year 06-07 (to date) 19 mediation cases referred. Of these 5 reached agreement;12 resulted in one or more parties choosing to withdraw; 1 where the mediator deemed mediation not appropriate; 1 currently ongoing.
Incorporating crime prevention through environmental design principles into new private housing developments | New developments adhere to secure by design principles. | PCs John Baxter & Craig Rankine - Central Scotland Police | All Ochilview Housing Association properties are compliant. Presentation made to Council Planning Department in January 2007; relationship to be developed further.
Providing support to victims of ASB | Referral systems/ Reassurance visits | Sgt. Billy Drummond - Central Scotland Police Douglas Ralph | Police and ASB Team both have referral mechanisms to Victim Support for victims of ASB.
Implementation of strategy: key roles
Community Safety Partnership | Community Planning Theme Team: strategic lead on ASB | Chair: Supt Gavin Buist - Central Scotland Police | Partnership meets quarterly; ASB reports from Policy Exec & Operational Groups | Longer term view to combined Community Safety/ ASB strategy: to be confirmed
ASB Policy Group | ASB policy & strategy review; monitoring Outcome Agreement | Chair: Elaine McPherson - Council Strategic Policy | Has been meeting quarterly following Partnership to progress policy issues. | Agreed 20th Feb that will in future meet prior to Partnership to better inform decision making at Theme Team level.
ASB Operational Group | Coordinating implemetation of ASB strategy; lead on multi-agency problem solving | Chair: Douglas Ralph - ASB Co-ordinator | Monthly meetings now established following Central Scotland Police Tactical Tasking and Co-ordinating Group; information sharing and problem solving approaches are bedding in. Recent joint working through the Operational Group has resulted in the granting of one full and one interim ASBO relating to individuals in dwelling houses which have been acting as magnets for ASB. | Membership of the Operational Group will be kept under review with additional membership sought from eg. Housing Management & Social Services. The core membership will be supplemented where this is necessary according to the issues in hand.
ASB Outcome Agreement (OA) | Links outcomes in strategy to Scot Exec funding for ASB | Christine MacLean - Council Strategic Policy | Revised OA accepted by Scot Exec in late 2006. Now more focused on dedicated funding stream. Funding for 2007 - 08 confirmed. | Annual report for 2006 - 2007 due April 30th.
Noise Investigation Team | Establishment of Joint Clacks & Stirling Noise Investigation Team through Scot Exec Part 5 funding | Ian Doctor - Council Environmental Health | Staff recruited and joint team established. Protocols established between Stirling Council Call Centre & Central Scotland Police Control Centre | Two main challenges face the team: 1) Raising the public awareness of the service they provide and 2) to be satisfied that the resolution adopting the Part 5 powers covers the periods when most noise problems are occuring
Joint ASB Team: Community Wardens & Police Officers | Community Wardens working alongside dedicated Community Police Officers | Douglas Ralph | 1 Supervisor; 6 Community Wardens; 1 Environmental Link Warden posts. Patrols cover all areas in Clacks. Main focus is community safety/ wellbeing; youth issues; noise; dog fouling & fly-tipping | 1 Warden post presently vacant; resource based on short-term funding to end in March 2008. Work ongoing to look at sustainability.
ASB Analyst | Appointment of Analyst to support Community Safety Partnership | Sgt. Billy Drummond - Central Scotland Police | Analyst took up post in July 2006. Problem profiles for Sauchie & Tillicoultry completed; intelligence gathered prior to and during Dispersal Order in Sauchie. Providing ongoing support to Operational Group in identifying emerging problems: a monthy priority report is circualted prior to meetings of the group. Specialist profiles also being made available such as one on vandalism in Alva. | Current intelligence based on Police Systems. Need to facilitate access to Council held information - this is being progressed under supervision of the ASB Policy Group. Some progress has been made. Tasking process for the Analyst will be agreed this month.
CALM Team | Deals with most complex cases of ASB | Douglas Ralph | Ongoing key role in strategy implementation and membership of Operational Group. | Two posts currently vacant; steps to fill are in process; see below for figures on cases addressed via Professional Mediation Scheme