APPENDIX 3: DEVELOPMENT & ENVIRONMENTAL SERVICES SERVICE PLAN PROGRESS REPORT - SUMMARY

| ### Target Outcome | No. of targets 2007-08 | Complete / Good progress – on track | Running behind | Unlikely to complete | ### Comments |
| --- | --- | --- | --- | --- | --- |
| PROPERTY SERVICES |  |  |  |  |  |
| Provide Improved Asset Management | 4 | 75% | 25% | 0% | A slight delay in the process has been caused by the decision of the new Council to form a working group to take forward any proposals for asset management. |
| Deliver HRA Capital Improvements | 12 | 100% | 0% | 0% | Good progress |
| Deliver General Services Capital Programme for Services to People | 3 | 67% | 33% | 0% | Delayed pending outcome of AMP working group. |
| Deliver General Services Capital Programme for Development and Environmental Services | 8 | 63% | 38% | 0% | Some roads projects have been delayed due to failure to recruit a replacement design engineer. This has now been addressed. |
| Deliver General Services Capital Programme for Corporate Development and Chief Executives | 1 | 100% | 0% | 0% | Good progress |
| Develop internal processes to provide improved services | 9 | 89% | 0% | 11% | Proposals for the current structure of the roads service are being reviewed. This has changed the need to undertake some targets. |
| Improved Environmental Management | 2 | 100% | 0% | 0% | Good progress |
| #### DEVELOPMENT SERVICES |  |  |  |  |  |
| Deliver efficient, modernised Development Quality and Building standards Services | 5 | 100% | 0% | 0% | Achieving two of the remaining four tasks is dependant upon actions or decisions by the Scottish Government and therefore not wholly in control of the service. Work is going in order to achieve the other two targets. |
| Deliver efficient, modernised Roads and Transportation Service. | 11 | 82% | 18% | 0% | Achievement of some targets has been affected by changed priorities in the Capital Programme, staffing issues and issues not wholly within the control of the service. |

| ### Target Outcome | No. of targets 2007-08 | Complete / Good progress – on track | Running behind | Unlikely to complete | ### Comments |
| --- | --- | --- | --- | --- | --- |
| ENVIRONMENTAL SERVICES |  |  |  |  |  |
| Improve the health and life expectancy of the people of Clackmannanshire through Environmental improvements | 8 | 75% | 25% | 0% | Good Progress to Date |
| Provide improved Trading Standards Operation | 1 | 100% | 0% | 0% | Joint Working with Stirling continuing to give improved performance and responsiveness |
| Develop internal processes to provide improved services | 4 | 75% | 25% | 0% | Satisfactory Progress |
| Provide an improved Land Services operation | 2 | 50% | 50% | 0% | Performance in the year to date good. Pressure to be put on consultant to complete the Cemetery strategy draft. |
| Provide an Improved Waste management and Recycling Service | 8 | 50% | 38% | 13% | In absence of Scottish Executive input in-house team are concentrating on changes to routing and work balance aimed at reducing the financial overspends. Recycling rates continue to be excellent. |
| STRATEGY & SUPPORT SERVICES |  |  |  |  |  |
| Optimise use of Information technology | 7 | 71% | 29% | 0% | Good progress despite staff vacancies. |
| Support service improvement initiatives throughout Development and Environmental Services | 5 | 100% | 0% | 0% | Progress includes improved methods of customer consultation and staff absence monitoring. |
| High quality sustainable development | 12 | 92% | 8% | 0% | Progress on development plans, economic development and sustainability initiatives all on schedule. |
| ###### Total / Average | 102 | 81% | 17% | 2% |  |