CHIEF EXECUTIVE’S SERVICE PLAN PROGRESS REPORT:

SUMMARY

| ### Target Outcome | No. of targets 2007-08 | Complete / Good progress – on track | Running behind | Unlikely to complete | ### Comments |
| --- | --- | --- | --- | --- | --- |
| #### Strategic Policy |  |  |  |  |  |
| Effective external and internal strategic partnerships which meet the Council’s and its partners’ strategic objectives | 9 | 100% | 0% | 0% | Very good progress has been made in taking forward community planning and associated issues. Partnerships are maturing and evolving well. |
| Improved communications and information management | 4 | 50% | 50% | 0% | The loss of 2 key managers has limited progress in meeting these actions. There have also been recruitment difficulties for both posts which has compounded this. |
| Socio-economic regeneration of Clackmannanshire and its most deprived communities | 5 | 100% | 0% | 0% | The various programmes continue to be managed efficiently and effectively. Work has begun on the wind-up of these programmes since funding ceases in 2008. |
| #### Administration & Legal Services |  |  |  |  |  |
| Good standards of corporate governance are in place in respect of all Council activity | 10 | 80% | 20% | 0% | Progress overall has been very good. However, additional work on the Scheme of Delegation and Following the Public Pound need to be finished by the end of November. |
| Effective services are provided timeously to all internal and external customers | 7 | 71% | 29% | 0% | Service consultations exceed targets. |
| Legal aspects of significant projects are delivered to a high quality | 8 | 100% | 0% | 0% | The service continues to support major projects despite impact of long term sickness. |
| ### Administrative and legal services are subject to continuous improvement | 9 | 78% | 11% | 11% | Where progress has been less than expected, this has been largely due to external influences. |
| ###### Total / Average | 52 | 85% | 13% | 2% |  |

CHIEF EXECUTIVE’S SERVICE PLAN PROGRESS REPORT: DETAIL

STRATEGIC POLICY

| #### TARGET OUTCOME 1 |  | Effective external and internal strategic partnerships which meet the Council’s and its partners’ strategic objectives |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Ref. | 3 Year Target | Target 2007/08 | Completed | Good progress – on track with development | Running behind with development progress | Unlikely to complete | Position at 30th September 2007 and impact of / reasons for delays |
| 1.1 | A cohesive Community Planning framework | Establish community planning performance framework |  |  |  |  | A review of the CP framework is underway and is running to schedule. |
| 1.2 | Continuous strategic improvement of the Community Safety Partnership | Complete implementation and evaluation of Outcome Agreement for Anti Social Behaviour |  |  |  |  | Revised arrangements are in place for integrating ASB strategy with community safety strategy as per national guidance. Strategic community safety assessment is underway. |
| 1.3 | Develop, monitor and report on Health improvement policy via the CHP and the Clacks Integrated Health Improvement Team (CIHIT) | Publish 2007 – 2010 JHIP |  |  |  |  | Integrated Team operating well and reporting regularly to joint management group, Health improvement performance framework agreed by the CHP Committee. New JHIP in preparation. |
| 1.4 | Development of shared services with other local authorities and partner organisations | Establish cohesive and corporate approach to CCTV development; contribute to review of Forth Valley system |  |  |  |  | Review has been completed and will be brought to Council. |
| 1.5 | Co-ordinate input to potential joint management with Stirling Council | Represent Council on Joint Steering Group and support operation of the Political Monitoring and Joint Political Monitoring Groups |  |  |  |  | Work is ongoing. The feasibility study funded by the Scottish Government is nearing completion. |
| 1.6 | Manage performance reporting across partnership structures | Improve links between Council Corporate Objectives and the Community Plan |  |  |  |  | A parallel review is underway of the Community Plan and the Council's Corporate Plan. The Community Plan vision/priorities will inform the Corporate Plan and revised priorities. |
| 1.7 | Effective management of externally funded projects | Provide support to ensure external funding monitoring and evaluation commitments are met |  |  |  |  | Ongoing support being provided within the Council and to other agencies as appropriate. |
| 1.8 | Agree and implement revised planning and performance management framework within the Council which is integrated with community planning | Future community planning, corporate and service priorities agreed with Elected Members and CMT |  |  |  |  | Framework agreed by the Alliance and being implemented by Theme Teams/ |
| 1.9 | Provide effective integrated emergency management arrangements | Implement civil contingencies legislation and manage civil contingencies awareness in the community through implementation of the joint strategy. |  |  |  |  | Ongoing provision of emergency planning support in line with legislation and other requirements, |

| #### TARGET OUTCOME 2 |  | Improved communications and information management |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Ref. | 3 Year Target | Target 2007/08 | Completed | Good progress – on track with development | Running behind with development progress | Unlikely to complete | Position at 30th September 2007 and impact of / reasons for delays |
| 2.1 | Improve image of Clackmannanshire as an area to live, work and visit | Promote and protect the image and reputation of the Council through effective media management |  |  |  |  | Little development work is possible due to the departure of the manager responsible for this area of work. The post has not yet been filled which will impact on the potential to be proactive. However, day to day media management is being covered. |
| 2.2 | Improved flow of information in Council and externally with local partners | Contribute to the development of a corporate knowledge management (KM) strategy |  |  |  |  | Several strands of this are now being taken forward. |
| 2.3 | Continued development of the internet as a corporate tool | Implement core & priority online services and review technical platform |  |  |  |  | Due to the departure of the Web Development Manager, the capacity to develop Clacksweb has been significantly reduced. The post has not yet been filled which will continue to mean developments will not be able to be pursued as planned. |
| 2.4 | Provision of appropriate information and data to support service development, performance reporting and policy development | Maintain agreed support for statutory information reporting and corporate information strategy |  |  |  |  | This work is ongoing and is supporting a range of services across the Council. |

| #### TARGET OUTCOME 3 |  | Socio-economic regeneration of Clackmannanshire and its most deprived communities |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Ref. | 3 Year Target | Target 2007/08 | Completed | Good progress – on track with development | Running behind with development progress | Unlikely to complete | Position at 30th September 2007 and impact of / reasons for delays |
| 3.1 | Support the development of and implementation of an Economic Development Strategy for Clackmannanshire | Review of Building Clackmannanshire |  |  |  |  | This strategy is being reviewed by the Economic Development Theme Team. |
| 3.2 | Manage, monitor and evaluate regeneration programmes and initiatives | Co-ordinate and manage Regeneration Outcome Agreement, Tullibody Healthy Living Initiative and Working For Families Initiative |  |  |  |  | Ongoing support is being provided to these initiatives. Work is beginning on managing the wind up should further funding not be forthcoming. |
| 3.3 | Encourage tourism in the area | Oversee implementation of Clacks Tourism Strategy |  |  |  |  | Relevant activities from action plan being undertaken. Recently announced national changes in organisation of economic development and tourism may impact in due course. |
| 3.4 | Community Capacity Building & Local Advocacy | Implement partnership community engagement mechanisms (e.g. Clacks 1000) |  |  |  |  | Clacks 1000 3rd survey has reported. Findings are being fed into policy development as appropriate within the Council and across partner agencies. |
| 3.5 | Support transnational initiatives | Manage twinning links and co-ordinate twinning activities |  |  |  |  | Significant involvement of the service in twinning visits and developing these further. |

ADMINISTRATION & LEGAL SERVICES

| #### TARGET OUTCOME 1 |  | Good standards of corporate governance are in place in respect of all Council activity |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Ref. | 3 Year Target | Target 2007/08 | Completed | Good progress – on track with development | Running behind with development progress | Unlikely to complete | Position at 30th September 2007 and impact of / reasons for delays |
| 1.1 | Procedures ensure that good standards of corporate governance continue to be achieved and maintained. | Review of Core Documentation |  |  |  |  |  |
|  |  |  Contract Standing Orders |  |  |  |  | Further diealogue with Procurement Manager is required. Should complete before end of financial year. |
|  |  |  Standard Terms and Conditions of Contract |  |  |  |  |  |
|  |  | Complete review of New Political Structure |  |  |  |  |  |
|  |  | Develop Member Resource Pack |  |  |  |  |  |
|  |  | Extend access to electronic information |  |  |  |  |  |
|  |  | Review of Impact of FOI |  |  |  |  | This work was deprioritised as a consequence of the elections/long term sick. Additional resources are being earmarked against this target |
|  |  | Implement FOI Action Plan |  |  |  |  | This work was deprioritised as a consequence of the elections/long term sick. Additional resources are being earmarked against this target |
|  |  | Internal customer consultation Training Needs Analysis 2008 |  |  |  |  |  |
|  |  | Deliver 2007 training programme for officers and a training Programme for Members |  |  |  |  | Training Programme for Members complete and training needs now under review. Training Programme for officers will be postponed due to temporary depletion of staffing resource. |

| #### TARGET OUTCOME 2 |  | Effective services are provided timeously to all internal and external customers |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Ref. | 3 Year Target | Target 2007/08 | Completed | Good progress – on track with development | Running behind with development progress | Unlikely to complete | Position at 30th September 2007 and impact of / reasons for delays |
| 2.1 | Re-engineered Licensing Function | Training new board members following election |  |  |  |  | Board members now able to work under new licensing regime. Training will continue in line with members TNA requirements. |
|  |  | Continue Training programme on the legislative framework. |  |  |  |  |  |
|  |  | Amend procedures to comply with new statutory Regime |  |  |  |  |  |
|  |  | Training Needs Analysis 2008 |  |  |  |  | Will be updated when full detail of legislative vhange is known |
| 2.2 | New National Planning Framework | Training for Elected Members Action plan to correspond with Executives proposed timetable |  |  |  |  | This objective is being revisited in consultation with Development Services. Indicative Programme will be offered to elected members by end November 2007 |
|  |  | Deliver Action Plan Objectives 07/08 |  |  |  |  | This objective is being revisited in consultation with Development Services. Account will be taken of departure of Head of Service |
| 2.3 | Efficient and Effective Election Administration and Management  Procedures and processes  Staff Resources  Essential Skills Base  Planned Approach to legislative change | Deliver Local Government and Scottish Parliamentary Elections to statutory timetable |  |  |  |  |  |

| #### TARGET OUTCOME 3 |  | Legal aspects of significant projects are delivered to a high quality |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Ref. | 3 Year Target | Target 2007/08 | Completed | Good progress – on track with development | Running behind with development progress | Unlikely to complete | Position at 30th September 2007 and impact of / reasons for delays |
| 3.1 | Effective inter service approach to tackling anti social behaviour with Police and other partners to reduce crime and anti-social behaviour through Implementation of ABS measures (Anti-Social Behaviour Act) to ensure | Implementation and Review of Efficiency and Compliance |  |  |  |  |  |
|  |  | Action Plan |  |  |  |  | Appointment of legal trainee (secondment from CALM Team) has bolstered Service capacity |
|  |  | Complete Year 1 Training Solicitor Post |  |  |  |  | Trainee has shown good work ethic, willingness to learn and technical capability |
| 3.2 | Mental Health Act Implementation.  Effective procedures and processes  Compliance with statutory requirements  Required skills and resource base Adoption and Children’s Act | Review and Improvement |  |  |  |  | Progress in relation to Adoption and Childrens Act has been hampered as new legislatio in not yet in place. |
|  |  | Establish effective procedures. Processes and training programme |  |  |  |  | Progress in relation to Adoption and Childrens Act has been hampered as new legislatio in not yet in place. |
| 3.3 | Freight and Passenger transport link from Stirling to Kincardine. | Operations Framework Phase 2 Complete Major Infrastructure Programme |  |  |  |  | Phase 2 likely to complete in current financial year. Line operational for traffic May 2008 |
|  |  | 75%2.5 FTE Working days per week (Max) |  |  |  |  | head of Service to manage input down to 1FTE working days by end December 2007 |
| 3.4 | Schools Estates Project. | Service input 2 FTE days per week |  |  |  |  | Input has decreased significantly post financial close. Service continues to support the Project dealing with issues as they arise. |

| #### TARGET OUTCOME 4 |  | ### Administrative and legal services are subject to continuous improvement |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Ref. | 3 Year Target | Target 2007/08 | Completed | Good progress – on track with development | Running behind with development progress | Unlikely to complete | Position at 30th September 2007 and impact of / reasons for delays |
| 4.1 | Further enhance provisions of effective Support Services. | Team Plans |  |  |  |  |  |
|  |  | Performance monitoring with client input. |  |  |  |  | This is ongoing |
| 4.2 | Provision of customer focussed service delivery. Appropriate consultations mechanisms for internal and external service users to inform team plans | Service Consultation |  |  |  |  | Consultations exceeding targets |
|  |  | Commence staff/stakeholder consultation on service structure |  |  |  |  | This has been deferred pending appointment of Head of Service |
| 4.3 | Improved use of web for PPRg and on line transactions.  Modernising Govt | Review and evaluate internet usage. |  |  |  |  | This has been taken as far as possible with no Webmaster appointed |
| 4.4 | Improved office efficiency | Implement Office Technology Action Plan. |  |  |  |  |  |
| 4.5 | Development opportunities allow staff to adapt to changes in service delivery and maximise personal potential.  Proper management of service skills base  Improved efficiency through training and broadened skills base | Undertake Training Needs Analysis. |  |  |  |  | Training needs continue to be met in accordance with need identified through PRD |
|  |  | Deliver actions specified in Service 2007 Training and Development Plan. |  |  |  |  | Ongoing |
| 4.6 | Monitor and respond to levels of staff Morale and output. | Management Reporting and Planning. Arrange Service away day |  |  |  |  | Service away day 26/11/07 will focus on emotional intelligence and the Service model for delegation. |