## Appendix 2 (hidden)
APPENDIX 2
CLACKMANNANSHIRE COUNCIL
CAPITAL PROGRAMME 2007/08
NET BORROWING REQUIREMENT |  |  | Draft Final Position c |  | Dec Out-Turn |  | Dec - Draft Final Diff |  | Jan Out-Turn |  | Oct Out-Turn |  | Jan - Oct Diff |  | Oct Out-Turn |  | August Out-Turn |  | Oct - Aug Diff
|  |  |  | 2007/08 |  | 2007/08 |  | 2007/08 |  | 2007/08 |  | 2007/08 |  | 2007/08 |  | 2007/08 |  | 2007/08 |  | 2007/08
|  |  | £'000 | £'000 | £'000 | £'000 | £'000 | £'000 | £'000 | £'000 | £'000 | £'000 | £'000 | £'000 | £'000 | £'000 | £'000 | £'000 | £'000 | £'000
2007/08 Approved Budget Excluding SAK Rail Link & Before Transfers (8th February 2007) | [7 empty] | 0 |  | 6978 |  | 6978 |  | 0 |  | 6978 |  | 6978 |  | 0
Adj for Projects not shown in Appendix 1:
|  | Museum & Heritage | [7 empty] | 250 |  | 250 |  | 0 |  | 250 |  | 250 |  | 0
|  | Alloa Library Refurbishment | [7 empty] | 100 |  | 100 |  | 0 |  | 100 |  | 100 |  | 0
|  | IT Hardware Replacement in Schools | [7 empty] | -60 |  | -60 |  | 0 |  | -60 |  | -60 |  | 0
Net Expenditure as per Appendix 1, Excluding PPP Scheme |  |  |  | 0 |  | 0 |  | 0 |  | 7268 |  | 7268 |  | 0 |  | 7268 |  | 7268 |  | 0
2007/08 Projects Transferred to 2006/07 as per Draft-Final 06/07 Position as at May 07 | [6 empty] | 0 |  | -204 |  | -204 |  | 0 |  | -204 |  | -204 |  | 0
2006/07 Projects Transferred to 2007/08 as per Draft Final 06/07 Position as at May 07 | [6 empty] | 0 |  | 4474 |  | 4474 |  | 0 |  | 4474 |  | 4474 |  | 0
[9 empty] | 4270 |  | 4270 |  | 0 |  | 4270 |  | 4270 |  | 0
|  | Adj for Projects not shown in Appendix 1: |  |  |  |  | 0
|  | Museum & Heritage | [6 empty] | -250 |  | -250 |  | 0 |  | -250 |  | -250 |  | 0
|  | Alloa Library Refurbishment | [6 empty] | -100 |  | -100 |  | 0 |  | -100 |  | -100 |  | 0
|  | IT Hardware Replacement in Schools | [6 empty] | 60 |  | 60 |  | 0 |  | 60 |  | 60 |  | 0
Transfers between 07/08 & 06/07 as agreed per Appendix 1 |  |  |  | 0 |  | 0 |  | 0 |  | 3980 |  | 3980 |  | 0 |  | 3980 |  | 3980 |  | 0
|  |  |  | 0 |  | 0 |  | 0 |  | 11248 |  | 11248 |  | 0 |  | 11248 |  | 11248 |  | 0
Projects Brought Forward from 2008/09
|  | Joint FVNHS/ Adult Care Premises |  |  |  |  | 0 |  | 50 |  | 50 |  | 0 |  | 50 |  | 50 |  | 0
|  | Menstrie House En-suite Conversion |  |  |  |  | 0 |  | 362 |  | 362 |  | 0 |  | 362 |  | 362 |  | 0
|  |  |  | 0 |  | 0 |  | 0 |  | 412 |  | 412 |  | 0 |  | 412 |  | 412 |  | 0
|  |  |  | 0 |  | 0 |  | 0 |  | 11660 |  | 11660 |  | 0 |  | 11660 |  | 11660 |  | 0
Further Projects proposed transfer from 08/09 to 07/08
| 85 | ICT Hardware Replacement | [6 empty] | 18 |  |  |  | 18 | [5 empty] | 0
| 35 | Roads & Footpath (to be trf to 93 - A907 project) | [6 empty] | 150 |  |  |  | 150
| 89 | Cochrane Hall, Alva, Refurbishment & Upgrading | [6 empty] | 5 |  | 5 |  | 0 |  | 5 |  | 5 |  | 0
| 33 | Flood Prevention | [8 empty] | 76 |  | -76 |  | 76 |  | 76 |  | 0
| 114 | Lime Tree Walk Phase 2 | [6 empty] | 150 |  | 150 |  | 0 |  | 150 |  | 150 |  | 0
| 107 | A908/B908 Hallpark, Sauchie (NB: trf from 09/10 to 07/08) | [10 empty] | 0 |  |  |  | 65 |  | -65
[10 empty] | 323 |  | 231 |  | 92 |  | 231 |  | 296 |  | -65
Overspends/ Unbudgeted Expenditure
|  | Vehicle Replacement |  |  |  |  | #VALUE! | [5 empty] | 0 | [5 empty] | 0
|  | Finance IT Servers |  |  |  |  | #VALUE! | [5 empty] | 0 | [5 empty] | 0
|  | Shared Services Centre |  |  |  |  | #VALUE! | [5 empty] | 0 | [5 empty] | 0
|  | Mailroom Facilities & Franking Machine |  |  |  |  | #VALUE! | [5 empty] | 0 | [5 empty] | 0
|  | Land Aquisition for Alva School & Road works |  |  |  |  | 0 |  | 150 |  | 150 |  | 0 |  | 150 |  | 150 |  | 0
| 87 | Alloa Townhall Reddelopment | [6 empty] | 14 |  |  |  | 14
[10 empty] | 164 |  | 150 |  | 14 |  | 150 |  | 150 |  | 0
Additional Spend funded from additional grants
|  | Additional Capital Grant Expenditure | [6 empty] | 658 |  | 658 |  | 0 |  | 658 |  | 658 |  | 0
| 9 | Additional Schools Grant Expenditure | [6 empty] | 506 |  | 506 |  | 0 |  | 506 |  | 506 |  | 0
| 107 | A908/B908 Hallpark, Sauchie | [10 empty] | 0 |  |  |  | 285 |  | -285
| 56 | National Cycle Route | [6 empty] | 50 |  | 50 |  | 0 |  | 50 |  | 50 |  | 0
|  | Alloa East Gateway | [6 empty] | 34 |  | 34 |  | 0 |  | 34 |  | 34 |  | 0
| 70 | Kilncarigs 1936 Building | [6 empty] | 75 |  | 75 |  | 0 |  | 75 |  | 75 |  | 0
[10 empty] | 1323 |  | 1323 |  | 0 |  | 1323 |  | 1608 |  | -285
Savings
| 21 | Joint FVNHS/ Adult Care Premises - Savings |  |  |  |  | 0 |  | -250 |  | -250 |  | 0 |  | -250 |  | -250 |  | 0
| 23 | Ludgate House External Fabric - Savings |  |  |  |  | 0 |  | -20 |  | -20 |  | 0 |  | -20 |  | -20 |  | 0
| 97 | Wheeled Litter Bins - savings |  |  |  |  | 0 |  | -81 |  | -40 |  | -41 |  | -40 |  | -40 |  | 0
| 122 | Sun Tube, Lime Tree House |  |  |  |  | 0 |  | -20 |  | -20 |  | 0 |  | -20 |  | 0 |  | -20
| 121 | Greenfield Heating - Savings | [6 empty] | -150 |  | -150 |  | 0 |  | -150 |  | -150 |  | 0
[10 empty] | -521 |  | -480 |  | -41 |  | -480 |  | -460 |  | -20
Decrease in Expenditure as a result of shortfall in grant
| 55 | Clackmannan Tolbooth - reduce exp due to shortfall in grant | [6 empty] | -55 |  | -55 |  | 0 |  | -55 |  | -55 |  | 0
|  |  |  | 0 |  | 0 |  | 0 |  | -55 |  | -55 |  | 0 |  | -55 |  | -55 |  | 0
Projects Transferred to 08/09
| 8 | Schools Alarms | [6 empty] | -7 |  | -7 |  | 0 |  | -7 |  | -7 |  | 0
| 10 | Tulligarth Sports field Resurfacing |  |  |  |  | 0 |  | -40 |  | -40 |  | 0 |  | -40 |  | -40 |  | 0
| 19 | Reconfiguration of Council Services & Property Assets in Tullicoultry |  |  |  |  | 0 |  | -125 |  | -125 |  | 0 |  | -125 |  | -125 |  | 0
| 21 | Joint FVNHS/ Adult Care Premises |  |  |  |  | 0 |  | -50 |  | -50 |  | 0 |  | -50 |  | -50 |  | 0
| 28 | A91 East Stirling St, Alva roundabout to access new school site |  |  |  |  | 0 |  | -450 |  | -450 |  | 0 |  | -450 |  | -450 |  | 0
| 31b | B9140 Collyands to Glenochil (West) |  |  |  |  | 0 |  | -856 |  | -856 |  | 0 |  | -856 |  | -856 |  | 0
|  | Accident Prevention & Traffic Management |  |  |  |  | 0 | [5 empty] | 0 | [5 empty] | 0
| 33 | Flood Prevention | [6 empty] | -121 |  |  |  | -121
| 47 | BlackDevon Landfill Gas Collection & Treatment project |  |  |  |  | 0 |  | -400 |  | -400 |  | 0 |  | -400 |  | -400 |  | 0
| 48 | Cemetery Strategy |  |  |  |  | 0 |  | -117 |  | -117 |  | 0 |  | -117 |  | -117 |  | 0
| 54 | Waste Recycling Project |  |  |  |  | 0 |  | -400 |  | -400 |  | 0 |  | -400 |  | -400 |  | 0
| 55 | Clackmannan Tolbooth |  |  |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| 56 | National Cycle Route |  |  |  |  | 0 |  | -12 |  | -12 |  | 0 |  | -12 |  | -12 |  | 0
| 57 | Old Alloa Heritage Phase 2 |  |  |  |  | 0 |  | -178 |  | -178 |  | 0 |  | -178 |  | -178 |  | 0
| 58 | Landscape Partnership - conserve Ochils / Hillfoots | [6 empty] | -1115 |  | -1115 |  | 0 |  | -1115 |  | -1115 |  | 0
| 59 | Core Path Network access | [6 empty] | -50 |  | -50 |  | 0 |  | -50 |  | -50 |  | 0
| 64 | Efficient Governmnet /Customer First | [6 empty] | -14 |  |  |  | -14
| 68 | Eastern Clackmannanshire Development Opportunities |  |  |  |  | 0 |  | -100 |  | -100 |  | 0 |  | -100 |  | -100 |  | 0
| 63 | Vehicle Replacement | [6 empty] | -329 |  |  |  | -329
| 65 | IT Services | [6 empty] | -17 |  |  |  | -17
| 73 | Pavilions Phase 2 |  |  |  |  | 0 |  | -340 |  | -340 |  | 0 |  | -340 |  | -340 |  | 0
| 74 | Dumyat Phase 3 |  |  |  |  | 0 |  | -40 |  | -40 |  | 0 |  | -40 |  | -40 |  | 0
| 110 | Alloa Town Centre Regeneration: Speirs Centre | [6 empty] | -40 |  | -40 |  | 0 |  | -40 |  | 0 |  | -40
| 111 | Alloa Town Centre: Public Realm Phase 2 | [8 empty] | 0 |  | 0 |  | 0 |  | -220 |  | 220
| 115 | Shillinghill to Town Hall: Environmental Regeneration | [8 empty] | 0 |  | 0 |  | 0 |  | -150 |  | 150
| 116 | New Alloa Infrastructure | [6 empty] | -240 |  | -240 |  | 0 |  | -240 |  | -240 |  | 0
| 122 | Sun Tube, Lime Tree House |  |  |  |  | 0 | [5 empty] | 0 |  |  |  | -20 |  | 20
| 123 | Keilliebank - Thermal Efficiency Windows |  |  |  |  | 0 | [5 empty] | 0 |  |  |  | -22 |  | 22
| 83 | Greenfield Driveway & Parking |  |  |  |  | 0 | [5 empty] | 0 |  |  |  | -84 |  | 84
| 75 | CCTV |  |  |  |  | 0 |  | -44 |  | -44 |  | 0 |  | -44 |  | -44 |  | 0
|  |  |  | 0 |  | 0 |  | 0 |  | -5085 |  | -4604 |  | -481 |  | -4604 |  | -5060 |  | 456
Income / Grants carried forward or Shortfall
| 28 | Income for Project 28 delayed to 08/09 |  |  |  |  | 0 |  | 225 |  | 225 |  | 0 |  | 225 |  | 225 |  | 0
| 55 | Clackamannan Tolbooth - shorfall in HS grant |  |  |  |  | 0 |  | 55 |  | 55 |  | 0 |  | 55 |  | 55 |  | 0
| 58 | Landscape Partnership - conserve Ochils / Hillfoots - Grant delayed to 08/09 | [6 empty] | 900 |  | 900 |  | 0 |  | 900 |  | 900 |  | 0
| 68 | Eastern Clackmannanshire Development Opportunities - Grant delayed | [6 empty] | 12 |  | 12 |  | 0 |  | 12 |  | 12 |  | 0
| 116 | New Alloa Infrastructure - Grant delayed | [6 empty] | 53 |  | 53 |  | 0 |  | 53 |  | 53 |  | 0
[10 empty] | 1245 |  | 1245 |  | 0 |  | 1245 |  | 1245 |  | 0
Additional Income / Grant
|  | Additional Special Capital Grant | [6 empty] | -658 |  | -658 |  | 0 |  | -658 |  | -658 |  | 0
| 9 | Additional School Fund | [6 empty] | -506 |  | -506 |  | 0 |  | -506 |  | -506 |  | 0
| 107 | Additional income for project 107 | [10 empty] | 0 |  |  |  | -285 |  | 285
| 56 | National Cycle Route - SUStran | [6 empty] | -50 |  | -50 |  | 0 |  | -50 |  | -50 |  | 0
|  | Alloa East Gateway | [6 empty] | -34 |  | -34 |  | 0 |  | -34 |  | -34 |  | 0
| 70 | Kilncraigs 1936 Building - grant from HS | [6 empty] | -75 |  | -75 |  | 0 |  | -75 |  | -75 |  | 0
| 77 | Additional General Capital Receipts | [6 empty] | -12 |  | -12 |  | 0 |  | -12 |  |  |  | -12
|  |  |  | 0 |  | 0 |  | 0 |  | -1335 |  | -1335 |  | 0 |  | -1335 |  | -1608 |  | 273
Net Expenditure 07/08 |  |  |  | 0 |  | 0 |  | 0 |  | 7719 |  | 8135 |  | -416 |  | 8135 |  | 7776 |  | 359
Miscellaneous
|  |  |  | 0 |  | 0 | 0 | [5 empty] | 0 | [5 empty] | 0
[7 empty] | 0 | [5 empty] | 0 | [5 empty] | 0
[7 empty] | 0 | [5 empty] | 0 | [5 empty] | 0
|  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0

## A1 3 yr GSC 07-0 to 09-10 Summ (hidden)
| 1 | 1b | 2 |  | 3 | 4 | 5 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 9 | 10 | 11
|  |  | General Services Capital Programme |  | 2006/07 |  |  | 2007/08 |  |  | 2008/09 |  |  | 2009/10 |  |  | 2008/09 |  |  | APPENDIX 1 | Recurring Revenue consequences
|  |  | 3 Year Summary 2007/08 to 2009/10 |  | Must be read with ref. to Appendix 2 |  |  | Must be read with ref. to Appendix 2 |  |  | Must be read with ref. to Appendix 3 |  |  | Must be read with ref. to Appendix 4 |  |  | (See Appendix 4)
[5 empty] | Gross after Adj (as at Oct 2006) | External Grants/ Allocated Cap Recpts | Net (Council Contribution) as at Oct 2006 | Gross after Adj | External Grants/ Allocated Cap Recpts | Net (Council Contribution) | Gross after Adj | External Grants/ Allocated Cap Recpts | Net (Council Contribution) | Gross after Adj | External Grants/ Allocated Cap Recpts | Net (Council Contribution) | Gross | External Grants | Net (Council Contribution)
|  |  | Service / Project Name |  | £'000 | £'000 | £'000 | £'000 | £'000 | £'000 | £'000 | £'000 | £'000 | £'000 | £'000 | £'000 | £'000 | £'000 | £'000
SERVICES TO PEOPLE
EDUCATION & COMMUNITY SERVICES
18 | 17b |  | Primary & Nursery School Developments |  |  |  | 0 |  |  | 0 | 1000 |  | 1000 | 1000 |  | 1000 |  |  | 0
| 4 |  | DDA Compliance |  | 133 |  | 133 |  |  | 0 |  |  | 0 |  |  | 0
2.918 |  |  | Lochies School |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
3.0328 |  |  | Lochies School - Excellence Fund |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
3.1475 |  |  | Lochies School - Schools Budget Income |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
3.2623 |  |  | Museum & Heritage Centre - External Income |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
3.377 |  |  | Property Maintenance |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
3.4918 |  |  | Public Art |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
3.6066 |  |  | Retentions/Legally committed |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
3.7213 |  |  | SEN Adaptations |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
8 | 8 |  | School Building Alarm Systems |  | 304 |  | 304 | 348 |  | 348 | 300 |  | 300 |  |  | 0 |  |  | 0 |  | some maintenance but reduction in insurance
9 | 9 |  | Schools Fund |  | 1307 | 1307 | 0 | 1055 | 1055 | 0 |  |  | 0 |  |  | 0 |  |  | 0
| 13 |  | Heavy Equipment in Secondary Schools - Kilns etc |  | 40 |  | 40 |  |  | 0 |  |  | 0 |  |  | 0
15 | 14 |  | IT Hardware Replacement in Schools |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
16 | 15 |  | Legal Commitments - for projects undertaking in previous years |  | 25 |  | 25 | 25 |  | 25 | 50 |  | 50 |  |  | 0 |  |  | 0
15 | 85,86 | # | ICT Hardware Replacement in Sec Schls & New IT Installation in Schools |  |  |  | 0 |  |  | 0 | 1600 |  | 1600 |  |  | 0 |  |  | 0
| 104 |  | Purchase of White Boards for new Secondary Schools |  |  |  | 0 |  |  | 0 | 450 |  | 450 |  |  | 0
SPORTS & LEISURE SERVICES
11 | 10 |  | Tulligarth Sports Resurfacing - requirement of Lottery funding |  |  |  | 0 | 40 |  | 40 |  |  | 0 |  |  | 0 |  |  | 0
17 | 16 | # | Leisure Bowl - refurbishment |  | 261 |  | 261 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
| 19 |  | Reconfiguration of Council Services & Property Asset in Tillicoultry |  |  |  |  | 125 |  | 125 |  |  | 0 | 500 |  | 500
| 88 |  | Alva Sports Complex Refurbishment & Upgrading |  |  |  | 0 | 25 |  | 25 | 25 |  | 25 | 3000 | 200 | 2800
| 89 |  | Cochrane Hall - Refurbishment & Upgrading |  |  |  | 0 |  |  | 0 | 25 |  | 25 | 500 |  | 500
| 91 |  | Clackmannanshire's Outdoor Activity Centre |  |  |  | 0 |  |  | 0 | 25 |  | 25 | 500 | 200 | 300
| 92 |  | Running Track at Lornshill Academy |  |  |  | 0 |  |  | 0 |  |  | 0 | 460 | 200 | 260
| 103 |  | Demolition of Lornshill Academy & construct car parking & football pitch |  |  |  | 0 |  |  | 0 |  |  | 0 | 1250 |  | 1250
|  |  | Total Education & Community Service |  | 2070 | 1307 | 763 | 1618 | 1055 | 563 | 3475 | 0 | 3475 | 7210 | 600 | 6610 | 0 | 0 | 0 |  | 0 | 0 | 0
General Fund Housing - Enabling
SOCIAL SERVICES/ GENERAL HOUSING
|  |  | Ludgate House (c/f from 00/01) |  |  | #REF! | #REF! |  | #REF! | #REF!
|  |  | Office Relocations |  |  | #REF! | #REF! |  | #REF! | #REF!
|  |  | Whins Resource Centre - Floor Heating System |  |  | #REF! | #REF! |  | #REF! | #REF!
|  |  | Care in Community Safety (** new proposal - see attached schedule) |  |  | #REF! | #REF! |  | #REF! | #REF!
|  |  | Upgrade 6 Marshill Alloa |  |  | #REF! | #REF! |  | #REF! | #REF!
|  |  | Document Imaging System (** new proposal - see attached schedule) |  |  | #REF! | #REF! |  | #REF! | #REF!
22 | 20 |  | DDA Compliance |  | 0 |  | 0 | 37 |  | 37 |  |  | 0 |  |  | 0 |  |  | 0
| 21 |  | Joint FVNHS/ Adult Care Premises Occupation |  | 0 |  | 0 | 300 |  | 300 |  |  | 0 |  |  | 0
25 | 22 |  | Menstrie House En-Suite Conversion |  | 838 |  | 838 | 512 |  | 512 | 38 |  | 38 |  |  | 0 |  |  | 0
26 | 23 |  | Ludgate House External Fabric |  | 1 |  | 1 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
27 | 24 |  | Mental Health Services - Retentions |  | 1 |  | 1 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
| 25 |  | Menstrie House - Increased Parking & Security Fencing |  |  |  | 0 | 150 |  | 150 |  |  | 0 |  |  | 0
27 | 66b |  | Ludgate House Traffic Management - Retentions |  | 1 |  | 1 | 1 |  | 1 |  |  | 0 |  |  | 0 |  |  | 0
|  |  | Total Social Services |  | 841 | 0 | 841 | 1000 | 0 | 1000 | 38 | 0 | 38 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
DEVELOPMENT & ENVIRONMENTAL SERVICES
Transportation
|  |  | A907 (carry forward of unused additional consent) | }
|  |  | A907 - Council Contribution | }
28 | 26 |  | Accident Prevention & Traffic Management |  | 100 |  | 100 | 100 |  | 100 | 100 |  | 100 |  |  | 0 |  |  | 0 |  | 0 | 0 | 0
29 | 27 |  | Alloa Town Centre |  | 992 | 607 | 385 | 320 |  | 320 |  |  | 0 |  |  | 0 |  |  | 0 |  | -200 | -200 | -200
|  |  | Accident Prevention & Traffic Management - Safer Roads, Cycling |  |  |  | 0 |  | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
30 | 28 |  | A91 East Stirling St. Alva Roundabout to access new school site |  | 0 |  | 0 | 450 | 225 | 225 |  |  | 0 |  |  | 0 |  |  | 0
32 | 31a |  | B9140/ Collylands Cross Upgrade |  | 403 |  | 403 | 40 |  | 40 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 | 0
33 | 31b |  | B9140 Realignment of Bends (Collylands to Glenochil - West) |  | 20 |  | 20 | 838 |  | 838 | 10 |  | 10 |  |  | 0 |  |  | 0
| 31c |  | B9140 Realignment of Bends (Collylands to Fishcross/Maggies wood - East) |  |  |  | 0 |  |  | 0 | 30 |  | 30 | 500 |  | 500
34 | 32 |  | Bridge Strengthening |  | 587 |  | 587 | 400 |  | 400 | 150 |  | 150 | 30 |  | 30 |  |  | 0 |  | 0 | 0 | 0
|  |  | Eastern Link Road |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
|  |  | Hall Park |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
|  |  | Footpath Maintenance |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
|  |  | Roads Maintenance |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
|  |  | Smithfield Loan |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
|  |  | Roads Structural Maintenance |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
35 | 33 |  | Flood Prevention |  | 100 |  | 100 | 100 |  | 100 | 100 |  | 100 |  |  | 0 |  |  | 0 |  | 0 | 0 | 0
36 | 34 |  | Retentions |  | 60 |  | 60 | 60 |  | 60 | 60 |  | 60 |  |  | 0 |  |  | 0 |  | 0 | 0 | 0
37 | 35 |  | Road & Footway Improvements (SRMCS), including town centres |  | 484 |  | 484 | 500 |  | 500 | 520 |  | 520 | 500 |  | 500 |  |  | 0 |  | 0 | 0 | 0
38 | 36 |  | Cycling , Walking ,Safer Streets (CWSS) |  | 84 | 84 | 0 | 86 | 86 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 | 0
39 | 37 |  | Street Lighting |  | 150 |  | 150 | 165 |  | 165 | 185 |  | 185 | 200 |  | 200 |  |  | 0 |  | 0 | 0 | 0
|  |  | Tullibody Bypass (to be funded from special capital receipts) |  |  |  | 0 |  | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
40 | 38 |  | Total SAK Rail Project & Alloa ELR Project Costs |  | 815 |  | 815 | 110 |  | 110 |  |  | 0 |  |  | 0 |  |  | 0 |  | -20 | -20 | -20
43 | 41 |  | 20mph speed reduction |  | 107 | 107 | 0 | 109 | 109 | 0 |  |  | 0 |  |  | 0 |  |  | 0
43 | 43 |  | SESTRAN public Transport & Walking |  | 220 | 220 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
| 93 |  | A907 B910 / Helensfield Junction for Railway Line / Realignment |  | 20 |  | 20 | 430 |  | 430 |  |  | 0 | 200 |  | 200 |  |  | 0
| 106 |  | Shillinghill Roundabout |  |  |  | 0 |  |  | 0 | 40 |  | 40 | 400 |  | 400
| 107 |  | A908/B908 Hallpark, Sauchie |  |  |  | 0 |  |  | 0 |  |  | 0 | 350 |  | 350
|  |  | Total Transportation |  | 4142 | 1018 | 3124 | 3708 | 420 | 3288 | 1195 | 0 | 1195 | 2180 | 0 | 2180 | 0 | 0 | 0
Environment
| 46 |  | Black Devon Landfill / Incinerator |  | 20 |  | 20 | 78 |  | 78 |  |  | 0 |  |  | 0
46 | 47 |  | Black Devon Landfill Gas Collection & Treatment Project |  |  |  | 0 | 400 |  | 400 |  |  | 0 |  |  | 0 |  |  | 0
47 | 48 |  | Cemeteries Strategy |  | 51 |  | 51 | 157 |  | 157 |  |  | 0 |  |  | 0 |  |  | 0 |  | # | # | #
| 49 |  | Cycle Path Network |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
| 50 |  | Dollar Cemetery |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
| 51 |  | Environmental Improvements |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
| 52 |  | Old Alloa THI Project |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
| 53 |  | Hillfoots Initiative |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
| 54 |  | Incineration Plant Demolition |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
| 55 |  | Landward Village Initiative |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
48 | 49 |  | Contaminated Land |  | 217 | 67 | 150 | 50 | 50 | 0 | 50 | 50 | 0 | 50 | 50 | 0 |  |  | 0 |  | Budget already in place for Land Officer
| 57 |  | Tullis Factory Demolition |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
49 | 50 | # | Parks & Open Spaces |  | 80 |  | 80 | 80 |  | 80 | 83 |  | 83 |  |  | 0 |  |  | 0
50 | 51 | # | Outdoor Play Area Strategy |  |  |  | 0 | 75 |  | 75 | 78 |  | 78 |  |  | 0 |  |  | 0
53 | 54a |  | Waste Recycling Project |  |  |  | 0 | 400 |  | 400 |  |  | 0 |  |  | 0 |  |  | 0
| 54b |  | Wheeled / Litter Bins |  | 60 |  | 60 | 100 |  | 100 | 100 |  | 100 | 100 |  | 100 |  |  | 0
|  |  | Gateways & Roundabouts |  | 45 |  | 45 |  |  | 0 |  |  | 0 |  |  | 0
[5 empty] | 473 | 67 | 406 | 1340 | 50 | 1290 | 311 | 50 | 261 | 150 | 50 | 100 | 0 | 0 | 0
Policy & Implementation
54 | 55 |  | Clackmannan Tolbooth |  | 56 |  | 56 | 104 | 104 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | # | # | #
55 | 56 |  | National Cycle Route |  |  |  | 0 | 62 |  | 62 |  |  | 0 |  |  | 0 |  |  | 0 |  | # | # | #
56 | 57 |  | Old Alloa Townscape Heritage Phase 2 |  | 20 |  | 20 | 235 |  | 235 |  |  | 0 |  |  | 0 |  |  | 0 |  | # | # | #
57 | 58 |  | Landscape Partnership - Conserve Ochills / Hillfoots |  |  |  | 0 | 1125 | 900 | 225 |  |  | 0 |  |  | 0 |  |  | 0
58 | 59 |  | Core Path Network for Access |  |  |  | 0 | 50 | 12 | 38 |  |  | 0 |  |  | 0 |  |  | 0
67 | 68 |  | Econ. Dev. Infrastructure: Eastern Clackmannanshire Development Opportunities |  | 0 |  | 0 | 100 |  | 100 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 | 5
72 | 73 | # | Pavilions Business Park Phase 2 |  | 40 |  | 40 | 300 |  | 300 |  |  | 0 |  |  | 0 |  |  | 0
73 | 74 |  | Dumyat Business Park Phase 3 |  | 0 |  | 0 | 40 |  | 40 |  |  | 0 |  |  | 0 |  |  | 0
| 110 |  | Alloa Town Centre Regeneration: Speirs Centre |  |  |  | 0 | 330 |  | 330 |  |  | 0 |  |  | 0
| 111 |  | Alloa Town Centre: Public Realm Phase 2 |  |  |  | 0 | 220 |  | 220 |  |  | 0 |  |  | 0
| 114 |  | Lime Tree Walk Phase 2 |  |  |  | 0 |  |  | 0 | 200 |  | 200 | 50 |  | 50
| 115 |  | Shillinghill to Town Hall: Environmental Regeneration |  |  |  | 0 | 150 |  | 150 | 50 |  | 50 |  |  | 0
| 116 |  | New Alloa Infrastructure |  |  |  | 0 | 240 | 53 | 187 | 10 | 10 | 0 |  |  | 0
| 118 |  | Pavilions Phase 3 |  |  |  | 0 |  |  | 0 | 50 |  | 50 |  |  | 0
[5 empty] | 116 | 0 | 116 | 2956 | 1069 | 1887 | 310 | 10 | 300 | 50 | 0 | 50 | 0 | 0 | 0
Property Services
| 60 |  | Asbestos Removal - Retentions |  | 0 |  | 0 | 0 |  | 0 |  |  | 0 |  |  | 0
60 | 61 |  | Centralised Kitchen |  | 0 |  | 0 | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
61 | 62 |  | Disability Discrimination Act |  | 15 |  | 15 |  |  | 0 | 20 |  | 20 |  |  | 0 |  |  | 0
| 61 |  | Centralised Kitchen |  | 24 |  | 24 |  |  | 0 |  |  | 0 |  |  | 0
62 | 63a |  | Vehicle Replacement Programme |  | 989 |  | 989 | 630 |  | 630 | 500 |  | 500 | 612 |  | 612 |  |  | 0
| 63b |  | Keilarsbrae land Purchases |  |  |  | 0 | 11 |  | 11 |  |  | 0 |  |  | 0 |  |  | 0
Retentions Carry forward (projects to be identified)
| 70 |  | Kilncraigs Mill 1936 Building Envelop |  |  |  | 0 | 0 |  | 0 |  |  | 0 |  |  | 0
60 | 70 |  | Kilncraigs Mill 1936 Building Envelop |  | 1569 | 315 | 1254 | 35 |  | 35 |  |  | 0 |  |  | 0 |  |  | 0
60 | 71 |  | Kilncraigs Mill 1904 Development of 3rd & 4th Floors |  | 720 |  | 720 |  |  | 0 | 30 |  | 30 |  |  | 0 |  |  | 0
60 | 72b |  | Kilncraigs Mill 1904 Access Control & Zoning Services |  | 80 |  | 80 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
60 | 72a |  | Kilncraigs Mill 1904 Mill Conversion |  | 17 |  | 17 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
60 | 98 | # | Kilncraigs Mill 1904 Upgrade of Existing |  | 350 |  | 350 | 410 |  | 410 |  |  | 0 |  |  | 0 |  |  | 0
| 99 |  | Forthbank Accommodation Rationalisation |  |  |  | 0 |  |  |  | 75 |  | 75 |  |  | 0
| 120 |  | Air Conditioning System - Class Cuisine, Sauchie |  |  |  | 0 | 30 |  | 30 |  |  | 0 |  |  | 0
| 121 |  | Greefield Heating |  |  |  | 0 | 150 |  | 150 |  |  | 0 |  |  | 0
| 122 |  | Sun Tube, Lime Tree House |  |  |  | 0 | 20 |  | 20 |  |  | 0 |  |  | 0
| 123 |  | Kelliebank - Thermal Efficiency Windows |  |  |  | 0 | 22 |  | 22 |  |  | 0 |  |  | 0
[5 empty] | 3764 | 315 | 3449 | 1308 | 0 | 1308 | 625 | 0 | 625 | 612 | 0 | 612 | 0 | 0 | 0
|  |  | Total Development & Environmental Services |  | 8495 | 1400 | 7095 | 9312 | 1539 | 7773 | 2441 | 60 | 2381 | 2992 | 50 | 2942 | 0 | 0 | 0 |  | -220 | -220 | -215
CORPORATE DEVELOPMENT
CCTV - Alloa South & East
Community Planning
63 | 64 |  | Efficient Government/Customer First Developments |  | 141 |  | 141 | 100 |  | 100 | 100 |  | 100 | 500 |  | 500 |  |  | 0
|  |  | Business Change & Organisational Development | }
|  |  | Clack Web - eServices & eCommunity | }
|  |  | Content & Knowledge Management | }
|  |  | One Stop Shop & Customer Services Centre | }
|  |  | Shared Services & Data Sharing | }
Council Office - Rewiring
Information Services - Salaries
Kilncraigs Mill Develop. (consent brought forward)
64 | 65 |  | IT Services |  | 360 |  | 360 | 330 |  | 330 | 300 |  | 300 | 363 |  | 363 |  |  | 0
65 | 66a |  | Finance Services - General Ledger system |  | 30 |  | 30 | 30 |  | 30 | 40 |  | 40 |  |  | 0 |  |  | 0
| 83 |  | Greenfield Driveway & Parking |  |  |  | 0 | 84 |  | 84 |  |  | 0 |  |  | 0
|  |  | Rewiring/Cabling - Greenfield House |  | 28 |  | 28 |  |  | 0 |  |  | 0 |  |  | 0
|  |  | Total Corporate Development |  | 559 | 0 | 559 | 544 | 0 | 544 | 440 | 0 | 440 | 863 | 0 | 863 | 0 | 0 | 0 |  | 0 | 0 | 0
CHIEF EXECUTIVE SERVICES
|  |  | Miscellaneous | [12 empty] | 0
75 | 76 |  | DDA & Asbestos Removal |  | 0 |  | 0 | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 | 0
| 75 |  | CCTV |  | 53 |  | 53 |  |  | 0 |  |  | 0 |  |  | 0
| 76 |  | DDA & Asbestos Removal |  | 44 |  | 44 |  |  | 0 |  |  | 0 |  |  | 0
|  |  | Mailroom facilities & franking machine |  | 16 |  | 16 |  |  | 0 |  |  | 0 |  |  | 0
| 82 | # | Council Office Improvements |  |  |  | 0 |  |  | 0 | 140 |  | 140 |  |  | 0
|  |  | Total Chief Executives Services |  | 113 | 0 | 113 | 0 | 0 | 0 | 140 | 0 | 140 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
|  |  | TOTAL CAPITAL PROGRAMME |  | 12078 | 2707 | 9371 | 12474 | 2594 | 9880 | 6534 | 60 | 6474 | 11065 | 650 | 10415 | 0 | 0 | 0 |  | -220 | -220 | -215
|  |  | UNALLOCATED FUNDING | [17 empty] | Key for Recurring Revenue Costs Section
76 | 77 |  | Capital Receipts Estimate (NET OF EXPENSES) - Now trf for PPP Project - see below | [15 empty] | #REF!
| 78 |  | Sale of Land - Dumyat Park/ rear of St. Mungo's
78 | 80 |  | ERDF Grants (from Kilncraigs to be used to refund extra s94 advance in previous years) |  |  |  | 119 | [13 empty] | Blank cells = | no info from service
|  |  | Trf from 08/09 - Surplus from PPP sales | [12 empty] | 996
|  |  | TOTAL - ESTIMATED UNALLOCATED FUNDING |  |  |  | 119 |  |  | 0 |  |  | 0 |  |  | 996 |  |  | #REF!
NET FUNDING (SURPLUS) / DEFICIT
FINANCED BY C.F.C.R.
|  |  | Net Capital Expenditure to be Funded from Prudential Borrowing |  |  |  | 9252 |  |  | 9880 |  |  | 6474 |  |  | 9419 |  |  | #REF!
List of Assets Sale Receipts allocated to specific projects referred
to above
| 79a |  | Expected increase in sale receipts from the three school sites to part fund project 19 above
| 79b |  | Expected increase in sale receipts from the three school sites to part fund project 85/86 above - Now Trf to PPP - see Below
| 79c |  | Expected increase in sale receipts from the three school sites to part fund project 104 above - Now Trf to PPP - See below
| 79d |  | Expected increase in sale receipts from the three school sites to part fund project 88 above
| 79e |  | Expected increase in sale receipts from the three school sites to fund project 103 above
| 84 |  | Capital Receipts from sale of earmarked asset to fund Speirs Centre project 110 - Now Trf to PPP - See Below
| 84 |  | Capital Receipts from sale of earmarked asset to fund ATC Precinct project 113 - Now Trf to PPP - See Below
[6 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0
List of External Allocated Funding referred to above
Contributions from other sources
| 27 |  | Asda - Alloa Town Centre |  |  | 607
| 28 |  | A91 East Stirling St. Alva Roundabout to access new school site | [5 empty] | 225
| 55 |  | Heritage Lottery Fund for Clackmannan Tolbooth |  |  | 0 |  |  | 32
| 55 |  | Historic Scotland Grant for Clackmannan Tolbooth | [5 empty] | 72
| 70 |  | CHT - Kilncraigs Mill 1936 Building Envelop |  |  | 315
| 58 |  | Heritage Lottery Fund for Landscape Partnership Project | [5 empty] | 900
| 59 |  | SNH - Core Path Network for Access | [5 empty] | 12
| 116 |  | ERDF - New Alloa Infrastructure | [5 empty] | 53 |  |  | 10
| 64 |  | Grant Efficient Government/Customer First Developments (not yet known) #
| 88 |  | The Sports Scotland Fund - Alva Academy Sports Complex | [11 empty] | 200
| 91 |  | The Sports Scotland Fund - Outdoor Activity Centre | [11 empty] | 200
| 92 |  | The Sports Scotland Fund - Running Track, Lornshill Academy | [11 empty] | 200
[6 empty] | 922 |  |  | 1294 |  |  | 10 |  |  | 600
Central Government Grants
| 9 |  | Special Grant for Schools Estate Renewal Programme |  |  | 1307 |  |  | 1055
| 36 |  | Cycling, Walking, Safer Streets (CWSS) from SE |  |  | 84 |  |  | 86
| 41 |  | 20mph Grant from Scottish Executive |  |  | 107 |  |  | 109
| 43 |  | SESTRAN Public Transport & walking |  |  | 220
| 49 |  | Contaminated Land |  |  | 67 |  |  | 50 |  |  | 50 |  |  | 50
[6 empty] | 1785 |  |  | 1300 |  |  | 50 |  |  | 50
|  |  | Total External Funding Allocated / Asset Sale Receipts Allocated |  |  | 2707 |  |  | 2594 |  |  | 60 |  |  | 650
SERVICES TO PEOPLE
PPP PROJECT
1 | 1-3,5 |  | PPP Capital Contribution for 09/10 |  | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 700 | 700 | 0 |  |  | 0
| 1-3,5 |  | PPP Capital Contribution for 08/09 | [7 empty] | 5200 | 5200
1 | 1-3,5 |  | PPP Capital Contribution to Costs c/f from previous year |  | 0 | 0 | 0 |  |  | 0 | 11750 | 11750 | 0 |  |  | 0 |  |  | 0
| 17a |  | School Development Allocated to PPP |  | 0 | 0 | 0 |  |  | 0 | 175 | 175 | 0 |  |  | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 17125 | 17125 | 0 | 700 | 700 | 0
FUNDING FROM SPECIFIC CAPITAL RECEIPTS FOR PPP PROJECT
| 79b |  | Expected increase in sale receipts from the three school sites to fund project 85/86 above | [8 empty] | 0 | 0
| 79c |  | Expected increase in sale receipts from the three school sites to fund project 104 above | [8 empty] | 0 | 0
| 77 |  | Capital Receipts Estimate (NET OF EXPENSES) - Now trf to fund PPP project | [8 empty] | 0 | 0
|  |  | Sale of Specific assets | [8 empty] | 16350
| 78 |  | Sale of Land - land @ rear of St. Mungo's | [7 empty] | 1230
| 78 |  | Sale of Land - Dumyat Park & Ditch - Tullibody Bypass | [7 empty] | 2025
| 124 |  | Commercial Property A declared surplus (CLAREMOUNT BUSINESS CENTRE) | [7 empty] | 150
| 124 |  | Commercial Property B declared surplus (FORMER TULLIS SITE) | [7 empty] | 350
| 124 |  | Commercial Property C not declared surplus yet (BANK STREET / DRYSDALE STREET) | [7 empty] | 75
| 124 |  | Plot Property D not declared surplus yet (PLOT 10 SOUTH ALLOA) | [7 empty] | 500
| 124 |  | Property E declared surplus (DITCH FARM - LAND) | [7 empty] | 300
| 124 |  | Property F declared surplus (DITCH FARM - FARM HOUSE) | [7 empty] | 200
| 124 |  | Property G - not declared surplus yet (ALVA ACADEMY) | [7 empty] | 2330
| 124 |  | Property H - not declared surplus yet (ALLOA ACADEMY) | [7 empty] | 9716
| 124 |  | Property I - not declared surplus yet (FAIRFIELD SCHOOL) | [7 empty] | 470
|  |  | Trf to 09/10 General Services Capital | [7 empty] | -996
|  |  | Total Asset Sale Receipts allocated to PPP Project |  |  | 0 |  |  | 0 |  |  | 16350 |  |  | 0
Central Government Grants allocated to PPP Project
| 9 |  | Schools Fund for PPP |  |  | 0 |  |  | 0 |  |  | 775 |  |  | 700
|  |  | Total Central Government Grants allocated to PPP Project |  |  | 0 |  |  | 0 |  |  | 775 |  |  | 700

## Appendix 3 (hidden)
APPENDIX 3
CLACKMANNANSHIRE COUNCIL
CAPITAL PROGRAMME 2007/08-2009/10
MOVEMENT IN THE 3-YEAR CAPITAL PROGRAMME SINCE COUNCIL APPROVAL IN FEBRUARY 2007
|  |  | 2007/08 | 2008/09 | 2009/10 | Total
Gross Expenditure
| As approved by Special Council Meeting on 8th Feb 2007 |  | 12474 | 6534 | 11065 | 30073
|  | Transfers of 06/07 budgets to 07/08, following finalisation of 06/07 accounts | 1780 |  |  | 1780
|  | Transfer of budgets from 08/09 to 07/08 as per Aug 07 Out-turns | 231 | -231 |  | 0
|  | Transfer of budgets from 09/10 to 07/08 as per Aug 07 Out-turns | 65 |  | -65 | 0
|  | Transfer of budgets from 07/08 to 08/09 as per Aug 07 Out-turns | -5060 | 5060 |  | 0
|  | Additional Grant funded expenditure | 1608 |  |  | 1608
Additional Expenditure funded by Capital Receipts from FVJB
|  | Reduced Expenditure on reduction of Grant | -55 |  |  | -55
|  | Savings (budgets not required) | -460 |  | -285 | -745
|  | Overspends | 150 |  |  | 150
| Gross Expenditure as per Aug 07 Out-turns |  | 10733 | 11363 | 10715 | 32811 | 0
Grants & Capital Receipts
| Grants - As approved by Special Council Meeting on 8th Feb 2007 |  | 2594 | 60 | 650 | 3304
|  | Additional Grants Receiveable | 1608 | 0 | 0 | 1608
|  | Income / Grants shortfall or delayed to 08/09 | -1245 | 1190 |  | -55
| Capital Receipts - As approved by Special Council Meeting on 8th Feb 2007 |  | 0 | 0 | 996 | 996
|  | Changes since Feb 07 | 0 | 0 | 0 | 0
| Grants & Capital Receipts as per July 07 Out-turns |  | 2957 | 1250 | 1646 | 5853 | 0
Net Expenditure (Council Borrowing)
| As approved by Special Council Meeting on 8th Feb 2007 |  | 9880 | 6474 | 9419 | 25773 | 0
| Net Expenditure as per August 07 Out-turns |  | 7776 | 10113 | 9069 | 26958 | 0
Variance between Feb 07 to Aug 07 Out-turns | [5 empty] | 1185
The variance is made up as follows:
|  | Additional transfers of budgets from 06/07 (does not contribute to overall increase in borrowing, as it will have reducsed 06/07 borrowing) |  |  |  | 1780
Net Savings in budgets:
|  | Land Acquisition for Alva School & Road works - unbudgeted expenditure |  |  |  | 150
| 21 | Joint FVNHS/ Adult Care Premises - Savings |  |  |  | -250
| 23 | Ludgate House External Fabric - Savings |  |  |  | -20
| 54b | Wheeled Litter Bins - Savings |  |  |  | -40
| 121 | Greenfield Heating - To be funded by Additional Capital Grant |  |  |  | -150
| 107 | A908 / B908 Hallpark, Sauchie - To be funded by FVNHS Contribution |  |  |  | -285
1185

## GSC 07-08 to Jan 08
| 0.8 | [6 empty] | OK |  | OK |  |  | OK | OK |  | Actual Out | Out-Turn Out |  | OK |  |  |  | OK | OK
| General Services Capital Programme 2007/08 to 2009/10 | Service | Service Units | New Ledger Code | Old Ledger Codes | Total Gross for 07/08 | Contracted | APPROVED BUDGET 2007/08 before transfers between years |  |  | 2007/08 - after all transfers |  |  | Actual for 10 Months to 31st January 2008 |  |  | 07/08 Out-turn as at 25/02/08 |  |  |  |  | Project Update reported at 25/02/07 to Capital Monitoring Group | Proposed Budget + all transfers for 2008/09 presented to Council on 21/2/08 Borrowing (Council Contribution) | Proposed Budget + all transfers for 2008/09 presented to Council on 21/2/08 Borrowing (Council Contribution) | Total for 3 years 07/08 to 09/10 Borrowing (Council Contribution)
[8 empty] | Approved Budget | Grants/Capital Receipts | Borrowing (Council Contribution) | Projects transferred from / (to) 06/07 | Projects transferred from / (to) 08/09 | Revised Borrowing (Council Contribution) | Total Expenditure | Total Income | Borrowing (Council Contribution) | Total Expenditure | Total Income | Borrowing (Council Contribution) | Out-turn Variance on 07/08 Budget | Variance on Jan O/T | [5 empty] | CFCR DR/(CR) 0002 | Loans Fund DR/(CR) 0003 | Cap Recp Applied DR/(CR) 0001 | Description
[8 empty] | Gross |  | Net |  |  |  | Gross |  | Net |  |  | Net
[6 empty] | £ | £ | £ | £ | £ | £ | £ | £ | £ | £ | £ | £ | £ | £ | £ | £ |  | £ | £ | £ |  | £ | £ | £
PROJECT
4 | DDA Compliance | S2P | 1E | 90 10 6000 |  | 18000 |  | 0 | 0 | 0 | 18000 |  | 18000 | 12605.97 |  | 12605.97 | 18000 |  | 18000 | 0 | 0 | Full spend expected this year |  |  | 18000 |  |  | -113673 |  | Capital Funded by Loans
8 | School Building Alarm Systems | S2P | 1E | 90 10 5700 |  | 469000 | 311023 | 348000 | 0 | 348000 | 121000 |  | 469000 | 347551.46 |  | 347551.46 | 462000 |  | 462000 | 7000 | 7000 | Phase 2 is complete. Phase 3 now scheduled for 09/10. Any underspend will be carried forward to 08/09 | 7000 | 300000 | 769000
9 | Schools Fund | S2P | 1E | 90 10 4900 |  | 1055000 | 998560 | 1055000 | -1055000 | 0 | 0 |  | 0 | 1247924.7 | -616368 | 631556.7 | 1561000 | -1561000 | 0 | 0 | 0 | Full spend expected on set programme, including an 'Additional Grant' of £426k. In addition there is £80k of s75 income for available for capital purposes, which will be transferred from revenue. | 81000 | 656000 | 737000
10 | Tulligarth Sports Resurfacing - requirement of Lottery funding | S2P | 2L |  |  | 40000 |  | 40000 |  | 40000 | 0 |  | 40000 |  |  | 0 |  |  | 0 | 40000 | 40000 | The synthetic carpet is in good condition and does not need replacing just yet. Carry forward budget to 08/09 | 40000 |  | 40000 |  |  | -183524.05 |  | Capital Funded by Loans
15 | Legal Commitments - for projects undertaking in 04/05 | S2P | 1E | 90 10 6900 |  | 25000 |  | 25000 | 0 | 25000 | 0 |  | 25000 |  |  | 0 | 5000 |  | 5000 | 20000 | 20000 | £20k will be utilised for Leisure Bowl retention |  |  | 5000
16 | Leisure Bowl - refurbishment | S2P | 2L | 90 15 0100 |  | 0 | 17674 | 75000 | 0 | 75000 | -75000 |  | 0 | 0 |  | 0 | 20000 |  | 20000 | -20000 | -20000 | Retention of £20k expected which will be funded from Retention budget (project 15) |  |  | 20000 |  |  | -10539.67 |  | Capital Funded by Loans
17 | Primary & Nursery School Development | S2P | 1E | 90 10 7200 |  | 0 | [7 empty] | 0 |  | 0 |  |  | 0 | 0 |  | Planning of projects is subject to 3-12 Review, once Council decision is made |  | 1000000 | 1000000 |  |  | -1586.49 |  | Capital Funded by Loans
19 | Reconfiguration of Council Services & Property Assets in Tillicoultry | S2P | 1E |  |  | 125000 |  | 125000 | 0 | 125000 | 0 |  | 125000 |  |  | 0 |  |  | 0 | 125000 | 125000 | Tillicoultry community centre was temporarily leased to a joint Clackmannanshire/Stirling "Get Ready for Work" programme until December. Preliminary discussions with library consultants on layout etc have taken place with a view to relocating library by April 2008. Project plan will now be developed with the spend being scheduled for next year. | 125000 | 500000 | 625000 |  |  | 0
20 | DDA Compliance - Social Services | S2P | 3S | 90 30 1800 |  | 19000 |  | 1000 | 0 | 1000 | 18000 |  | 19000 | 1691.94 |  | 1691.94 | 19000 |  | 19000 | 0 | 0 | Works will be completed this year and full spend expected |  |  | 19000
21 | Joint FVNHS/ Adult Care Premises Occupation | S2P | 3S |  |  | 300000 |  | 250000 |  | 250000 |  | 50000 | 300000 |  |  | 0 | 0 |  | 0 | 300000 | 300000 | Following discussions with Head of Service, the project manager advised that it is now clear that the full £300k will not be needed. FVNHS will support some expenditure. Clackmannanshire Council contribution is expected to be £50k but will not require this until 08/09. | 50000 |  | 50000
22 | Menstrie House En-Suite Conversion | S2P | 3S | 90 30 0350 |  | 590000 | 590275 | 150000 | 0 | 150000 | 78000 | 362000 | 590000 | 537278.45 |  | 537278.45 | 590000 |  | 590000 | 0 | 0 | Projects 22 & 25 are interrelated. Projects will be completed in November 2007 and full spend is expected, with a possible minor overspend. Next year's budget is for retention. | 38000 |  | 628000 |  |  | -270159.04 |  | Capital Funded by Loans
23 | Ludgate House External Fabric | S2P | 3S | 90 30 1600 |  | 20000 | 782 |  | 0 | 0 | 20000 |  | 20000 | 31679.58 |  | 31679.58 | 0 |  | 0 | 20000 | 20000 | This budget will not be required now as work was completed using revenue budget. |  |  | 0
25 | Menstrie House - Increased Parking & Security Fencing | S2P | 3S |  |  | 150000 |  | 150000 |  | 150000 |  |  | 150000 |  |  | 0 | 150000 |  | 150000 | 0 |  | See comments in project 22 |  |  | 150000 |  |  | 0
26 | Accident Prevention & Traffic Management | D&E | 4R | 90 40 1020 |  | 100000 |  | 100000 | 0 | 100000 | 0 |  | 100000 | 42352.61 |  | 42352.61 | 45000 |  | 45000 | 55000 | 55000 | Proposed to transfer £60k of this budget to project 93. £5k overspend to be funded from retentions | 100000 | 200000 | 345000 |  |  | -17690.02 |  | Capital Funded by Loans
| Menstrie House Ext & Tele System | S2P | 3S | 90 30 1500 | [20 empty] | 0
27 | Alloa Town Centre | D&E | 6M | 90 40 1750 |  | 180000 |  | 0 | 0 | 0 | 180000 |  | 180000 | 387378.11 |  | 387378.11 | 180000 |  | 180000 | 0 | 0 | Project linked with 111 & 115 below. Link to Shillinghill & Asda (Ph1)and Central Reservation to Shillinghill (Ph3) is complete. Ring Road Crossing to Station Square (Ph2) 95% complete. There may be some carry forward relating to work at Station Building & Central Reservation. |  |  | 180000 |  |  | 0
28 | A91 East Stirling St. Alva Roundabout to access new school site | D&E | 4R |  |  | 450000 |  | 450000 | -225000 | 225000 | 0 |  | 225000 |  |  | 0 | 0 |  | 0 | 225000 | 225000 | Project Manager has proposed to move this project to 08/09 because of lack of resources due to retirement of Roads Engineer and staff illness. No design or preliminary works carried out yet | 225000 |  | 225000 |  |  | -730341.73 |  | Capital Funded by Loans
30 | B9140 Collylands to Glenochil (West) | D&E | 4R | 90 40 4400 |  | 856000 | 18438 | 860000 | 0 | 860000 | -4000 |  | 856000 | 2751 |  | 2751 |  |  | 0 | 856000 | 856000 | Project Manager has proposed to move this project to 08/09 because of lack of resources. Design work carried out. No construction until next year | 838000 | 10000 | 848000 |  |  | 0
| SEN Adaptions | S2P | 1E | 90 10 0901 | [9 empty] | 0 |  | 0 |  |  | 0 | [5 empty] | 0 |  |  | 0
| Property Maintenance | S2P | 1E | 90 10 2000 | [9 empty] | 0 |  | 0 | [8 empty] | 0 |  |  | -116905.19 |  | Capital Funded by Loans
31 | B9140 Realignment of Bends (Collylands to Fishcross/Maggies Wood - East | D&E | 4R |  |  | 0 |  |  |  | 0 |  |  | 0 | [5 empty] | 0 | 0 |  | No design work planned as yet. Project now put back to 2010/11 | 0 | 0 | 0
| Menstrie P S Capital Improvement | S2P | 1E | 90 10 5900 | [9 empty] | 0 |  | 0 |  |  | 0 | 0 |  |  |  |  | 0
32 | Bridge Strengthening | D&E | 4R | 90 40 1700 |  | 466000 | 331562 | 400000 | 0 | 400000 | 66000 |  | 466000 | 441806.57 |  | 441806.57 | 466000 |  | 466000 | 0 | 0 | Full spend of budget this year on Shavelhaugh bridge | 150000 | 30000 | 646000
33 | Flood Prevention | D&E | 4R | 90 40 2700 |  | 124000 |  | 100000 | 0 | 100000 | 24000 |  | 124000 | 2371.45 |  | 2371.45 | 3000 |  | 3000 | 121000 | 121000 | Scottish Water will carry out all works in Elistoun Drive in Tillicoultry, including prevention work which the Council are obliged to do. The work will now be completed next year. | 221000 | 100000 | 324000
34 | Retentions | D&E | 4R |  |  | 60000 |  | 60000 | 0 | 60000 | 0 |  | 60000 |  |  | 0 | 6000 |  | 6000 | 54000 | 54000 |  | 60000 |  | 66000 |  |  | 0
35 | Road & Footway Improvements (SRMCS), including town centres | D&E | 4R | 90 40 3000 |  | 640000 |  | 500000 | 0 | 500000 | 140000 |  | 640000 | 324938.74 |  | 324938.74 | 390000 |  | 390000 | 250000 | 250000 | Proposed to transfer £250k to project 93 | 370000 | 750000 | 1510000 |  |  | -407759.84 |  | Capital Funded by Loans
36 | Cycling , Walking ,Safer Streets (CWSS) | D&E | 4R | 90 40 1310 |  | 86000 |  | 86000 | -86000 | 0 |  |  | 0 | 45957.74 |  | 45957.74 | 86000 | -86000 | 0 | 0 | 0 | Any spend will be grant funded |  |  | 0 |  |  | -1813 |  | Capital Funded by Loans
37 | Street Lighting | D&E | 4R | 90 40 4000 |  | 165000 |  | 165000 | 0 | 165000 | 0 |  | 165000 | 48738.48 |  | 48738.48 | 165000 |  | 165000 | 0 | 0 | Full spend expected on planned projects. £80k will be for Clackmannan Road (Project 153) and £35k for Lime Tree. | 185000 | 200000 | 550000
38 | Total SAK Rail Project & Alloa ELR Project Costs | D&E | 4R | 90 50 3100 |  | 55000 |  |  |  | 0 | 55000 |  | 55000 | 14336674.07 | -20313469 | -5976794.93 | 14350000 | -14295000 | 55000 | 0 | 0 | With the exception of Clackmannanshire's contribution of £2.5m in total, the project is financed by other parties, principally Transport Scotland. To date the Council has contributed £2.445m leaving a final balance of £55k. Arrangements have been in place to ensure that the Council is reimbursed by TS in advance of the expenditure so that the Council is not disadvantaged. The project is due for completion in 2008/09 and is regularly reviewed by project management. The latest projections indicate that the total cost of the project may well increase to over £80m |  |  | 55000 |  |  | -521073.46 |  | Capital Funded by Loans
40 | Tullibody By Pass | D&E | 4R | 90 40 3900 | [9 empty] | 629 | 0 | 629 | [8 empty] | 0 |  |  | -75676 |  | Capital Funded by Loans
41 | 20mph speed reduction | D&E | 4R | 90 40 3200 |  | 109000 |  | 109000 | -109000 | 0 | 0 |  | 0 | 18665.38 |  | 18665.38 | 109000 | -109000 | 0 | 0 | 0 | Any spend will be grant funded | 100000 | 100000 | 200000 |  |  | 0
43 | SESTRAN Public Transport & Walking | D&E | 4R | 90 40 3600 |  | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 70237.51 | 0 | 70237.51 | 190000 | -190000 | 0 | 0 | 0 | Any spend will be grant funded | 141000 | 141000 | 282000 |  |  | -343431.47 |  | Capital Funded by Loans
45 | SUSTRAN - Cycle Routes | D&E | 4R | 90 40 3700 |  | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 48198.5 | -12025 | 36173.5 |  |  | 0 | 0 | 0 | 2 projects; Alloa & Cambus to Devon Bridge. Any spend will be grant funded |  |  | 0 |  |  | -634.08 |  | Capital Funded by Loans
46 | Black Devon Landfill | D&E | 5N | 90 42 0100 |  | 86000 |  |  | 0 | 0 | 86000 |  | 86000 | 58661.69 |  | 58661.69 | 86000 |  | 86000 | 0 | 0 | Full spend expected this year |  |  | 86000 |  |  | -175488.24 |  | Capital Funded by Loans
47 | Black Devon Landfill Gas Collection & Treatment Project | D&E | 5N | 90 40 0200 |  | 400000 |  | 400000 | 0 | 400000 | 0 |  | 400000 |  |  | 0 | 0 |  | 0 | 400000 | 400000 | The site treatment & gas collection is the last phase of the original £2.8m project. This phase involves a complex arrangement with SEPA, with a regulatory regime. No solution in place as yet but the budget will be required as this is a committed project. | 0 | 400000 | 400000 |  |  | -870041.73 |  | Capital Funded by Loans
48 | Cemeteries Strategy | D&E | 5N | 90 41 0110 |  | 187000 |  |  | 0 | 0 | 187000 |  | 187000 | 18677.27 |  | 18677.27 | 70000 |  | 70000 | 117000 | 117000 | The Cemetery Strategy has not yet been approved. There is still a problem with the proposed Dollar cemetery and Tillicoultry site purchase. A new Strategy report is yet to be presented to the Council which may change the capital allocation. In the meantime, the outturn is expected to be £70k for previous strategy. | 117000 |  | 187000 |  |  | -5861.2
49 | Contaminated Land | D&E | 5N | 90 42 0055 | 90 41 0200 | 59000 |  | 50000 | -50000 | 0 | 9000 |  | 9000 | 64869.02 | -10659.36 | 54209.66 | 92000 | -50000 | 42000 | -33000 | -33000 | Anticipated spend has increased to £92k, of which £50k will be grant funded, £9k from budget brought forward from last year. The additional spend has been approved by Director of Service. The overspend of £33k will be funded from retention budget. | 50000 | 50000 | 142000 |  |  | 0
50 | Parks & Open Spaces | D&E | 5N | 90 41 0400 |  | 80000 |  | 80000 | 0 | 80000 | 0 |  | 80000 | 40371.13 |  | 40371.13 | 80000 |  | 80000 | 0 | 0 | All projects have been planned and commenced. Full spend expected | 83000 |  | 163000 |  |  | -3167.5 |  | Capital Funded by Loans
51 | Outdoor Play Area Strategy | D&E | 5N | 90 42 0085 |  | 75000 |  | 75000 | 0 | 75000 | 0 |  | 75000 | 59175.78 |  | 59175.78 | 75000 |  | 75000 | 0 | 0 | All projects have been planned and majority commenced. Full spend expected | 78000 |  | 153000 |  |  | -12786.83 |  | Capital Funded by Loans
54 | Waste Recycling Project | D&E | 5N |  |  | 400000 |  | 400000 | 0 | 400000 | 0 |  | 400000 |  |  | 0 |  |  | 0 | 400000 | 400000 | This is development of Forthbank site. It is not yet at implementation stage, awaiting outcome of bid on Strategic Outline Case submitted to Scottish Executive. This project forms part of that bid. Further details will be provided in future report. The budget will be c/f to 08/09. | 400000 |  | 400000 |  |  | 0
55 | Clackmannan Tollbooth | D&E | 6M | 90 50 3400 |  | 113000 |  | 104000 | -104000 | 0 | 9000 |  | 9000 | 21076.9 |  | 21076.9 | 58000 | -49000 | 9000 | 0 | 0 | Work completed on Mercat Cross & Stone of Mannan. £58k spend this year will be on enhancing Tolbooth, £32k being funded by Clackmannan Heritage Trust & £17k by Heritage Scotland. Proposal to approach HS for further grants for environmental improvements. Work is on target | 70000 | 5000 | 84000 |  |  | -20457.6 |  | Capital Funded by Loans
56 | National Cycle Route | D&E | 6M |  |  | 62000 |  |  | 0 | 0 | 62000 |  | 62000 |  |  | 0 | 100000 | -50000 | 50000 | 12000 | 12000 | Two Cycle Link projects involved: (a) Link at Helensfield is in progress. Additional SUStran funding being investigated. (b) Link at Cambus is delayed pending negotiations with affected landowner for part of proposed route. Part of £62k will be spent for (a) with balance carried forward to 08/09. Additional funding from SUStran may be added to give total overall spend this year to £100k | 12000 |  | 62000
57 | Old Alloa Townscape Heritage Phase 2 | D&E | 6M | 90 50 2700 |  | 253000 |  | 0 | 0 | 0 | 253000 |  | 253000 | 30950 |  | 30950 | 75000 |  | 75000 | 178000 | 178000 | 2 projects involved: (a) Candleriggs Lane (£65k) now awaiting design proposals following renovation of 1936 Kilncraigs building. Possible delays. (b) Lime Tree Walk being progressed with PPP. Trees to be replaced in south section and remainder programmed for completion in advance of school completion in October 2008 | 178000 |  | 253000
58 | Landscape Partnership - converse Ochills / Hillfoots | D&E | 6M |  |  | 1125000 |  | 1125000 | -900000 | 225000 | 0 |  | 225000 |  |  | 0 | 10000 |  | 10000 | 215000 | 215000 | HLF Grant of £47.5 approved to progress grant application. Only £10k of the Council's allocation of £225k will be spent this financial year. Carry forward to 2009/10. | 0 | 145000 | 155000 |  |  | -71915.18 |  | Capital Funded by Loans
59 | Core Path network for Access | D&E | 6M |  |  | 50000 |  | 50000 | -12000 | 38000 | 0 |  | 38000 |  |  | 0 |  |  | 0 | 38000 | 38000 | Possible legal challenge. This will affect programme | 38000 |  | 38000 |  |  | -82003.22 |  | Capital Funded by Loans
60 | Asbestos Removal - Property Services | D&E | 7P | 90 40 3300 |  | 15000 |  | 0 | 0 | 0 | 15000 |  | 15000 |  |  | 0 | 15000 |  | 15000 | 0 | 0 | Expected to be utilised as and when asbestos is discovered during building works |  |  | 15000 |  |  | 0
62 | Disability Discrimination Act - Property Services | D&E | 7P | 90 46 0030 |  | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 777.37 |  | 777.37 | 1000 |  | 1000 | -1000 | -1000 | Funded from retention | 20000 |  | 21000 |  |  | 0
63 | Vehicle Replacement Programme | D&E | 7P |  |  | 833000 |  | 570000 | 0 | 570000 | 263000 |  | 833000 | 399611.64 | 0 | 399611.64 | 504000 |  | 504000 | 329000 | 329000 | Carry forward of £329k expected. Some leases have been extended and some services are still re-assessing their needs. Total budget still expected to be utilised over a 3 year period. | 879000 | 612000 | 1995000 |  |  | -40368.95 |  | Capital Funded by Loans
64 | Efficient Government/Customer First Developments | CD | 8C | 90 70 1900 |  | 172000 |  | 100000 | 0 | 100000 | 72000 |  | 172000 | 1583.32 |  | 1583.32 | 158000 |  | 158000 | 14000 | 14000 | The next project is EDRMS. The balance of the budget is to be carried forward. | 114000 | 500000 | 772000 |  |  | -46252.77 |  | Capital Funded by Loans
65 | IT Services | CD | 8C | 90 70 0451 |  | 377000 |  | 330000 | 0 | 330000 | 47000 |  | 377000 | 206875.51 |  | 206875.51 | 360000 |  | 360000 | 17000 | 17000 | Final spend of £360k expected, with balance carried forward to 2008/09. Spend includes Fibre Link in partnership with Stirling Council. Clackmannanshire Council contribution will be £110k (to be funded from IT capital £30k, and 'Additional Capital Grant' of £80k. An ERDF claim has been submitted). | 317000 | 363000 | 1040000 |  |  | 0
66 | Finance Services - General Ledger system | CD | 8C | 90 70 1125 |  | 42000 |  | 30000 | 0 | 30000 | 12000 |  | 42000 | 6650 |  | 6650 | 42000 |  | 42000 | 0 | 0 | Full spend expected. | 40000 |  | 82000
67 | Ludgate Traffic Management - Retentions | S2P | 3S | 90 30 1900 |  | 1000 |  | 1000 | 0 | 1000 | 0 |  | 1000 | 782.03 |  | 782.03 | 1000 |  | 1000 | 0 | 0 | Retention |  |  | 1000
68 | Econ. Dev. Infrastructure: Eastern Clackmannanshire Development Opportunities | D&E | 6M |  |  | 100000 |  |  | 0 | 0 | 100000 |  | 100000 |  |  | 0 |  |  | 0 | 100000 | 100000 | Project is being assessed with Grant Officer for development opportunities. Possible split between (a) Roundabout works at Forrest Mill and (b) other Eastern Developments. Programme is being finalised. | 100000 |  | 100000 |  |  | -2160 |  | Capital Funded by Loans
69 | Kilncraigs Mill Conversion | D&E | 7P | 90 50 3000 |  | 7000 |  | 0 | 0 | 0 | 7000 |  | 7000 |  |  | 0 | 7000 |  | 7000 | 0 | 0 | see comments in project 71 |  |  | 7000
70 | Kilncraigs Mill 1936 Building Envelop | D&E | 7P | 90 50 4500 |  | 246000 |  | 0 | 0 | 0 | 246000 |  | 246000 | 167936 | -15543.69 | 152392.31 | 321000 | -75000 | 246000 | 0 | 0 | The 1936 building envelop work will be completed this financial year. |  |  | 246000 |  |  | -16872.18 |  | Capital Funded by Loans
71 | Kilncraigs Mill 1904 Development of 3rd & 4th Floors | D&E | 7P | 90 50 4600 |  | 305000 |  |  | 0 | 0 | 305000 |  | 305000 | 1054233.62 |  | 1054233.62 | 305000 |  | 305000 | 0 | 0 | It is proposed that these 4 Kilncraig's budgets (69,71,72 & 98) be treated as one whole. Total spend on these projects to 06/07 was £1,700k. and a further £1,511k to completion, bringing the total anticipated spend to £3,211k. The spend is well within the budget allocated. Additional spend of £150k is anticipated but this will be funded from HRA as part of Housing capital works. | 30000 |  | 335000 |  |  | 0
72 | Kilncraigs Mill 1904 Access Control & Zoning Services | D&E | 7P |  |  | 80000 |  | 0 | 0 | 0 | 80000 |  | 80000 |  |  | 0 | 80000 |  | 80000 | 0 | 0 | see comments in project 71 |  |  | 80000 |  |  | 0
73 | Pavilions Business Park Phase 2 | D&E | 6M | 90 50 2900 |  | 340000 |  |  | 0 | 0 | 340000 |  | 340000 | 135000 |  | 135000 |  |  | 0 | 340000 | 340000 | Building complete and being marketed – AI issued to add the work for car park extension for Phase 3 which is now complete. (additional ERDF grant approved). Project managed & spent by CSBP. Clackmannanshire contribution of £340k will be made to CSBP as & when building is occupied by tenants. | 340000 |  | 340000 |  |  | 0
74 | Dumyat Business Park Phase 3 | D&E | 6M | 90 50 2800 |  | 40000 |  | 0 | 0 | 0 | 40000 |  | 40000 |  |  | 0 |  |  | 0 | 40000 | 40000 | Planning approval granted and CSBP partners continuing to process funding with Bank. Building Warrant submitted. Programme start on site delayed. Council contribution of £40k will be made to CSBP on completion. | 40000 |  | 40000
75 | CCTV | CE | 9X | 90 20 0600 |  | 45000 |  |  |  | 0 | 45000 |  | 45000 | 822.5 | -441.31 | 381.19 | 1000 |  | 1000 | 44000 | 44000 | Possible carry forward required pending approval of proposed projects. It is highly likely that some of the cameras will need replacing next year and this budget may be utilised for the purpose. | 44000 | 65000 | 110000
76 | DDA & Asbestos Removal - Corporate Development Services | CD | 8C | 90 50 4300 |  | 17000 |  |  | 0 | 0 | 17000 |  | 17000 |  |  | 0 | 17000 |  | 17000 | 0 | 0 | Expected to be utilised as and when asbestos is discovered during building works |  |  | 17000 |  |  | -13038 |  | Capital Funded by Loans
82 | Council Office Improvements | CD | 8C |  |  | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | No design or preliminary work commenced yet | 140000 |  | 140000 |  | 0 | see below | 0 | 0
| Dollar Public Convenience | D&E | 5N | 90 40 2500 | [11 empty] | 0 |  |  | 0 |  |  | Funded from retention budget |  |  | 0 |  |  | -313235.66 |  | Capital Funded by Loans
83 | Greenfield Driveway & Parking | CD | 8C | 90 60 1600 |  | 84000 |  | 84000 | 0 | 84000 | 0 |  | 84000 | 33000 |  | 33000 | 84000 |  | 84000 | 0 | 0 | Works completed. Awaiting billing from Roads Contract |  |  | 84000 |  |  | -18090.53 |  | Capital Funded by Loans
85 | ICT Hardware Replacement in Sec Schls & New IT Installation in Schools | S2P | 1E | 90 10 7600 |  | 0 |  |  |  | 0 |  |  | 0 | 17487 |  | 17487 | 18000 |  | 18000 | -18000 |  | Projects are related to and to be commenced in conjunction with the PPP programme. | 1582000 |  | 1600000 |  |  | -825.25 |  | Capital Funded by Loans
87 | Alloa Town Hall Redevlopment | S2P | 2L | 90 15 0175 | [9 empty] | 5819.61 |  | 5819.61 | 14000 |  | 14000 | -14000 | -14000 | Project proposed for 2011/12. Initial fees in this year will be temporary borrowing in advance |  |  | 14000
88 | Development of Community Facilities in Alva | S2P | 1E | 90 15 0180 |  | 25000 |  | 25000 | 0 | 25000 | 0 |  | 25000 | 210 |  | 210 | 25000 |  | 25000 | 0 | 0 | Project not started yet. Some design fees will be payable this year. Sheila advised that she will be applying for Sports Lottery grant for this project, which may reduce Council contribution | 25000 | 2800000 | 2850000 |  |  | 0
89 | Cochrane Hall, Alva Refurbishment & Upgrading | S2P | 1E | 90 15 0170 |  | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 4490 |  | 4490 | 5000 |  | 5000 | -5000 | -5000 | Project not started yet. Condition survey has been carried out. Spend of £5k will be funded by transfer of budget from 08/09 | 20000 | 500000 | 525000 |  |  | -1042717.8 |  | Capital Funded by Loans
91 | Clackmannanshire's Outdoor Activity Centre | S2P | 1E |  |  | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | Projects to be developed in conjunction with PPP project | 25000 | 300000 | 325000 |  |  | -414787.24 |  | Capital Funded by Loans
92 | Running Track at Lornshill Academy | S2P | 1E |  |  | 0 | [12 empty] | 0 | 0 |  | Projects to be developed in conjunction with PPP project. Stage 1 lottery bid to be submitted in 08/09 |  | 260000 | 260000 |  |  | 0
93 | A907 B910/Helensfield Junction for Railway Line/Marywood Improvement | D&E | 4R | 90 40 4700 |  | 425000 |  | 7000 | 0 | 7000 | 418000 |  | 425000 | 882565.62 |  | 882565.62 | 885000 |  | 885000 | -460000 | -460000 | There is now an additional spend of £150k from the position reported in the last report. The £460k will be funded from transfers of £250k from project 35 and £60k from project 26 (as reported previously) and the additional £150k from Roads & Footpaths budget from 2008/09. This is in relation to the extended roundabout works along A907 towards Helensfield. |  | 0 | 885000 |  |  | -9684.44 |  | Capital Funded by Loans
97 | Wheeled / Litter Bins | D&E | 5N | 90 42 0065 |  | 100000 |  | 100000 | 0 | 100000 | 0 |  | 100000 | 18056 |  | 18056 | 19000 |  | 19000 | 81000 | 81000 | Expected outturn is £19k. The balance of the budget will not be required. | 100000 | 60000 | 179000 |  |  | 0
98 | Kilncraigs Mill 1904 Upgrade of Existing | D&E | 7P |  |  | 760000 |  | 20000 | 0 | 20000 | 740000 |  | 760000 |  |  | 0 | 760000 |  | 760000 | 0 | 0 | see comments in project 71 |  |  | 760000 |  |  | 0
99 | Forthbank Accommodation Rationalisation | D&E | 7P |  |  | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | No design or preliminary work commenced yet, but essential replacement. | 75000 |  | 75000 |  |  | 0
103 | Demolition of Lornshill Academy & Construct Car Parking & Football Pitch | S2P | 1E |  |  | 0 | [12 empty] | 0 | 0 |  | Possible funding from Sports Lottery & Sport Scotland. |  | 1250000 | 1250000 |  |  | -7588.62 |  | Capital Funded by Loans
104 | Purchase of White Boards for new schools | S2P | 1E |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | Projects are related to and to be commenced in conjunction with the PPP programme. | 450000 |  | 450000 |  |  | -27518.21 |  | Capital Funded by Loans
106 | Shillinghill Roundabout | D&E | 4R |  |  | 0 |  |  |  | 0 |  |  | 0 | [5 empty] | 0 | 0 | 0 | No design or preliminary works carried out yet. Possible that project may change | 40000 | 0 | 40000
107 | A908/B908 Hallpark, Sauchie | D&E | 4R | 90 40 4800 |  | 0 |  |  |  | 0 |  |  | 0 | 900 |  | 900 |  |  | 0 | 0 |  | Work to commence in April 08. Will still be complete in time for hospital opening. The Council contribution will be reduced from £350k to £65k as FV Health Board have agreed to contribute £285k for this project. | 90000 | 0 | 90000 |  |  | 0
110 | Alloa Town Centre Regeneration: Speirs Centre | D&E | 6M | 90 50 4900 |  | 330000 |  | 330000 |  | 330000 |  |  | 330000 | 44304.86 |  | 44304.86 | 290000 |  | 290000 | 40000 | 40000 | Briefing meetings & outline proposals prepared. Programme being finalised to take to pre-tender stage. Other funders are now involved with the funding to be added to the project to give a substantially bigger overall project total. Of the Council contribution of £330k, only £290k will be spent this year on fees. Outline programme: detailed design - July 2008; tender - Sept 2008; on site - Feb 2009; completion - July 2010 | 380000 | 1650000 | 2320000
111 | Alloa Town Centre: Public Realm Phase 2 | D&E | 6M |  |  | 220000 |  | 220000 |  | 220000 |  |  | 220000 |  |  | 0 | 220000 |  | 220000 | 0 | 0 | Being progressed in conjunction with project 27 above as part of Ph4. May need to c/f full budget to 08/09 |  |  | 220000
114 | Lime Tree Walk Phase 2 | D&E | 6M |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  | 0 | 150000 |  | 150000 | -150000 | -150000 | Budget brought forward from 08/09 and added to Phase 1 in No. 57 above. Design work committed to tender stage. | 935000 | 250000 | 1335000 |  |  | 0
115 | Shillinghill to Town Hall: Environmental Regeneration | D&E | 6M |  |  | 150000 |  | 150000 |  | 150000 |  |  | 150000 |  |  | 0 | 150000 |  | 150000 | 0 | 0 | Being progressed in conjunction with project 27 as part of Ph4. May need to c/f full budget to 08/09 | 50000 |  | 200000 |  |  | 0
116 | New Alloa Infrastructure | D&E | 6M |  |  | 240000 |  | 240000 | -53000 | 187000 |  |  | 187000 |  |  | 0 |  |  | 0 | 187000 | 187000 | Being delayed pending MCA development proposals. | 187000 |  | 187000 |  |  | 0
118 | Pavilions Phase 3 | D&E | 6M |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 |  |  | 0 |  | 0
120 | Air Conditioning System - Class Cuisine Sauchie (See 61 above) | D&E | 7P | 90 50 4400 |  | 30000 |  | 30000 |  | 30000 | 0 |  | 30000 | 28374.21 |  | 28374.21 | 30000 |  | 30000 | 0 |  | Project completed . Unspent budget will be carried forward for retention. |  |  | 30000 |  |  | -24732 |  | Capital Funded by Loans
121 | Greenfield Heating | CD | 8C | 90 60 1800 |  | 150000 |  | 150000 |  | 150000 | 0 |  | 150000 | 5113.91 | -331500 | -326386.09 | 150000 | -150000 | 0 | 150000 |  | Work ongoing. Boiler replaced . Rest of work dependent on weather conditions. Work will now be financed by 'Additional Capital Grant". This will reduce Council Borrowing by £150k. |  |  | 0 |  |  | 0
122 | Sun Tube, Lime Tree House | D&E | 7P |  |  | 20000 |  | 20000 |  | 20000 | 0 |  | 20000 |  |  | 0 |  |  | 0 | 20000 |  | Budget will not be required as project has proved not to be necessary. |  |  | 0
123 | Kelliebank - Thermal Efficieny Windows | D&E | 7P | 90 46 0055 |  | 22000 |  | 22000 |  | 22000 | 0 |  | 22000 | 17950.19 |  | 17950.19 | 22000 |  | 22000 | 0 |  | Project is complete. Full expenditure yet to be posted. |  |  | 22000
125 | Gateways & Roundabouts | D&E | 6M | 90 41 0300 |  | 51000 |  |  |  | 0 | 51000 |  | 51000 | 50830.28 |  | 50830.28 | 51000 |  | 51000 | 0 | 0 |  |  |  | 51000
126 | Muchart Primary Heating Plant - Additional capital grant | S2P | 1E | 90 10 7300 | [9 empty] | 66424 | 0 | 66424 | 88000 | -88000 | 0 | 0 |  | Scottish Exec made available a special grant for £663k to fund projects which "maximise future savings to the Council". Council approved these 5 projects in June 2007. The Council also approved a sixth project, Greenfield Heating System, which was due to be financed by Council borrowing. However, since it meets the grant's criteria, it was agreed that the project would be funded by the grant, with a corresponding saving of £150k on Council borrowing. (see project 121) |  |  | 0
127 | Park Primary Heating Plant - Additional capital grant | S2P | 1E | 90 10 7500 | [10 empty] | 0 | 0 | 55000 | -55000 | 0 | 0 |  | see comments in project 126 |  |  | 0
128 | St Serf's Primary Heating Plant - Additional capital grant | S2P | 1E | [11 empty] | 0 | 0 | 55000 | -55000 | 0 | 0 |  | see comments in project 126 |  |  | 0 |  |  | -525577.86 |  | Capital Funded by Loans
129 | Fibre Optic Link - Additional capital grant | CD | 8C | [11 empty] | 0 | 0 | 80000 | -80000 | 0 | 0 |  | see comments in project 126 |  |  | 0 |  |  | -525577.86 |  | Capital Funded by Loans
130 | West Haugh Travelling People's site - Additional capital grant | S2P | 3S | 90 30 2100 | [9 empty] | 11194.87 |  | 11194.87 | 230000 | -230000 | 0 | 0 |  | see comments in project 126 |  |  | 0 |  |  | -525577.86 |  | Capital Funded by Loans
134 | Extention & Refurbishment of CLICk (Glebe Hall) | S2P | 1E | [12 empty] | 0 |  |  | 0 | 0 |  |  | 120000 |  | 120000 |  |  | -525577.86 |  | Capital Funded by Loans
138 | ERDF Grant Programme 2007-13 Match Funding for various projects | CE | 9X | [12 empty] | 0 |  |  | 0 | 0 |  |  | 750000 |  | 750000 |  |  | -525577.86 |  | Capital Funded by Loans
140 | Shillinghill to TownHall: Relocated Road Crossing | D&E | 6M | [12 empty] | 0 |  |  | 0 | 0 |  |  | 285000 |  | 285000
147 | Mixed Leisure Route Upgrading | D&E | 4R | [12 empty] | 0 |  |  | 0 | 0 |  |  | 10000 |  | 10000 |  |  | -525577.86 |  | Capital Funded by Loans
150 | B9140/ Collylands Cross Upgrade | D&E | 4R | 90 40 4500 |  | 35000 |  | 100000 | 0 | 100000 | -65000 |  | 35000 | 32897.19 |  | 32897.19 | 35000 |  | 35000 | 0 | 0 | Project is complete. Full spend expected |  |  | 35000
152 | Capital Contribution to Police Board | CE | 9X | [12 empty] | 0 |  |  | 0 | 0 |  |  | 225000 | 225000 | 450000
153 | Alloa East Gateway - Clackmannan Road | D&E | 6M | 90 50 4700 | [9 empty] | 151411.9 |  | 151411.9 | 331000 | -331000 | 0 | 0 |  | Tenders received, contract accepted with AEL Ltd. Commenced on site 10th Sept. Programmed for completion by Feb 2008. Street Lighting added to contract. Funded by ERDF, although grant will not be received until 2008/09. In the meantime expenditure will be funded by temporary borrowing. |  |  | 0
155 | Straegic Waste Fund | D&E | 5N | [12 empty] | 0 |  |  | 0 | 0 |  |  | 28000 | 28000 | 56000
| A907 Improvements | D&E | 4R | 90 40 1650 | [9 empty] | 42 |  | 42 | [8 empty] | 0
| Kirkgate | D&E | 6M | 90 51 8808 | [9 empty] | 20007 |  | 20007 | 20000 | -20000 | 0 | 0 |  | Final Heritage Lottery Claim of £20k has now been received to off set this expenditure |  |  | 0
| Old Parish Church | D&E | 6M | 90 51 8812 | [9 empty] | 5578.95 |  | 5578.95 | 5000 |  | 5000 | -5000 |  | No further funding available from CHT. Will be funded from retention. |  |  | 5000
| Repairing Obelisk Gate Piers | D&E | 6M | 90 51 8806 | [9 empty] | 1814.02 |  | 1814.02 | 2000 |  | 2000 | -2000 |  | No further funding available from CHT. Will be funded from retention. |  |  | 2000 |  |  | 0
| Upgrading of Toilets | D&E | 5N | 90 46 0020 | [9 empty] | 5466.84 |  | 5466.84 | 8000 |  | 8000 | -8000 |  | Funded from retention budget |  |  | 8000
| Land Acquisition for Schools PPP | S2P | 1E | 90 10 6800 | [9 empty] | 149160.64 |  | 149160.64 | 150000 |  | 150000 | -150000 |  | This expenditure includes road & access works in connection with the new Alva school. This is unbudgeted capital expenditure. |  |  | 150000
| Other Regional Transport Projects | D&E | 4R | [12 empty] | 0 |  |  | 0 | 0 |  |  | 335000 | 335000 | 670000
0
| ERDF | D&E | 6M | 90 90 0990 | [10 empty] | -397940 | -397940 | [8 empty] | 0
77 | Unallocated Capital Receipts | D&E | 7P | 90 90 xxxx | [9 empty] | 8926.14 | -20854.68 | -11928.54 | -12000 |  | -12000 | 12000 |  | With effect from last year, the Council has approved to ring fence Capital receipts for the next 3 to 4 years. The target is £17m, staged over specific trigger dates depending on market conditions. To date £3.23m receipts have been set aside with the expectation that balance will be achieved on target dates. A number of surplus properties have been earmarked for sale this year depended on planning permission etc. | 0 | -996000 | -1008000
300 | General Capital Grant from Scottish Government | CD | 8C | [12 empty] | 0 |  |  | 0 | 0 |  |  | -2283000 | -3064000 | -5347000
| TOTAL CAPITAL PROGRAMME (excluding Schools PPP Project) | [6 empty] | 9862000 | -2594000 | 7268000 | 3980000 | 412000 | 11660000 | 21779510.27 | -21718801.04 | 60709.23 | 25193000 | -17474000 | 7719000 | 3941000 | 3942000 |  | 9250000 | 9725000 | 26694000
SCHOOLS PPP PROJECT
1,3,5 | PPP Capital Support | S2P | PPP | 90 10 7000 |  |  |  | 3600000 | 0 | 3600000 | 4650000 | -8250000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | The budgets for the Council contribution to PPP scheme is now to be financed from capital receipts from sale of assets rather than borrowing. The capital budgets together with capital receipts are therefore shown separately from the main capital programme and have been c/f to future years to be utilised as and when required under the PPP contract. | 16350000 | 0 | 16350000
5 | PPP Capital Support - Addional allocation | S2P | PPP | [19 empty] | 2000000 | 500000 | 2500000
9 | School Developments - Allocated to PPP | S2P | PPP |  |  |  |  | 0 | 0 | 0 | 175000 | -175000 | 0 |  |  | 0 | 0 |  | 0 | 0 | 0 |  | 775000 | 200000 | 975000
| Sale of Specific Assets (Detailed separately) | S2P | PPP | [19 empty] | -16350000 |  | -16350000
300 | General Capital Grant (Allocation for School Fund) | S2P | PPP | [19 empty] | -775000 | -200000 | -975000
| Total PPP Project |  |  |  |  | 0 | 0 | 3600000 | 0 | 3600000 | 4825000 | -8425000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2000000 | 500000 | 2500000 | 0 | 0 | 0 | 0 | 0
DETAILS PROPERTY CAPITAL RECEIPTS
77 | 22/4 Candleriggs, Alloa |  |  | 9090 6800 | [11 empty] | 0 |  |  | 0
77 | Skip Site - Hallpark, Sauchie |  |  | 9090 0726 | [11 empty] | 0 |  |  | 0
77 | Dewar St, Lorne Lane , Dollar |  |  | 9090 0800 | [11 empty] | 0 |  |  | 0
77 | Collyland - Fishcross |  |  | 9070 1700 | [11 empty] | 0 |  |  | 0
77 | Cowan Terrace Dollar |  |  | 9090 0875 | [11 empty] | 0 |  |  | 0
77 | Candleriggs, Alloa |  |  | 9090 0950 | [11 empty] | 0 |  |  | 0
77 | General Receipts |  |  | 9090 1000 | [11 empty] | 0 |  |  | 0
77 | Alexandra Street, Devonside |  |  | 9090 2200 | [11 empty] | 0 |  |  | 0
77 | Gap Site - Drysdale/Mill Street |  |  | 9090 1050 | [11 empty] | 0 |  |  | 0
77 | Bedford Place Alloa |  |  | 9090 1100 | [11 empty] | 0 |  |  | 0
77 | Bedford House - Alloa |  |  | 9090 1125 | [11 empty] | 0 |  |  | 0
77 | Cowden Park Alloa |  |  | 9090 1175 | [11 empty] | 0 |  |  | 0
77 | Forestmill Primary School |  |  | 9090 1325 | [11 empty] | 0 |  |  | 0
77 | Former School Clackmannan |  |  | 9090 1400 | [11 empty] | 0 |  |  | 0
77 | Orchard Tullibody - Housing Land |  |  | 9090 1525 | [11 empty] | 0 |  |  | 0
77 | Alloa West |  |  | 9090 0550 | [11 empty] | 0 |  |  | 0
77 | Alloa West - Autism Site |  |  | 9090 5800 | [11 empty] | 0 |  |  | 0
77 | Menstrie Centre Playground |  |  | 9090 1600 | [11 empty] | 0 |  |  | 0
77 | Collyland Road - Fishcross Housing Site |  |  | 9090 1700 | [11 empty] | 0 |  |  | 0
77 | Shops - Sauchie |  |  | 9090 1850 | [11 empty] | 0 |  |  | 0
77 | Kirkgate - Alloa |  |  | 9090 2100 | [11 empty] | 0 |  |  | 0
77 | Alexandra Street, Devonside |  |  | 9090 2200 | [11 empty] | 0 |  |  | 0
77 | Long Row Menstrie - Land |  |  | 9090 2700 | [11 empty] | 0 |  |  | 0
77 | Mar Place Sauchie WC |  |  | 9090 2800 | [11 empty] | 0 |  |  | 0
77 | 5 Muirside Road, Tullibody |  |  | 9090 3025 | [11 empty] | 0 |  |  | 0
77 | Park Street, Alva |  |  | 9090 3500 | [11 empty] | 0 |  |  | 0
77 | Bankhead - Devon Village |  |  | 9090 6100 | [11 empty] | 0 |  |  | 0
77 | Claremont Business Centre |  |  | 9090 1025 | [9 empty] | 54.5 |  | 54.5 |  |  | 0
77 | Dumyat Business Park |  |  | 9090 7000 | [11 empty] | 0 |  |  | 0
77 | Dumyat Business Park - Belhaven Breweries |  |  | 9090 7400 | [11 empty] | 0 |  |  | 0
77 | Earlsfield/Alloa Park |  |  | 9090 1750 | [11 empty] | 0 |  |  | 0 | [8 empty] | -48 |  | Capital Funded by Loans
77 | Fishcross - Devon Riding Centre |  |  | 9090 6900 | [11 empty] | 0 |  |  | 0 | [9 empty] | 154.32 | Cap Recp applied to Cap Exp
77 | Land - Ochilvale Mill Alva |  |  | 9090 3900 | [11 empty] | 0 |  |  | 0 | [8 empty] | 0
77 | St Mungo's Wynd Alloa |  |  | 9090 4000 | [11 empty] | 0 |  |  | 0 | [8 empty] | 0
77 | 28 Ramsay Street, Clackmannan |  |  | 9090 4100 | [11 empty] | 0 |  |  | 0 | [8 empty] | 0
77 | Old Toll House, Muckhart |  |  | 9090 4200 | [11 empty] | 0 |  |  | 0 | [8 empty] | 0
77 | Main St Coalsnaughton |  |  | 9090 4300 | [11 empty] | 0 |  |  | 0 | [8 empty] | 0
77 | Baingle Crescent |  |  | 9090 4400 | [11 empty] | 0 |  |  | 0 | [8 empty] | 0
77 | Gas Governor at the Baingle |  |  | 9090 4500 | [11 empty] | 0 |  |  | 0 | [8 empty] | 0
77 | Fairfield Sauchie |  |  | 9090 4600 | [11 empty] | 0 |  |  | 0 | [8 empty] | 0
77 | Scout Hall Main Street Sauchie |  |  | 9090 4700 | [11 empty] | 0 |  |  | 0 | [8 empty] | 0
77 | 3/5 Lower Mains Dollar |  |  | 9090 4800 | [11 empty] | 0 |  |  | 0 | [8 empty] | 0
77 | Railway Station Alloa Road |  |  | 9090 4900 | [11 empty] | 0 |  |  | 0 | [8 empty] | 0
77 | Land at Shawpark garage |  |  | 9090 5000 | [11 empty] | 0 |  |  | 0 | [8 empty] | 0
77 | Service Station Site / Ditch Farm |  |  | 9090 5100 | [11 empty] | 0 |  |  | 0 | [8 empty] | 0
77 | Pavilions Phase 2 |  |  | 9090 5200 | [11 empty] | 0 |  |  | 0 | [8 empty] | 0
77 | TOMA CPO |  |  | 9090 5300 | [11 empty] | 0 |  |  | 0 | [8 empty] | 0
77 | Sinclairs Haulage - Land |  |  | 9090 5400 | [11 empty] | 0 |  |  | 0 | [8 empty] | 0
77 | Alva House Stable Block |  |  | 9090 5500 | [11 empty] | 0 |  |  | 0 | [8 empty] | 0
77 | 3/5 Henderson Avenue, Alloa |  |  | 9090 5600 | [11 empty] | 0 |  |  | 0 | [8 empty] | 0
77 | Land at Rear 78/80 West Stirling Street Alva |  |  | 9090 5700 | [11 empty] | 0 |  |  | 0 | [8 empty] | 0
77 | Fishcross - Land at Devonbank Cottage |  |  | 9090 7100 | [11 empty] | 0 |  |  | 0 | [8 empty] | 0
77 | Washington House - Alva |  |  | 9090 5900 | [11 empty] | 0 |  |  | 0 | [8 empty] | 0
77 | 23 Main Street Sauchie |  |  | 9090 6000 | [11 empty] | 0 |  |  | 0 | [8 empty] | 0
77 | Bank Head, Devon Village Rescue |  |  | 9090 6100 | [11 empty] | 0 |  |  | 0 | [8 empty] | 0
77 | Smithfield Loan - Railway Embankment |  |  | 9090 6200 | [11 empty] | 0 |  |  | 0 | [8 empty] | 0
77 | Superiority - Smithfield Loan |  |  | 9090 6300 | [11 empty] | 0 |  |  | 0 | [8 empty] | 0
77 | Land at Broad Street, Alloa |  |  | 9090 6400 | [11 empty] | 0 |  |  | 0 | [8 empty] | 0
77 | Land for Access to Stirling St |  |  | 9090 6500 | [11 empty] | 0 |  |  | 0 | [8 empty] | 0
77 | Garage Site Gartmorn Dam House |  |  | 9090 6600 | [11 empty] | 0 |  |  | 0 | [8 empty] | 0
77 | Lochy Falls,15 Upper Hillfoot, Dollar |  |  | 9090 6700 | [11 empty] | 0 |  |  | 0 | [8 empty] | 0
77 | Former Toilets - Alva |  |  | 9090 7800 | [11 empty] | 0 |  |  | 0 | [8 empty] | 0
77 | Hillpark |  |  | 9090 3700 | [11 empty] | 0 |  |  | 0 | [8 empty] | 0
77 | Hallpark/Main Street Sauchie |  |  | 9090 0700 | [11 empty] | 0 |  |  | 0 | [8 empty] | 0
77 | Land at Park St Tillicoultry |  |  | 9090 7300 | [11 empty] | 0 |  |  | 0 | [8 empty] | 0
77 | Land at Ditch Farm |  |  | 9090 7500 | [9 empty] | 2831.64 |  | 2831.64 |  |  | 0 | [8 empty] | -2677.32 | -154.32 | Capital Funded by Loans/ Cap Receipts
77 | Land/Car Park - Erskine ST Alloa |  |  | 9090 3800 | [11 empty] | 0 |  |  | 0 | [8 empty] | 0
77 | Housing Land The Orchard Tullibody |  |  | 9090 1525 | [11 empty] | 0 |  |  | 0 | [8 empty] | 0
77 | Property Conversion Feasibility Study |  |  | 9090 7200 | [11 empty] | 0 |  |  | 0 | [8 empty] | 0
77 | Former Thistle Brewery |  |  | 9090 7700 | [11 empty] | 0 |  |  | 0 | [8 empty] | 0
77 | Tullis Factory |  |  | 9090 1575 | [11 empty] | 0 |  |  | 0 | [8 empty] | -119.07 |  | Capital Funded by Loans
77 | Sale of Land at Tullibody (Ditch Farm) |  |  | 9090 5100 | [11 empty] | 0 |  |  | 0 | [8 empty] | -30 |  | Capital Funded by Loans
77 | Title swop with Ceteris |  |  | 9090 8000 | [10 empty] | -20854.68 | -20854.68 |  |  | 0 | [8 empty] | 71068.68 | -50214 | Capital Funded by Loans/ Cap Receipts
| Sale of Alloa/Alva Secondary Schools |  |  | 9090 8200 | [9 empty] | 6040 |  | 6040 |  |  | 0
77 | North Castle Street |  |  | 9090 8100 | [11 empty] | 0 |  |  | 0 | [9 empty] | 50214 | Cap Recp applied to Cap Exp
[16 empty] | 0 |  |  | 0
0
| Total - Property Sales | [12 empty] | 8926.14 | -20854.68 | -11928.54 | 0 | 0 | 0 | [7 empty] | 0 | 68194.29 | 0 | 0
DETAILS VEHICLE REPLACEMENT PROGRAMME
63a | DLO Vehicle - Property Contracts |  |  | 9045 0100 |  |  |  | 52400 |  | 52400 | 45000 |  | 97400 | 48729 |  | 48729 | 97400 |  | 97400 | 0 | 0 | [6 empty] | -191240 |  | Capital Funded by Loans
63a | DLO Vehicle - Refuse Collection |  |  | 9045 0110 | [5 empty] | 0 |  |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | [6 empty] | -330592 |  | Capital Funded by Loans
63a | DLO Vehicle - Street Cleaning |  |  | 9045 0120 |  |  |  | 161500 |  | 161500 | 84000 |  | 245500 | 199643 |  | 199643 | 245500 |  | 245500 | 0 | 0 | [6 empty] | 0
63a | DLO Vehicle - Land Services |  |  | 9045 0130 |  |  |  | 93000 |  | 93000 | 60000 |  | 153000 | 16910 |  | 16910 | 153000 |  | 153000 | 0 | 0 | [6 empty] | -135204 |  | Capital Funded by Loans
63a | DLO Vehicle - Roads Contracts |  |  | 9045 0140 |  |  |  | 109100 |  | 109100 | 48000 |  | 157100 | 38925 |  | 38925 | 157100 |  | 157100 | 0 | 0 | [6 empty] | -58907.15 |  | Capital Funded by Loans
63a | DLO Vehicle - Roads Client |  |  | 9045 0260 |  |  |  | 12500 |  | 12500 |  |  | 12500 | 11003.89 |  | 11003.89 | 12500 |  | 12500 | 0 | 0
63a | DLO Vehicle - Catering Services |  |  | 9045 0150 |  |  |  | 12500 |  | 12500 |  |  | 12500 |  |  | 0 | 12500 |  | 12500 | 0 | 0 | [6 empty] | 0
63a | DLO Vehicle - Transport Pool |  |  | 9045 0160 | [5 empty] | 0 |  |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | [6 empty] | -28331 |  | Capital Funded by Loans
63a | DLO Vehicle - Leisure |  |  | 9045 0170 | [5 empty] | 0 |  |  | 0 |  |  | 0 | 0 |  | 0 | 0 | 0 | [6 empty] | 0
63a | DLO Vehicle - Social Services |  |  | 9045 0200 |  |  |  | 53000 |  | 53000 |  |  | 53000 |  |  | 0 | 53000 |  | 53000 | 0 | 0 | [6 empty] | 0
63a | DLO Vehicle - Burial Services |  |  | 9045 0210 | [5 empty] | 0 |  |  | 0 | 6995 |  | 6995 | 0 |  | 0 | 0 | 0 | [6 empty] | -30207 |  | Capital Funded by Loans
63a | DLO Vehicle - Countryside Rangers |  |  | 9045 0220 | [5 empty] | 0 |  |  | 0 |  |  | 0 | 0 |  | 0 | 0 | 0 | [6 empty] | 0
63a | DLO Vehicle - G F Housing |  |  | 9045 0225 | [5 empty] | 0 |  |  | 0 | 8000 |  | 8000 | 0 |  | 0 | 0 | 0 | [6 empty] | 0
63a | DlLO Vehicle - Waste Disp & Containers |  |  | 9045 0230 | [5 empty] | 0 |  |  | 0 | 29802.75 |  | 29802.75 |  |  | 0 | 0 | 0
63a | DLO Vehicle - HRA Amenity Team |  |  | 9045 0250 | [5 empty] | 0 |  |  | 0 | 10021 |  | 10021 |  |  | 0 | 0 | 0
63a | DLO Vehicle - Glenochil Nursery | [6 empty] | 15000 |  | 15000 |  |  | 15000 |  |  | 0 | 15000 |  | 15000 | 0 | 0 | [6 empty] | 0
63a | DLO Vehicle - Chief Executive |  |  | 9045 0240 | [5 empty] | 0 |  |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | [6 empty] | -11801 |  | Capital Funded by Loans
63a | DLO Vehicle - Black Devon | [8 empty] | 0 | 26000 |  | 26000 |  |  | 0 | 26000 |  | 26000 | 0 | 0 | [6 empty] | 0
63a | DLO Vehicle - Dog Warden |  |  | 9045 0280 |  |  |  | 17500 |  | 17500 |  |  | 17500 | 19015 |  | 19015 | 17500 |  | 17500 | 0 | 0
63a | DLO Vehicle - Pest Control |  |  | 9045 0270 |  |  |  | 12000 |  | 12000 |  |  | 12000 | 10567 |  | 10567 | 12000 |  | 12000 | 0 | 0
63a | DLO Vehicle - Education | [6 empty] | 60100 |  | 60100 |  |  | 60100 |  |  | 0 | 60100 |  | 60100 | 0 | 0
| Reduction | [6 empty] | -28600 |  | -28600 |  |  | -28600 |  |  | 0 | -28600 |  | -28600 | 0 | 0
| Total - Vehicle Programme | [6 empty] | 570000 | 0 | 570000 | 263000 |  | 833000 | 399611.64 | 0 | 399611.64 | 833000 | 0 | 833000 | 0 | 0 | [5 empty] | 0 | -786282.15 | 0 | 0
| DO NOT ENTER ANYTHING IN THE BLUE BOX BELOW | [25 empty] | 0 |  |  | DR CFCR Allocation
| SUMMARY OF SERVICE UNITS | [26 empty] | #VALUE! |  | DR: Loans Fund Allocation to Gen Fund
| Education & Community |  | 1E |  |  |  |  | 1578000 | -1055000 | 523000 | 139000 | 0 | 662000 | 1845853.77 | -616368 | 1229485.77 | 2442000 | -1759000 | 683000 | -21000 |  |  | 2435000 | 7566000 | 10684000
| Leisure |  | 2L |  |  |  |  | 115000 | 0 | 115000 | -75000 | 0 | 40000 | 5819.61 | 0 | 5819.61 | 34000 | 0 | 34000 | 6000 |  |  | 40000 | 0 | 74000
| Social Services |  | 3S |  |  |  |  | 552000 | 0 | 552000 | 116000 | 412000 | 1080000 | 582626.87 | 0 | 582626.87 | 990000 | -230000 | 760000 | 320000 |  |  | 88000 | 0 | 848000
| Roads & Transportation |  | 4R |  |  |  |  | 2937000 | -420000 | 2517000 | 634000 | 0 | 3151000 | 16299725.86 | -20325494 | -4025768.14 | 16730000 | -14680000 | 2050000 | 1101000 |  |  | 2865000 | 1866000 | 6781000
| Environment |  | 5N |  |  |  |  | 1105000 | -50000 | 1055000 | 282000 | 0 | 1337000 | 265277.73 | -10659.36 | 254618.37 | 430000 | -50000 | 380000 | 957000 |  |  | 856000 | 538000 | 1774000
| Policy & Implementation |  | 6M |  |  |  |  | 2219000 | -1069000 | 1150000 | 1035000 | 0 | 2185000 | 848352.02 | -397940 | 450412.02 | 1642000 | -450000 | 1192000 | 993000 |  |  | 2615000 | 2050000 | 5857000
| Property Services |  | 7P |  |  |  |  | 662000 | 0 | 662000 | 1656000 | 0 | 2318000 | 1677809.17 | -36398.37 | 1641410.8 | 2033000 | -75000 | 1958000 | 360000 |  |  | 1004000 | -384000 | 2578000
| Corporate Development |  | 8C |  |  |  |  | 694000 | 0 | 694000 | 148000 | 0 | 842000 | 253222.74 | -331500 | -78277.26 | 891000 | -230000 | 661000 | 181000 |  |  | -1672000 | -2201000 | -3212000
| Chief Executive |  | 9X |  |  |  |  | 0 | 0 | 0 | 45000 | 0 | 45000 | 822.5 | -441.31 | 381.19 | 1000 | 0 | 1000 | 44000 |  |  | 1019000 | 290000 | 1310000
[8 empty] | 9862000 | -2594000 | 7268000 | 3980000 | 412000 | 11660000 | 21779510.27 | -21718801.04 | 60709.23 | 25193000 | -17474000 | 7719000 | 3941000 |  |  | 9250000 | 9725000 | 26694000
| Schools PPP Programme |  | PPP |  |  |  |  | 3600000 | 0 | 3600000 | 4825000 | -8425000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2000000 | 500000 | 2500000
| Total Capital Including Schools PPP Programme | [6 empty] | 13462000 | -2594000 | 10868000 | 8805000 | -8013000 | 11660000 | 21779510.27 | -21718801.04 | 60709.23 | 25193000 | -17474000 | 7719000 | 3941000 |  |  | 11250000 | 10225000 | 29194000
[8 empty] | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK |  |  | OK | OK | OK
Note on R14: superuser: £8,903.01 trf to DDA (project 4)
Note on R15: superuser: £468,268k trf to Schools Fund (9)
Note on R30: superuser: £1880 trf to Schools Fund (9)
Note on R112: superuser: Capital grant arrcued from 06/07
Note on S31: superuser: this money seems to be from Openreach which is to do with SAK Rail
Note on S34: superuser: Credit from Roads DSO
Note on S41: superuser: Sustrans Ltd

## Sheet1 (hidden)
GENERAL SERVICES CAPITAL 2007/08
SUMMARY OF CAPITAL RETENTION BUDGETS
| Project No | D&E | Education
|  | £ | £
Budget |  | 60000 | 25000
Utulised for:
Leisure Bowl - refurbishment | 16 |  | -20000
Contaminated Land | 49 | -33000
DDA Property Services | 62 | -1000
Upgrading of Toilets |  | -8000
Old Parish Church |  | -5000
Obelisk Gate Piers |  | -2000
Additional asked for but not reported yet to SC
Road & Footway Improvements (SRMCS), including town centres | 35 | -5000
|  | 6000 | 5000

## 07-08 at Aug 07 (hidden)
[5 empty] | Budget Out | [5 empty] | #REF! |  | #REF!
| General Services Capital Programme 2007/08 | Service | Service Units | Ledger Code | GROSS EXPENDITURE 2007/08 |  |  |  | Grants & Capital Receipts 2007/08 |  |  | Net Expenditure (Council Contribution) 2007/08 |  | APPENDIX
[5 empty] | Budget as at Aug 2007 out-turn reported to SC on 11/10/07 | Projects transferred (to)/from 08/09 | Projects transferred (to)/from 09/10 | Revised Budget after proposed transfers | Budget as at Aug 2007 out-turn reported to SC on 11/10/07 | Projects transferred (to)/from 08/09 | Revised Budget after proposed transfers | Borrowing as at Aug 2007 out-turn reported to SC on 11/10/07 | Revised Borrowing (Council Contribution) |  | CFCR DR/(CR) 0002 | Loans Fund DR/(CR) 0003 | Cap Recp Applied DR/(CR) 0001 | Description
[5 empty] | £'000 | £'000 | £'000 | £'000 | £'000 | £'000 | £'000 | £'000 | £'000 |  | £ | £ | £
PROJECT
4 | DDA Compliance | S2P | 1E | 90 10 6000 | 18 |  |  | 18 |  |  | 0 | 18 | 18 |  |  | -113673 |  | Capital Funded by Loans
8 | School Building Alarm Systems | S2P | 1E | 90 10 5700 | 469 | -7 |  | 462 |  |  | 0 | 469 | 462 |  |  | -183524.05 |  | Capital Funded by Loans
9 | Schools Fund | S2P | 1E | 90 10 4900 | 1561 |  |  | 1561 | 1561 |  | 1561 | 0 | 0
15 | Legal Commitments - for projects undertaking in 04/05 | S2P | 1E | 90 10 6900 | 5 |  |  | 5 |  |  | 0 | 5 | 5 |  |  | -10539.67 |  | Capital Funded by Loans
19 | Reconfiguration of Council Services & Property Assets in Tillicoultry | S2P | 1E |  | 125 | -125 |  | 0 |  |  | 0 | 125 | 0 |  |  | -1586.49 |  | Capital Funded by Loans
88 | Development of Community Facilities in Alva | S2P | 1E |  | 25 |  |  | 25 |  |  | 0 | 25 | 25 |  |  | 0
89 | Cochrane Hall, Alva Refurbishment & Upgrading | S2P | 1E | 90 15 0170 |  | 5 |  | 5 |  |  | 0 | 0 | 5 |  |  | -270159.04 |  | Capital Funded by Loans
91 | Clackmannanshire's Outdoor Activity Centre | S2P | 1E |  | 0 |  |  | 0 |  |  | 0 | 0 | 0
92 | Running Track at Lornshill Academy | S2P | 1E |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 |  |  | 0
103 | Demolition of Lornshill Academy & Construct Car Parking & Football Pitch | S2P | 1E |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 |  |  | -17690.02 |  | Capital Funded by Loans
104 | Purchase of White Boards for new schools | S2P | 1E |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 |  |  | 0
126 | Muchart Primary Heating Plant - Additional capital grant | S2P | 1E |  | 88 |  |  | 88 | 88 |  | 88 | 0 | 0 |  |  | -730341.73 |  | Capital Funded by Loans
127 | Park Primary Heating Plant - Additional capital grant | S2P | 1E |  | 55 |  |  | 55 | 55 |  | 55 | 0 | 0 |  |  | 0
128 | St Serf's Primary Heating Plant - Additional capital grant | S2P | 1E |  | 55 |  |  | 55 | 55 |  | 55 | 0 | 0 |  |  | 0
17b | Primary & Nursery School Development | S2P | 1E | 90 10 7200 |  |  |  | 0 |  |  | 0 | 0 | 0 |  |  | -116905.19 |  | Capital Funded by Loans
85,86 | ICT Hardware Replacement in Sec Schls & New IT Installation in Schools | S2P | 1E |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 |  |  | 0
| Land Acquisition for Schools PPP | S2P | 1E | 90 10 6800 | 150 |  |  | 150 |  |  | 0 | 150 | 150 |  |  | -407759.84 |  | Capital Funded by Loans
10 | Tulligarth Sports Resurfacing - requirement of Lottery funding | S2P | 2L |  | 40 | -40 |  | 0 |  |  | 0 | 40 | 0
16 | Leisure Bowl - refurbishment | S2P | 2L | 90 15 0100 | 20 |  |  | 20 |  |  | 0 | 20 | 20 |  |  | -521073.46 |  | Capital Funded by Loans
20 | DDA Compliance - Social Services | S2P | 3S | 90 30 1800 | 19 |  |  | 19 |  |  | 0 | 19 | 19 |  |  | -75676 |  | Capital Funded by Loans
21 | Joint FVNHS/ Adult Care Premises Occupation | S2P | 3S |  |  |  |  | 0 |  |  | 0 | 0 | 0 |  |  | 0
22 | Menstrie House En-Suite Conversion | S2P | 3S | 90 30 0350 | 590 |  |  | 590 |  |  | 0 | 590 | 590 |  |  | -343431.47 |  | Capital Funded by Loans
23 | Ludgate House External Fabric | S2P | 3S | 90 30 1600 | 0 |  |  | 0 |  |  | 0 | 0 | 0 |  |  | -634.08 |  | Capital Funded by Loans
25 | Menstrie House - Increased Parking & Security Fencing | S2P | 3S |  | 150 |  |  | 150 |  |  | 0 | 150 | 150 |  |  | -175488.24 |  | Capital Funded by Loans
130 | West Haugh Travelling People's site - Additional capital grant | S2P | 3S |  | 230 |  |  | 230 | 230 |  | 230 | 0 | 0 |  |  | -870041.73 |  | Capital Funded by Loans
66b | Ludgate Traffic Management - Retentions | S2P | 3S | 90 30 1900 | 1 |  |  | 1 |  |  | 0 | 1 | 1 |  |  | -5861.2
26 | Accident Prevention & Traffic Management | D&E | 4R | 90 40 1020 | 40 |  |  | 40 |  |  | 0 | 40 | 40 |  |  | 0
28 | A91 East Stirling St. Alva Roundabout to access new school site | D&E | 4R |  | 450 | -450 |  | 0 | 225 | -225 | 0 | 225 | 0 |  |  | -3167.5 |  | Capital Funded by Loans
32 | Bridge Strengthening | D&E | 4R | 90 40 1700 | 466 |  |  | 466 |  |  | 0 | 466 | 466 |  |  | -12786.83 |  | Capital Funded by Loans
33 | Flood Prevention | D&E | 4R | 90 40 2700 | 124 | 76 |  | 200 |  |  | 0 | 124 | 200 |  |  | 0
34 | Retentions | D&E | 4R |  | 34 |  |  | 34 |  |  | 0 | 34 | 34 |  |  | -20457.6 |  | Capital Funded by Loans
35 | Road & Footway Improvements (SRMCS), including town centres | D&E | 4R | 90 40 3000 | 390 |  |  | 390 |  |  | 0 | 390 | 390 |  |  | -71915.18 |  | Capital Funded by Loans
36 | Cycling , Walking ,Safer Streets (CWSS) | D&E | 4R | 90 40 1310 | 86 |  |  | 86 | 86 |  | 86 | 0 | 0 |  |  | -82003.22 |  | Capital Funded by Loans
37 | Street Lighting | D&E | 4R | 90 40 4000 | 165 |  |  | 165 |  |  | 0 | 165 | 165 |  |  | 0
38 | Total SAK Rail Project & Alloa ELR Project Costs | D&E | 4R | 90 50 3100 | 14000 |  |  | 14000 | 13945 |  | 13945 | 55 | 55 |  |  | 0
41 | 20mph speed reduction | D&E | 4R | 90 40 3200 | 109 |  |  | 109 | 109 |  | 109 | 0 | 0 |  |  | -40368.95 |  | Capital Funded by Loans
43 | SESTRAN Public Transport & Walking | D&E | 4R | 90 40 3600 | 0 |  |  | 0 |  |  | 0 | 0 | 0 |  |  | -46252.77 |  | Capital Funded by Loans
45 | SUSTRAN - Cycle Routes | D&E | 4R | 90 40 3700 | 0 |  |  | 0 |  |  | 0 | 0 | 0 |  |  | 0
93 | A907 B910/Helensfield Junction for Railway Line/Marywood Improvement | D&E | 4R | 90 40 4700 | 735 |  |  | 735 |  |  | 0 | 735 | 735 |  |  | -2160 |  | Capital Funded by Loans
106 | Shillinghill Roundabout | D&E | 4R |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 |  |  | 0
107 | A908/B908 Hallpark, Sauchie | D&E | 4R |  | 285 |  | 65 | 350 | 285 |  | 285 | 0 | 65 |  |  | 0
31a | B9140/ Collylands Cross Upgrade | D&E | 4R | 90 40 4500 | 35 |  |  | 35 |  |  | 0 | 35 | 35 |  |  | 0
31b | B9140 Collylands to Glenochil (West) | D&E | 4R | 90 40 4400 | 856 | -856 |  | 0 |  |  | 0 | 856 | 0 |  |  | -13038 |  | Capital Funded by Loans
31c | B9140 Realignment of Bends (Collylands to Fishcross/Maggies Wood - East | D&E | 4R |  |  |  |  | 0 |  |  | 0 | 0 | 0 |  | 0 | see below | 0 | 0
| Cochrane Hall / Park Footpaths | D&E | 5N | 90 47 0200 | 9 |  |  | 9 |  |  | 0 | 9 | 9 |  |  | -69552 |  | Capital Funded by Loans
46 | Black Devon Landfill | D&E | 5N | 90 40 0100 | 86 |  |  | 86 |  |  | 0 | 86 | 86 |  |  | -313235.66 |  | Capital Funded by Loans
47 | Black Devon Landfill Gas Collection & Treatment Project | D&E | 5N | 90 40 0200 | 400 | -400 |  | 0 |  |  | 0 | 400 | 0 |  |  | -18090.53 |  | Capital Funded by Loans
48 | Cemeteries Strategy | D&E | 5N | 90 41 0110 | 187 | -117 |  | 70 |  |  | 0 | 187 | 70 |  |  | -825.25 |  | Capital Funded by Loans
49 | Contaminated Land | D&E | 5N | 90 41 0200 | 64 |  |  | 64 | 50 |  | 50 | 14 | 14 |  |  | 0
50 | Parks & Open Spaces | D&E | 5N | 90 41 0400 | 80 |  |  | 80 |  |  | 0 | 80 | 80 |  |  | -1042717.8 |  | Capital Funded by Loans
51 | Outdoor Play Area Strategy | D&E | 5N | 90 42 0085 | 75 |  |  | 75 |  |  | 0 | 75 | 75 |  |  | -414787.24 |  | Capital Funded by Loans
54a | Waste Recycling Project | D&E | 5N |  | 400 | -400 |  | 0 |  |  | 0 | 400 | 0 |  |  | 0
54b | Wheeled / Litter Bins | D&E | 5N | 90 45 0230 | 60 |  |  | 60 |  |  | 0 | 60 | 60 |  |  | -9684.44 |  | Capital Funded by Loans
| Dollar Public Conveniences | D&E | 5N | 90 40 2500 | 6 |  |  | 6 |  |  | 0 | 6 | 6 |  |  | 0
27 | Alloa Town Centre | D&E | 6M | 90 40 1750 | 180 |  |  | 180 |  |  | 0 | 180 | 180 |  |  | 0
55 | Clackmannan Tollbooth | D&E | 6M | 90 50 3400 | 58 |  |  | 58 | 49 |  | 49 | 9 | 9 |  |  | 0
56 | National Cycle Route | D&E | 6M |  | 112 | -12 |  | 100 | 50 |  | 50 | 62 | 50 |  |  | -7588.62 |  | Capital Funded by Loans
57 | Old Alloa Townscape Heritage Phase 2 | D&E | 6M | 90 50 2700 | 253 | -178 |  | 75 |  |  | 0 | 253 | 75 |  |  | -27518.21 |  | Capital Funded by Loans
58 | Landscape Partnership - converse Ochills / Hillfoots | D&E | 6M |  | 1125 | -1115 |  | 10 | 900 | -900 | 0 | 225 | 10
59 | Core Path network for Access | D&E | 6M |  | 50 | -50 |  | 0 | 12 | -12 | 0 | 38 | 0 |  |  | 0
68 | Econ. Dev. Infrastructure: Eastern Clackmannanshire Development Opportunities | D&E | 6M |  | 100 | -100 |  | 0 |  |  | 0 | 100 | 0
73 | Pavilions Business Park Phase 2 | D&E | 6M | 90 50 2900 | 340 | -340 |  | 0 |  |  | 0 | 340 | 0
74 | Dumyat Business Park Phase 3 | D&E | 6M | 90 50 2800 | 40 | -40 |  | 0 |  |  | 0 | 40 | 0 |  |  | 0
110 | Alloa Town Centre Regeneration: Speirs Centre | D&E | 6M |  | 330 |  |  | 330 |  |  | 0 | 330 | 330 |  |  | 0
111 | Alloa Town Centre: Public Realm Phase 2 | D&E | 6M |  | 220 | -220 |  | 0 |  |  | 0 | 220 | 0 |  |  | 0
114 | Lime Tree Walk Phase 2 | D&E | 6M |  |  | 150 |  | 150 |  |  | 0 | 0 | 150
115 | Shillinghill to Town Hall: Environmental Regeneration | D&E | 6M |  | 150 | -150 |  | 0 |  |  | 0 | 150 | 0 |  |  | -24732 |  | Capital Funded by Loans
116 | New Alloa Infrastructure | D&E | 6M |  | 240 | -240 |  | 0 | 53 | -53 | 0 | 187 | 0 |  |  | 0
118 | Pavilions Phase 3 | D&E | 6M |  | 0 |  |  | 0 |  |  | 0 | 0 | 0
125 | Gateways & Roundabouts | D&E | 6M | 90 41 0300 | 51 |  |  | 51 |  |  | 0 | 51 | 51
| Alloa East Gateway - Clackmannan Road | D&E | 6M | 90 50 4700 | 34 |  |  | 34 | 34 |  | 34 | 0 | 0
| Kirkgate | D&E | 6M | 90 51 8808 |  |  |  | 0 |  |  | 0 | 0 | 0
60 | Asbestos Removal | D&E | 7P | 90 40 3300 | 15 |  |  | 15 |  |  | 0 | 15 | 15 |  |  | -525577.86 |  | Capital Funded by Loans
62 | Disability Discrimination Act | D&E | 7P | 90 40 3400 | 1 |  |  | 1 |  |  | 0 | 1 | 1
70 | Kilncraigs Mill 1936 Building Envelop | D&E | 7P | 90 50 4500 | 321 |  |  | 321 | 75 |  | 75 | 246 | 246
71 | Kilncraigs Mill 1904 Development of 3rd & 4th Floors | D&E | 7P | 90 50 4600 | 305 |  |  | 305 |  |  | 0 | 305 | 305
98 | Kilncraigs Mill 1904 Upgrade of Existing | D&E | 7P |  | 760 |  |  | 760 |  |  | 0 | 760 | 760
99 | Forthbank Accommodation Rationalisation | D&E | 7P |  | 0 |  |  | 0 |  |  | 0 | 0 | 0
120 | Air Conditioning System - Class Cuisine Sauchie (See 61 above) | D&E | 7P | 90 50 4400 | 30 |  |  | 30 |  |  | 0 | 30 | 30
122 | Sun Tube, Lime Tree House | D&E | 7P |  | 20 | -20 |  | 0 |  |  | 0 | 20 | 0
123 | Kelliebank - Thermal Efficieny Windows | D&E | 7P |  | 22 | -22 |  | 0 |  |  | 0 | 22 | 0
63a | Vehicle Replacement Programme | D&E | 7P |  | 833 |  |  | 833 |  |  | 0 | 833 | 833
72a | Kilncraigs Mill 1904 Access Control & Zoning Services | D&E | 7P |  | 80 |  |  | 80 |  |  | 0 | 80 | 80 |  |  | -16872.18 |  | Capital Funded by Loans
72b | Kilncraigs Mill Conversion | D&E | 7P | 90 50 3000 | 7 |  |  | 7 |  |  | 0 | 7 | 7
64 | Efficient Government/Customer First Developments | CD | 8C | 90 70 1900 | 172 |  |  | 172 |  |  | 0 | 172 | 172
65 | IT Services | CD | 8C | 90 70 0451 | 377 |  |  | 377 |  |  | 0 | 377 | 377
76 | DDA & Asbestos Removal - Corporate Development Services | CD | 8C | 90 50 4300 | 17 |  |  | 17 |  |  | 0 | 17 | 17
82 | Council Office Improvements | CD | 8C |  |  |  |  | 0 |  |  | 0 | 0 | 0
83 | Greenfield Driveway & Parking | CD | 8C |  | 84 | -84 |  | 0 |  |  | 0 | 84 | 0
121 | Greenfield Heating - Additional Grant | CD | 8C |  | 150 |  |  | 150 | 150 |  | 150 | 0 | 0
129 | Fibre Optic Link - Additional capital grant | CD | 8C |  | 80 |  |  | 80 | 80 |  | 80 | 0 | 0 |  |  | 0
66a | Finance Services - General Ledger system | CD | 8C | 90 70 1125 | 42 |  |  | 42 |  |  | 0 | 42 | 42
75 | CCTV | CE | 9X | 90 20 0600 | 45 | -44 |  | 1 |  |  | 0 | 45 | 1
77 | Unallocated Capital Receipts Estimate | D&E | 7P | 90 90 xxxx | 5 |  |  | 5 |  |  | 0 | 5 | 5 |  |  | see below
| TOTAL CAPITAL PROGRAMME (EXCLUDING SCHOOLS' PPP PROJECT) |  |  |  | 29392 | -4779 | 65 | 24678 | 18092 | -1190 | 16902 | 11300 | 7776
Details of Grants & Capital Receipts referred to above
9 | SE Grant - Schools Fund | S2P | 1E | [5 empty] | 1561 |  | 1561
126 | SE Special Additional Grant - Muchart Primary Heating Plant | S2P | 1E | [5 empty] | 88 |  | 88
127 | SE Special Additional Grant - Park Primary Heating Plant | S2P | 1E | [5 empty] | 55 |  | 55
128 | SE Special Additional Grant - St Serf's Primary Heating Plant | S2P | 1E | [5 empty] | 55 |  | 55
130 | SE Special Additional Grant - West Haugh Travelling People's site | S2P | 3S | [5 empty] | 230 |  | 230
28 | Private Developer - A91 East Stirling St. Alva Roundabout to access new school site | D&E | 4R | [5 empty] | 225 | -225 | 0
36 | SE Grant - Cycling , Walking ,Safer Streets (CWSS) | D&E | 4R | [5 empty] | 86 |  | 86
38 | SE - SAK Rail Project & Alloa ELR Project | D&E | 4R | [5 empty] | 13728 |  | 13728
38 | Network Rail - SAK Rail Project & Alloa ELR Project | D&E | 4R | [5 empty] | 217 |  | 217
41 | SE Grant - 20mph speed reduction | D&E | 4R | [5 empty] | 109 |  | 109
107 | FVHB Contribution - A908/B908 Hallpark, Sauchie | D&E | 4R | [5 empty] | 285 |  | 285
49 | SE Grant - Contaminated Land | D&E | 5N | [5 empty] | 50 |  | 50
55 | CHT - Clackmannan Tollbooth | D&E | 6M | [5 empty] | 32 |  | 32
55 | HS - Clackmannan Tollbooth | D&E | 6M | [5 empty] | 17 |  | 17
56 | SE SUStran funding - National Cycle Route | D&E | 6M | [5 empty] | 50 |  | 50
58 | Heritage Lottery Fund - Landscape Partnership - converse Ochills / Hillfoots | D&E | 6M | [5 empty] | 900 | -900 | 0
59 | SNH - Core Path Network for Access | D&E | 6M | [5 empty] | 12 | -12 | 0
116 | ERDF - New Alloa Infrastructure | D&E | 6M | [5 empty] | 53 | -53 | 0
| ERDF - Alloa East Gateway - Clackmannan Road | D&E | 6M | [5 empty] | 34 |  | 34
70 | Historic Scotland Grant - Kilncraigs Mill 1936 Building Envelop | D&E | 7P | [5 empty] | 75 |  | 75
121 | SE Special Additional Grant - Greenfield Heating | CD | 8C | [5 empty] | 150 |  | 150
129 | SE Special Additional Grant - Fibre Optic Link | CD | 8C | [5 empty] | 80 |  | 80
77 | Unallocated Capital Receipts | D&E | 7P | [5 empty] | 0 |  | 0
[9 empty] | 18092 | -1190 | 16902
SCHOOLS PPP PROJECT
1,3,5 | PPP Capital Support | S2P | PPP | 90 10 7000 | 8250 | -8250 |  |  | 8250 | -8250 | 0 | 0 | 0
17a | School Developments - Allocated to PPP | S2P | PPP |  | 175 | -175 |  |  | 175 | -175 | 0 | 0 | 0
| Total PPP Project |  |  |  | 8425 | -8425 | 0 | 0 | 8425 | -8425 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
Details of Grants / Cap Receipts funding for SCHOOL'S PPP PROJECT
| Capital Receipts from sale of assets allocated to PPP contribution | S2P | PPP | [5 empty] | 8250 | -8250 | 0
| Schools Fund for PPP | S2P | PPP | [5 empty] | 175 | -175 | 0
[9 empty] | 8425 | -8425 | 0 |  |  |  | 0 | 0 | 0 | 0
DETAILS PROPERTY CAPITAL RECEIPTS
77 | 22/4 Candleriggs, Alloa |  |  | 9090 6800 | [8 empty] | #VALUE!
77 | Skip Site - Hallpark, Sauchie |  |  | 9090 0726 | [8 empty] | #VALUE!
77 | Dewar St, Lorne Lane , Dollar |  |  | 9090 0800 | [8 empty] | #VALUE!
77 | Collyland - Fishcross |  |  | 9070 1700 | [8 empty] | #VALUE!
77 | Cowan Terrace Dollar |  |  | 9090 0875 | [8 empty] | #VALUE!
77 | Candleriggs, Alloa |  |  | 9090 0950 | [8 empty] | #VALUE!
77 | General Receipts |  |  | 9090 1000 | [8 empty] | #VALUE!
77 | Alexandra Street, Devonside |  |  | 9090 2200 | [8 empty] | #VALUE!
77 | Gap Site - Drysdale/Mill Street |  |  | 9090 1050 | [8 empty] | #VALUE!
77 | Bedford Place Alloa |  |  | 9090 1100 | [8 empty] | #VALUE!
77 | Bedford House - Alloa |  |  | 9090 1125 | [8 empty] | #VALUE!
77 | Cowden Park Alloa |  |  | 9090 1175 | [8 empty] | #VALUE!
77 | Forestmill Primary School |  |  | 9090 1325 | [8 empty] | #VALUE!
77 | Former School Clackmannan |  |  | 9090 1400 | [8 empty] | #VALUE!
77 | Orchard Tullibody - Housing Land |  |  | 9090 1525 | [8 empty] | #VALUE!
77 | Alloa West |  |  | 9090 0550 | [8 empty] | #VALUE!
77 | Alloa West - Autism Site |  |  | 9090 5800 | [8 empty] | #VALUE!
77 | Menstrie Centre Playground |  |  | 9090 1600 | [8 empty] | #VALUE!
77 | Collyland Road - Fishcross Housing Site |  |  | 9090 1700 | [8 empty] | #VALUE!
77 | Shops - Sauchie |  |  | 9090 1850 | [8 empty] | #VALUE!
77 | Kirkgate - Alloa |  |  | 9090 2100 | [8 empty] | #VALUE!
77 | Alexandra Street, Devonside |  |  | 9090 2200 | [8 empty] | #VALUE!
77 | Long Row Menstrie - Land |  |  | 9090 2700 | [8 empty] | #VALUE!
77 | Mar Place Sauchie WC |  |  | 9090 2800 | [8 empty] | #VALUE!
77 | 5 Muirside Road, Tullibody |  |  | 9090 3025 | [8 empty] | #VALUE!
77 | Park Street, Alva |  |  | 9090 3500 | [8 empty] | #VALUE!
77 | Bankhead - Devon Village |  |  | 9090 6100 | [8 empty] | #VALUE!
77 | Claremont Business Centre |  |  | 9090 1025 | [8 empty] | #VALUE!
77 | Dumyat Business Park |  |  | 9090 7000 | [8 empty] | #VALUE!
77 | Dumyat Business Park - Belhaven Breweries |  |  | 9090 7400 | [8 empty] | #VALUE!
77 | Earlsfield/Alloa Park |  |  | 9090 1750 | [8 empty] | #VALUE! |  |  | -48 |  | Capital Funded by Loans
77 | Fishcross - Devon Riding Centre |  |  | 9090 6900 | [8 empty] | #VALUE! |  |  |  | 154.32 | Cap Recp applied to Cap Exp
77 | Land - Ochilvale Mill Alva |  |  | 9090 3900 | [8 empty] | #VALUE! |  |  | 0
77 | St Mungo's Wynd Alloa |  |  | 9090 4000 | [8 empty] | #VALUE! |  |  | 0
77 | 28 Ramsay Street, Clackmannan |  |  | 9090 4100 | [8 empty] | #VALUE! |  |  | 0
77 | Old Toll House, Muckhart |  |  | 9090 4200 | [8 empty] | #VALUE! |  |  | 0
77 | Main St Coalsnaughton |  |  | 9090 4300 | [8 empty] | #VALUE! |  |  | 0
77 | Baingle Crescent |  |  | 9090 4400 | [8 empty] | #VALUE! |  |  | 0
77 | Gas Governor at the Baingle |  |  | 9090 4500 | [8 empty] | #VALUE! |  |  | 0
77 | Fairfield Sauchie |  |  | 9090 4600 | [8 empty] | #VALUE! |  |  | 0
77 | Scout Hall Main Street Sauchie |  |  | 9090 4700 | [8 empty] | #VALUE! |  |  | 0
77 | 3/5 Lower Mains Dollar |  |  | 9090 4800 | [8 empty] | #VALUE! |  |  | 0
77 | Railway Station Alloa Road |  |  | 9090 4900 | [8 empty] | #VALUE! |  |  | 0
77 | Land at Shawpark garage |  |  | 9090 5000 | [8 empty] | #VALUE! |  |  | 0
77 | Service Station Site / Ditch Farm |  |  | 9090 5100 | [8 empty] | #VALUE! |  |  | 0
77 | Pavilions Phase 2 |  |  | 9090 5200 | [8 empty] | #VALUE! |  |  | 0
77 | TOMA CPO |  |  | 9090 5300 | [8 empty] | #VALUE! |  |  | 0
77 | Sinclairs Haulage - Land |  |  | 9090 5400 | [8 empty] | #VALUE! |  |  | 0
77 | Alva House Stable Block |  |  | 9090 5500 | [8 empty] | #VALUE! |  |  | 0
77 | 3/5 Henderson Avenue, Alloa |  |  | 9090 5600 | [8 empty] | #VALUE! |  |  | 0
77 | Land at Rear 78/80 West Stirling Street Alva |  |  | 9090 5700 | [8 empty] | #VALUE! |  |  | 0
77 | Fishcross - Land at Devonbank Cottage |  |  | 9090 7100 | [8 empty] | #VALUE! |  |  | 0
77 | Washington House - Alva |  |  | 9090 5900 | [8 empty] | #VALUE! |  |  | 0
77 | 23 Main Street Sauchie |  |  | 9090 6000 | [8 empty] | #VALUE! |  |  | 0
77 | Bank Head, Devon Village Rescue |  |  | 9090 6100 | [8 empty] | #VALUE! |  |  | 0
77 | Smithfield Loan - Railway Embankment |  |  | 9090 6200 | [8 empty] | #VALUE! |  |  | 0
77 | Superiority - Smithfield Loan |  |  | 9090 6300 | [8 empty] | #VALUE! |  |  | 0
77 | Land at Broad Street, Alloa |  |  | 9090 6400 | [8 empty] | #VALUE! |  |  | 0
77 | Land for Access to Stirling St |  |  | 9090 6500 | [8 empty] | #VALUE! |  |  | 0
77 | Garage Site Gartmorn Dam House |  |  | 9090 6600 | [8 empty] | #VALUE! |  |  | 0
77 | Lochy Falls,15 Upper Hillfoot, Dollar |  |  | 9090 6700 | [8 empty] | #VALUE! |  |  | 0
77 | Former Toilets - Alva |  |  | 9090 7800 | [8 empty] | #VALUE! |  |  | 0
77 | Hillpark |  |  | 9090 3700 | [8 empty] | #VALUE! |  |  | 0
77 | Hallpark/Main Street Sauchie |  |  | 9090 0700 | [8 empty] | #VALUE! |  |  | 0
77 | Land at Park St Tillicoultry |  |  | 9090 7300 | [8 empty] | #VALUE! |  |  | 0
77 | Land at Ditch Farm |  |  | 9090 7500 | [7 empty] | 2301.64 | #VALUE! |  |  | #VALUE! | -154.32 | Capital Funded by Loans/ Cap Receipts
77 | Land/Car Park - Erskine ST Alloa |  |  | 9090 3800 | [8 empty] | #VALUE! |  |  | 0
77 | Housing Land The Orchard Tullibody |  |  | 9090 1525 | [8 empty] | #VALUE! |  |  | 0
77 | Property Conversion Feasibility Study |  |  | 9090 7200 | [8 empty] | #VALUE! |  |  | 0
77 | Former Thistle Brewery |  |  | 9090 7700 | [8 empty] | #VALUE! |  |  | 0
| Claremont Business Centre |  |  | 9090 1025 | [7 empty] | 54.5 | #VALUE!
77 | Tullis Factory |  |  | 9090 1575 | [8 empty] | #VALUE! |  |  | -119.07 |  | Capital Funded by Loans
77 | Sale of Land at Tullibody (Ditch Farm) |  |  | 9090 5100 | [8 empty] | #VALUE! |  |  | -30 |  | Capital Funded by Loans
77 | Title swop with Ceteris |  |  | 9090 8000 | [8 empty] | #VALUE! |  |  | #VALUE! | -50214 | Capital Funded by Loans/ Cap Receipts
77 | North Castle Street |  |  | 9090 8100 | [8 empty] | #VALUE! |  |  |  | 50214 | Cap Recp applied to Cap Exp
| Total - Property Sales | [10 empty] | 2356.14 | #VALUE! |  | 0 | #VALUE! | 0 | 0
DETAILS VEHICLE REPLACEMENT PROGRAMME
63a | DLO Vehicle - Property Contracts | D&E | 7P | 9045 0100 | 97.4 | [5 empty] | 0 | 97.4 | 97.4 |  |  | -191240 |  | Capital Funded by Loans
63a | DLO Vehicle - Refuse Collection | D&E | 7P | 9045 0110 | [6 empty] | 0 | 0 | 0 |  |  | -330592 |  | Capital Funded by Loans
63a | DLO Vehicle - Street Cleaning | D&E | 7P | 9045 0120 | 245.5 | [5 empty] | 0 | 245.5 | 245.5 |  |  | 0
63a | DLO Vehicle - Land Services | D&E | 7P | 9045 0130 | 153 | [5 empty] | 0 | 153 | 153 |  |  | -135204 |  | Capital Funded by Loans
63a | DLO Vehicle - Roads Contracts | D&E | 7P | 9045 0140 | 157.1 | [5 empty] | 0 | 157.1 | 157.1 |  |  | -58907.15 |  | Capital Funded by Loans
63a | DLO Vehicle - Roads Client | D&E | 7P |  | 12.5 | [5 empty] | 0 | 12.5 | 12.5
63a | DLO Vehicle - Catering Services | D&E | 7P | 9045 0150 | 12.5 | [5 empty] | 0 | 12.5 | 12.5 |  |  | 0
63a | DLO Vehicle - Transport Pool | D&E | 7P | 9045 0160 | [6 empty] | 0 | 0 | 0 |  |  | -28331 |  | Capital Funded by Loans
63a | DLO Vehicle - Leisure | D&E | 7P | 9045 0170 | [6 empty] | 0 | 0 | 0 |  |  | 0
63a | DLO Vehicle - Social Services | D&E | 7P | 9045 0200 | 53 | [5 empty] | 0 | 53 | 53 |  |  | 0
63a | DLO Vehicle - Burial Services | D&E | 7P | 9045 0210 | [6 empty] | 0 | 0 | 0 |  |  | -30207 |  | Capital Funded by Loans
63a | DLO Vehicle - Countryside Rangers | D&E | 7P | 9045 0220 | [6 empty] | 0 | 0 | 0 |  |  | 0
63a | DLO Vehicle - G F Housing | D&E | 7P | 9045 0225 | [6 empty] | 0 | 0 | 0 |  |  | 0
63a | DLO Vehicle - HRA Amenity Team | D&E | 7P | 9045 0250 | [6 empty] | 0 | 0 | 0
63a | DLO Vehicle - Glenochil Nursery | D&E | 7P |  | 15 | [5 empty] | 0 | 15 | 15 |  |  | 0
63a | DLO Vehicle - Chief Executive | D&E | 7P | 9045 0240 | [6 empty] | 0 | 0 | 0 |  |  | -11801 |  | Capital Funded by Loans
63a | DLO Vehicle - Black Devon | D&E | 7P |  | 26 | [5 empty] | 0 | 26 | 26 |  |  | 0
63a | DLO Vehicle - Dog Warden | D&E | 7P |  | 17.5 | [5 empty] | 0 | 17.5 | 17.5
63a | DLO Vehicle - Pest Control | D&E | 7P |  | 12 | [5 empty] | 0 | 12 | 12
63a | DLO Vehicle - Education | D&E | 7P |  | 60.1 | [5 empty] | 0 | 60.1 | 60.1
| Reduction | D&E | 7P |  | -28.6 | [5 empty] | 0 | -28.6 | -28.6
| Total - Vehicle Programme |  |  |  | 833 |  |  |  | 0 | 0 | 0 | 833 | 833 |  | 0 | -786282.15 | 0 | 0
| DO NOT ENTER ANYTHING IN THE BLUE BOX BELOW | [13 empty] | 0 |  |  | DR CFCR Allocation
| SUMMARY OF SERVICE UNITS | [14 empty] | #VALUE! |  | DR: Loans Fund Allocation to Gen Fund
| Education & Community |  | 1E |  | 2551 | -127 | 0 | 2424 | 1759 | 0 | 1759 | 792 | 665
| Leisure |  | 2L |  | 60 | -40 | 0 | 20 | 0 | 0 | 0 | 60 | 20
| Social Services |  | 3S |  | 990 | 0 | 0 | 990 | 230 | 0 | 230 | 760 | 760
| Roads & Transportation |  | 4R |  | 17775 | -1230 | 65 | 16610 | 14650 | -225 | 14425 | 3125 | 2185
| Environment |  | 5N |  | 1367 | -917 | 0 | 450 | 50 | 0 | 50 | 1317 | 400
| Policy & Implementation |  | 6M |  | 3283 | -2295 | 0 | 988 | 1098 | -965 | 133 | 2185 | 855
| Property Services |  | 7P |  | 2399 | -42 | 0 | 2357 | 75 | 0 | 75 | 2324 | 2282
| Corporate Development |  | 8C |  | 922 | -84 | 0 | 838 | 230 | 0 | 230 | 692 | 608
| Chief Executive |  | 9X |  | 45 | -44 | 0 | 1 | 0 | 0 | 0 | 45 | 1
[5 empty] | 29392 | -4779 | 65 | 24678 | 18092 | -1190 | 16902 | 11300 | 7776
| Schools PPP Programme |  | PPP |  | 8425 | -8425 | 0 | 0 | 8425 | -8425 | 0 | 0 | 0
| Total Capital Including Schools PPP Programme |  |  |  | 37817 | -13204 | 65 | 24678 | 26517 | -9615 | 16902 | 11300 | 7776
[5 empty] | OK | OK | OK | OK | OK | OK | OK | OK | OK
Note on S31: superuser: Accrue TS income £3,785060. Also, ERDF grant recd in Advance in 06/07 £216765
Note on T31: superuser: Accrue TS income £3,785060. Also, ERDF grant recd in Advance in 06/07 £216765
Note on U31: superuser: Accrue TS income £3,785060. Also, ERDF grant recd in Advance in 06/07 £216765

## 08-09 at Aug 07 (hidden)
|  | Service | Service Units |  | Gross Expenditure 2008/09 | [5 empty] | Grants / Specific Cap Receipts 2008/09 |  |  |  | Net Expenditure (Council Contribution) 2008/09 |  | APPENDIX 2 | Recurring Revenue consequences
| General Services Capital Programme 2008/09 |  |  |  | Budget as at Aug 2007 out-turn reported to SC on 11/10/07 | New Projects | Projects transferred (to)/from 07/08 | Projects transferred (to)/from 09/10 | Revised Budget after proposed transfers |  | Budget as at Aug 2007 out-turn reported to SC on 11/10/07 | New Projects | Projects transferred (to)/from 07/08 | Revised Budget after proposed transfers | Borrowing as at Aug 2007 out-turn reported to SC on 11/10/07 | Revised Borrowing (Council Contribution)
[5 empty] | £'000 |  | £'000 | £'000 | £'000 |  | £'000 |  | £'000 | £'000 | £'000 | £'000
| PROJECT |  |  |  | BUDGET OUT |  | BUDGET OUT | BUDGET OUT | BUDGET OUT |  |  |  | BUDGET OUT | BUDGET OUT
Abercromby PS
Alva Primary Extension
Beechwood Park
Lornshill Academy Sports Complex Phase 1
Lornshill Academy Sports Complex Phase 2
Pre Fives
Property Maintenance - additional from Revenue
Alloa Academy
Safer Routes to school
Strathdevon Primary
8 | School Building Alarm Systems | S2P | 1E |  | 300 |  | 7 | -300 | 7 |  |  |  |  | 0 | 300 | 7
15 | Legal Commitments - for projects undertaking in previous years | S2P | 1E |  | 50 | -50 |  |  | 0 |  |  |  |  | 0 | 50 | 0
19 | Reconfiguration of Council Services & Property Assets in Tillicoultry | S2P | 1E |  |  |  | 125 |  | 125 |  |  |  |  | 0 | 0 | 125
88 | Development of Community Facilities in Alva | S2P | 1E |  | 25 |  |  |  | 25 |  |  |  |  | 0 | 25 | 25
89 | Cochrane Hall, Alva Refurbishment & Upgrading | S2P | 1E |  | 25 |  | -5 |  | 20 |  |  |  |  | 0 | 25 | 20
91 | Clackmannanshire's Outdoor Activity Centre | S2P | 1E |  | 25 |  |  |  | 25 |  |  |  |  | 0 | 25 | 25
104 | Purchase of White Boards for new Secondary Schools | S2P | 1E |  | 450 |  |  |  | 450 |  |  |  |  | 0 | 450 | 450
18 | Fir Ski Park Centre - upgrade to building | S2P | [6 empty] | 0 |  |  |  |  | 0 | 0 | 0
17b | Primary & Nursery Schools Development | S2P | 1E |  | 1000 |  |  |  | 1000 |  |  |  |  | 0 | 1000 | 1000
85,86 | ICT Hardware Replacement in Sec Schls & New IT Installation in Schools | S2P | 1E |  | 1600 |  |  |  | 1600 |  |  |  |  | 0 | 1600 | 1600
134 | Extension & Refurbishment of CLICk (Glebe Hall) | S2P | 1E |  |  | 120 |  |  | 120 |  |  |  |  | 0 | 0 | 120
10 | Tulligarth Sports Resurfacing - requirement of Lottery funding | S2P | 2L |  |  |  | 40 |  | 40 |  |  |  |  | 0 | 0 | 40
| Ludgate House (c/f from 00/01) |  | 1E | [12 empty] | 0
| Office Relocations |  | 1E | [12 empty] | 0
| Whins Resource Centre - Floor Heating System |  | 1E | [12 empty] | 0
| Care in Community Safety (** new proposal - see attached schedule) |  | 1E | [12 empty] | 0
| Upgrade 6 Marshill Alloa |  | 1E | [12 empty] | 0
| Document Imaging System (** new proposal - see attached schedule) |  | 1E | [12 empty] | 0
20 | DDA Compliance |  | 1E | [11 empty] | 0 | 0
21 | Joint FVNHS/ Adult Care Premises Occupation | S2P | 3S |  |  |  | 50 |  | 50 |  |  |  |  | 0 | 0 | 50
22 | Menstrie House En-Suite Conversion | S2P | 3S |  | 38 |  |  |  | 38 |  |  |  |  | 0 | 38 | 38
23 | Ludgate House Resource Centre | [7 empty] | 0 |  |  |  |  | 0 | 0 | 0
24 | Mental Health Services | [7 empty] | 0 |  |  |  |  | 0 | 0 | 0
131 | Alloa Centre (Day & Adult Care) move to Alternative Accomodation | S2P | 3S |  |  | 700 |  |  | 700 |  |  | 260 |  | 260 | 0 | 440
26 | Accident Prevention & Traffic Management | D&E | 4R |  | 100 |  |  |  | 100 |  |  |  |  | 0 | 100 | 100 |  | 0 | 0 | 0
27 | Alloa Town Centre | [7 empty] | 0 |  |  |  |  | 0 | 0 | 0 |  | -200 | -200 | -200
| Accident Prevention & Traffic Management - Safer Roads, Cycling | [7 empty] | 0 |  |  |  |  | 0 | 0 | 0
28 | A91 East Stirling St. Alva Roundabout to access new school site | [7 empty] | 0 |  |  |  |  | 0 | 0 | 0
29 | A908/B908 Sauchie, Roundabout to facilitate new hospital | [7 empty] | 0 |  |  |  |  | 0 | 0 | 0
31 | B9140/ Collylands Cross Upgrade | [7 empty] | 0 |  |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0
| B9140 Realignment of Bends | [7 empty] | 0 |  |  |  |  | 0 | 0 | 0
28 | A91 East Stirling St. Alva Roundabout to access new school site | D&E | 4R |  |  |  | 450 |  | 450 |  |  |  | 225 | 225 | 0 | 225
32 | Bridge Strengthening | D&E | 4R |  | 150 |  |  |  | 150 |  |  |  |  | 0 | 150 | 150
33 | Flood Prevention | D&E | 4R |  | 100 |  | -76 |  | 24 |  |  |  |  | 0 | 100 | 24
34 | Retentions | D&E | 4R |  | 60 |  |  |  | 60 |  |  |  |  | 0 | 60 | 60 |  | 0 | 0 | 0
| Eastern Link Road | D&E | 4R | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0
| Hall Park | D&E | 4R | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0
| Footpath Maintenance | D&E | 4R | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0
| Roads Maintenance | D&E | 4R | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0
| Smithfield Loan | D&E | 4R | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0
| Roads Structural Maintenance | D&E | 4R | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0
35 | Road & Footway Improvements (SRMCS), including town centres | D&E | 4R |  | 520 |  |  |  | 520 |  |  |  |  | 0 | 520 | 520 |  | 0 | 0 | 0
36 | Cycling , Walking ,Safer Streets (CWSS) | D&E | 4R | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0
37 | Street Lighting | D&E | 4R |  | 185 |  |  |  | 185 |  |  |  |  | 0 | 185 | 185 |  | 0 | 0 | 0
41 | 20mph speed reduction | D&E | 4R |  | 0 |  |  |  | 0 |  |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0
43 | SESTRAN Public Transport & Walking | D&E | 4R |  | 0 |  |  |  | 0 |  |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0
| Tullibody Bypass (to be funded from special capital receipts) | D&E | 4R | [5 empty] | 0 | [5 empty] | 0 | 0
38 | Total SAK Rail Project & Alloa ELR Project Costs | D&E | 4R | [5 empty] | 0 | [5 empty] | 0 | 0 |  | -20 | -20 | -20
39 | Tullibody By Pass | D&E | 4R | [5 empty] | 0 | [5 empty] | 0 | 0
40 | Tullibody By Pass c/f from 2004/05 | D&E | 4R | [5 empty] | 0 | [5 empty] | 0 | 0
45 | SUSTRAN - Cycle Routes | D&E | 4R |  | 0 |  |  |  | 0 |  |  |  |  | 0 | 0 | 0
42 | Footways at Muirside, Tullibody | D&E | 4R | [11 empty] | 0 | 0
106 | Shillinghill Roundabout | D&E | 4R |  | 40 |  |  |  | 40 |  |  |  |  | 0 | 40 | 40
44 | SESTRAN Public Bus | D&E | 4R | [11 empty] | 0 | 0
31b | B9140 Realignment of Bends (Collylands to Glenochil - West) | D&E | 4R |  | 10 |  | 856 |  | 866 |  |  |  |  | 0 | 10 | 866
31c | B9140 Realignment of Bends (Collylands to Fishcross/Maggies Wood - East | D&E | 4R |  | 30 |  |  |  | 30 |  |  |  |  | 0 | 30 | 30
46 | Black Devon Landfill / Incinerator | [7 empty] | 0 |  |  |  |  | 0 | 0 | 0 |  | minimal savings >>>>>>>>>>>>>>
47 | Black Devon Landfill Gas Collection & Treatment Project | [7 empty] | 0 |  |  |  |  | 0 | 0 | 0
48 | Cemeteries Strategy |  |  |  | 0 |  |  |  | 0 |  |  |  |  | 0 | 0 | 0 |  | # | # | #
| Cycle Path Network | [7 empty] | 0 |  |  |  |  | 0 | 0 | 0
| Dollar Cemetery | [7 empty] | 0 |  |  |  |  | 0 | 0 | 0
| Environmental Improvements | [7 empty] | 0 |  |  |  |  | 0 | 0 | 0
| Old Alloa THI Project | [7 empty] | 0 |  |  |  |  | 0 | 0 | 0
| Hillfoots Initiative | [7 empty] | 0 |  |  |  |  | 0 | 0 | 0
| Incineration Plant Demolition | [7 empty] | 0 |  |  |  |  | 0 | 0 | 0
| Landward Village Initiative | [7 empty] | 0 |  |  |  |  | 0 | 0 | 0
47 | Black Devon Landfill Gas Collection & Treatment Project | D&E | 5N |  |  |  | 400 |  | 400 |  |  |  |  | 0 | 0 | 400 |  | Budget already in place for Land Officer
| Tullis Factory Demolition | D&E | [6 empty] | 0 |  |  |  |  | 0 | 0 | 0
48 | Cemeteries Strategy | D&E | 5N |  |  |  | 117 |  | 117 |  |  |  |  | 0 | 0 | 117
49 | Contaminated Land | D&E | 5N |  | 50 |  |  |  | 50 |  | 50 |  |  | 50 | 0 | 0 |  | Budget already in place for Land Officer
50 | Parks & Open Spaces | D&E | 5N |  | 83 |  |  |  | 83 |  |  |  |  | 0 | 83 | 83
51 | Outdoor Play Area Strategy | D&E | 5N |  | 78 |  |  |  | 78 |  |  |  |  | 0 | 78 | 78
52 | Shared Compost Facility @ Polmaise | D&E | 5N |  | 0 |  |  |  | 0 |  |  |  |  | 0 | 0 | 0
53 | Shared Transfer Facility @ Polmaise | D&E | 5N |  | 0 |  |  |  | 0 |  |  |  |  | 0 | 0 | 0
54a | Waste Recycling Project | D&E | 5N |  |  |  | 400 |  | 400 |  |  |  |  | 0 | 0 | 400
54b | Wheeled / Litter Bins | D&E | 5N |  | 100 |  |  |  | 100 |  |  |  |  | 0 | 100 | 100
55 | Clackmannan Tollbooth | D&E | 6M | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0
56 | National Cycle Route | D&E | 6M |  |  |  | 12 |  | 12 |  |  |  |  | 0 | 0 | 12
57 | Old Alloa Townscape Heritage Phase 2 | D&E | 6M |  |  |  | 178 |  | 178 |  |  |  |  | 0 | 0 | 178
58 | Landscape Partnership - converse Ochills / Hillfoots | D&E | 6M |  |  |  | 1115 |  | 1115 |  |  |  | 900 | 900 | 0 | 215
59 | Core Path network for Access | D&E | 6M |  |  |  | 50 |  | 50 |  |  |  | 12 | 12 | 0 | 38
68 | Econ. Dev. Infrastructure: Eastern Clackmannanshire Development Opportunities | D&E | 6M |  |  |  | 100 |  | 100 |  |  |  |  | 0 | 0 | 100
73 | Pavilions Business Park Phase 2 | D&E | 6M |  |  |  | 340 |  | 340 |  |  |  |  | 0 | 0 | 340
74 | Dumyat Business Park Phase 3 | D&E | 6M |  |  |  | 40 |  | 40 |  |  |  |  | 0 | 0 | 40
110 | Alloa Town Centre Regeneration: Speirs Centre | D&E | 6M |  | 0 |  |  |  | 0 |  |  |  |  | 0 | 0 | 0
111 | Alloa Town Centre: Public Realm Phase 2 | D&E | 6M |  |  |  | 220 |  | 220 |  |  |  |  | 0 | 0 | 220
114 | Lime Tree Walk Phase 2 | D&E | 6M |  | 200 |  | -150 |  | 50 |  |  |  |  | 0 | 200 | 50
115 | Shillinghill to Town Hall: Environmental Regeneration | D&E | 6M |  | 50 |  | 150 |  | 200 |  |  |  |  | 0 | 50 | 200
116 | New Alloa Infrastructure | D&E | 6M |  | 10 |  | 240 |  | 250 |  | 10 |  | 53 | 63 | 0 | 187
118 | Pavilions Business Park Phase 3 | D&E | 6M |  | 50 |  |  |  | 50 |  |  |  |  | 0 | 50 | 50
62 | Disability Discrimination Act | D&E | 7P |  | 20 |  |  |  | 20 |  |  |  |  | 0 | 20 | 20
71 | Kilncraigs Mill 1904 Development of 3rd & 4th Floors | D&E | 7P |  | 30 |  |  |  | 30 |  |  |  |  | 0 | 30 | 30
| Retentions Carry forward (projects to be identified) | D&E | 7P | [5 empty] | 0 |  |  |  |  | 0 |  | 0
63b | Keilarsbrae land Purchases | D&E | 7P |  | 0 |  |  |  | 0 |  |  |  |  | 0 | 0 | 0
99 | Forthbank Accommodation Rationalisation | D&E | 7P |  | 75 |  |  |  | 75 |  |  |  |  | 0 | 75 | 75
122 | Sun Tube, Lime Tree House | D&E | 7P |  |  |  | 20 |  | 20 |  |  |  |  | 0 | 0 | 20
123 | Kelliebank - Thermal Efficieny Windows | D&E | 7P |  |  |  | 22 |  | 22 |  |  |  |  | 0 | 0 | 22
63a | Vehicle Replacement Programme | D&E | 7P |  | 500 |  |  |  | 500 |  |  |  |  | 0 | 500 | 500
| CCTV - Alloa South & East | [14 empty] | 0
| Community Planning | [14 empty] | 0
64 | Efficient Government/Customer First Developments | CD | 8C |  | 100 |  |  |  | 100 |  |  |  |  | 0 | 100 | 100
| Business Change & Organisational Development |  |  | } | [5 empty] | } | [5 empty] | 0
| Clack Web - eServices & eCommunity |  |  | } | [5 empty] | } | [5 empty] | 0
| Content & Knowledge Management |  |  | } | [5 empty] | } | [5 empty] | 0
| One Stop Shop & Customer Services Centre |  |  | } | [5 empty] | } | [5 empty] | 0
| Shared Services & Data Sharing |  |  | } | [5 empty] | } | [5 empty] | 0
| Council Office - Rewiring | [14 empty] | 0
| Information Services - Salaries | [14 empty] | 0
| Kilncraigs Mill Develop. (consent brought forward) | [14 empty] | 0
65 | IT Services | CD | 8C |  | 300 |  |  |  | 300 |  |  |  |  | 0 | 300 | 300
66 | Finance Services - General Ledger system | CD | 8C |  | 40 |  |  |  | 40 |  |  |  |  | 0 | 40 | 40
82 | Council Office Improvements | CD | 8C |  | 140 |  |  |  | 140 |  |  |  |  | 0 | 140 | 140
| Dumyat Business Park Phase 2 | [14 empty] | 0
83 | Greenfield Driveway & Parking | CD | 8C |  |  |  | 84 |  | 84 |  |  |  |  | 0 | 0 | 84
76 | DDA & Asbestos Removal |  |  |  | 0 |  |  |  | 0 |  |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0
75 | CCTV | CE | 9X |  |  |  | 44 |  | 44 |  |  |  |  | 0 | 0 | 44
77 | Unallocated Capital Receipts Estimate (NET OF EXPENSES) - Now trf to PPP - see below | D&E | 7P |  | 0 | [5 empty] | 6800 |  |  | 6800 | -6800 | -6800
| Earmarked for Secondary Schools' PPP Procurement | D&E | 7P | [7 empty] | -6800 |  |  | -6800 | 6800 | 6800
| TOTAL CAPITAL PROGRAMME (EXCLUDING SCHOOLS' PPP PROJECT) |  |  |  | 6534 | 770 | 4829 | -300 | 11833 |  | 60 | 260 | 1190 | 1510 | 6474 | 10323 |  | #VALUE! | #VALUE! | #VALUE! | 0
Details of Grants & Capital Receipts referred to above
17b | SE Grant - Primary & Secondary School Developments | S2P | 1E | [10 empty] | 0 | [6 empty] | 10113 | Aug o/t per SC 11/10/07 report
28 | Private Developer - A91 East Stirling St. Alva Roundabout to access new school site | S2P | 1E | [9 empty] | 225 | 225 | [6 empty] | 770 | New Projects
131 | Sale of Land to College- Alloa Centre (Day & Adult Care) move to Alternative Accomodation | S2P | 3S | [8 empty] | 260 |  | 260 | [6 empty] | -300 | new trf to 9/10
49 | SE Grant - Contaminated Land | D&E | 5N | [7 empty] | 50 |  |  | 50 | [6 empty] | -260 | new grants/receipts
58 | HLF - Landscape Partnership - converse Ochills / Hillfoots | D&E | 6M | [9 empty] | 900 | 900 | [6 empty] | 10323
59 | SNH - Core Path network for Access | D&E | 6M | [9 empty] | 12 | 12
116 | ERDF - New Infrastructure | D&E | 6M | [7 empty] | 10 |  | 53 | 63
[11 empty] | 60 | 260 | 1190 | 1510
SCHOOLS PPP PROJECT
1-3,5 | PPP Capital Contribution to Costs - 08/09 allocation | S2P | PPP |  | 8100 |  |  |  | 8100 |  | 8100 |  |  | 8100 | 0 | 0
1-3,5 | PPP Capital Contribution to Costs - Carried from previous year | S2P | PPP |  |  |  | 8250 |  | 8250 |  |  |  | 8250 | 8250 | 0 | 0
17a | School Developments - Allocated to PPP | S2P | PPP |  | 600 |  | 175 |  | 775 |  | 600 |  | 175 | 775 | 0 | 0
| Total PPP Project |  |  |  | 8700 | 0 | 8425 | 0 | 17125 |  | 8700 | 0 | 8425 | 17125 | 0 | 0 |  |  |  |  | 0
Details of Grants / Cap Receipts funding for SCHOOL'S PPP PROJECT
79b | Expected increase in sale receipts from the three school sites to fund project 85/86 above | [14 empty] | 0
79c | Expected increase in sale receipts from the three school sites to fund project 104 above | [14 empty] | 0
77 | Capital Receipts Estimate (NET OF EXPENSES) - Now trf to fund PPP project | [14 empty] | 0
| Sale of Specific assets (Detailed list provided separately) | S2P | PPP | [7 empty] | 12020 |  | 4330 | 16350
9 | SE Grant - Schools Fund for PPP | S2P | PPP | [7 empty] | 600 |  | 175 | 775
78 | Sale of Land - land @ rear of St. Mungo's | S2P | PPP | [9 empty] | 1230 | 1230
78 | Sale of Land - Dumyat Park & Ditch - Tullibody Bypass | S2P | PPP | [9 empty] | 2025 | 2025
124 | Commercial Property A declared surplus (CLAREMOUNT BUSINESS CENTRE) | S2P | PPP | [9 empty] | 150 | 150
124 | Commercial Property B declared surplus (FORMER TULLIS SITE) | S2P | PPP | [9 empty] | 350 | 350
124 | Commercial Property C not declared surplus yet (BANK STREET / DRYSDALE STREET) | S2P | PPP | [9 empty] | 75 | 75
124 | Plot Property D not declared surplus yet (PLOT 10 SOUTH ALLOA) | S2P | PPP | [9 empty] | 500 | 500
124 | Property E declared surplus (DITCH FARM - LAND) | S2P | PPP | [7 empty] | 300 |  |  | 300
124 | Property F declared surplus (DITCH FARM - FARM HOUSE) | S2P | PPP | [7 empty] | 200 |  |  | 200
124 | Property G - not declared surplus yet (ALVA ACADEMY) | S2P | PPP | [7 empty] | 2330 |  |  | 2330
124 | Property H - not declared surplus yet (ALLOA ACADEMY) | S2P | PPP | [7 empty] | 9716 |  |  | 9716
124 | Property I - not declared surplus yet (FAIRFIELD SCHOOL) | S2P | PPP | [7 empty] | 470 |  |  | 470
| Trf to 09/10 | S2P | PPP | [7 empty] | -996 |  |  | -996
[11 empty] | 12620 | 0 | 4505 | 17125
| DO NOT ENTER ANYTHING IN THE BLUE BOX BELOW | [16 empty] | 0
| SUMMARY OF SERVICE UNITS | [17 empty] | #VALUE!
| Education & Community |  | 1E |  | 3475 | 70 | 127 | -300 | 3372 |  | 0 | 0 | 0 | 0 | 3475 | 3372
| Leisure |  | 2L |  | 0 | 0 | 40 | 0 | 40 |  | 0 | 0 | 0 | 0 | 0 | 40
| Social Services |  | 3S |  | 38 | 700 | 50 | 0 | 788 |  | 0 | 260 | 0 | 260 | 38 | 528
| Roads & Transportation |  | 4R |  | 1195 | 0 | 1230 | 0 | 2425 |  | 0 | 0 | 225 | 225 | 1195 | 2200
| Environment |  | 5N |  | 311 | 0 | 917 | 0 | 1228 |  | 50 | 0 | 0 | 50 | 261 | 1178
| Policy & Implementation |  | 6M |  | 310 | 0 | 2295 | 0 | 2605 |  | 10 | 0 | 965 | 975 | 300 | 1630
| Property Services |  | 7P |  | 625 | 0 | 42 | 0 | 667 |  | 0 | 0 | 0 | 0 | 625 | 667
| Corporate Development |  | 8C |  | 580 | 0 | 84 | 0 | 664 |  | 0 | 0 | 0 | 0 | 580 | 664
| Chief Executive |  | 9X |  | 0 | 0 | 44 | 0 | 44 |  | 0 | 0 | 0 | 0 | 0 | 44
[5 empty] | 6534 | 770 | 4829 | -300 | 11833 |  | 60 | 260 | 1190 | 1510 | 6474 | 10323
| Schools PPP Programme |  | PPP |  | 8700 | 0 | 8425 | 0 | 17125 |  | 8700 | 0 | 8425 | 17125 | 0 | 0
| Total Capital Including Schools PPP Programme |  |  |  | 15234 | 770 | 13254 | -300 | 28958 |  | 8760 | 260 | 9615 | 18635 | 6474 | 10323
[5 empty] | OK | OK | OK | OK | OK |  | OK | OK | OK | OK | OK | OK

## 09-10 at Aug 07 (hidden)
1 | 2 |  |  | 3 | [5 empty] | 4 | 4 | 4 |  | 5 | 5
|  | Service | Service Units | Gross Expenditure 2009/10 | [5 empty] | Grants / Specific Cap Receipts 2009/10 |  |  |  | Net Expenditure (Council Contribution) 2009/10 |  | APPENDIX 3 | Recurring Revenue consequences
| General Services Capital Programme 2009/10 |  |  | Budget as at Aug 2007 out-turn reported to SC on 11/10/07 | New Projects | Projects transferred (to)/from 08/09 | Projects transferred (to)/from 10/11 | Revised Budget after proposed transfers |  | Budget as at Aug 2007 out-turn reported to SC on 11/10/07 | Projects transferred (to)/from 08/09 | Revised Budget after proposed transfers |  | Borrowing as at Aug 2007 out-turn reported to SC on 11/10/07 | Revised Borrowing (Council Contribution) |  | for the proposed project
|  |  |  | £'000 |  | £'000 | £'000 | £'000 |  | £'000 | £'000 | £'000 |  | £'000 | £'000
| PROJECT |  |  | BUDGET OUT
8 | School Building Alarm Systems | S2P | 1E |  |  | 300 |  | 300 |  |  |  | 0 |  | 0 | 300
85,86 | ICT Hardware Replacement in Sec Schls & New IT Installation in Schools |  | 1E | [8 empty] | 0 |  | 0 | 0
16 | Leisure Bowl - Complete refurbishment per 20yr Development plan |  | 1E | [8 empty] | 0 |  | 0 | 0
18 | Fir Ski Park Centre - upgrade to building |  | 1E | [8 empty] | 0 |  | 0 | 0
17b | Primary & Nursery School Developments | S2P | 1E | 1000 |  |  |  | 1000 |  |  |  | 0 |  | 1000 | 1000
19 | Reconfiguration of Council Services & Property Asset in Tillicoultry | S2P | 1E | 500 |  |  |  | 500 |  |  |  | 0 |  | 500 | 500
88 | Development of Community Facilities in Alva | S2P | 1E | 3000 |  |  |  | 3000 |  | 200 |  | 200 |  | 2800 | 2800
89 | Cochrane Hall - Refurbishment & Upgrading | S2P | 1E | 500 |  |  |  | 500 |  |  |  | 0 |  | 500 | 500
91 | Clackmannanshire's Outdoor Activity Centre | S2P | 1E | 500 |  |  |  | 500 |  | 200 |  | 200 |  | 300 | 300
92 | Running Track at Lornshill Academy | S2P | 1E | 460 |  |  |  | 460 |  | 200 |  | 200 |  | 260 | 260
103 | Demolition of Lornshill Academy & construct car parking & football pitch | S2P | 1E | 1250 |  |  |  | 1250 |  |  |  | 0 |  | 1250 | 1250
| Office Relocations | [10 empty] | 0 |  | 0 | 0
| Whins Resource Centre - Floor Heating System | [10 empty] | 0 |  | 0 | 0
| Care in Community Safety (** new proposal - see attached schedule) | [10 empty] | 0 |  | 0 | 0
| Upgrade 6 Marshill Alloa | [10 empty] | 0 |  | 0 | 0
| Document Imaging System (** new proposal - see attached schedule) | [10 empty] | 0 |  | 0 | 0
20 | DDA Compliance | [10 empty] | 0 |  | 0 | 0
21 | Joint FVNHS/ Adult Care Premises Occupation | [10 empty] | 0 |  | 0 | 0
22 | Menstrie House En-Suite Conversion | [10 empty] | 0 |  | 0 | 0
23 | Ludgate House Resource Centre | [10 empty] | 0 |  | 0 | 0
24 | Mental Health Services | [10 empty] | 0 |  | 0 | 0
| A907 - Council Contribution | } | [9 empty] | 0 |  | 0 | 0
26 | Accident Prevention & Traffic Management | [10 empty] | 0 |  | 0 | 0 |  | 0 | 0 | 0
27 | Alloa Town Centre | [10 empty] | 0 |  | 0 | 0 |  | -200 | -200 | -200
| Accident Prevention & Traffic Management - Safer Roads, Cycling | [10 empty] | 0 |  | 0 | 0
28 | A91 East Stirling St. Alva Roundabout to access new school site | [10 empty] | 0 |  | 0 | 0
29 | A908/B908 Sauchie, Roundabout to facilitate new hospital | [10 empty] | 0 |  | 0 | 0
31 | B9140/ Collylands Cross Upgrade | [10 empty] | 0 |  | 0 | 0 |  | 0 | 0 | 0
| B9140 Realignment of Bends | [10 empty] | 0 |  | 0 | 0
31 | B9140 Realignment of Bends | [10 empty] | 0 |  | 0 | 0
31c | B9140 Realignment of Bends (Collylands to Fishcross/Maggies Wood - East | D&E | 4R | 500 |  |  |  | 500 |  |  |  | 0 |  | 500 | 500 |  | 0 | 0 | 0
| Eastern Link Road |  | 4R |  |  |  |  | 0 |  |  |  | 0 |  | 0 | 0
| Hall Park |  | 4R |  |  |  |  | 0 |  |  |  | 0 |  | 0 | 0
| Footpath Maintenance |  | 4R |  |  |  |  | 0 |  |  |  | 0 |  | 0 | 0
| Roads Maintenance |  | 4R |  |  |  |  | 0 |  |  |  | 0 |  | 0 | 0
| Smithfield Loan |  | 4R |  |  |  |  | 0 |  |  |  | 0 |  | 0 | 0
| Roads Structural Maintenance |  | 4R |  |  |  |  | 0 |  |  |  | 0 |  | 0 | 0
32 | Bridges | D&E | 4R | 30 |  |  |  | 30 |  |  |  | 0 |  | 30 | 30
33 | Flood Prevention | D&E | 4R |  |  |  |  | 0 |  |  |  | 0 |  | 0 | 0 |  | 0 | 0 | 0
34 | Retentions | D&E | 4R |  |  |  |  | 0 |  |  |  | 0 |  | 0 | 0 |  | 0 | 0 | 0
35 | Road & Footway Improvements (SRMCS), including town centres | D&E | 4R | 500 |  |  |  | 500 |  |  |  | 0 |  | 500 | 500 |  | 0 | 0 | 0
36 | Cycling , Walking ,Safer Streets (CWSS) | D&E | 4R |  |  |  |  | 0 |  |  |  | 0 |  | 0 | 0 |  | 0 | 0 | 0
37 | Street Lighting | D&E | 4R | 200 |  |  |  | 200 |  |  |  | 0 |  | 200 | 200 |  | 0 | 0 | 0
| Tullibody Bypass (to be funded from special capital receipts) | D&E | 4R |  |  |  |  | 0 |  |  |  | 0 |  | 0 | 0
38 | Total SAK Rail Project & Alloa ELR Project Costs | D&E | 4R |  |  |  |  | 0 |  |  |  | 0 |  | 0 | 0 |  | -20 | -20 | -20
39 | Tullibody By Pass | D&E | 4R |  |  |  |  | 0 |  |  |  | 0 |  | 0 | 0
40 | Tullibody By Pass c/f from 2004/05 | D&E | 4R |  |  |  |  | 0 |  |  |  | 0 |  | 0 | 0
41 | 20mph speed reduction | D&E | 4R |  |  |  |  | 0 |  |  |  | 0 |  | 0 | 0
42 | Footways at Muirside, Tullibody | D&E | 4R |  |  |  |  | 0 |  |  |  | 0 |  | 0 | 0
43 | SESTRAN Public Transport & Walking | D&E | 4R |  |  |  |  | 0 |  |  |  | 0 |  | 0 | 0
44 | SESTRAN Public Bus | D&E | 4R |  |  |  |  | 0 |  |  |  | 0 |  | 0 | 0
45 | SUSTRAN - Cycle Routes | D&E | 4R |  |  |  |  | 0 |  |  |  | 0 |  | 0 | 0
93 | A907 B910 / Helensfield Junction for Railway Line/ Realignment | D&E | 4R | 200 |  |  |  | 200 |  |  |  | 0 |  | 200 | 200
106 | Shillinghill Roundabout | D&E | 4R | 400 |  |  |  | 400 |  |  |  | 0 |  | 400 | 400
107 | A908/B908 Hallpark, Sauchie | D&E | 4R | 350 |  | -350 |  | 0 |  |  |  | 0 |  | 350 | 0
46 | Black Devon Landfill / Incinerator | [10 empty] | 0 |  | 0 | 0 |  | minimal savings >>>>>>>>>>>>>>
47 | Black Devon Landfill Gas Collection & Treatment Project | [10 empty] | 0 |  | 0 | 0
48 | Cemeteries Strategy | [10 empty] | 0 |  | 0 | 0 |  | # | # | #
| Cycle Path Network | [10 empty] | 0 |  | 0 | 0
| Dollar Cemetery | [10 empty] | 0 |  | 0 | 0
| Environmental Improvements | [10 empty] | 0 |  | 0 | 0
| Old Alloa THI Project | [10 empty] | 0 |  | 0 | 0
| Hillfoots Initiative | [10 empty] | 0 |  | 0 | 0
| Incineration Plant Demolition | [10 empty] | 0 |  | 0 | 0
| Landward Village Initiative | [10 empty] | 0 |  | 0 | 0
49 | Contaminated Land | D&E | 5N | 50 |  |  |  | 50 |  | 50 |  | 50 |  | 0 | 0 |  | Budget already in place for Land Officer
| Tullis Factory Demolition |  | 5N |  |  |  |  | 0 |  |  |  | 0 |  | 0 | 0
50 | Parks & Open Spaces |  | 5N |  |  |  |  | 0 |  |  |  | 0 |  | 0 | 0
51 | Outdoor Play Area Strategy |  | 5N |  |  |  |  | 0 |  |  |  | 0 |  | 0 | 0
52 | Shared Compost Facility @ Polmaise |  | 5N |  |  |  |  | 0 |  |  |  | 0 |  | 0 | 0
53 | Shared Transfer Facility @ Polmaise |  | 5N |  |  |  |  | 0 |  |  |  | 0 |  | 0 | 0
54b | Wheeled / Litter Bins | D&E | 5N | 100 |  |  |  | 100 |  |  |  | 0 |  | 100 | 100
55 | Clackmannan Tolbooth | [10 empty] | 0 |  | 0 | 0 |  | # | # | #
56 | National Cycle Route | [10 empty] | 0 |  | 0 | 0 |  | # | # | #
57 | Old Alloa Townscape Heritage | [10 empty] | 0 |  | 0 | 0 |  | # | # | #
58 | Landscape Partnership - Conserve Ochills / Hillfoots | [10 empty] | 0 |  | 0 | 0
59 | Core Path Network for Access | [10 empty] | 0 |  | 0 | 0
114 | Lime Tree Walk Phase 2 | D&E | 6M | 50 |  |  |  | 50 |  |  |  | 0 |  | 50 | 50
60 | Asbestos Removal | [10 empty] | 0 |  | 0 | 0
61 | Centralised Kitchen | [10 empty] | 0 |  | 0 | 0
62 | Disability Discrimination Act | [10 empty] | 0 |  | 0 | 0
63a | Vehicle Replacement Programme | D&E | 7P | 612 |  |  |  | 612 |  |  |  | 0 |  | 612 | 612
| Retentions Carry forward (projects to be identified) | [10 empty] | 0 |  | 0 | 0
63b | Keilarsbrae land Purchases | [10 empty] | 0 |  | 0 | 0
71 | Kilncraigs Mill 1904 Development of 3rd & 4th Floors | [10 empty] | 0 |  | 0 | 0
99 | Forthbank Accommodation Rationalisation | [10 empty] | 0 |  | 0 | 0
| CCTV - Alloa South & East | [10 empty] | 0 |  | 0 | 0
| Community Planning | [10 empty] | 0 |  | 0 | 0
64 | Efficient Government/Customer First Developments | CD | 8C | 500 |  |  |  | 500 |  |  |  | 0 | # | 500 | 500
| Business Change & Organisational Development | } | [6 empty] | } |  |  | 0 |  | 0 | 0
| Clack Web - eServices & eCommunity | } | [6 empty] | } |  |  | 0 |  | 0 | 0
| Content & Knowledge Management | } | [6 empty] | } |  |  | 0 |  | 0 | 0
| One Stop Shop & Customer Services Centre | } | [6 empty] | } |  |  | 0 |  | 0 | 0
| Shared Services & Data Sharing | } | [6 empty] | } |  |  | 0 |  | 0 | 0
| Council Office - Rewiring | [10 empty] | 0 |  | 0 | 0
| Information Services - Salaries | [10 empty] | 0 |  | 0 | 0
| Kilncraigs Mill Develop. (consent brought forward) | [10 empty] | 0 |  | 0 | 0
65 | IT Services | CD | 8C | 363 |  |  |  | 363 |  |  |  | 0 |  | 363 | 363
75 | CCTV - Alloa South & East | CE | 9X |  | 65 |  |  | 65 |  |  |  | 0 |  | 0 | 65
77 | Unallocated Capital Receipts | D&E | 7P | 0 |  |  |  | 0 |  | 996 |  | 996 |  | -996 | -996
| TOTAL CAPITAL PROGRAMME (EXCLUDING SCHOOLS' PPP PROJECT) |  |  | 11065 | 65 | -50 | 0 | 11080 |  | 1646 | 0 | 1646 |  | 9419 | 9434 |  | #VALUE! | #VALUE! | #VALUE! | 0
List of Assets Sale Receipts allocated to specific projects referred to above
79a | Expected increase in sale receipts from the three school sites to part fund project 19 above - Now trf to PPP
79d | Expected increase in sale receipts from the three school sites to part fund project 88 above
79e | Expected increase in sale receipts from the three school sites to fund project 103 above
[10 empty] | 0 | 0 | 0
Details of Grants & Capital Receipts referred to above
49 | SE Grant - Contaminated Land | [8 empty] | 50 |  | 50 | [7 empty] | 9069 | Aug o/t per SC 11/10/07 report
64 | SE Grant - Efficient Government/Customer First Developments (not yet known) # | [10 empty] | 0 | # | [6 empty] | 65 | New projects
88 | The Sports Scotland Fund - Alva Academy Sports Complex | [8 empty] | 200 |  | 200 | [7 empty] | 300 | new trf from 08/09
91 | The Sports Scotland Fund - Outdoor Activity Centre | [8 empty] | 200 |  | 200 | [7 empty] | 9434
92 | The Sports Scotland Fund - Running Track, Lornshill Academy | [8 empty] | 200 |  | 200
0
77 | Unallocated Capital Receipts - Balance left after allocating receipts for School's PPP (see 08/09) | [8 empty] | 996 |  | 996
[10 empty] | 1646 | 0 | 1646
SCHOOLS PPP PROJECT
1-3,5 | PPP Capital Contribution to Costs - 09/10 allocation | S2P | PPP | 700 |  |  |  | 700 |  | 700 |  | 700 |  | 0 | 0
| Total PPP Project |  |  | 700 | 0 | 0 | 0 | 700 |  | 700 | 0 | 700 |  | 0 | 0 |  |  |  |  | 0
Details of Grants / Cap Receipts funding for SCHOOL'S PPP PROJECT
| SE Grant - Schools Fund for PPP | S29 | PPP | [6 empty] | 700 |  | 700
[10 empty] | 700 | 0 | 700
| DO NOT ENTER ANYTHING IN THE BLUE BOX BELOW | [15 empty] | 0
| SUMMARY OF SERVICE UNITS | [16 empty] | 0
| Education & Community |  | 1E | 7210 | 0 | 300 | 0 | 7510 |  | 600 | 0 | 600 |  | 6610 | 6910
| Leisure |  | 2L | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0
| Social Services |  | 3S | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0
| Roads & Transportation |  | 4R | 2180 | 0 | -350 | 0 | 1830 |  | 0 | 0 | 0 |  | 2180 | 1830
| Environment |  | 5N | 150 | 0 | 0 | 0 | 150 |  | 50 | 0 | 50 |  | 100 | 100
| Policy & Implementation |  | 6M | 50 | 0 | 0 | 0 | 50 |  | 0 | 0 | 0 |  | 50 | 50
| Property Services |  | 7P | 612 | 0 | 0 | 0 | 612 |  | 996 | 0 | 996 |  | -384 | -384
| Corporate Development |  | 8C | 863 | 0 | 0 | 0 | 863 |  | 0 | 0 | 0 |  | 863 | 863
| Chief Executive |  | 9X | 0 | 65 | 0 | 0 | 65 |  | 0 | 0 | 0 |  | 0 | 65
|  |  |  | 11065 | 65 | -50 | 0 | 11080 |  | 1646 | 0 | 1646 |  | 9419 | 9434
| Schools PPP Programme |  | PPP | 700 | 0 | 0 | 0 | 700 |  | 700 | 0 | 700 |  | 0 | 0
| Total Capital Including Schools PPP Programme |  |  | 11765 | 65 | -50 | 0 | 11780 |  | 2346 | 0 | 2346 |  | 9419 | 9434
|  |  |  | OK | OK | OK | OK | OK |  | OK | OK | OK |  | OK | OK
Note on G36: superuser: £500k transferred from 08/09 budget!!
Note on I60: superuser: Saving of £285k re. grant from FVNHS. Bal of £65k trf to 07/08

## 10-11 at Aug 07 (hidden)
1 | 2 |  |  | 3 |  |  |  | 4 | 4 | 4 |  | 5 | 5
|  | Service | Service Units | Gross Expenditure 2010/11 |  |  |  | Grants / Specific Cap Receipts 2010/11 |  |  |  | Net Expenditure (Council Contribution) 2010/11 |  | APPENDIX 4 | Recurring Revenue consequences
| General Services Capital Programme 2010/11 |  |  | Proposed Budget | Projects transferred (to)/from 09/10 | Revised Budget after proposed transfers |  | Proposed Budget | Projects transferred (to)/from 09/10 | Revised Budget after proposed transfers |  | Proposed Borrowing | Revised Borrowing (Council Contribution) |  | for the proposed project
|  |  |  | £'000 | £'000 | £'000 |  | £'000 | £'000 | £'000 |  | £'000 | £'000
| PROJECT |  |  | BUDGET OUT
17b | Primary & Nursery School Developments | S2P | 1E | 1000 |  | 1000 |  |  |  | 0 |  | 1000 | 1000
85,86 | ICT Hardware Replacement in Sec Schls & New IT Installation in Schools |  | 1E | [6 empty] | 0 |  | 0 | 0
16 | Leisure Bowl - Complete refurbishment per 20yr Development plan |  | 1E | [6 empty] | 0 |  | 0 | 0
18 | Fir Ski Park Centre - upgrade to building |  | 1E | [6 empty] | 0 |  | 0 | 0
| Office Relocations | [8 empty] | 0 |  | 0 | 0
| Whins Resource Centre - Floor Heating System | [8 empty] | 0 |  | 0 | 0
| Care in Community Safety (** new proposal - see attached schedule) | [8 empty] | 0 |  | 0 | 0
| Upgrade 6 Marshill Alloa | [8 empty] | 0 |  | 0 | 0
| Document Imaging System (** new proposal - see attached schedule) | [8 empty] | 0 |  | 0 | 0
20 | DDA Compliance | [8 empty] | 0 |  | 0 | 0
21 | Joint FVNHS/ Adult Care Premises Occupation | [8 empty] | 0 |  | 0 | 0
22 | Menstrie House En-Suite Conversion | [8 empty] | 0 |  | 0 | 0
23 | Ludgate House Resource Centre | [8 empty] | 0 |  | 0 | 0
24 | Mental Health Services | [8 empty] | 0 |  | 0 | 0
| A907 - Council Contribution | } | [7 empty] | 0 |  | 0 | 0
26 | Accident Prevention & Traffic Management | [8 empty] | 0 |  | 0 | 0 |  | 0 | 0 | 0
27 | Alloa Town Centre | [8 empty] | 0 |  | 0 | 0 |  | -200 | -200 | -200
| Accident Prevention & Traffic Management - Safer Roads, Cycling | [8 empty] | 0 |  | 0 | 0
28 | A91 East Stirling St. Alva Roundabout to access new school site | [8 empty] | 0 |  | 0 | 0
29 | A908/B908 Sauchie, Roundabout to facilitate new hospital | [8 empty] | 0 |  | 0 | 0
31 | B9140/ Collylands Cross Upgrade | [8 empty] | 0 |  | 0 | 0 |  | 0 | 0 | 0
| B9140 Realignment of Bends | [8 empty] | 0 |  | 0 | 0
31 | B9140 Realignment of Bends | [8 empty] | 0 |  | 0 | 0
135 | Schools Security | S2P | 1E | 600 |  | 600 |  |  |  | 0 |  | 600 | 600
31c | B9140 Realignment of Bends (Collylands to Fishcross/Maggies Wood - East | D&E | 4R |  |  | 0 |  |  |  | 0 |  | 0 | 0 |  | 0 | 0 | 0
| Eastern Link Road |  | 4R |  |  | 0 |  |  |  | 0 |  | 0 | 0
| Hall Park |  | 4R |  |  | 0 |  |  |  | 0 |  | 0 | 0
| Footpath Maintenance |  | 4R |  |  | 0 |  |  |  | 0 |  | 0 | 0
| Roads Maintenance |  | 4R |  |  | 0 |  |  |  | 0 |  | 0 | 0
| Smithfield Loan |  | 4R |  |  | 0 |  |  |  | 0 |  | 0 | 0
| Roads Structural Maintenance |  | 4R |  |  | 0 |  |  |  | 0 |  | 0 | 0
32 | Bridges | D&E | 4R |  |  | 0 |  |  |  | 0 |  | 0 | 0
33 | Flood Prevention | D&E | 4R |  |  | 0 |  |  |  | 0 |  | 0 | 0 |  | 0 | 0 | 0
34 | Retentions | D&E | 4R |  |  | 0 |  |  |  | 0 |  | 0 | 0 |  | 0 | 0 | 0
35 | Road & Footway Improvements (SRMCS), including town centres | D&E | 4R |  |  | 0 |  |  |  | 0 |  | 0 | 0 |  | 0 | 0 | 0
36 | Cycling , Walking ,Safer Streets (CWSS) | D&E | 4R |  |  | 0 |  |  |  | 0 |  | 0 | 0 |  | 0 | 0 | 0
37 | Street Lighting | D&E | 4R |  |  | 0 |  |  |  | 0 |  | 0 | 0 |  | 0 | 0 | 0
| Tullibody Bypass (to be funded from special capital receipts) | D&E | 4R |  |  | 0 |  |  |  | 0 |  | 0 | 0
38 | Total SAK Rail Project & Alloa ELR Project Costs | D&E | 4R |  |  | 0 |  |  |  | 0 |  | 0 | 0 |  | -20 | -20 | -20
39 | Tullibody By Pass | D&E | 4R |  |  | 0 |  |  |  | 0 |  | 0 | 0
40 | Tullibody By Pass c/f from 2004/05 | D&E | 4R |  |  | 0 |  |  |  | 0 |  | 0 | 0
41 | 20mph speed reduction | D&E | 4R |  |  | 0 |  |  |  | 0 |  | 0 | 0
42 | Footways at Muirside, Tullibody | D&E | 4R |  |  | 0 |  |  |  | 0 |  | 0 | 0
43 | SESTRAN Public Transport & Walking | D&E | 4R |  |  | 0 |  |  |  | 0 |  | 0 | 0
44 | SESTRAN Public Bus | D&E | 4R |  |  | 0 |  |  |  | 0 |  | 0 | 0
45 | SUSTRAN - Cycle Routes | D&E | 4R |  |  | 0 |  |  |  | 0 |  | 0 | 0
93 | A907 B910 / Helensfield Junction for Railway Line/ Realignment | D&E | 4R |  |  | 0 |  |  |  | 0 |  | 0 | 0
106 | Shillinghill Roundabout | D&E | 4R |  |  | 0 |  |  |  | 0 |  | 0 | 0
107 | A908/B908 Hallpark, Sauchie | D&E | 4R |  |  | 0 |  |  |  | 0 |  | 0 | 0
46 | Black Devon Landfill / Incinerator | [8 empty] | 0 |  | 0 | 0 |  | minimal savings >>>>>>>>>>>>>>
47 | Black Devon Landfill Gas Collection & Treatment Project | [8 empty] | 0 |  | 0 | 0
48 | Cemeteries Strategy | [8 empty] | 0 |  | 0 | 0 |  | # | # | #
| Cycle Path Network | [8 empty] | 0 |  | 0 | 0
| Dollar Cemetery | [8 empty] | 0 |  | 0 | 0
| Environmental Improvements | [8 empty] | 0 |  | 0 | 0
| Old Alloa THI Project | [8 empty] | 0 |  | 0 | 0
| Hillfoots Initiative | [8 empty] | 0 |  | 0 | 0
| Incineration Plant Demolition | [8 empty] | 0 |  | 0 | 0
| Landward Village Initiative | [8 empty] | 0 |  | 0 | 0
49 | Contaminated Land | D&E | 5N |  |  | 0 |  |  |  | 0 |  | 0 | 0 |  | Budget already in place for Land Officer
| Tullis Factory Demolition |  | 5N |  |  | 0 |  |  |  | 0 |  | 0 | 0
50 | Parks & Open Spaces |  | 5N |  |  | 0 |  |  |  | 0 |  | 0 | 0
51 | Outdoor Play Area Strategy |  | 5N |  |  | 0 |  |  |  | 0 |  | 0 | 0
52 | Shared Compost Facility @ Polmaise |  | 5N |  |  | 0 |  |  |  | 0 |  | 0 | 0
53 | Shared Transfer Facility @ Polmaise |  | 5N |  |  | 0 |  |  |  | 0 |  | 0 | 0
50 | Parks & Open Spaces | D&E | 5N | 80 |  | 80 |  |  |  | 0 |  | 80 | 80
51 | Outdoor Play Strategy | D&E | 5N | 80 |  | 80 |  |  |  | 0 |  | 80 | 80
55 | Clackmannan Tolbooth | [8 empty] | 0 |  | 0 | 0 |  | # | # | #
56 | National Cycle Route | [8 empty] | 0 |  | 0 | 0 |  | # | # | #
57 | Old Alloa Townscape Heritage | [8 empty] | 0 |  | 0 | 0 |  | # | # | #
58 | Landscape Partnership - Conserve Ochills / Hillfoots | [8 empty] | 0 |  | 0 | 0
59 | Core Path Network for Access | [8 empty] | 0 |  | 0 | 0
132 | Pitch Strategy | D&E | 5N | 150 |  | 150 |  |  |  | 0 |  | 150 | 150
133 | Street Trees | D&E | 5N | 75 |  | 75 |  |  |  | 0 |  | 75 | 75
60 | Asbestos Removal | [8 empty] | 0 |  | 0 | 0
61 | Centralised Kitchen | [8 empty] | 0 |  | 0 | 0
62 | Disability Discrimination Act | [8 empty] | 0 |  | 0 | 0
63a | Vehicle Replacement Programme | D&E | 7P | 1670 |  | 1670 |  |  |  | 0 |  | 1670 | 1670
| Retentions Carry forward (projects to be identified) | [8 empty] | 0 |  | 0 | 0
63b | Keilarsbrae land Purchases | [8 empty] | 0 |  | 0 | 0
71 | Kilncraigs Mill 1904 Development of 3rd & 4th Floors | [8 empty] | 0 |  | 0 | 0
99 | Forthbank Accommodation Rationalisation | [8 empty] | 0 |  | 0 | 0
| CCTV - Alloa South & East | [8 empty] | 0 |  | 0 | 0
| Community Planning | [8 empty] | 0 |  | 0 | 0
| Business Change & Organisational Development | } |  |  |  |  | } |  |  | 0 |  | 0 | 0
| Clack Web - eServices & eCommunity | } |  |  |  |  | } |  |  | 0 |  | 0 | 0
| Content & Knowledge Management | } |  |  |  |  | } |  |  | 0 |  | 0 | 0
| One Stop Shop & Customer Services Centre | } |  |  |  |  | } |  |  | 0 |  | 0 | 0
| Shared Services & Data Sharing | } |  |  |  |  | } |  |  | 0 |  | 0 | 0
| Council Office - Rewiring | [8 empty] | 0 |  | 0 | 0
| Information Services - Salaries | [8 empty] | 0 |  | 0 | 0
| Kilncraigs Mill Develop. (consent brought forward) | [8 empty] | 0 |  | 0 | 0
65 | IT Services | CD | 8C | 330 |  | 330 |  |  |  | 0 |  | 330 | 330
66a | Finance Systems Upgrades | CD | 8C | 50 |  | 50 |  |  |  | 0 |  | 50 | 50
75 | CCTV - Alloa South & East | CE | 9X | 65 |  | 65 |  |  |  | 0 |  | 65 | 65
77 | Unallocated Capital Receipts | D&E | 7P |  |  | 0 |  |  |  | 0 |  | 0 | 0
| TOTAL CAPITAL PROGRAMME (EXCLUDING SCHOOLS' PPP PROJECT) |  |  | 4100 | 0 | 4100 |  | 0 | 0 | 0 |  | 4100 | 4100 |  | #VALUE! | #VALUE! | #VALUE! | 0
List of Assets Sale Receipts allocated to specific projects referred to above
79a | Expected increase in sale receipts from the three school sites to part fund project 19 above - Now trf to PPP
79d | Expected increase in sale receipts from the three school sites to part fund project 88 above
79e | Expected increase in sale receipts from the three school sites to fund project 103 above
[8 empty] | 0 | 0 | 0
Details of Grants & Capital Receipts referred to above
49 | SE Grant - Contaminated Land | [8 empty] | 0
64 | SE Grant - Efficient Government/Customer First Developments (not yet known) # | [8 empty] | 0 | #
88 | The Sports Scotland Fund - Alva Academy Sports Complex | [8 empty] | 0
91 | The Sports Scotland Fund - Outdoor Activity Centre | [8 empty] | 0
92 | The Sports Scotland Fund - Running Track, Lornshill Academy | [8 empty] | 0
0
77 | Unallocated Capital Receipts - Balance left after allocating receipts for School's PPP (see 08/09) | [8 empty] | 0
[8 empty] | 0 | 0 | 0
SCHOOLS PPP PROJECT
1-3,5 | PPP Capital Contribution to Costs - 09/10 allocation | S2P | PPP |  |  | 0 |  |  |  | 0 |  | 0 | 0
| Total PPP Project |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  |  |  |  | 0
Details of Grants / Cap Receipts funding for SCHOOL'S PPP PROJECT
| SE Grant - Schools Fund for PPP | S29 | PPP | [6 empty] | 0
[8 empty] | 0 | 0 | 0
| DO NOT ENTER ANYTHING IN THE BLUE BOX BELOW | [13 empty] | 0
| SUMMARY OF SERVICE UNITS | [14 empty] | 0
| Education & Community |  | 1E | 1600 | 0 | 1600 |  | 0 | 0 | 0 |  | 1600 | 1600
| Leisure |  | 2L | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0
| Social Services |  | 3S | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0
| Roads & Transportation |  | 4R | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0
| Environment |  | 5N | 385 | 0 | 385 |  | 0 | 0 | 0 |  | 385 | 385
| Policy & Implementation |  | 6M | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0
| Property Services |  | 7P | 1670 | 0 | 1670 |  | 0 | 0 | 0 |  | 1670 | 1670
| Corporate Development |  | 8C | 380 | 0 | 380 |  | 0 | 0 | 0 |  | 380 | 380
| Chief Executive |  | 9X | 65 | 0 | 65 |  | 0 | 0 | 0 |  | 65 | 65
|  |  |  | 4100 | 0 | 4100 |  | 0 | 0 | 0 |  | 4100 | 4100
| Schools PPP Programme |  | PPP | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0
| Total Capital Including Schools PPP Programme |  |  | 4100 | 0 | 4100 |  | 0 | 0 | 0 |  | 4100 | 4100
|  |  |  | OK | OK | OK |  | OK | OK | OK |  | OK | OK

## Project List (hidden)
1 | Alva Academy PPP Support
2 | Alloa Academy PPP Support
3 | Lonshill Academy & Tulligarth Phase 2 PPP Support
4 | DDA - Education - taken out, but not avaialble as it is used for DDA Edu generally
5 | General PPP Support
6 | Lochies Specialist Accomodation
7 | Museum & Heritage Centre
8 | School Building Alarm System
9 | Schools Fund
10 | Tulligarth Sports Resurfacing - requirement of Lottery funding
11 | Library Refurbishment
12
13 | Heavy Equipment in Secondary Schools - Kilns etc
14 | IT Hardware Replacement in Schools
15 | Legal Commitments - for projects undertaking in previous years
16 | Leisure Bowl - refurbishment
17a | Schools Development - PPP Support
17b | Primary & Nursery Schools Development
18 | Fir Park Ski Centre - Upgrade to Building
19 | Reconfiguration of Council Services & Property Asset in Tillicoultry
20 | DDA Compliance - Sicial Services
21 | Joint FVNHS/ Adult Care Premises Occupation
22 | Menstrie House En-Suite Conversion
23 | Ludgate House External Fabric - Retentions
24 | Mental Health Services - Retentions
25 | Menstrie House - Increased Parking & Security Fencing
26 | Accident Prevention & Traffic Management
27 | Alloa Town Centre - delete this. It is already opened as 87
28 | A91 East Stirling St. Alva Roundabout to access new school site
29 | A908/B908 Sauchie, Roundabout Facility to New Hospital
30
31a | B9140/ Collylands Cross Upgrade
31b | B9140 Realignment of Bends
32 | Bridge Strengthening
33 | Flood Prevention
34 | Retentions
35 | Road & Footway Improvements (SRMCS), including town centres
36 | Cycling , Walking ,Safer Streets (CWSS)
37 | Street Lighting
38 | Total SAK Rail Project & Alloa ELR Project Costs
39 | Tullibody By Pass
40 | Tullibody By Pass c/f from 2004/05
41 | 20mph speed reduction
42 | Footways at Muirside, Tullibody
43 | SESTRAN Public Transport & Walking
44 | SESTRAN Public Bus
45 | SUSTRAN Cycle Routes
46 | Black Devon Landfill / Incinerator
47 | Black Devon Landfill Gas Collection & Treatment Project
48 | Cemeteries Strategy
49 | Contaminated Land
50 | Parks & Open Spaces
51 | Outdoor Play Area
52 | Shared Compost Facility at Polmaise
53 | Shared Transfer Facility at Polmaise
54a | Waste Recycling Project
54b | Wheeled / Litter Bins
55 | Clackmannan Tolbooth
56 | National Cycle Route
57 | Old Alloa Townscape Heritage
58 | Landscape Partnership - Conserve Ochills / Hillfoots
59 | Core Path Network for Access
60 | Asbestos Removal - Property Services
61 | Centralised Kitchen
62 | DDA - Property Services
63a | Vehicle Replacement Programme
63b | Keilarsbrae Land Purchase
64 | Efficient Government/Customer First Developments
65 | IT Services
66a | Finance Services
66b | Ludgate House Traffic Management - Retentions
67 | CSBP Restructuring - taken out
68 | Econ. Dev. Infrastructure: Eastern Clackmannanshire Development Opportunities
69
70 | Kilncraigs Mill 1936 Building Envelop
71 | Kilncraigs Mill 1904 Development of 3rd & 4th Floors
72a | Kilncraigs Mill 1904 Mill Conversion
72b | Kilncraigs Mill 1904 Access Control & Zoning Services
73 | Pavilions Business Park Phase 2
74 | Dumyat Business Park Phase 3
75 | CCTV - Sauchie - taken out but avaibale as it has been used for CCTV generally
76 | DDA / Asbestos Removal - Chief Exec
77 | Capita Receipts General
78 | Sale of Land - Dumyat Park / Land @ rear of St.Mungo's
79 | Expected increase in sale receipts from the three achool sites
80 | ERDF Grants
81 | Earmarked Asset Sale Receipts for Collyland (31b) project - now deleted (as at Jan 2007)
82 | Council Office Improvements
83 | Greenfield Driveway & Parking
84 | Earmarked Asset Sale Receipts for Alloa Town Centre projects 110 & 113
85 | New IT Instalation in Schools
86 | ICT Hardware Replacement in Secondary Schools
87 | Alloa Town Hall
88 | Development of Community Facilities in Alva/ Alva Academy Sports Complex, Refurbishment & Upgrading
89 | Cochrane Hall, Alva Refurbishement & Upgrading
90 | Gynastic Centre - upgrading
91 | Clackmannanshire's Outdoor Activity Centre
92 | Running Track at Lornshill Academy
93 | A907 B910 / Helensfield Juncion for Railway Line
94 | Biodiversity taken out
95 | Services Sites for Business Development taken out
96 | Feasibility Studies taken out
97
98 | Kilncraigs Mill 1904 Upgrade of Existing
99 | Forthbank Accomodation Rationalisation
100 | Sustainable Treescape - taken out
101 | Alloa Day Centre
102 | Mailroom Facilities & Franking Machine
103 | Demolition of Lornshill Academy & construct car parking & football pitch
104 | Purchase of Whit Boards for new Secondar Schools
105 | A907 - Marywood to Parkmill Roundabout
106 | Shillinghill Roundabout
107 | A908/B908 Hallpark, Sauchie
108 | Castle Street Business Units
109 | Forth Valley College
110 | Alloa Town Centre Regeneration: Speirs Centre
111 | Alloa Town Centre: Public Realm Phase 2
112 | Alloa Town Centrw: Public Realm Phase 3
113 | Alloa Town Centre: Alloa Town Hall Precinct
114 | Lime Tree Walk Phase 2
115 | Shillinhill to Town Hall: Environmental Regeneration
116 | New Alloa Infrastructure
117 | Castlebridge Infrastructure
118 | Pavilions Business Paek Phase 3
119 | Westhaugh Travelling People's site
120 | Air Conditioning System - Class Cuisine, Sauchie
121 | Greefield Heating
122 | Sun Tube, Lime Tree House
123 | Kelliebank Thermal Efficiency Windows
124 | Sale of Properties listed by Gordon (from A to I)
125 | Alloa East Gateway - Clackmannan Road
126 | Muchart Primary Heating Plant - Additional capital grant
127 | Park Primary Heating Plant - Additional capital grant
128 | St Serf's Primary Heating Plant - Additional capital grant
129 | Fibre Optic Link - Additional capital grant
130 | West Haugh Travelling People's site - Additional capital grant
131 | Alloa Centre (Child Care, Day Care move to Alternative Accomodation
132 | Pitch Strategy
133 | Trees Strategy
134 | Extention & Refurbishment of CLICk (Glebe Hall)
135 | School Security