## 2007-08 Exp & Income to 310108
[5 empty] | OK | OK | [7 empty] | Out-turn Out |  | OK | OK | OK | Out-turn Out |  |  | Out-turn Out | OK
17
Housing Capital Programme 2007/08 |  |  | New | Underspent 06/07 budget. Proposed c/f to 07/08 | Approved Budget for 2007/08 | Revised Budget 2007/08 |  | To 31st January 2008 | [6 empty] | % of actual over Out-turn | Out-turn for year as per Mid-Year Report to Council | Out-turn for year (as intimated at HCL meeting on 26/07/07) | Out-turn as Per SC Report (as at 5/9/07) | Out-turn for year (as intimated at HCL meetings) | Variance of Mid Year figures with Budget | Variance of out-turn with Budget | Budget for 2008/09 (including transfers) | Budget for 2009/10 (including transfers) | Project Status as at 5th Sept 2007 | Project Status as intimated at HCL meeting on 20/12/07 | Notes on Other Expenditure | - 0001 Allocation of Receipts | - 0003 Allocation of Borrowing |  | Description
| Project | Ledger | Ledger | 05/06 budget |  |  |  | Contract | Payments to | Prof | Other | Total | Income | Net | [11 empty] | provided by Bill Clark
| Code | Code | Code | possible c/f |  |  |  | Payments | DSO/DLO | Fees | Expend | Expend |  | Expend
[5 empty] | £ | £ |  | £ |  | £ | £ | £ | £ | £ | % | £ | [5 empty] | £ | £ |  |  |  | £ | £
SCOTTISH HOUSING QUALITY STANDARD
TACKLING SERIOUS DISREPAIR
PRIMARY BUILDING ELEMENTS
[24 empty] | Full spend has been committed against 07/08 budget . Work being undertaken at Cobblecrook Gardens, Alva, monitoring of structural issues in Shaftesbury/Hill Street areas of Alloa, and possible further remedial works to Blackburn properties. Asbestos removal works may be required in a number of properties and allowance of £50k for these will be proposed within mid year report | Full spend has been committed against 07/08 budget . Work being undertaken at Cobblecrook Gardens, Alva may be delayed due to owner-occupier participation issues. Housing will continue to seek cooperation and legal advice. Monitoring of structural issues in Shaftesbury/Hill Street areas of Alloa continues. Asbestos removal works may be required in a number of properties. Current survey indicates number of affected properties will be reduced from £50k estimated in the previous report. Hence the reduction in the out-turn from the previous prediction.
Structural Works |  |  |  |  | 200000 | 200000 | [9 empty] | 250000 | 200000 | 250000 | 225000 | 50000 | 25000 | 200000 | 85000
47 Hareburn Rd Sound Insulation |  | 92 02 0140 | [9 empty] | 0 |  | 0
Cavity Wall Insulation - Garden Terrac. |  | 92 02 0141 | [9 empty] | 0 |  | 0
Cavity Wall Insulation - Garden Terrac. |  | 92 02 0141 | [9 empty] | 0 |  | 0
Substructure Works-Upgrade Dorran Houses Dollar | 1640(a) | 92 02 0146 | [9 empty] | 0 |  | 0
Structural Condition Report - Dollar (Dorrans) | 1640(b) | 92 02 0142 | 92000001 | [8 empty] | 0 |  | 0
99/00 Johnston Crescent | [11 empty] | 0 |  | 0
99/00 Asbestos Survey/Rem | [11 empty] | 0 |  | 0
03/04 Dorrans Upgrade, Dollar (new code) | 1640[c] | 92 02 0143 | [9 empty] | 0 |  | 0
Home Safety |  | 92 02 0151 | [9 empty] | 0 |  | 0
Structural Investigation Weir Alva | 1746 | 92020144 | 92000002 | [5 empty] | 690.88 | 721.75 |  | 1412.63 |  | 1412.63 | [15 empty] | Capital Funded by Capital Receipts
Lintel renewal Dollar, etc | 1880 | 92 02 0181 | [9 empty] | 0 |  | 0
Porches Rosebank/Holton | 1708 | 92 02 0812 | [9 empty] | 0 |  | 0
Victim Centered Approach |  | 92 02 0152 | [9 empty] | 0 |  | 0
97/98 Crime Prevention |  | 0156 | [9 empty] | 0 |  | 0
Lintel Renewal (Alva) | 1524 | 0160/0606 | [9 empty] | 0 |  | 0
Stabilisation |  | 0163 | [9 empty] | 0 |  | 0
Henderson Ave. Structural | 1489 | 0164 | [9 empty] | 0 |  | 0
Craigview, Sauchie |  | 0165 | [9 empty] | 0 |  | 0
30 Windsor Street Menstrie | 1489(a) | 0166 | [9 empty] | 0 |  | 0
Garden Wall 46 Earn Court Alloa | 1328 | 92 02 0167 | [9 empty] | 0 |  | 0
Asbestos Survey Renewal |  | 92 02 0168 | [9 empty] | 0 |  | 0
Replacement Screens, Sauchie | 1487 | 92 02 0169 | [9 empty] | 0 |  | 0
Asbestos Works |  | 92020170 | 92000005 |  |  |  |  | 2561 | 5751.34 |  | 17412 | 25724.34 |  | 25724.34 | [11 empty] | £17012 Gordons Environment ; £210 Pyeroy Ltd |  |  |  | Capital Funded by Capital Receipts
01/02 Asbestos Survey | [11 empty] | 0 |  | 0 | [15 empty] | Capital Funded by Capital Receipts
Upgrade 49 Mansfield Avenue |  | 0158 | [9 empty] | 0 |  | 0 | [15 empty] | Capital Funded by Capital Receipts
Demolish 3 + 5 Henderson Avenue |  | 0301 | [9 empty] | 0 |  | 0 | [15 empty] | Capital Funded by Capital Receipts
General - 2006/09 Asbestos testing - Term contract | 2102 | 92020173 | 92020173 |  |  |  |  | 34292 |  | 7151 |  | 41443 |  | 41443 | [15 empty] | Capital Funded by Capital Receipts
Argyle Place | 2072 | 92020470 | 92000006 | [8 empty] | 0 |  | 0 | [15 empty] | Capital Funded by Capital Receipts
Replacement of Retaining Walls - Various Locations | 1961 | 92021961 | 92000007 |  |  |  |  | -239.81 |  |  | 97.13 | -142.68 |  | -142.68 | [11 empty] | £97.13 CRA Ltd |  |  |  | Capital Funded by Capital Receipts
Asbestos Testing - Term Contract 2004/06 | 1978 | 92 02 0172 | [9 empty] | 0 |  | 0 | [15 empty] | Capital Funded by Capital Receipts
Mill St, Alloa | 1579 | 92 02 0800 | [9 empty] | 0 |  | 0 | [15 empty] | Capital Funded by Capital Receipts
Walkway, Primrose Place, Tilly | 1466 | 92 02 0802 | [9 empty] | 0 |  | 0 | [15 empty] | Capital Funded by Capital Receipts
Walkway, High St, Tilly | 1598 | 92 02 0808 | [9 empty] | 0 |  | 0 | [15 empty] | Capital Funded by Capital Receipts
Walkway, High St, Tilly | 1677 | [10 empty] | 0 |  | 0 | [15 empty] | Capital Funded by Capital Receipts
Wier Timber Houses Alva |  | 92 02 0809 | [9 empty] | 0 |  | 0 | [15 empty] | Capital Funded by Capital Receipts
Beam Strengthening Jamieson Gdns | 1799 | 92 02 0811 | [9 empty] | 0 |  | 0 | [15 empty] | Capital Funded by Capital Receipts
Retaining Wall - Deerpark/Beechwood | 1860 | 92 07 1860 | [9 empty] | 0 |  | 0 | [15 empty] | Capital Funded by Capital Receipts
25-31 Moir St Alloa - Replacement Lintels | 2071 | 92021813 | 92000010 | [8 empty] | 0 |  | 0 | [15 empty] | Capital Funded by Capital Receipts
Underpinning at Engelen Drive | 2093 | 92021880 | 92990232 | [6 empty] | 348.91 |  | 348.91 |  | 348.91 | [15 empty] | Capital Funded by Capital Receipts
Lock Ups - Murray Place Dollar (Remove - old) |  | 92021890 | 92021890 | [8 empty] | 0 |  | 0
Rem Works at Clackmannan | 2097 | 92020417 | 92000012 |  |  |  |  | 1601.66 |  |  |  | 1601.66 |  | 1601.66 | [15 empty] | Capital Funded by Capital Receipts
Structural Works at Cobblecrook Gardens | 2203 | 92021897 | 92021897 |  |  |  |  | 3925.78 |  |  |  | 3925.78 |  | 3925.78
Structural Works |  |  |  | 0 | 200000 | 200000 |  | 42140.63 | 6442.22 | 8221.66 | 17509.13 | 122762.96 | -239.81 | 122523.15 | 61.26% | 250000 | 200000 | 250000 | 225000 | 50000 | 25000 | 200000 | 85000 |  |  |  | 0 | 0 | 122523.15
SECONDARY BUILDING ELEMENTS
[24 empty] | Full spend anticipated in eradication of identified damp/rot at a number of locations | No change from previous report. Full spend completed in eradication of identified damp/rot at a number of locations. Costs to be transferred.
Damp/Rot |  |  |  |  | 30000 | 30000 | [9 empty] | 30000 | 30000 | 30000 | 30000 | 0 | 0 | 30000 | 30000
Damp/Rot Area Teams) |  | 92020200 | 92100001 | [7 empty] | 55 | 55 |  | 55 | [11 empty] | £55 Disturbance Allowance |  |  |  | Capital Funded by Capital Receipts
Damp/Rot Sundries |  | 0201 | [9 empty] | 0 |  | 0
99/00 Ashley Terrace Ph 1 | 1528} | 92 02 0210 | [9 empty] | 0 |  | 0
01/02 Ashley Terrace Ph 2 | 1723 | 92 02 0211 | [9 empty] | 0 |  | 0
Damp/Rot |  |  |  | 0 | 30000 | 30000 |  | 0 | 0 | 0 | 55 | 55 | 0 | 55 | 0.1833% | 30000 | 30000 | 30000 | 30000 | 0 | 0 | 30000 | 30000 |  |  |  | 0 | 0 | 55
[24 empty] | Budget fully committed with tender recently accepted with Forster Roofing. This involves work at a variety of locations in Dollar, Alva and Alloa. Site start due in October. | Budget fully committed with tender accepted with Forster Roofing. This involves work at a variety of locations in Dollar, Alva and Alloa. Site start started in October. The increase in the expenditure above the budget is for rerendering at Newbridge which is now proceeding at an estimated cost of £166k. The reported outturn has reduced by £155k from previous report, due to a contractor in receivership. This work will now be completed in 08/09..
Roofs / Rainwater / External Walls |  |  |  | 26000 | 400000 | 426000 | [9 empty] | 426000 | 414000 | 426000 | 568000 | 0 | 144000 | 400000 | 300000
97/98 Cladding Ash Grove E/E | 1442 | 92020455 | 92990129 | [8 empty] | 0 |  | 0
98/99 Pitched Roofs | 1490 | 92020426 | 92990112 | [8 empty] | 0 |  | 0
98/99 Flat Roofs | 1473 | 92020410 | 92990106 | [8 empty] | 0 |  | 0
Flat Roofs Remedial Works |  | 92020411 | 92990107 | [8 empty] | 0 |  | 0
99/00 Cambus | 1320 | 92020453/0465 | 92990127 | [8 empty] | 0 |  | 0
Remedial Render High St Tilly * | 1469 | 92020457 | 92990131 | [8 empty] | 0 |  | 0
00/01 Cruden Roofs | 1523 | 92020415 | 92990109 | [8 empty] | 0 |  | 0
99/00 Cruden Roofs | 1622(a)/1632 | 92020416 | [9 empty] | 0 |  | 0
01/02 Cruden Roofs | 1777 | 92020412 | [9 empty] | 0 |  | 0
99/00 Pitched Roofs Phase 1 | 1526(a) | 92020427 | [9 empty] | 0 |  | 0
99/00 Pitched Roofs Phase 2 | 1526(b) | 92020428 | [9 empty] | 0 |  | 0
99/00 Pitched Roofs Phase 3 | 1526(c) | 92020429 | [9 empty] | 0 |  | 0
01-02 Pitched Roofs Phase 1 | 1757 (A) | 92020434 | [9 empty] | 0 |  | 0
Chappelle Crescent | 1886 (A) | 92020435 | [9 empty] | 0 |  | 0
03/04 Chapelle Cres Roofing | 1801 | 92020437 | [9 empty] | 0 |  | 0
99/00 Maple Court | 1436 | 92020433/0904 | [9 empty] | 0 |  | 0
[12 empty] | 0 |  | 0
Insulation of No Fines Mar Estate | 1686 | 92020459 | [9 empty] | 0 |  | 0
100 Gean Rd Re-Inst. Roof | 1644 | 92020430 | [9 empty] | 0 |  | 0
01/02 Maple Court Alloa (re-render) | 1751 | 92020810 | [9 empty] | 0 |  | 0
00/01 Roof Recladding | 1693 | 92020431 | [9 empty] | 0 |  | 0
2002/04 Felt Roofing Term Contract | 1809 | 92020436 | [9 empty] | 0 |  | 0
2003/04 Pitched Roofs Phase 1 Coalsn't'n & Clack | 1932 | 92020438 | [9 empty] | 0 |  | 0 | [15 empty] | Capital Funded by Capital Receipts
2004/05 Pitched Roofs Phase 1: Sauchie | 1992(a) | 92020439 | [9 empty] | 0 |  | 0
2004/05 Re-roofing Phase 2 Sauchie | 1992(b) | 92020440 | [9 empty] | 0 |  | 0 | [15 empty] | Capital Funded by Capital Receipts
2005/06 Re-roofing Tullibody | 2082 | 92020441 | [9 empty] | 0 |  | 0 | [15 empty] | Capital Funded by Capital Receipts
Re-rendering at Clackmannan & Cambus | 1925 | 92020813 | [9 empty] | 0 |  | 0
2005/06 Re-Roofing Main Street Sauchie |  | 92020442 | [9 empty] | 0 |  | 0
14-28 Scotland Place, Tilly - Removal of Findlock gutters | 2104 | 92020443 | [9 empty] | 0 |  | 0 | [15 empty] | Capital Funded by Capital Receipts
Term Contract - 2006/09 flat roof repairs | 2110 | 92020444 | [9 empty] | 0 |  | 0 | [13 empty] | 0 |  | Capital Funded by Capital Receipts
Alloa/Tullibody 94/95 Pitched Roof A/1238 | A/1238 | 92020463 | [9 empty] | 0 |  | 0 | [13 empty] | 0 |  | Capital Funded by Capital Receipts
02/03 Re-roofing | 1817 | 92021817 | [9 empty] | 0 |  | 0 | [13 empty] | 0 |  | Capital Funded by Capital Receipts
03/04 Re-roofing | 1817(a) | 92021809 | [9 empty] | 0 |  | 0 | [13 empty] | 0 |  | Capital Funded by Capital Receipts
New Roof-Window 22 Stirling Street Tillicoultry | 2114 | 92021850 | [9 empty] | 0 |  | 0 | [13 empty] | 0 |  | Capital Funded by Capital Receipts
2006/07 Pitched Roof Replacements Phase 1 | 2129(a) | 92020445 | [7 empty] | 534.74 |  | 534.74 |  | 534.74 | [15 empty] | Capital Funded by Capital Receipts
Budget transferred to Central Heating for Backwood & Lochbrae |  |  |  |  | -2000 | -2000
2006/07 Pitched Roof Replacements Fascia Repairs | 2129(b) | 92020446 | 92020446 | [6 empty] | 60.66 |  | 60.66 |  | 60.66 | [15 empty] | Capital Funded by Capital Receipts
2006/07 Various Pitched Roofs | 2129 | 92020447 | 92020447 | [8 empty] | 0 |  | 0 | [15 empty] | Capital Funded by Capital Receipts
All Areas - Inspection of flat roofs | 2141 | 92020450 | 92990124 | [7 empty] | 1247 | 1247 |  | 1247 | [11 empty] | £1247 Architects fees
2006/07 Flat Roof Upgrading | 2141(a) | 92020448 | 92020448 |  |  |  |  | 99058.5 | 536.38 | 1688.19 | 2048.5 | 103331.57 |  | 103331.57 | [11 empty] | £2048.50 Architects Fees |  |  |  | Capital Funded by Capital Receipts
2006/07 Pitched Roofs : Chimney Upgrades | 2129 (c) | 92020449 | 92020449 | [5 empty] | 962 | 1727.43 | 962 | 3651.43 |  | 3651.43 | [11 empty] | £962 Architects fees
Alloa & Alva 2007/08 Pitched Roof Replacement Phase 1 | 2181(a) | 92020474 | [8 empty] | 3381 | 3381 |  | 3381 | [11 empty] | £3381 Architects Fees
Braehead, Alva - Roof Repairs | 2067 | 92021812 | [9 empty] | 0 |  | 0 | [15 empty] | Capital Funded by Capital Receipts
Blackburn Houses |  | 92021855 | [9 empty] | 0 |  | 0
Non Traditional Inspection | 2122 | 92020668 | [5 empty] | 40260.49 |  |  |  | 40260.49 |  | 40260.49 | [15 empty] | Capital Funded by Capital Receipts
2004/06 Flat Roof Improvements | 1968 | 92021811 | [9 empty] | 0 |  | 0
Structural Work at Fairfield |  | 92021896 | [8 empty] | 2100.05 | 2100.05 |  | 2100.05 | [11 empty] | £1548.65 Disturbance Allowance ; £551.4 Removal Charges |  |  |  | Capital Funded by Capital Receipts
Roofs / Rainwater / External Walls |  |  |  | 26000 | 398000 | 424000 |  | 139318.99 | 1498.38 | 4011.02 | 9738.55 | 262291.2 | 0 | 262291.2 | 63.36% | 426000 | 414000 | 426000 | 413000 | 0 | -11000 | 555000 | 300000 |  |  |  | 0 | 0 | 262291.2
[24 empty] | 2007/08 should mark completion of the programme with anticipated spend of £327k | No change from previous position . 2007/08 should mark completion of the programme with anticipated spend of £314k
External Door, etc |  |  |  | 27000 | 300000 | 327000 | [9 empty] | 327000 | 284000 | 327000 | 314000 | 0 | 3000 | 0 | 0
98-99 Home Security Doors Phase 1 | 1491(a) | 0190 | [9 empty] | 0 |  | 0
98-99 Home Security Doors Phase 2 | 1491(b) | 0191 | [9 empty] | 0 |  | 0
98-99 Home Security Doors Phase 3 | 1491(c) | 0192 | [9 empty] | 0 |  | 0
98-99 Home Security Doors Phase 4 | 1491(d) | 0193 | [9 empty] | 0 |  | 0
99-00 Home Security Doors Phase 1 | 1534(a) | 92 02 0194 | [9 empty] | 0 |  | 0
99-00 Home Security Doors Phase 2 | 1534(b) | 0195 | [9 empty] | 0 |  | 0
99-00 Home Security Doors Phase 3 | 1534(c) | 0196 | [9 empty] | 0 |  | 0
99-00 Home Security Doors Phase 4 | 1534(d) | 92 02 0197 | [9 empty] | 0 |  | 0
99-00 Home Security Doors Phase 5 | 1534(e) | 92 02 0198 | [9 empty] | 0 |  | 0
99-00 Home Security Doors Phase 6 | 1534(f) | 92 02 0199 | [9 empty] | 0 |  | 0
99-00 Home Security Doors Phase 7 | 1534(g) | 92 02 0220 | [9 empty] | 0 |  | 0
99-00 Home Security Doors Phase 8 | 1534(h) | 92 02 0221 | [9 empty] | 0 |  | 0
Doors General | 1761 | 92 02 0223 | [9 empty] | 0 |  | 0
02-03 Doors general | 1820 | 92 02 1820 | [9 empty] | 0 |  | 0
02-03 Doors Ph 1 | 1820A | 92 02 1821 | [9 empty] | 0 |  | 0
01-02 Home Security Doors Phase 1 | 1759 (A/B) | 92 02 0224 | [9 empty] | 0 |  | 0
01-02 Home Security Doors Phase 2 | 1759 (B) | 0225 | [9 empty] | 0 |  | 0
01-02 Home Security Doors Phase 3 | 1759 (C/D) | 92 02 0226 | [9 empty] | 0 |  | 0 | [15 empty] | Capital Funded by Capital Receipts
01-02 Home Security Doors Phase 4 | 1759 (D) | 92 02 0227 | [9 empty] | 0 |  | 0 | [15 empty] | Capital Funded by Capital Receipts
01-02 Home Security Doors General | 1759 | 92 02 0228 | [9 empty] | 0 |  | 0 | [15 empty] | Capital Funded by Capital Receipts
Elmgrove | [11 empty] | 0 |  | 0 | [15 empty] | Capital Funded by Capital Receipts
[12 empty] | 0 |  | 0 | [15 empty] | Capital Funded by Capital Receipts
Screens & Windows (Bill Wardrop) |  | 92 02 0229 | [9 empty] | 0 |  | 0 | [15 empty] | Capital Funded by Capital Receipts
00-01 Home Security External Lighting | 1616(e) | 92 02 0240 | [9 empty] | 0 |  | 0 | [15 empty] | Capital Funded by Capital Receipts
03-04 Door Replacement Alloa & Clack | 1873 | 92 02 1873 | [9 empty] | 0 |  | 0 | [15 empty] | Capital Funded by Capital Receipts
03-04 Door Replacements Phase 1 (Hadden) | 1873(a) | 92 02 1874 | [9 empty] | 0 |  | 0 | [15 empty] | Capital Funded by Capital Receipts
Budget transferred to Central Heating for Backwood & Lochbrae |  |  |  |  | -16000 | -16000
03-04 Door Replacements Phase 2 | 1873(b) | 92021876 | 92120005 |  |  |  |  | 13579.02 |  |  |  | 13579.02 |  | 13579.02 | [15 empty] | Capital Funded by Capital Receipts
03-04 Door Replacement Alva | 1873(c) | 92021875 | [9 empty] | 0 |  | 0 | [15 empty] | Capital Funded by Capital Receipts
2004/05 Door Replacement - Phase 1 - Alva | 1950(a) | 92021828 | [9 empty] | 0 |  | 0 | [15 empty] | Capital Funded by Capital Receipts
2004/05 Fear of Crime (Door Replacement) (start 2004/05) | 1950(b) | 92021825 | 92120008 |  |  |  |  | 32098.64 |  |  |  | 32098.64 |  | 32098.64 | [15 empty] | Capital Funded by Capital Receipts
2005/06 Door Improvements - Various | 2011 | 92021829 | [9 empty] | 0 |  | 0 | [15 empty] | Capital Funded by Capital Receipts
2005/06 Door Improvements - Phase 1 - Alloa | 2011(a) | 92021833 | 92120010 |  |  |  |  | 1045 |  |  |  | 1045 |  | 1045 | [15 empty] | Capital Funded by Capital Receipts
2005/06 Door Improvements - Phase 2 - Tillicoultry | 2011(b) | 92021834 | 92120011 | [8 empty] | 0 |  | 0 | [15 empty] | Capital Funded by Loans
2005/06 Door Improvements - Phase 3 - Tullibody | 2011(c) | 92021835 | [9 empty] | 0 |  | 0 | [15 empty] | Capital Funded by Capital Receipts
Various Home Security - External lights phase 3 | 2011 (f) | 92021836 | [5 empty] | 571.5 |  |  |  | 571.5 |  | 571.5 | [15 empty] | Capital Funded by Capital Receipts
Various Home Security - Doors Phase 4 | 2011 (g) | 92021837 | [9 empty] | 0 |  | 0 | [15 empty] | Capital Funded by Loans
Crime Prevention |  | 92020156 | 92990038 | [6 empty] | 210 |  | 210 |  | 210
2005/06 Home Security - External Lights | 2011(d) | 92021832 | [9 empty] | 0 |  | 0 | [15 empty] | Capital Funded by Capital Receipts
General - 2006/07 Home Security Door Replacements | 2090 | 92021877 | [9 empty] | 0 |  | 0 | [15 empty] | Capital Funded by Loans
Phase 1 Alloa - 2006/07 Home Security door replacements | 2090(A) | 92021878 | [5 empty] | 530.55 |  |  |  | 530.55 |  | 530.55 | [15 empty] | Capital Funded by Capital Receipts
Dollar & Tilly - 2006/07 Door Replacements phase 2 | 2090(B) | 92021879 | [5 empty] | 136406.17 |  |  |  | 136406.17 |  | 136406.17 | [15 empty] | Capital Funded by Capital Receipts
[12 empty] | 0 |  | 0
External Door, etc |  |  |  | 27000 | 284000 | 311000 |  | 184230.88 | 0 | 210 | 0 | 228819.64 | 0 | 228819.64 | 80.57% | 327000 | 284000 | 327000 | 314000 | 0 | 3000 | 0 | 0 |  |  |  | 0 | 0 | 228819.64
ENERGY EFFICIENCY
[24 empty] | Full budget spend anticipated. Tender accepted for replacements systems at Newmills Tullibody, Menstrie and Maple Court Alloa Site start date likely to be late October. New systems also being installed at Backwood Court & Lochbrae Programme of CO detector replacement underway, plus ventilation upgrading works to be undertaken to meet new gas regulations. New heating term contract also in place. | Full budget spend anticipated. Tender accepted for replacements systems at Newmills Tullibody, Menstrie and Maple Court Alloa Site work started. Programme of CO detector replacement underway, plus ventilation upgrading works to be undertaken to meet new gas regulations. New heating term contract also in place.
Full/Efficient Central Heating |  |  |  | 40000 | 1000000 | 1040000 | [9 empty] | 1040000 | 1292000 | 1040000 | 890000 | 0 | 0 | 1140000 | 560000
99/00 Heating | 1533(b) | 0617 | [9 empty] | 0 |  | 0
99/00 Heating Phase 2 | 1533(c) | 0619 | [9 empty] | 0 |  | 0
99/00 Heating Phase 1 | 1533(a) | 92 02 0620 | [9 empty] | 0 |  | 0
00/01 Heating Phase 2 | 1617(b) | 92 02 0626 | [9 empty] | 0 |  | 0
00/01 Heating Phase 3 | 1617[c] | 92 02 0629 | [9 empty] | 0 |  | 0
00/01 term contract | 1652 | [10 empty] | 0 |  | 0
Gas Supply |  | 92 02 0627 | [9 empty] | 0 |  | 0
01/02 Term Contract | 1758 | 92 02 0631 | [9 empty] | 0 |  | 0
Caroline Cres - Alva - Heating Renewal | 1740 | 92 02 0632 | [9 empty] | 0 |  | 0
00/01 term contract | 1652 | 92 02 0621/0625 | [9 empty] | 0 |  | 0
00/01 Fuel Changeover | [11 empty] | 0 |  | 0
Fuel Change - Pers Pref |  | 0625 | [9 empty] | 0 |  | 0
00/01 Electric/Gas Conversions |  | 0630 | [9 empty] | 0 |  | 0
Term Ctrct Solid Fuel C/H 02/03 | 1641 | 92 02 1641 | [9 empty] | 0 |  | 0
Term Contract | 1816/1 | 92 02 0633 | [9 empty] | 0 |  | 0
Term Heating Contract (new phase) | 1816/7 | 92 02 0633 | [9 empty] | 0 |  | 0
Heating Safety |  | 92 02 0634 | [9 empty] | 0 |  | 0
2003-04 Heating Contract | 1882 | 92 02 0635 | [9 empty] | 0 |  | 0
Heating Enhancements -Warm Deal Initiative |  | 92 02 0636 | [9 empty] | 0 |  | 0
Gas Link - Mar Policies |  | 92 02 0638 | [9 empty] | 0 |  | 0
Gas Safety Incident | 1979 | 92 02 0639 | [9 empty] | 0 |  | 0
Budget for Backwood & Lochbrae |  |  |  |  | -150000 | -150000
2004/05 Heating Replacements - Mar Estate (Remaining) | 1976(a) | 92 02 0641 | [9 empty] | 0 |  | 0 | [15 empty] | Capital Funded by Capital Receipts
2004/05 Heating Replacements - Phase 2 | 1976(b) | 92 02 0644 | [9 empty] | 0 |  | 0
2004/05 Electric Central Heating Installation - Various | 1976(c) | 92 02 0645 | [9 empty] | 0 |  | 0
2004/05 Central Heating Replacements - Term Contract | 1977 | 92 02 0642 | [9 empty] | 0 |  | 0
2004/05 Central Heating Replacements - Warm Deal Initiative | 1977 | 92 02 0643 | [9 empty] | 0 |  | 0
Gas Link Monies - Fuel Switch Grant |  | 92 02 0646 | [9 empty] | 0 |  | 0
Heating Appliances |  | 92 02 0640 | [9 empty] | 0 |  | 0
2005/06 Term Contract - Heating Repairs | 2041 | 92 02 1647 | [9 empty] | 0 |  | 0
2005/06 Heating Replacements - Phase 1 | 2074(a) | 92 02 0648 | 92200011 |  |  |  |  | 10458.82 |  |  |  | 10458.82 |  | 10458.82 | [15 empty] | Capital Funded by Capital Receipts
2005/06 Heating Replacements - Phase 2 | 2074(b) | 92 02 0649 | [9 empty] | 0 |  | 0 | [15 empty] | Capital Funded by Capital Receipts
2005/06 Heating Replacements - Phase 3 : Various | 2074(c) | 92 02 0656 | [9 empty] | 0 |  | 0 | [15 empty] | Capital Funded by Capital Receipts
2005/06 Electric Central Heating - Phase 2 | 2074(d) | 92 02 0657 | 92200014 |  |  |  |  | 1370.79 |  |  |  | 1370.79 |  | 1370.79 | [15 empty] | Capital Funded by Capital Receipts
Various Locations - 2007-2010 Central Heating Term Contract | 2179 | 92 02 0658 | [8 empty] | 1050 | 1050 |  | 1050 | [11 empty] | £1050 Architects Fees
Various 2005/07 Central Heating term Contract | 2035 | 92 02 0660 | [7 empty] | 726 |  | 726 |  | 726 | [15 empty] | Capital Funded by Loans
General - 2005/06 Heating Replacements | 2074 | 92 02 0661 | [9 empty] | 0 |  | 0 | [15 empty] | Capital Funded by Capital Receipts
2006/07 Central Heating Contract Phase 1 | 2115(a) | 92 02 0662 | [5 empty] | 80069.9 | 162.87 |  | 1127 | 81359.77 |  | 81359.77 | [11 empty] | £1127 Disturbance Allowance |  |  |  | Capital Funded by Loans
2006/07 Central Heating Chapelle Crescent | 2115(b) | 92 02 0663 | [8 empty] | 851 | 851 |  | 851 | [11 empty] | £851 Disturbance Allowance |  |  |  | Capital Funded by Capital Receipts
03-04 Central Heating Mar Policies moved from Rewiring | 1882(a) | 92 02 0637 | [9 empty] | 0 |  | 0
| 2173 | [7 empty] | 15345 |  |  | 15345 |  | 15345
[12 empty] | 0 |  | 0
Full/Efficient Central Heating |  |  |  | 40000 | 850000 | 890000 |  | 91899.51 | 15507.87 | 726 | 3028 | 388406.38 | -57.5 | 388348.88 | 30.06% | 1040000 | 1292000 | 1040000 | 890000 | 0 | 0 | 1140000 | 560000 |  |  |  | 0 | 0 | 388348.88
[24 empty] | Work complete at Achray, Katrine & Maree Courts. Further investigative work at Weir Multi-Cons in Alva indicates that extent of required work is less than originally anticipated. Property Services developing proposals based on latest findings and spend should be accommodated within the projected 07/08 out-turn reported and the 08/09 capital budget. | Work complete at Achray, Katrine & Maree Courts. Spend to date has been limited to payment of retentions. Further investigative work at Weir Multi-Cons in Alva indicates that extent of required work is less than originally anticipated. Property Services are in discussion with adjoining private owners with a view to plan works to be carried out to council properties in 08/09. In the mean time, it is proposed that the underspend of £567k on this budget is utilised in the kitchen & roof programmes.
Thermal Insulation |  |  |  | -74000 | 800000 | 726000 | [9 empty] | 142000 | 726000 | 142000 | 159000 | -584000 | -567000 | 575000 | 125000
Achray Court, Alloa Insulated Render to no fines Hse Phase 1 | 2075(A) | 92 02 0472 | 92210002 |  |  |  |  | 7482.96 |  |  |  | 7482.96 |  | 7482.96 | [15 empty] | Capital Funded by Capital Receipts
2006/07 Katrine Court Insulation | 2117(a) | 92 02 0666 | [7 empty] | 1122.09 |  | 1122.09 |  | 1122.09 | [15 empty] | Capital Funded by Capital Receipts
2006/07 Maree Court Render | 2117(b) | 92 02 0667 | [7 empty] | 1140.23 |  | 1140.23 |  | 1140.23 | [15 empty] | Capital Funded by Capital Receipts
06/07 Warmdeal : Attic Insulation | 2163 | 92 02 0671 | [5 empty] | 76851.49 |  | 2293 |  | 79144.49 |  | 79144.49 | [11 empty] | £2293 Architects Fees |  |  |  | Capital Funded by Capital Receipts
General - 2006/07 Insulated Render Systems | 2117 | 92 02 0672 | [5 empty] | 60 |  |  | 507 | 567 |  | 567 | [11 empty] | £507 Architects Fees
No fines Houses Insulated Rendering | 2075 | 92 02 0471 | 92210003 | [8 empty] | 0 |  | 0 | [15 empty] | Capital Funded by Capital Receipts
[12 empty] | 0 |  | 0
Thermal Insulation |  |  |  | -74000 | 800000 | 726000 |  | 84394.45 | 0 | 4555.32 | 507 | 125280.33 | 0 | 125280.83 | 17.26% | 142000 | 726000 | 142000 | 159000 | -584000 | -567000 | 575000 | 125000 |  |  |  | 0 | 0 | 125280.83
MODERN FACILITIES & SERVICES
[24 empty] | All phases of 07/08 programme underway, with contracts in place committing full spend. Actual out-turn will be dependent on contractor performance on site. Some early problems in Rok contract being addressed. Pyramid and Sidey contracts progressing satisfactorily. Full explanation will be provided by Housing for the variance of £526k in their Mid Year report. | All phases of 07/08 programme underway, with contracts in place committing full spend. Actual out-turn will be dependent on contractor performance on site. A number of factors has resulted in the out-turn being reduced from that reported previously - a combination of good value per kitchen, reduction in the number of properties and some poor contractor performance, which is being dealt with by our Architects. The reduction in spend of £270k from previous report will be carried forward to 08/09.
Kitchen Renewal |  |  |  | 274000 | 4000000 | 4274000 | [9 empty] | 4800000 | 4900000 | 4800000 | 4275000 | 526000 | 104000 | 3860000 | 3200000
Budget transferred To Central Heating for Backwood & Lochbrae |  |  |  |  | -103000 | -103000
New Spend | 1760 | 92 02 0230 | [9 empty] | 0 |  | 0
02/03 Kitchens Ph 1 | 1819 | 92 02 1819 | [9 empty] | 0 |  | 0
02/03 Kitchens Ph 2 | 1819(a) | 92 02 1822 | [9 empty] | 0 |  | 0
03/04 Kitchens Ph 1 Tullibody | 1895(a) | 92 02 1823 | 92300001 |  |  |  |  | 80.28 |  |  |  | 80.28 |  | 80.28
2004/05 Kitchen replacements - various | 1949 | 92 02 1824 | [9 empty] | 0 |  | 0
2004/05 Kitchen replacements - Tullibody | 1949(a) | 92 02 1826 | [9 empty] | 0 |  | 0 | [15 empty] | Capital Funded by Capital Receipts
2004/05 Kitchen replacements Phase 2 - Sauchie | 1949(b) | 92 02 1827 | [9 empty] | 0 |  | 0 | [15 empty] | Capital Funded by Capital Receipts
2004/05 Kitchen replacement Phase 3 | 1949(c) | 92 02 1830 | 92300005 |  |  |  |  | 106.01 |  |  |  | 106.01 |  | 106.01 | [15 empty] | Capital Funded by Capital Receipts
2004/05 Kitchen Replacements - Term Contract | 2012 | 92 02 1843 | 92300006 |  |  |  |  | 1871 |  |  |  | 1871 |  | 1871 | [15 empty] | Capital Funded by Capital Receipts
2005/06 Kitchen Replacements - various | 2006 | 92 02 1840 | [9 empty] | 0 |  | 0 | [15 empty] | Capital Funded by Capital Receipts
2005/06 Kitchen Replacements - Phase 1 Sauchie | 2006(a) | 92 02 1841 | 92300008 |  |  |  |  | 10939.43 |  |  |  | 10939.43 |  | 10939.43 | [15 empty] | Capital Funded by Capital Receipts/Loans
2005/06 Kitchen Replacements - Phase 2 Tillicoultry | 2006(b) | 92 02 1842 | 92300009 |  |  |  |  | 30777.03 |  | 1744.16 |  | 32521.19 |  | 32521.19 | [15 empty] | Capital Funded by Capital Receipts
2005/06 Kitchen Replacements - Phase 3 Alloa | 2006(c) | 92 02 1845 | 92300010 |  |  |  |  | 27723.79 |  | 837.3 | 182 | 28743.09 |  | 28743.09 | [11 empty] | £182 Disturbance Allowance |  |  |  | Capital Funded by Capital Receipts
General - 2006/07 Kitchen replacements | 2100(a) | 92 02 1846 | [5 empty] | 211656.65 | 134.8 | 571.37 | 6990.1 | 219352.92 |  | 219352.92 | [11 empty] | £6990.10 Disturbance Allowance |  |  |  | Capital Funded by Loans
Phase 2 - 2006/07 Kitchen Replacements | 2100(b) | 92 02 1847 | [5 empty] | 334055 |  | 44962.5 | 12469.87 | 391487.37 |  | 391487.37 | [11 empty] | £12562.87 Disturbance Allowance |  |  |  | Capital Funded by Loans
Phase 3 - 2006/07 Kitchen Replacements | 2100 (c) | 92 02 1848 | [5 empty] | 62351.37 |  |  | 744 | 63095.37 |  | 63095.37 | [11 empty] | £744 Disturbance Allowance |  |  |  | Capital Funded by Loans
Phase 4 - 2006/07 Kitchen Replacements | 2100(d) | 92 02 1849 | [5 empty] | 909723.69 |  | 4712.5 | 29811.07 | 944247.26 |  | 944247.26 | [11 empty] | £22261.07 Disturbance Allowance : £1081 Woodborer Eradication : £2470 SP Distribution |  |  |  | Capital Funded by Loans
Various - 2007/08 Kitchen Replacements : General | 2147 | 92 02 1851 | [8 empty] | 796.5 | 796.5 |  | 796.5 | [11 empty] | £796.50 Architects Fees
Phase 1 - 2007/08 Kitchen Replacements | 2147(a) | 92 02 1852 | [5 empty] | 138486.24 | 888 | 9997.92 | 4870.5 | 154242.66 |  | 154242.66 | [11 empty] | £1814.50 Disturbance Payments ; £888 Architects Fees
Alloa - 2007/08 Kitchen Replacements, Phase 2 | 2147(b) | 92 02 1853 | [6 empty] | 666 | 8174.39 | 4679.5 | 13519.89 |  | 13519.89 | [11 empty] | £666 Architects Fees
Capital Enhancements |  | 92 07 0300 | 92300011 | [5 empty] | 3594.56 |  |  | 3594.56 |  | 3594.56
Kitchen Renewal |  |  |  | 274000 | 3897000 | 4171000 |  | 1727770.49 | 5283.36 | 71000.14 | 60543.54 | 3258546.11 | 0 | 3258546.11 | 66.5% | 4800000 | 4900000 | 4800000 | 4005000 | 526000 | -166000 | 4130000 | 3200000 |  |  |  | 0 | 0 | 3258546.11
[24 empty] | 2007/08 contracts in place with Pyramid and Easyheat. Fitting underway in both contracts. It will be proposed to Council that the budget underspend should be transferred to other projects | 2007/08 represents the first full year of the bathroom replacement programme. Two contracts have been undertaken this year. Housing and Architectural Services are closely monitoring the performance of one of the contractors due to initial contractor performance. Performance by the second contractor is progressing well and has enabled more properties to be added to the contract.However, the predicted outturn for the year has reduced by £162k from previous report - this spend will be carried forward to 08/09.
Bathrooms |  |  |  | 78000 | 1300000 | 1378000 | [5 empty] | 0 |  | 0 |  | 1359000 | 1309000 | 1359000 | 1352000 | -19000 | 43000 | 1000000 | 800000
Budget transferred To Central Heating for Backwood & Lochbrae |  |  |  |  | -69000 | -69000
Bathroom Replacements Various Locations | 2180 | 92 02 1650 | [5 empty] | 213347.68 |  | 10347.6 |  | 223695.28 |  | 223695.28 | [15 empty] | Capital Funded by Capital Receipts
2006/07 Bathroom Cambus/Alva | 2128 | 92 02 1661 | [5 empty] | 16675.93 |  | 1578.6 | 2723 | 20977.53 |  | 20977.53 | [11 empty] | £2723 Disturbance Allowance |  |  |  | Capital Funded by Loans
Sauchie & Tilly - 2005/06 Bathroom Replacement | 2076 | 92 02 1660 | [9 empty] | 0 |  | 0 | [15 empty] | Capital Funded by Capital Receipts
Bathrooms |  |  |  | 78000 | 1231000 | 1309000 | 0 | 230023.61 | 0 | 11926.2 | 2723 | 696108.58 | 0 | 696108.58 | 53.18% | 1359000 | 1309000 | 1359000 | 1190000 | -19000 | -119000 | 1162000 | 800000 |  |  |  | 0 | 0 | 696108.58
[5 empty] | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0
HEALTHY, SAFE & SECURE
Internal Lead Pipework |  | 92 02 |  |  | 0 | 0 | [20 empty] | 0 | 0
99/00 Lead Pipe Renewal | 1554 | 92 02 0804 | [9 empty] | 0 |  | 0
Lead Pipe Renewal Sundries |  | 92 02 0805 | [9 empty] | 0 |  | 0 |  | 0
[12 empty] | 0 |  | 0
Internal Lead Pipework |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0
[24 empty] | Testing contract ongoing, wiring contract commenced in Sauchie. Out-turn may be affected by access issues. Investment Programmes team visiting tenants to encourage access. c£100k of projected overspend is as a result of additional work being carried out to void properties which is necessary to meet new regulatory standards. The total overspend now projected is £148k, and the extra £48k relates to the Service finally getting access to some properties where tenants had previously not given access. (The access problem has been reported before ). | In the past, tendering and access problems have hindered progress. However, despite continuing access problems, improved programming this year indicates that the programme is progressing satisfactorily. Investment Programmes team have been visiting tenants to encourage access. c£100k of projected overspend is as a result of additional work being carried out to void properties which is necessary to meet new regulatory standards. The total overspend now projected is £148k, and the extra £40k relates to the Service finally getting access to some properties where tenants had previously not given access.
Safe Electrical Systems |  |  |  | 54000 | 400000 | 454000 | [9 empty] | 602000 | 438000 | 602000 | 575000 | 148000 | 140000 | 465000 | 300000
97/98 Phase 1 (Hart) | 1372(a) | 0307 | [9 empty] | 0 |  | 0
98/99 Phase 1 (Sauchie/Tillicoultry) | 1465(a) | 92 02 0311 | [9 empty] | 0 |  | 0
Electrical Earth Testing * | 1507 | 0312 | [9 empty] | 0 |  | 0
98/99 Phase 2 * | 1465(b) | 0313 | [9 empty] | 0 |  | 0
99/00 Electrical Earth Testing | 1573 | 0314 | [9 empty] | 0 |  | 0
99/00 Rewiring Phase 1 | 1574(a) | 92 02 0316 | [9 empty] | 0 |  | 0
99/00 Rewiring Phase 2 | 1574(b) | 92 02 0317 | [9 empty] | 0 |  | 0
00-01 Electrical Earth Testing | 1642 | 92 02 0318 | [9 empty] | 0 |  | 0
00-01 Electrical Rewiring | 1694 | 92 02 0319 | [9 empty] | 0 |  | 0
00-01 Electrical Rewiring Phase 1 | 1694(a) | 92 02 0320 | [9 empty] | 0 |  | 0
00-01 Electrical Rewiring Phase 2 | 1694(b) | 92 02 0321 | [9 empty] | 0 |  | 0
00-01 Electrical Rewiring Sundries |  | 0329 | [9 empty] | 0 |  | 0
98/99 Close Lighting |  | 0950 | [9 empty] | 0 |  | 0
01-02 Electrical inspections | 1756 | 92 02 0330 | [9 empty] | 0 |  | 0
01-02 Rewire | 1781(a) | 92 02 0323 | [9 empty] | 0 |  | 0 | [15 empty] | Capital Funded by Capital Receipts
02-03 Rewiring | 1818 | 92 02 1818 | [9 empty] | 0 |  | 0
02-03 Electrical Installations | 1838 | 92 02 1838 | [9 empty] | 0 |  | 0
03-04 Electrical Inspection | 1936 (?) | 92 02 1863 | [9 empty] | 0 |  | 0 | [15 empty] | Capital Funded by Capital Receipts
03-04 Electrical Inspection: Various | 1863 | 92 02 1864 | [9 empty] | 0 |  | 0 | [15 empty] | Capital Funded by Capital Receipts
2004/05 Electrical Inspections: Alloa | 1938 | 92 02 1866 | [9 empty] | 0 |  | 0 | [15 empty] | Capital Funded by Capital Receipts
Budget transferred To Central Heating for Backwood & Lochbrae |  |  |  |  | -19000 | -19000
04-05 Electrical Rewiring Various | 2017(a) | 92 02 1865 | 92410003 | [8 empty] | 0 |  | 0 | [15 empty] | Capital Funded by Capital Receipts
05-06 Electrical Inspections - Various | 2055 | 92 02 1867 | [9 empty] | 0 |  | 0 | [15 empty] | Capital Funded by Capital Receipts
All Areas - 2006/07 Electrical Testing - General | 2143 | 92 02 1870 | [8 empty] | 687 | 687 |  | 687 | [11 empty] | £687 Architects Fees
Phase 1 : 2005/06 Electrical Rewiring | 2083(a) | 92 02 0332 | 92410005 | [7 empty] | 150 | 150 |  | 150 | [11 empty] | £150 Disturbance Allowance |  |  |  | Capital Funded by Capital Receipts
Phase 1 : 2006/07 Electrical Rewiring | 2116(a) | 92 02 0665 | [5 empty] | 298259.15 | 34.55 |  | 15506 | 313799.7 |  | 313799.7 | [11 empty] | £15265 Disturbance Allowance |  |  |  | Capital Funded by Capital Receipts
2006/07 Electrical Testing, Phase One | 2143(a) | 92 02 1868 | [8 empty] | 1235 | 1235 |  | 1235 | [11 empty] | £1235 Architects fees |  |  |  | Capital Funded by Capital Receipts
2006/07 Periodic Inspections Phase Two | 2143(b) | 92 02 1869 | [5 empty] | 8970.8 |  |  | 842 | 9812.8 |  | 9812.8 | [11 empty] | £842 Architects Fees |  |  |  | Capital Funded by Capital Receipts
2006/2007 General Rewiring | 2116 | 92 02 0664 | [9 empty] | 0 |  | 0 | [15 empty] | Capital Funded by Capital Receipts
Electrical Enhancement Works Void Properties 2006/07 |  | 92 02 0820 | [6 empty] | 65638.29 |  |  | 65638.29 |  | 65638.29 | [15 empty] | Capital Funded by Capital Receipts
Electrical rewiring programme at various locations | 2083 | 92 02 0331 | 92410006 |  |  |  |  | 7460.74 |  |  |  | 7460.74 |  | 7460.74 | [15 empty] | Capital Funded by Capital Receipts
[12 empty] | 0 |  | 0
Safe Electrical Systems |  |  |  | 54000 | 381000 | 435000 |  | 314690.69 | 65672.84 | 0 | 18420 | 480998.04 | 0 | 480998.04 | 109.8% | 602000 | 438000 | 602000 | 575000 | 148000 | 140000 | 465000 | 300000 |  |  |  | 0 | 0 | 480998.04
[24 empty] | Various projects being undertaken by Housing Operations staff. They confirm that they anticipate full spend for the year | Various projects being undertaken by Housing Operations staff. They confirm all works have been committed, but slippage of £21k will be carried forward to 08/09.
Communal Areas (Environmentals) |  |  |  | -33000 | 150000 | 117000 | [9 empty] | 117000 | 85000 | 117000 | 85000 | 0 | 0 | 100000 | 100000
98/99 Projects | [11 empty] | 0 |  | 0
98/99 Env Imps General | 1480/1437 | 4000/0900 | [9 empty] | 0 |  | 0
98/99 Env Imps Garage Sites | 1481/1655 | 4001 | [9 empty] | 0 |  | 0
98/99 Env Imps Door Entry Etc | 1482 | 4002 | [9 empty] | 0 |  | 0
98/99 Env Imps Fencing Works | 1483 | 92 03 4003 | [9 empty] | 0 |  | 0
98/99 Env Imps Back Court Areas | 1484 | 4004 | [9 empty] | 0 |  | 0
99/00 Stair Lighting |  | 92 03 4005 | [9 empty] | 0 |  | 0
Budget transferred To Central Heating for Backwood & Lochbrae |  |  |  |  | -32000 | -32000
05/06 Communal Areas Envoironmental Improvements |  | 92 03 4022 | 92420001 |  |  |  |  | 3490.94 | 5248.4 |  | 3982 | 12721.34 |  | 12721.34 | [11 empty] | £3467 Clear level ,red chip ; £515 Clear brambles,hedges |  |  |  | Capital Funded by Capital Receipts
Door Entry Maintenance 02/04 | 1808 | 92 03 1808 | [9 empty] | 0 |  | 0 | [15 empty] | Capital Funded by Capital Receipts
Door Entry | 1559/1631/1665 | 92 03 4006/12 | [9 empty] | 0 |  | 0 | [15 empty] | Capital Funded by Capital Receipts
Door Entry | 1665 | [10 empty] | 0 |  | 0 | [15 empty] | Capital Funded by Capital Receipts
Door Entry | 1761 | 9202 0223 | [9 empty] | 0 |  | 0 | [15 empty] | Capital Funded by Capital Receipts
99/00 Earthworks, Eden Rd, Alloa |  | 4007 | [9 empty] | 0 |  | 0 | [15 empty] | Capital Funded by Capital Receipts
99/00 CarPark Lighting Menstrie Rd. | 1667/1668 | 4009 | [9 empty] | 0 |  | 0 | [15 empty] | Capital Funded by Capital Receipts
01/02 Env Imps Various |  | 4010-4017 | [9 empty] | 0 |  | 0 | [15 empty] | Capital Funded by Capital Receipts
00/01 Env Imps Various | 1559 et al/1755 | 4018 | [9 empty] | 0 |  | 0 | [15 empty] | Capital Funded by Capital Receipts
99/00 Lock Up's |  | 1050 | [9 empty] | 0 |  | 0 | [15 empty] | Capital Funded by Capital Receipts
Door Entry Newmills, Tullibody | 1879 | 92 03 1879 | 92120026 | [8 empty] | 0 |  | 0 | [15 empty] | Capital Funded by Capital Receipts
Close Improvements Backwood Court | 1413 (c) | 92 03 1225 | [9 empty] | 0 |  | 0 | [15 empty] | Capital Funded by Capital Receipts
2004/06 Term Contract - Housing Door Entry Maintenance | 1969 | 92 02 1810 | [9 empty] | 0 |  | 0 | [15 empty] | Capital Funded by Capital Receipts
Garage Lighting |  | 2209 | [9 empty] | 0 |  | 0 | [15 empty] | Capital Funded by Capital Receipts
Retaining Wall Alloa Centre | 1995 | 92 02 1962 | [9 empty] | 0 |  | 0 | [15 empty] | Capital Funded by Capital Receipts
Upgrading Craigview Nos 3-21 | 2096 | 92 02 0165 | [9 empty] | 0 |  | 0 | [15 empty] | Capital Funded by Capital Receipts
3-21 Craigview, Sauchie - House Letting Initiative Phase 2 | 2078 | 92 02 1815 | 92420002 | [8 empty] | 0 |  | 0 | [15 empty] | Capital Funded by Capital Receipts
2006/07 Comm Improvement | 2124(a) | 92 02 0669 | [9 empty] | 0 |  | 0 | [15 empty] | Capital Funded by Capital Receipts
0
Communal Areas (Environmentals) |  |  |  | -33000 | 118000 | 85000 |  | 3490.94 | 5248.4 | 0 | 3982 | 37411.7 | 0 | 37411.7 | 44.01% | 117000 | 85000 | 117000 | 64000 | 0 | 0 | 121000 | 100000 |  |  |  | 0 | 0 | 37411.7
NON-SHS ELEMENTS
PARTICULAR NEEDS HOUSING (CITC)
[24 empty] | No new projects identified to commence in 2007/08. It will be proposed to Council that small budget underspend should be transferred to other projects. | Budgets for Backwood Court & Lochbrae have been transferred to 'Conversions & Upgradings' section, totalling £418k. Of this, £388k has been spent and full spend expected this year. New heating systems have been installed at Backwood Court & Lochbrae. The balance of the budget (£36k) is for general conversion & upgradings. Only £5k is expected to be spent this year as no new projects have been identified. The underspend will be transferred to other projects.
Conversions & Upgradings |  |  |  | -14000 | 50000 | 36000 | [9 empty] | 0 | 36000 | 0 | 423000 | -36000 | -31000 | 70000 | 50000
98/99 Womens Aid | 2010 | 0401 | [9 empty] | 0 |  | 0
85 Upper Mill St (Women's Aid) | 1464 | 0402 | [9 empty] | 0 |  | 0
98/99 Sheltered Housing U/G - MS |  | 92 01 0210 | [9 empty] | 0 |  | 0
00/01 Sh Housing upgrade Phase 1 | 1651 | 92 01 0211 | [9 empty] | 0 |  | 0
99/00 Sheltered Housing U/G Phase 1 | 1557 | [10 empty] | 0 |  | 0
01/02 Sh Housing u/g Ph 2 | 1755 | 92 01 0213 | [9 empty] | 0 |  | 0
Curlers Court, Dollar - 2005/06 Amenity Conversions | 2077 | 92 02 1814 | [9 empty] | 0 |  | 0 | [15 empty] | Capital Funded by Capital Receipts
03/04 Sh Housing u/g Ph 3 |  | 92 01 0214 | [9 empty] | 0 |  | 0 | [15 empty] | Capital Funded by Capital Receipts
Ochil Court | 1822 | 92 01 1822 | [9 empty] | 0 |  | 0 | [15 empty] | Capital Funded by Capital Receipts
Chalet Refurbishment | 1513 | 92 01 0156 | [9 empty] | 0 |  | 0 | [15 empty] | Capital Funded by Capital Receipts
House Upgrading 1 School Rd, Muck. | 1504 | 0157 | [9 empty] | 0 |  | 0 | [15 empty] | Capital Funded by Capital Receipts
Relocatable Chalet Homes |  | 92 01 0150 | [9 empty] | 0 |  | 0 | [15 empty] | Capital Funded by Capital Receipts
Structural Work Floor replacements/Joists |  | 92 02 0148 | [9 empty] | 0 |  | 0 | [15 empty] | Capital Funded by Capital Receipts
Alterations to Maree Court Alloa | 1876 | 92 01 1876 | [9 empty] | 0 |  | 0 | [15 empty] | Capital Funded by Capital Receipts
General Conversions & Upgradings |  | 92 02 1881 | [9 empty] | 0 |  | 0 | [15 empty] | Capital Funded by Capital Receipts
Budget transferred from various budget heads for Backwood & Lochbrae |  |  |  |  | 418000 | 418000
Backwood Court |  | 92 02 0659 | [7 empty] | 18711 | 248370 | 267081 |  | 267081
Lochbrae |  | 92 02 0673 | [7 empty] | 9327 | 111517 | 120844 |  | 120844
[12 empty] | 0 |  | 0
Conversions & Upgradings |  |  |  | -14000 | 468000 | 454000 |  | 0 | 0 | 28038 | 359887 | 392578.37 | 0 | 392578.37 | 1090% | 0 | 36000 | 0 | 423000 | -36000 | -31000 | 70000 | 50000 |  |  |  | 0 | 0 | 392578.37
[24 empty] | Spend against this budget is demand led. Housing OTs anticipate commitment of full budget and brought forward amounts this year. Delays at PCU on costings and knock on effect on works programming may affect actual out-turn. | Spend against this budget is demand led. Housing OTs anticipate committed spend this year will now only amount to £380k.This is an underspend of £71k on revised budget.
Disabled Adaptations |  |  |  | 71000 | 380000 | 451000 | [9 empty] | 451000 | 451000 | 451000 | 451000 | 0 | 0 | 375000 | 300000
00/01 Heating Adaptations |  | 92 01 0202 | [9 empty] | 0 |  | 0
Conversions and Extensions | 1661/1721/1610 | 92 01 07/0807 | [9 empty] | 0 |  | 0
03/04 Heating Adaptations | 1882 | 92 01 0203 | [9 empty] | 0 |  | 0
2004/05 Central Heating Replacements - Disabled Adaptations | 1977 | 92 01 0204 | [9 empty] | 0 |  | 0
27 Garvalley Crescent Alloa - Disabled adaptations | 2101 | 92 01 0205 | [6 empty] | 15.95 |  |  | 15.95 |  | 15.95 | [15 empty] | Capital Funded by Capital Receipts
Extension 6 Burnside Cres Clackmannan | 1836 | 92 02 0183 | [9 empty] | 0 |  | 0
Aids & Adaptations | 1419 | 92 01 0200 | 92560003 | [5 empty] | 61524.72 | 16930 | 1647.7 | 80102.42 |  | 80102.42 | [11 empty] | £1295.70 Equipment Charges |  |  |  | Capital Funded by Capital Receipts
S.W. Minor Adaptations (Area Teams) | 1035 | 92 01 0201 | 92560004 | [5 empty] | 5244.99 |  |  | 5244.99 |  | 5244.99 | [15 empty] | Capital Funded by Capital Receipts
[12 empty] | 0 |  | 0
Disabled Adaptations |  |  |  | 71000 | 380000 | 451000 |  | 0 | 66785.66 | 16930 | 1647.7 | 133480.88 | 0 | 133480.88 | 29.6% | 451000 | 451000 | 451000 | 380000 | 0 | -71000 | 375000 | 300000 |  |  |  | 0 | 0 | 133480.88
[24 empty] | Various projects being undertaken by Housing Operations staff. They confirm that they anticipate full spend for the year | Various projects being undertaken by Housing Operations staff. They confirm that they anticipate full spend for the year
Area Improvements |  |  |  | 86000 | 100000 | 186000 | [9 empty] | 186000 | 170000 | 186000 | 159000 | 0 | 0 | 70000 | 45000
Replace Banking - Delph Pond |  | 92 07 1861 | [9 empty] | 0 |  | 0
Alloa Area |  | 92 03 2202 | [9 empty] | 0 |  | 0
Bowmar Area |  | 92 03 2203 | [9 empty] | 0 |  | 0
Alloa Area Improvements 2004-05 |  | 92 03 2302 | [9 empty] | 0 |  | 0
Sauchie Area |  | 92 03 2204 | [9 empty] | 0 |  | 0
Clackmanna Area |  | 92 03 2205 | [9 empty] | 0 |  | 0
Alva Area |  | 92 03 2206 | [9 empty] | 0 |  | 0
Alva Area Improvements 2004-05 |  | 92 03 2306 | [9 empty] | 0 |  | 0
Tullibody Area |  | 92 03 2208 | [9 empty] | 0 |  | 0
Tillicoultry Area | 1929(b) | 92 03 2207 | [9 empty] | 0 |  | 0
Budget transferred To Central Heating for Backwood & Lochbrae |  |  |  |  | -27000 | -27000
2004/05 Area Improvements - Tillicoultry | 2009(a) | 92 03 2307 | [9 empty] | 0 |  | 0 | [15 empty] | Capital Funded by Capital Receipts
2006/07 General Area Improvements | 2084/1 | 92 56 0005 | 92560005 |  |  |  |  | 61750 |  | 401.75 |  | 62151.75 |  | 62151.75
Area Improvements 2005/06 |  | 92 03 2310 | 92600006 |  |  |  |  | 3020 | 350 |  | 1540 | 4910 |  | 4910 | [11 empty] | Mono block parking area |  |  |  | Capital Funded by Capital Receipts
2004/05 Area Imp - Bin Stores 12-44b High St Tillicoultry | 2009(b) | 92 03 2317 | [9 empty] | 0 |  | 0
2004/05 Area Imp Tullibody | 2009(c ) | 92 03 2308 | [9 empty] | 0 |  | 0
Coalsnaughton - Housing Land | 1954(e) | 92 02 1963 | [9 empty] | 0 |  | 0
Public open spaces - East Alloa Env. Improvements | 1954(g) | 92 02 1964 | [9 empty] | 0 |  | 0
General - 2005/06 Area Improvements | 2084 | 92 03 2215 | [9 empty] | 0 |  | 0 | [15 empty] | Capital Funded by Capital Receipts
Maple Court - External Door Entry System | 1878 | 92 03 1878 | [9 empty] | 0 |  | 0 | [15 empty] | Capital Funded by Capital Receipts
[12 empty] | 0 |  | 0
Area Improvements |  |  |  | 86000 | 73000 | 159000 |  | 64770 | 350 | 401.75 | 1540 | 122542.19 | 0 | 122542.19 | 72.08% | 186000 | 170000 | 186000 | 159000 | 0 | 0 | 70000 | 45000 |  |  |  | 0 | 0 | 122542.19
[24 empty] | Work in Sauchie complete, next phase will be in Alloa, exact programming of areas to be agreed late September. | The project is on track with work in Sauchie complete. Full spend of budget is anticipated.
Water Supply Pipe Replacement |  |  |  | 53000 | 200000 | 253000 | [5 empty] | 0 |  | 0 |  | 253000 | 253000 | 253000 | 253000 | 0 | 0 | 150000 | 50000
2005/09 Lead Pipe Replacement | 2029 | 92 02 0501 | [9 empty] | 0 |  | 0 | [15 empty] | Capital Funded by Capital Receipts
2005-09 Lead Pipe Replacement Phase 2 | 2029(B) | 92 02 0502 | [5 empty] | 140401 |  |  | 2263 | 142664 |  | 142664 | [11 empty] | £2263 Architects fees
Water Supply Pipe Renewal |  | 92 02 0806 | [9 empty] | 0 |  | 0 | [15 empty] | Capital Receipts Applied to Cap Exp
[12 empty] | 0 |  | 0
Water Supply Pipe Replacement |  |  |  | 53000 | 200000 | 253000 |  | 140401 | 0 | 0 | 2263 | 142664 | 0 | 142664 | 56.39% | 253000 | 253000 | 253000 | 253000 | 0 | 0 | 150000 | 50000 |  |  |  | 0 | 0 | 142664
[24 empty] | Review of demolition strategy being undertaken within Housing. No demolitions now scheduled for 2007/08. It will be proposed to Council that budget underspend should be transferred to other projects. | Review of demolition strategy being undertaken within Housing. No demolitions now scheduled for 2007/08.
Demolitions |  |  |  | -3000 | 50000 | 47000 | [9 empty] | 0 | 47000 | 0 | 0 | -47000 | -47000 | 100000 | 50000
Elmgrove Home Loss |  | 92 07 0813 | [9 empty] | 0 |  | 0
Elmgrove Demolition | 1791 | 92 07 0814 | [9 empty] | 0 |  | 0
Newmills Demolition |  | 92 07 0816 | [9 empty] | 0 |  | 0 | [15 empty] | Capital Funded by Capital Receipts
Ashgrove Demolition |  | 92 07 0817 | [9 empty] | 0 |  | 0 | [15 empty] | Capital Funded by Capital Receipts
Demolition Garages Dollar | 1933 | 92 02 0891 | [9 empty] | 0 |  | 0 | [15 empty] | Capital Funded by Capital Receipts
Katrine Court 36-43 Refurb | 2130 | 92 02 0670 | [9 empty] | 0 |  | 0 | [15 empty] | Capital Funded by Capital Receipts
Alterations to 40-43 Katrine Court Alloa | 2098 | 92 01 1877 | [9 empty] | 0 |  | 0 | [15 empty] | Capital Funded by Capital Receipts
[12 empty] | 0 |  | 0
Demolitions |  |  |  | -3000 | 50000 | 47000 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 47000 | 0 | 0 | -47000 | -47000 | 100000 | 50000 |  |  |  | 0 | 0 | 0
This budget is for feasibility studies as required. Current assessment shows no change in out-turn and that full budget will be required.
Feasibility Work |  |  |  |  | 50000 | 50000 | [9 empty] | 50000 | 50000 | 50000 | 50000 | 0 | 0 | 30000 | 25000
General Advice - Architects | 1328 | 92 07 0990 | 92690001 | [6 empty] | 826.57 | 1175.52 | 2002.09 |  | 2002.09 | [11 empty] | £1175.52 CRA Ltd |  |  |  | Capital Funded by Capital Receipts
Standard Delivery Plan |  | 92 07 0995 | # | [8 empty] | 0 |  | 0
Mill St Housing Office - Access Audit | 2146(a) | 92 07 1870 | # | [7 empty] | 444 | 444 |  | 444 | [11 empty] | £444 Architrcts Fees
Institution Place, Tilly - Access Audit | 2146(b) | 92 07 1871 | # | [6 empty] | 370 |  | 370 |  | 370
New Project Contingency | [13 empty] | 0
Feasibility Work |  |  |  | 0 | 50000 | 50000 |  | 0 | 0 | 1196.57 | 1619.52 | 2816.09 | 0 | 2816.09 | 5.632% | 50000 | 50000 | 50000 | 50000 | 0 | 0 | 30000 | 25000 |  |  |  | 0 | 0 | 2816.09
[24 empty] | Current review shows that only £56k will be required (£40k for Bowmar Masterplan and £4k for computers). It will be proposed to Council that budget underspend should be transferred to other projects. | Current review shows that only £44k will be required (£40k for Bowmar Masterplan and £4k for computers). It will be proposed that budget underspend should be transferred to other projects.
Other Costs |  |  |  |  | 100000 | 100000 | [9 empty] | 44110 | 100000 | 44000 | 44000 | -55890 | -56000 | 100000 | 100000
Dev Services Staff Costs | [11 empty] | 0 |  | 0
Capital Programme Officer |  | 92 02 0100 | 92990026 | [8 empty] | 0 |  | 0
Covenant Repayment |  | 92 07 0650 | 92710001 | [8 empty] | 0 |  | 0
Master Plan Bowmar Regeneration |  | 92 02 1885 | # | [7 empty] | 23814 | 23814 |  | 23814 | [11 empty] | £23814 Patience & Highmore - Fees & Expenses |  |  |  | Capital Funded by Capital Receipts
Amenity Contract |  | 92 01 0100 | 92710002 | [8 empty] | 0 |  | 0 | [15 empty] | Capital Funded by Capital Receipts
Scottish Quality Standard |  | 92 07 0991 | 92710003 | [8 empty] | 0 |  | 0 | [15 empty] | Capital Funded by Capital Receipts
SHQS/Stock options 2004 |  | 92 07 0993 | 92990350 | [8 empty] | 0 |  | 0 | [15 empty] | Capital Funded by Capital Receipts
30 Lomond Court Alloa (to be recharged at y/e) |  | 92 07 0832 | 92990348 | [8 empty] | 0 |  | 0 | [15 empty] | Capital Funded by Capital Receipts
Kilncraigs Relocation of Housing |  | 92 07 0840 | 92710004 | [8 empty] | 0 |  | 0 | [15 empty] | Capital Funded by Capital Receipts
Homelessness Assessment Centre | 2189 | 92 07 0156 | # | [7 empty] | 1071.5 | 1071.5 |  | 1071.5 | [11 empty] | £1071.50 Architects Fees
Computer Equipment - New |  | 92 07 0841 | 92710005 | [7 empty] | 4108.01 | 4108.01 |  | 4108.01 | [11 empty] | £4108.01 Computer Equipment |  |  |  | Capital Funded by Capital Receipts
Walled Garden, Orchard Project, Alloa (start 2004/05) |  | 92 07 0815 | 92990315 | [8 empty] | 0 |  | 0
Other Costs |  |  |  | 0 | 100000 | 100000 |  | 0 | 0 | 0 | 28993.51 | 28993.51 | 0 | 28993.51 | 28.99% | 44110 | 100000 | 44000 | 44000 | -55890 | -56000 | 100000 | 100000 |  |  |  | 0 | 0 | 28993.51
TOTAL CAPITAL EXPENDITURE (EXC ILM) |  |  |  | 585000 | 9510000 | 10095000 |  | 3023131.19 | 166788.73 | 147216.66 | 512456.95 | 6423754.98 | -297.31 | 6423458.17 | 59.56% | 10077110 | 10785000 | 10077000 | 9174000 | -17890 | -900000 | 9273000 | 6120000 |  |  |  | 0 | 0 | 6423458.17
[24 empty] | Variance against budget due to repayment of £11k against final ESF claim, following the final audit. | The project is now complete and subject to external audit. It is anticipated that of the 'expenditure' of £119k shown, all but £11k will be off set by grants due from ERDF., subject to satisfactory completion of audit.
Plus AS&E ILM Funding |  |  |  |  | 0 | 0 | [9 empty] | 11000 | 0 | 11000 | 11000 | 11000 | 11000
Community Police Office |  | 92 07 0403 | ?? | [8 empty] | 0 |  | 0
LADA Centre | 1597 | 92 07 0404 | ?? | [8 empty] | 0 |  | 0
SIP ILM |  | 92 07 0900 | 92810001 | [8 empty] | 0 |  | 0
SIP |  | 92 07 0901 | 92810006 | [8 empty] | 0 |  | 0
Scottish Enterprise |  | 92 07 0902 | 92810005 | [8 empty] | 0 |  | 0
New Deal |  | 92 07 0903 | 92810004 | [8 empty] | 0 |  | 0
ESF |  | 92 07 0904 | 92810003 | [7 empty] | 10878 | 10878 |  | 10878 | [11 empty] | £10878 ESF Funding
ERDF |  | 92 07 0905 | 92810002 | [7 empty] | 108609 | 108609 |  | 108609 | [11 empty] | ERDF Grant
SIP PSHG Grant |  | 92 07 0906 | 92810007 | [8 empty] | 0 |  | 0
Training Costs |  | 92 07 0910 | 92810008 | [8 empty] | 0 |  | 0
Plus AS&E ILM Funding |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 119487 | 119487 | 0 | 119487 | 0 | 11000 | 0 | 11000 | 11000 | 11000 | 11000 | 0 | 0 |  |  |  | 0 | 0 | 119487
TOTAL CAPITAL EXPENDITURE (INC ILM) |  |  |  | 585000 | 9510000 | 10095000 |  | 3023131.19 | 166788.73 | 147216.66 | 631943.95 | 6543241.98 | -297.31 | 6542945.17 | 60.67% | 10088110 | 10785000 | 10088000 | 9185000 | -6890 | -889000 | 9273000 | 6120000 |  |  |  | 0 | 0 | 6542945.17
Small change of £100k from position previously reportedin relation to House sales.
Sale of Council Houses |  | 92 08 0100 | 92930001 |  | -3939000 | -3939000 |  | 307.03 |  | 42347.3 |  | 42654.33 | -801460 | -758805.67 | 19.26% | -2702000 | -3939000 | -2667000 | -2667000 | 1237000 | 1272000 | -4025000 | -3501000 | Significantly down against projections at this stage of the year. Out-turn revised to reflect anticipated decrease in the number of House sales. |  | £108 Sales |  |  |  | Capital Receipts Applied to Cap Exp
Sale of Council Shops |  | 92 08 0150 | 92930002 | [8 empty] | 0 |  | 0 | #DIV/0! |  |  |  |  | 0 | 0 | [8 empty] | Capital Receipts Applied to Cap Exp
Sale of HRA Land |  | 92 08 0200 | 92930003 | [7 empty] | 108 | 108 |  | 108 | #DIV/0! |  |  | 1000 | 1000 | 0 | 1000 | [8 empty] | Capital Receipts Applied to Cap Exp
Mortgage Rescue/Shared Ownership
Mortgage Rescue / Shared Ownership |  | 92 07 0200 | 92940001 | [8 empty] | 0 | -38535.07 | -38535.07 | 100% | -38000 | -38535 | -38000 | -38000 | -38000 | -38000 | [8 empty] | Capital Receipts Applied to Cap Exp
Homeless Units Upgrading * | 1486 | 92 01 0154 | 92940002 | [8 empty] | 0 |  | 0 | [6 empty] | 0
Homeless Strategy Broad Street | 2046 | 92 07 0155 | 92940003 |  |  |  |  | 1738.75 | 64.23 |  |  | 1802.98 |  | 1802.98 | [5 empty] | 0 | 0
[12 empty] | 0 |  | 0
SALE OF COUNCIL PROPERTY |  |  |  | 0 | -3939000 | -3939000 |  | 2045.78 | 64.23 | 42347.3 | 108 | 47093.33 | -2352520.07 | -2305426.74 | 57.96% | -2740000 | -3977535 | -2704000 | -2804000 | 1199000 | 1135000 | -4025000 | -3501000 |  |  |  | 0 | 0 | -2305426.74
GRANTS |  |  |  |  | 0 | 0
|  |  |  | 0 | 0 | 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0
NET EXPENDITURE |  |  |  | 585000 | 5571000 | 6156000 |  | 3025176.97 | 166852.96 | 189563.96 | 632051.95 | 6590335.31 | -2352817.38 | 4237518.43 | 62.25% | 7348110 | 6807465 | 7384000 | 6381000 | 1192110 | 246000 | 5248000 | 2619000 |  |  |  | 0 | 0 | 4237518.43
[27 empty] | DR 01 01 2000 0030 >>>>> | 0
Summary:
[11 empty] | Gross Expenditure |  | 6543241.98 |  | Marshall Construction invoice over paid .See e -mail from B.Clark to K.Parmar 24 April 2007
[11 empty] | Selling Expenditure |  | 47093.33
6590335.31
Income
[11 empty] | Capital Receipts |  | -2352520.07
[11 empty] | General Grants |  | 0
[11 empty] | Specific Grants |  | -297.31
4237517.93
Note on A232: 20 Newbiggin St Tullibody removed from contract
Note on A359: This should not come out of HRA budget. If there is any expenditurue here, will need to ask JG which budget it is from?
Note on I200: superuser: £9691.75 accrued from 06/07
Note on I408: superuser: Adjustment made for prepayment of £140k paid to Scottish Water in advance.
Note on I482: superuser: Journal adjustement to be put through to move expenditure to Homelessness Strategy.
Note on L464: superuser: ERDF Grant receivable of £108.6k was accrued. Grant expected to be received in 07/08
Note on N219: superuser: Warm Deal Grant accrued £54,720
Note on O482: superuser: Journal adjustement to be put through to move expenditure to Homelessness Strategy.

## Ledger Codes (hidden)
Porject (Cost Centre) Description | Project Ref | Ledger Code | Main Section | Sub-section | Mapped to in new AGL
TBC (????) |  | 92 03 4022 | ????
85 Upper Mill St (Women's Aid) | 1464 | 92 01 0402 | CARE IN THE COMMUNITY | Conversions & Upgradings
House Upgrading 1 School Rd, Muck. | 1504 | 92 01 0157 | CARE IN THE COMMUNITY | Conversions & Upgradings
Chalet Refurbishment | 1513 | 92 01 0156 | CARE IN THE COMMUNITY | Conversions & Upgradings
99/00 Sheltered Housing U/G Phase 1 | 1557 |  | CARE IN THE COMMUNITY | Conversions & Upgradings
00/01 Sh Housing upgrade Phase 1 | 1651 | 92 01 0211 | CARE IN THE COMMUNITY | Conversions & Upgradings
01/02 Sh Housing u/g Ph 2 | 1755 | 92 01 0213 | CARE IN THE COMMUNITY | Conversions & Upgradings
Ochil Court | 1822 | 92 01 1822 | CARE IN THE COMMUNITY | Conversions & Upgradings
Alterations to Maree Court Alloa | 1876 | 92 01 1876 | CARE IN THE COMMUNITY | Conversions & Upgradings
98/99 Womens Aid | 2010 | 92 01 0401 | CARE IN THE COMMUNITY | Conversions & Upgradings
Alterations to 40-43 Katrine Court Alloa | 2098 | 92 01 1877 | CARE IN THE COMMUNITY | Conversions & Upgradings
Relocatable Chalet Homes |  | 92 01 0150 | CARE IN THE COMMUNITY | Conversions & Upgradings
98/99 Sheltered Housing U/G - MS |  | 92 01 0210 | CARE IN THE COMMUNITY | Conversions & Upgradings
03/04 Sh Housing u/g Ph 3 |  | 92 01 0214 | CARE IN THE COMMUNITY | Conversions & Upgradings
S.W. Minor Adaptations (Area Teams) | 1035 | 92 01 0201 | CARE IN THE COMMUNITY | Disabled Adapt's/Conversions
Aids & Adaptations | 1419 | 92 01 0200 | CARE IN THE COMMUNITY | Disabled Adapt's/Conversions
03/04 Heating Adaptations | 1882 | 92 01 0203 | CARE IN THE COMMUNITY | Disabled Adapt's/Conversions | no code
2004/05 Central Heating Replacements - Disabled Adaptations | 1977 | 92 01 0204 | CARE IN THE COMMUNITY | Disabled Adapt's/Conversions | no code
27 Garvalley Crescent Alloa - Disabled adaptations | 2101 | 92 01 0205 | CARE IN THE COMMUNITY | Disabled Adapt's/Conversions
Conversions and Extensions | 1661/1721/1610 | 92 01 0707 | CARE IN THE COMMUNITY | Disabled Adapt's/Conversions
00/01 Heating Adaptations |  | 92 01 0202 | CARE IN THE COMMUNITY | Disabled Adapt's/Conversions
|  | 92 01 0807 | CARE IN THE COMMUNITY | Disabled Adapt's/Conversions
Homeless Units Upgrading * | 1486 | 92 07 0154 | CARE IN THE COMMUNITY | Homelessness
Homeless Strategy 19 Broad Street, Alloa | 2046 | 92 07 0155 | CARE IN THE COMMUNITY | Homelessness
99/00 Mortgage Rescue |  | 92 07 0200 | CARE IN THE COMMUNITY | Homelessness
07/08 Central Heating Replacement - 2175 | 2175 | 92 20 0022 | ENERGY EFFICIENCY | Heating | 92 20 0022
Various Locations - 2007-2010 Central Heating Term Contract | 2179 | 92 02 0658 | ENERGY EFFICIENCY | Heating
Phase 2 : 2005/06 Electrical Central Heating | 2074 (d) | 92 02 0657 | ENERGY EFFICIENCY | Heating
2005/06 Heating Replacements - Phase 1 | 2074(a) | 92 02 0648 | ENERGY EFFICIENCY | Heating
2005/06 Heating Replacements - Phase 2 | 2074(b) | 92 02 0649 | ENERGY EFFICIENCY | Heating
2005/06 Heating Replacements - Phase 3:Various | 2074© | 92 02 0656 | ENERGY EFFICIENCY | Heating
Backwood Court |  | 92 02 0659 | ENERGY EFFICIENCY | Heating
Lochbrae |  | 92 02 0673 | ENERGY EFFICIENCY | Heating
General - 2006/07 Insulated Render Systems | 2117 | 92 02 0672 | ENERGY EFFICIENCY | Thermal Insulation
2007/08 External Re-Rendering | 2186 | 92 21 0005 | ENERGY EFFICIENCY | Thermal Insulation
Katrine Court Alloa 2006/07 insulated render | 2117(a) | 92 02 0666 | ENERGY EFFICIENCY | Thermal Insulation
Maree Court Alloa 2006/07 render | 2117(b) | 92 02 0667 | ENERGY EFFICIENCY | Thermal Insulation
Cavity Wall Insulation - Garden Terrac. |  | 92 02 0141 | ENERGY EFFICIENCY | Thermal Insulation
99/00 Ashley Terrace Ph 1 | 1528} | 92 02 0210 | ENHANCEMENT | Damp/Rot
01/02 Ashley Terrace Ph 2 | 1723} | 92 02 0211 | ENHANCEMENT | Damp/Rot
Damp/Rot Area Teams) |  | 92 02 0200 | ENHANCEMENT | Damp/Rot
Damp/Rot Sundries |  | 92 02 0201 | ENHANCEMENT | Damp/Rot
Lintel renewal Dollar, etc | 1880 | 92 02 0181 | ENHANCEMENT
Elmgrove Demolition | 1791 | 92 07 0814 | ENVIRONMENTAL IMPROVEMENTS | Demolitions
Newmills Demolition | ??? | 92 07 0816 | ENVIRONMENTAL IMPROVEMENTS | Demolitions
Elmgrove Home Loss |  | 92 07 0813 | ENVIRONMENTAL IMPROVEMENTS | Demolitions
Ashgrove Demolition |  | 92 07 0817 | ENVIRONMENTAL IMPROVEMENTS | Demolitions
98/99 Env Imps Door Entry Etc | 1482 | 92 03 4002 | ENVIRONMENTAL IMPROVEMENTS
98/99 Env Imps Fencing Works | 1483 | 92 03 4003 | ENVIRONMENTAL IMPROVEMENTS
98/99 Env Imps Back Court Areas | 1484 | 92 03 4004 | ENVIRONMENTAL IMPROVEMENTS
Door Entry | 1665 | 92 03 4006 | ENVIRONMENTAL IMPROVEMENTS
Door Entry | 1761 | 92 02 0223 | ENVIRONMENTAL IMPROVEMENTS
Door Entry Maintenance 02/04 | 1808 | 92 02 1808 | ENVIRONMENTAL IMPROVEMENTS
Maple Court External Door Entry System | 1878 | 92 03 1878 | ENVIRONMENTAL IMPROVEMENTS
Newmills Tullibody Env Door Improvement | 1879 | 92 03 1879 | ENVIRONMENTAL IMPROVEMENTS
Replace Banking - Delph Pond | 1924 | 92 07 1861 | ENVIRONMENTAL IMPROVEMENTS
Replacement of Retaining Walls - Various Locations | 1961 | 92 02 1961 | ENVIRONMENTAL IMPROVEMENTS
2004/06 Term Contract - Housing Door Entry Maintenance | 1969 | 92 02 1810 | ENVIRONMENTAL IMPROVEMENTS
Retaining Wall Alloa Centre | 1995 | 92 02 1962 | ENVIRONMENTAL IMPROVEMENTS
General - 2005/06 Area Improvements | 2084 | 92 03 2215 | ENVIRONMENTAL IMPROVEMENTS
Close Improvements Backwood Court | 1413 (c) | 92 03 1225 | ENVIRONMENTAL IMPROVEMENTS
98/99 Env Imps General | 1480/1437 | 92 03 4000 | ENVIRONMENTAL IMPROVEMENTS
98/99 Env Imps Garage Sites | 1481/1655 | 92 03 4001 | ENVIRONMENTAL IMPROVEMENTS
00/01 Env Imps Various | 1559 et al | 92 03 4018 | ENVIRONMENTAL IMPROVEMENTS
Door Entry | 1559/1631/1665 | 92 03 4012 | ENVIRONMENTAL IMPROVEMENTS
99/00 CarPark Lighting Menstrie Rd. | 1667/1668 | 92 03 4009 | ENVIRONMENTAL IMPROVEMENTS
Tillicoultry Area | 1929(b) | 92 03 2207 | ENVIRONMENTAL IMPROVEMENTS
Coalsnaughton - Housing Land | 1954(e) | 92 02 1963 | ENVIRONMENTAL IMPROVEMENTS
Public open spaces - East Alloa Env. Improvements | 1954(g) | 92 02 1964 | ENVIRONMENTAL IMPROVEMENTS
2004/05 Area Imp - Bin Stores 12-44b High St Tillicoultry | 2009(a) | 92 03 2307 | ENVIRONMENTAL IMPROVEMENTS
2004/05 Area Improvements - Tillicoultry | 2009(b) | 92 03 2317 | ENVIRONMENTAL IMPROVEMENTS
Tullibody Area | 2009(c ) | 92 03 2208 | ENVIRONMENTAL IMPROVEMENTS
Door Entry M/N Term Contract 02/04 |  | 92 02 1808 | ENVIRONMENTAL IMPROVEMENTS
|  | 92 03 0900 | ENVIRONMENTAL IMPROVEMENTS
99/00 Lock Up's |  | 92 03 1050 | ENVIRONMENTAL IMPROVEMENTS
Alloa Area |  | 92 03 2202 | ENVIRONMENTAL IMPROVEMENTS
Alloa Area Improvements 2004-05 |  | 92 03 2302 | ENVIRONMENTAL IMPROVEMENTS
Bowmar Area |  | 92 03 2203 | ENVIRONMENTAL IMPROVEMENTS
Sauchie Area |  | 92 03 2204 | ENVIRONMENTAL IMPROVEMENTS
Clackmannan Area |  | 92 03 2205 | ENVIRONMENTAL IMPROVEMENTS
Alva Area |  | 92 03 2206 | ENVIRONMENTAL IMPROVEMENTS
Alva Area Improvements 2004-05 |  | 92 03 2307 | ENVIRONMENTAL IMPROVEMENTS
Garage Lighting |  | 92 03 2209 | ENVIRONMENTAL IMPROVEMENTS
2004/05 Area Imp Tullibody |  | 92 03 2308 | ENVIRONMENTAL IMPROVEMENTS
99/00 Stair Lighting |  | 92 03 4005 | ENVIRONMENTAL IMPROVEMENTS
99/00 Earthworks, Eden Rd, Alloa |  | 92 03 4007 | ENVIRONMENTAL IMPROVEMENTS
01/02 Env Imps Various |  | 92 03 4010 | ENVIRONMENTAL IMPROVEMENTS
|  | 92 03 4017 | ENVIRONMENTAL IMPROVEMENTS
SIP ILM |  | 92 07 0904 | ENVIRONMENTAL IMPROVEMENTS - Additional Training Work
General Advice - Architects | 1328 | 92 07 0990 | FEASIBILITY WORK & NEW PROJECTS | Feasibility Work
New Project Contingency |  |  | FEASIBILITY WORK & NEW PROJECTS | Feasibility Work
Standard Delivery Plan |  | 92 07 0995 | FEASIBILITY WORK & NEW PROJECTS | Feasibility Work
01-02 Home Security Doors General | 1759 | 92 02 0228 | HOME SAFETY | Fear of Crime
Doors General | 1761 | 92 02 0223 | HOME SAFETY | Fear of Crime
02-03 Doors general | 1820 | 92 02 1820 | HOME SAFETY | Fear of Crime
03-04 Door Replacement Alloa & Clack | 1873 | 92 02 1873 | HOME SAFETY | Fear of Crime
2005/06 Door Improvements - Various | 2011 | 92 02 1829 | HOME SAFETY | Fear of Crime
General - 2006/07 Home Security Door Replacements | 2090 | 92 02 1877 | HOME SAFETY | Fear of Crime
98-99 Home Security Doors Phase 1 | 1491(a) | 92 02 0190 | HOME SAFETY | Fear of Crime
98-99 Home Security Doors Phase 2 | 1491(b) | 92 02 0191 | HOME SAFETY | Fear of Crime
98-99 Home Security Doors Phase 3 | 1491(c) | 92 02 0192 | HOME SAFETY | Fear of Crime
98-99 Home Security Doors Phase 4 | 1491(d) | 92 02 0193 | HOME SAFETY | Fear of Crime
99-00 Home Security Doors Phase 1 | 1534(a) | 92 02 0194 | HOME SAFETY | Fear of Crime
99-00 Home Security Doors Phase 2 | 1534(b) | 92 02 0195 | HOME SAFETY | Fear of Crime
99-00 Home Security Doors Phase 3 | 1534(c) | 92 02 0196 | HOME SAFETY | Fear of Crime
99-00 Home Security Doors Phase 4 | 1534(d) | 92 02 0197 | HOME SAFETY | Fear of Crime
99-00 Home Security Doors Phase 5 | 1534(e) | 92 02 0198 | HOME SAFETY | Fear of Crime
99-00 Home Security Doors Phase 6 | 1534(f) | 92 02 0199 | HOME SAFETY | Fear of Crime
99-00 Home Security Doors Phase 7 | 1534(g) | 92 02 0220 | HOME SAFETY | Fear of Crime
99-00 Home Security Doors Phase 8 | 1534(h) | 92 02 0221 | HOME SAFETY | Fear of Crime
00-01 Home Security External Lighting | 1616(e) | 92 02 0240 | HOME SAFETY | Fear of Crime
01-02 Home Security Doors Phase 1 | 1759 (A/B) | 92 02 0224 | HOME SAFETY | Fear of Crime
01-02 Home Security Doors Phase 2 | 1759 (B) | 92 02 0225 | HOME SAFETY | Fear of Crime
01-02 Home Security Doors Phase 3 | 1759 (C/D) | 92 02 0226 | HOME SAFETY | Fear of Crime
01-02 Home Security Doors Phase 4 | 1759 (D) | 92 02 0227 | HOME SAFETY | Fear of Crime
02-03 Doors Ph 1 | 1820A | 92 02 1821 | HOME SAFETY | Fear of Crime
03-04 Door Replacement Alva | 1873 (c) | 92 02 1875 | HOME SAFETY | Fear of Crime
03-04 Door Replacements Phase 1 (Hadden) | 1873(a) | 92 02 1874 | HOME SAFETY | Fear of Crime
2004/05 Fear of Crime (Door Replacement) Phase 2 Alva & Cambus | 1950(b) | 92 02 1825 | HOME SAFETY | Fear of Crime
Various Home Security - External lights phase 3 | 2011 (f) | 92 02 1836 | HOME SAFETY | Fear of Crime
Various Home Security - Doors Phase 4 | 2011 (g) | 92 02 1837 | HOME SAFETY | Fear of Crime
2005/06 Door Improvements - Phase 1 - Alloa | 2011(a) | 92 02 1833 | HOME SAFETY | Fear of Crime
2005/06 Door Improvements - Phase 2 - Tillicoultry | 2011(b) | 92 02 1834 | HOME SAFETY | Fear of Crime
2005/06 Door Improvements - Phase 3 - Tullibody | 2011(c) | 92 02 1835 | HOME SAFETY | Fear of Crime
Phase 1 Alloa - 2006/07 Home Security door replacements | 2090(A) | 92 02 1878 | HOME SAFETY | Fear of Crime
Dollar & Tilly - 2006/07 Door Replacements phase 2 | 2090(B) | 92 02 1879 | HOME SAFETY | Fear of Crime
Screens & Windows (Bill Wardrop) |  | 92 02 0229 | HOME SAFETY | Fear of Crime
Elmgrove |  |  | HOME SAFETY | Fear of Crime
99/00 Lead Pipe Renewal | 1554 | 92 02 0804 | HOME SAFETY | Lead Pipe Replacement
Water Supply Pipe Renewal | 1717 | 92 02 0806 | HOME SAFETY | Lead Pipe Replacement
2005-09 Lead Pipe Replacement | 2029(A) | 92 02 0501 | HOME SAFETY | Lead Pipe Replacement
2005-09 Lead Pipe Replacement Phase 2 | 2029(B) | 92 02 0502 | HOME SAFETY | Lead Pipe Replacement
Lead Pipe Renewal Sundries |  | 92 02 0805 | HOME SAFETY | Lead Pipe Replacement
Garden Wall 46 Earn Ct, Zetland St,etc | 1328 | 92 02 0167 | HOME SAFETY | Upgrading Works
Walkway, Primrose Place, Tilly | 1466 | 92 02 0802 | HOME SAFETY | Upgrading Works
Replacement Screens, Sauchie | 1487 | 92 02 0169 | HOME SAFETY | Upgrading Works
Henderson Ave. Structural | 1489 | 92 02 0164 | HOME SAFETY | Upgrading Works
Lintel Renewal (Alva) | 1524 | 92 02 0160 | HOME SAFETY | Upgrading Works
Mill St, Alloa | 1579 | 92 02 0800 | HOME SAFETY | Upgrading Works
Walkway, High St, Tilly | 1598 | 92 02 0808 | HOME SAFETY | Upgrading Works
Walkway, High St, Tilly | 1677 |  | HOME SAFETY | Upgrading Works
Porches Rosebank/Holton | 1708 | 92 02 0812 | HOME SAFETY | Upgrading Works
Structural Investigation - Weir - Alva | 1746 | 92 02 0144 | HOME SAFETY | Upgrading Works
Beam Strengthening Jamieson Gdns | 1799 | 92 02 0811 | HOME SAFETY | Upgrading Works
Extension 6 Burnside Crescent Clackmannan | 1836 | 92 02 0183 | HOME SAFETY | Upgrading Works
Asbestos testing - Term Contract 2004/06 | 1978 | 92 02 0172 | HOME SAFETY | Upgrading Works
Upgrading Craigview, Sauchie No 3-21 | 2096 | 92 02 0165 | HOME SAFETY | Upgrading Works
General - 2006/09 Asbestos testing - Term contract | 2102 | 92 02 0173 | HOME SAFETY | Upgrading Works
30 Windsor Street Menstrie | 1489(a) | 92 02 0166 | HOME SAFETY | Upgrading Works
Substructure Works-Upgrade Dorran Houses Dollar | 1640(a) | 92 02 0146 | HOME SAFETY | Upgrading Works
Structural Condition Report - Dollar (Dorrans) | 1640(b) | 92 02 0142 | HOME SAFETY | Upgrading Works
03/04 Dorrans Upgrade, Dollar (new code) | 1640[c] | 92 02 0143 | HOME SAFETY | Upgrading Works
47 Hareburn Rd Sound Insulation |  | 92 02 0140 | HOME SAFETY | Upgrading Works
Structural Work Floor replacements/Joists |  | 92 02 0148 | HOME SAFETY | Upgrading Works
Home Safety |  | 92 02 0151 | HOME SAFETY | Upgrading Works
Victim Centered Approach |  | 92 02 0152 | HOME SAFETY | Upgrading Works
Crime Prevention |  | 92 02 0156 | HOME SAFETY | Upgrading Works
Upgrade 49 Mansfield Avenue |  | 92 02 0158 | HOME SAFETY | Upgrading Works
Stabilisation |  | 92 02 0163 | HOME SAFETY | Upgrading Works
Beams Screen Craigview Sauchie |  | 92 02 0165 | HOME SAFETY | Upgrading Works
Asbestos Survey Renewal |  | 92 02 0168 | HOME SAFETY | Upgrading Works
Asbestos Works |  | 92 02 0170 | HOME SAFETY | Upgrading Works
Demolish 3 + 5 Henderson Avenue |  | 92 02 0301 | HOME SAFETY | Upgrading Works
Wier Timber Houses Alva |  | 92 02 0809 | HOME SAFETY | Upgrading Works
99/00 Johnston Crescent |  |  | HOME SAFETY | Upgrading Works
99/00 Asbestos Survey/Rem |  |  | HOME SAFETY | Upgrading Works
01/02 Asbestos Survey |  |  | HOME SAFETY | Upgrading Works
Capitalised Enhancements |  | 92 07 0300 | IMPROVEMENT & ENHANCEMENT | Capitalised Enhancements
00/01 term contract | 1652 |  | IMPROVEMENT & UPGRADE | Heating
Curlers Court, Dollar - 2005/06 Amenity Conversions | 2077 | 92 02 1814 | IMPROVEMENTS | Conversions & Upgradings
General Conversions & Upgradings |  | 92 02 1881 | IMPROVEMENTS | Conversions & Upgradings
Master Plan Bowmar Regeneration |  | 92 02 1885 | IMPROVEMENTS | Conversions & Upgradings
Term Ctrct Solid Fuel C/H 02/03 | 1641 | 92 02 1641 | IMPROVEMENTS | Heating
00/01 term contract | 1652 | 92 02 0621 | IMPROVEMENTS | Heating
Caroline Cres - Alva - Heating Renewal | 1740 | 92 02 0632 | IMPROVEMENTS | Heating
01/02 Term Contract | 1758 | 92 02 0631 | IMPROVEMENTS | Heating
03/04 Heating Term Contract | 1882 | 92 02 0635 | IMPROVEMENTS | Heating
Heating Enhancements -Warm Deal Initiative | 1882 | 92 02 0636 | IMPROVEMENTS | Heating
2004/05 Central Heating Replacements - Warm Deal Initiative | 1977 | 92 02 0643 | IMPROVEMENTS | Heating
2004/05 Central Heating Replacements - Term Contract | 1977 | 92 02 0642 | IMPROVEMENTS | Heating
Gas Safety Incident | 1979 | 92 02 0639 | IMPROVEMENTS | Heating
Various 2005/07 Central heating term contract | 2035 | 92 02 0660 | IMPROVEMENTS | Heating
2005/06 Term Contract - Heating Repairs | 2041 | 92 02 1647 | IMPROVEMENTS | Heating
General - 2005/06 Heating Replacements | 2074 | 92 02 0661 | IMPROVEMENTS | Heating
36-43 Katrine Court Alloa Alterations & Refurbishment | 2130 | 92 02 0670 | IMPROVEMENTS | Heating
06/07 Warmdeal : Attic Insulation | 2163 | 92 02 0671 | IMPROVEMENTS | Heating
99/00 Heating Phase 1 | 1533(a) | 92 02 0620 | IMPROVEMENTS | Heating
99/00 Heating | 1533(b) | 92 02 0617 | IMPROVEMENTS | Heating
99/00 Heating Phase 2 | 1533(c) | 92 02 0619 | IMPROVEMENTS | Heating
00/01 Heating Phase 2 | 1617(b) | 92 02 0626 | IMPROVEMENTS | Heating
00/01 Heating Phase 3 | 1617[c] | 92 02 0629 | IMPROVEMENTS | Heating
Term Contract | 1816/1 | 92 02 0633 | IMPROVEMENTS | Heating
2004/05 Heating Replacements - Mar Estate (Remaining) | 1976(a) | 92 02 0641 | IMPROVEMENTS | Heating
2004/05 Heating Replacements - Phase 2 | 1976(b) | 92 02 0644 | IMPROVEMENTS | Heating
2004/05 Electric Central Heating Installation - Various | 1976(c) | 92 02 0645 | IMPROVEMENTS | Heating
2006/07 Central Heating Contract Phase 1 | 2115(a) | 92 02 0662 | IMPROVEMENTS | Heating
Chapelle Crescent 06/07 Central Heating Phase 2 | 2115(b) | 92 02 0663 | IMPROVEMENTS | Heating
Various 2006/07 Communal Improvement | 2124(a) | 92 02 0669 | IMPROVEMENTS | Heating
00/01 Fuel Changeover |  | 92 02 0625 | IMPROVEMENTS | Heating
Fuel Change - Pers Pref |  | 92 02 0625 | IMPROVEMENTS | Heating
Gas Supply |  | 92 02 0627 | IMPROVEMENTS | Heating
00/01 Electric/Gas Conversions |  | 92 02 0630 | IMPROVEMENTS | Heating
Heating Safety (new code) |  | 92 02 0634 | IMPROVEMENTS | Heating
Gas Link - Mar Policies |  | 92 02 0638 | IMPROVEMENTS | Heating
Heating Appliances |  | 92 02 0640 | IMPROVEMENTS | Heating
Gas Link Monies - Fuel Switch Grant |  | 92 02 0646 | IMPROVEMENTS | Heating
3-21 Craigview, Sauchie - House Letting Initiative Phase 2 | 2078 | 92 02 1815 | IMPROVEMENTS | House Letting Initiative
Sauchie & Tilly - 2005/06 Bathroom Replacement | 2076 | 92 02 1660 | IMPROVEMENTS | Modern Facilities & Services
Term Contract - 2006/09 Door Entry Maintenance | 2111 | 92 02 1815 | IMPROVEMENTS | Modern Facilities & Services
New Roof-Window 22 Stirling Street Tillicoultry | 2114 | 92 02 1850 | IMPROVEMENTS | Modern Facilities & Services
2006/07 Bathroom Replacements Cambus & Alva | 2128 | 92 02 1661 | IMPROVEMENTS | Modern Facilities & Services
Bathroom Replacements Various Locations | 2180 | 92 02 1650 | IMPROVEMENTS | Modern Facilities & Services
Bathroom Replacements 2007/08 Contract 2180(b) | 2180(b) | 92 31 0001 | IMPROVEMENTS | Modern Facilities & Services
Electrical Earth Testing * | 1507 | 92 02 0312 | IMPROVEMENTS | Rewiring
99/00 Electrical Earth Testing | 1573 | 92 02 0314 | IMPROVEMENTS | Rewiring
00-01 Electrical Earth Testing | 1642 | 92 02 0318 | IMPROVEMENTS | Rewiring
00-01 Electrical Rewiring | 1694 | 92 02 0319 | IMPROVEMENTS | Rewiring
01-02 Electrical inspections | 1756 | 92 02 0330 | IMPROVEMENTS | Rewiring
02-03 Rewiring | 1818 | 92 02 1818 | IMPROVEMENTS | Rewiring
02-03 Electrical Installations | 1838 | 92 02 1838 | IMPROVEMENTS | Rewiring
03-04 Electrical Inspection: Various | 1863 | 92 02 1864 | IMPROVEMENTS | Rewiring
2004/05 Electrical Inspections: Alloa | 1938 | 92 02 1866 | IMPROVEMENTS | Rewiring
2005/06 Electrical Inspections - Various | 2055 | 92 02 1867 | IMPROVEMENTS | Rewiring
2005/06 Electrical rewiring programme at Various Locations | 2083 | 92 02 0331 | IMPROVEMENTS | Rewiring
All Areas - 2006/07 Electrical Testing - General | 2143 | 92 02 1870 | IMPROVEMENTS | Rewiring
97/98 Phase 1 (Hart) | 1372(a) | 92 02 0307 | IMPROVEMENTS | Rewiring
98/99 Phase 1 (Sauchie/Tillicoultry) | 1465(a) | 92 02 0311 | IMPROVEMENTS | Rewiring
98/99 Phase 2 * | 1465(b) | 92 02 0313 | IMPROVEMENTS | Rewiring
99/00 Rewiring Phase 1 | 1574(a) | 92 02 0316 | IMPROVEMENTS | Rewiring
99/00 Rewiring Phase 2 | 1574(b) | 92 02 0317 | IMPROVEMENTS | Rewiring
00-01 Electrical Rewiring Phase 1 | 1694(a) | 92 02 0320 | IMPROVEMENTS | Rewiring
00-01 Electrical Rewiring Phase 2 | 1694(b) | 92 02 0321 | IMPROVEMENTS | Rewiring
01-02 Rewire | 1781(a) | 92 02 0323 | IMPROVEMENTS | Rewiring
03-04 Central Heating & Rewiring - Mar Policies | 1882(a) | 92 02 0637 | IMPROVEMENTS | Rewiring
03-04 Electrical Inspection | 1936 (?) | 92 02 1863 | IMPROVEMENTS | Rewiring
04-05 Electrical Rewiring Various | 2017(a) | 92 02 1865 | IMPROVEMENTS | Rewiring
Phase 1 : 2005/06 Electrical Rewiring | 2083(a) | 92 02 0332 | IMPROVEMENTS | Rewiring
2006/07 Electrical Testing, Phase One | 2143(a) | 92 02 1868 | IMPROVEMENTS | Rewiring
2006/07 Electrical Testing, Phase One | 2143(b) | 92 02 1869 | IMPROVEMENTS | Rewiring
00-01 Electrical Rewiring Sundries |  | 92 02 0329 | IMPROVEMENTS | Rewiring
98/99 Close Lighting |  | 92 02 0950 | IMPROVEMENTS | Rewiring
General - 2006/07 Electrical re-wiring | 2116 | 92 02 0664 | IMPROVEMENTS | re-wiring
Phase 1 2006/07 Electrical re-wiring | 2116(a) | 92 02 0665 | IMPROVEMENTS | re-wiring
99/00 Cambus | 1320 | 92 02 0453 | IMPROVEMENTS | Roofs / Rainwater / Cladding
Maple Court Alloa | 1436 | 92 02 0433 | IMPROVEMENTS | Roofs / Rainwater / Cladding
99/00 Maple Court | 1436 | 92 02 0904 | IMPROVEMENTS | Roofs / Rainwater / Cladding
97/98 Cladding Ash Grove E/E | 1442 | 92 02 0455 | IMPROVEMENTS | Roofs / Rainwater / Cladding
Remedial Render High St Tilly * | 1469 | 92 02 0457 | IMPROVEMENTS | Roofs / Rainwater / Cladding
98/99 Flat Roofs | 1473 | 92 02 0410 | IMPROVEMENTS | Roofs / Rainwater / Cladding
98/99 Pitched Roofs | 1490 | 92 02 0426 | IMPROVEMENTS | Roofs / Rainwater / Cladding
00/01 Cruden Roofs | 1523 | 92 02 0415 | IMPROVEMENTS | Roofs / Rainwater / Cladding
100 Gean Rd Re-Inst. Roof | 1644 | 92 02 0430 | IMPROVEMENTS | Roofs / Rainwater / Cladding
Insulation of No Fines Mar Estate | 1686 | 92 02 0459 | IMPROVEMENTS | Roofs / Rainwater / Cladding
00/01 Roof Recladding | 1693 | 92 02 0431 | IMPROVEMENTS | Roofs / Rainwater / Cladding
Flat Roofs Remedial Works | 1751 | 92 02 0810 | IMPROVEMENTS | Roofs / Rainwater / Cladding
01/02 Cruden Roofs | 1777 | 92 02 0412 | IMPROVEMENTS | Roofs / Rainwater / Cladding
Chapelle Crescent Roofing | 1801 | 92 02 0437 | IMPROVEMENTS | Roofs / Rainwater / Cladding
2002/04 Felt Roofing Term Contract | 1809 | 92 02 0436 | IMPROVEMENTS | Roofs / Rainwater / Cladding
02/03 Re-roofing | 1817 | 92 02 1817 | IMPROVEMENTS | Roofs / Rainwater / Cladding
Re-rendering at Clackmannan & Cambus | 1925 | 92 02 0813 | IMPROVEMENTS | Roofs / Rainwater / Cladding
2003/04 Pitched Roofs Phase 1 Coalsn't'n & Clack | 1932 | 92 02 0438 | IMPROVEMENTS | Roofs / Rainwater / Cladding
2004/06 Flat Roof Improvements | 1968 | 92 02 1811 | IMPROVEMENTS | Roofs / Rainwater / Cladding
Braehead, Alva - Roof Repairs | 2067 | 92 02 1812 | IMPROVEMENTS | Roofs / Rainwater / Cladding
25-31 Moir St Alloa - Replacement Lintols | 2071 | 92 02 1813 | IMPROVEMENTS | Roofs / Rainwater / Cladding
Argyle Place, Alloa - replacement rainwater goods | 2072 | 92 02 0470 | IMPROVEMENTS | Roofs / Rainwater / Cladding
No - fines houses insulated render | 2075 | 92 02 0471 | IMPROVEMENTS | Roofs / Rainwater / Cladding
2005/06 Re-Roofing Tullibody | 2082 | 92 02 0441 | IMPROVEMENTS | Roofs / Rainwater / Cladding
14-28 Scotland Place, Tilly - Removal of Findlock gutters | 2104 | 92 02 0443 | IMPROVEMENTS | Roofs / Rainwater / Cladding
Term Contract - 2006/09 flat roof repairs | 2110 | 92 02 0444 | IMPROVEMENTS | Roofs / Rainwater / Cladding
2006/07 Various Pitched Roofs | 2129 | 92 02 0447 | IMPROVEMENTS | Roofs / Rainwater / Cladding
All Areas - Inspection of flat roofs | 2141 | 92 02 0450 | IMPROVEMENTS | Roofs / Rainwater / Cladding
99/00 Pitched Roofs Phase 1 | 1526(a) | 92 02 0427 | IMPROVEMENTS | Roofs / Rainwater / Cladding
99/00 Pitched Roofs Phase 2 | 1526(b) | 92 02 0428 | IMPROVEMENTS | Roofs / Rainwater / Cladding
99/00 Pitched Roofs Phase 3 | 1526(c) | 92 02 0429 | IMPROVEMENTS | Roofs / Rainwater / Cladding
99/00 Cruden Roofs | 1622(a)/1632 | 92 02 0416 | IMPROVEMENTS | Roofs / Rainwater / Cladding
01-02 Pitched Roofs Phase 1 | 1757 (A) | 92 02 0434 | IMPROVEMENTS | Roofs / Rainwater / Cladding
03/04 Re-roofing | 1817(a) | 92 02 1809 | IMPROVEMENTS | Roofs / Rainwater / Cladding
Chappelle Crescent | 1886 (A) | 92 02 0435 | IMPROVEMENTS | Roofs / Rainwater / Cladding
2004/05 Pitched Roofs Phase 1; Sauchie | 1992(a) | 92 02 0439 | IMPROVEMENTS | Roofs / Rainwater / Cladding
2004/05 Re-Roofing Phase 2 Sauchie | 1992(b) | 92 02 0440 | IMPROVEMENTS | Roofs / Rainwater / Cladding
Achray Court, Alloa - insulated render to no-fines Hse. Phase 1 | 2075(A) | 92 02 0472 | IMPROVEMENTS | Roofs / Rainwater / Cladding
2006/07 Pitched Roof Replacements Phase 1 | 2129(a) | 92 02 0445 | IMPROVEMENTS | Roofs / Rainwater / Cladding
2006/07 Pitched Roof Replacements Fascia Repairs | 2129(b) | 92 02 0446 | IMPROVEMENTS | Roofs / Rainwater / Cladding
2006/07 Pitched Roofs : Chimney Upgrades | 2129© | 92 02 0449 | IMPROVEMENTS | Roofs / Rainwater / Cladding
2006/07 Flat Roof Upgrading | 2141(a) | 92 02 0448 | IMPROVEMENTS | Roofs / Rainwater / Cladding
Alloa & Alva 2007/08 Pitched Roof Replacement Phase 1 | 2181(a) | 92 02 0474 | IMPROVEMENTS | Roofs / Rainwater / Cladding
Alloa & Tullibody 1994/95 pitched roofs | A/1238 | 92 02 0473 | IMPROVEMENTS | Roofs / Rainwater / Cladding
Flat Roofs Remedial Works |  | 92 02 0411 | IMPROVEMENTS | Roofs / Rainwater / Cladding
Hareburn Rd Phase 2 Rend/Roofs |  | 92 02 0465 | IMPROVEMENTS | Roofs / Rainwater / Cladding
Various- Inspection of non-trad. Houses | 2122 | 92 02 0668 | IMPROVEMENTS | Structural Works
98/99 New Spend | 1479 | 92 02 0905 | IMPROVEMENTS | Windows
98/99 Maple Court |  | 92 02 0904 | IMPROVEMENTS | Windows
99/00 Window Replacements |  | 92 02 0906 | IMPROVEMENTS | Windows
Ashley Terrace |  | 92 02 1831 | IMPROVEMENTS | Windows
Rem Works at Clackmannan | 2097 | 92 02 0417 | IMPROVEMENTS
2005/08 Term Contract - Floor Coverings | 2043 | 92 02 0710 | INSULATION??? | Floor Coverings
New Spend | 1760 | 92 02 0230 | KITCHENS ETC.
02/03 Kitchens Ph 1 | 1819 | 92 02 1819 | KITCHENS ETC.
04/05 Kitchen Replacements - Various | 1949 | 92 02 1824 | KITCHENS ETC.
2005/06 Kitchen Replacements - various | 2006 | 92 02 1840 | KITCHENS ETC.
2004/05 Kitchen Replacements - Term Contract | 2012 | 92 02 1843 | KITCHENS ETC.
Various - 2007/08 Kitchen Replacements : General | 2147 | 92 02 1851 | KITCHENS ETC.
02/03 Kitchens Ph 2 | 1819(a) | 92 02 1822 | KITCHENS ETC.
03/04 Kitchen replacement Ph 1 Tullibody | 1895(a) | 92 02 1823 | KITCHENS ETC.
04/05 Kitchen replacement at Tullibody | 1949(a) | 92 02 1826 | KITCHENS ETC.
04/05 Kitchen replacement Phase 2 - Sauchie | 1949(b) | 92 02 1827 | KITCHENS ETC.
04/05 Kitchen replacement Phase 3 | 1949(c) | 92 02 1830 | KITCHENS ETC.
2005/06 Kitchen Replacements - Phase 1 Sauchie | 2006(a) | 92 02 1841 | KITCHENS ETC.
2005/06 Kitchen Replacements - Phase 2 Tillicoultry | 2006(b) | 92 02 1842 | KITCHENS ETC.
2005/06 Kitchen Replacements - Phase 3 Alloa | 2006© | 92 02 1845 | KITCHENS ETC.
General - 2006/07 Kitchen replacements | 2100(a) | 92 02 1846 | KITCHENS ETC.
Phase 2 - 2006/07 Kitchen Replacements | 2100(b) | 92 02 1847 | KITCHENS ETC.
Phase 4 - 2006/07 Kitchen Replacements | 2100(d) | 92 02 1849 | KITCHENS ETC.
Phase 3 - 2006/07 Kitchen Replacements | 2100© | 92 02 1848 | KITCHENS ETC.
Clackmannan 2007/08 - Kitchen Replacements, Phase 1 | 2147(a) | 92 02 1852 | KITCHENS ETC.
Alloa - 2007/08 Kitchen Replacements, Phase 2 | 2147(b) | 92 02 1853 | KITCHENS ETC.
Conversions and Extensions |  |  | Main Heading | Subheading
Retaining Wall _ Deerpark | 1860 | 92 07 1860 | OTHER COSTS AND PROJECTS
Homelessness Strat Broad Street | 2046 | 92 07 0155 | OTHER COSTS AND PROJECTS
Staff Costs - Sale of Council Property | 3000 | 92 08 0100 | OTHER COSTS AND PROJECTS
SHQS/Stock options 2004 | ??? | 92 07 0993 | OTHER COSTS AND PROJECTS
Mill St Housing Office - Access Audit | 2146(a) | 92 07 1870 | OTHER COSTS AND PROJECTS
Institution Place, Tilly - Access Audit | 2146(b) | 92 07 1871 | OTHER COSTS AND PROJECTS
OT Salaries |  | 92 01 0100 | OTHER COSTS AND PROJECTS
Capital Programme Officer |  | 92 02 0100 | OTHER COSTS AND PROJECTS
Senior Capital Program Officer |  | 92 02 0101 | OTHER COSTS AND PROJECTS
Kersegreen Clacks |  | 92 03 0400 | OTHER COSTS AND PROJECTS
Local Housing Strategy Funding (new code) |  | 92 07 0230 | OTHER COSTS AND PROJECTS
Right to Compensation |  | 92 07 0250 | OTHER COSTS AND PROJECTS
Computer Equipment * |  | 92 07 0350 | OTHER COSTS AND PROJECTS
Purchase of Transit Van |  | 92 07 0610 | OTHER COSTS AND PROJECTS
Covenant Repayment |  | 92 07 0650 | OTHER COSTS AND PROJECTS
Computer Equipment * |  | 92 07 0750 | OTHER COSTS AND PROJECTS
Insurance Claims Shortfall |  | 92 07 0805 | OTHER COSTS AND PROJECTS
Option Appraisal Elm Grove |  | 92 07 0806 | OTHER COSTS AND PROJECTS
SIMCO |  | 92 07 0809 | OTHER COSTS AND PROJECTS
Coop Drysdale Street |  | 92 07 0810 | OTHER COSTS AND PROJECTS
Posthill |  | 92 07 0811 | OTHER COSTS AND PROJECTS
Homelessness |  | 92 07 0812 | OTHER COSTS AND PROJECTS
Office Moves - Clacks |  | 92 07 0830 | OTHER COSTS AND PROJECTS
49 Chapelle Cresc Tilly |  | 92 07 0831 | OTHER COSTS AND PROJECTS
30 Lomond Court Alloa. Purchased by Council-email S Norris 23/6/04 (to be recharged to future owners at 04/05 y/e) |  | 92 07 0832 | OTHER COSTS AND PROJECTS
Kilncraigs Relocation of Housing |  | 92 07 0840 | OTHER COSTS AND PROJECTS
Scottish Quality Standard |  | 92 07 0991 | OTHER COSTS AND PROJECTS
Professional Fees |  | 92 07 0992 | OTHER COSTS AND PROJECTS
Newmills - Demolish Wall |  | 92 07 1811 | OTHER COSTS AND PROJECTS
Walled Garden, Orchard Project, Alloa |  | 92 07 0815 | OTHER COSTS AND PROJECTS
Housing Needs/Staff Resources |  |  | OTHER COSTS AND PROJECTS
2006/07 General Area Improvements | 2084/1 | 92 56 0005 | PARTICULAR NEEDS HOUSING | Area Improvements | 92 56 0005
Demolition of Garages Murray Place & West Burnside Dollar | 1933 | 92 02 1891 | PRIMARY BUILDING ELEMENTS | Structural Works
Underpinning at Engelen Drive | 2093 | 92 02 1880 | PRIMARY BUILDING ELEMENTS | Structural Works
Structural Work Fairfield Sauchie | 2122 | 92 02 1896 | PRIMARY BUILDING ELEMENTS | Structural Works
Structural Works at Cobblecrook Gardens | 2203 | 92 02 1897 | PRIMARY BUILDING ELEMENTS | Structural Works
Lock Ups - Murray Place Dollar |  | 92 02 1890 | PRIMARY BUILDING ELEMENTS | Structural Works
Chapelle Crescent Tillicoultry - Roof Trusses |  | 92 02 1895 | PRIMARY BUILDING ELEMENTS | Structural Works
Electrical Enhancement Works Void Properties 2006/07 |  | 92 02 0820 | SAFE ELECTRICAL SYSTEMS
Sale of Council Houses |  | 92 08 0100 | SALE OF COUNCIL PROPERTY
Sale of Council Shops |  | 92 08 0150 | SALE OF COUNCIL PROPERTY
Sale of HRA Land |  | 92 08 0200 | SALE OF COUNCIL PROPERTY
03-04 Door Replacements Phase 2 | 1873(b) | 92 02 1876 | SECONDARY BUILDING ELEMENTS | External Doors etc
2004/05 Door Replacement - Phase 1 - Alva | 1950(a) | 92 02 1828 | SECONDARY BUILDING ELEMENTS | External Doors etc
07/08-Door Replacement - Porches Alloa & Tullibody | 2206(b) | 92 12 0021 | SECONDARY BUILDING ELEMENTS | External Doors etc
2005/06 Re-Roofing Main Street Sauchie |  | 92 02 0442 | SECONDARY BUILDING ELEMENTS | Roofs / Rainwater / External Walls
LADA Centre | 1597 | 92 08 0404 | SIP
SIP ILM |  | 92 07 0900 | SIP
SIP |  | 92 07 0901 | SIP
Community Police Office |  | 92 08 0403 | SIP
Scottish Enterprise |  | 92 08 0902 | SIP
New Deal |  | 92 08 0903 | SIP
ESF |  | 92 08 0904 | SIP
Homelessness Assessment Centre | 2189 | 92 07 0156
2005/06 Home Security - External Lights | 2011(d) | 92 02 1832
Server Renewal |  | 92 07 0841
Scottish Enterprise |  | 92 07 0902
ERDF |  | 92 07 0905
Housing Capital PRE Go Suspense Code |  | 92 02 9999
Note on A10: New code 2/10/03. Should go to 7302-0084, David Newlands, Alloa SIP Office, Candleriggs. All coding now corrected, GL0974 & inv sent to David Newlands.
Note on A59: Code seet up 5/5/04
Note on A143: Code set up 8/10/03 - £29201 total budgeted spend
Note on A280: Set up 1/11/04
Note on B72: Not sure if this code relates to Tilli and ledger code

## Backwood Allocations (hidden)
CLACKMANNANSHIRE COUNCIL
HOUSING CAPITAL 2007/08
ALLOCATIONS FOR BACKWOOD COURT & LOCHBRAE
| WORKS |  |  | FEES |  |  | TOTAL
| 22-40 Backwood Court | 1-19 Backwood Court | 52-70 Lochbrae | 22-40 Backwood Court | 1-19 Backwood Court | 52-70 Lochbrae
Kitchens |  | 48163 | 48163 |  | 3539 | 3539 | 103404 | 103
Gas Supply | 12250 | 12250 |  | 974 | 886 | 886 | 27246 | 27
Central Heating | 36763 | 32100 | 32100 | 2626 | 2434 | 2434 | 108457 | 109
External Doors |  | 7626 | 7626 |  | 572 | 572 | 16396 | 16
Safe Electrical Systems | 5360 | 4830 | 4830 | 398 | 362 | 362 | 16142 | 16
Bathrooms | 26057 | 18798 | 18798 | 1688 | 1534 | 1534 | 68409 | 69
Stairwells | 12203 |  |  | 928 |  |  | 13131 | 13
CCTV/Door Entry (CAI) | 16970 |  |  | 1520 |  |  | 18490 | 19
External (AI) | 15000 |  |  | 1200 |  |  | 16200 | 16
| 124603 | 123767 | 111517 | 9334 | 9327 | 9327 | 387875 | 388
Various budget heads | [6 empty] | 252172 | 252
Central Heating & Gas Supply | [6 empty] | 135703 | 136
[7 empty] | 387875 | 388
The Journal is:
|  |  | DR | CR
Backwood Court | 92 02 0659 2760 |  | 267031 |  | Backwood Court Cap Exp
Lochbrae | 92 02 0673 2760 |  | 120844 |  | Lochbrae Cap Exp
Housing General |  |  |  | 387875 | Backwood Court & Lochbrae Cap Exp trf from Capital Budget